## Project Commitment (FYR) (hidden)
Project Commitment
Project Details |  |  |  | Project Phase | [7 empty] | Project Opening |  | Project Chater
Project ID | Project Name | Board ID | School Board | Phase 1 |  | Phase 2 |  | Phase 3 |  | Phase 4 |  | Opening |  | Linked
No. de projet | Nom du projet | No. du conseil | Conseil scolaire | Start | End | Start | End | Start | End | Start | End | School Opening | Child Care Opening
project.id | project.name | board.number | board.name
03-034 | Churchill Public Elementary School | 3 | Rainbow DSB | 2024-01-01 | 2024-05-01 | 2024-06-01 | 2024-11-01 | 2024-12-01 | 2025-04-01 | 2025-05-01 | 2025-09-01 | 2025-09-01 | 2025-10-01
03-036 | Levack Public Elementary School | 3 | Rainbow DSB | 2024-02-01 | 2024-06-01 | 2024-07-01 | 2024-12-01 | 2025-01-01 | 2025-05-01 | 2025-06-01 | 2025-09-01 | 2025-09-01 | 2025-10-01
03-037 | Sudbury Consolidation Public Elementary School | 3 | Rainbow DSB | 2024-03-01 | 2024-07-01 | 2024-08-01 | 2025-01-01 | 2025-02-01 | 2025-06-01 | 2025-07-01 | 2026-01-01 | 2026-01-01 | 2026-01-01
03-039 | Little Current Public Elementary School | 3 | Rainbow DSB | 2024-04-01 | 2024-08-01 | 2024-09-01 | 2025-02-01 | 2025-03-01 | 2025-07-01 | 2025-08-01 | 2026-01-01 | 2026-01-01 | 2026-01-01
[this reflects the project commitment unless there is a authorized revision]

## Project Commitment - E (hidden)
English
Output | English | French
Project Commitment
Label Out | Label English | Label French
Project Info | Project Info
Key | Key
Project ID | Project ID | Identification du projet
Project Name | Project Name | Nom du projet
Phase 1 - Start | Phase 1 - Start | Phase 1 - Début
Phase 1 - End | Phase 1 - End | Phase 1 - Fin
Phase 2 - Start | Phase 2 - Start | Phase 2 - Début
Phase 2 - End | Phase 2 - End | Phase 2 - Fin
Phase 3 - Start | Phase 3 - Start | Phase 3 - Début
Phase 3 - End | Phase 3 - End | Phase 3 - Fin
Phase 4 - Start | Phase 4 - Start | Phase 4 - Début
Phase 4 - End | Phase 4 - End | Phase 4 - Fin
Phase Dates | Phase Dates | Dates de phase
Key Milestones | Key Milestones | Étapes Clés
Site Purchase | Site Purchase | Achat du site
Space Template Finalized | Space Template Finalized | Gabarit des espaces finalisé
Signed Joint Use Agreement | Signed Joint Use Agreement
80% Design | 80% Design | Design à 80%
Class A Cost Estimate | Class A Cost Estimate | Rapport du consultant en coûts de classe A
Site Plan Approval | Site Plan Approval | Approbation du plan de site
Build Permit Obtained | Build Permit Obtained | Permis de construire obtenu
Tender Issued | Tender Issued | Projet soumissionné
Construction Start | Construction Start | Début de la construction
School/Addition Opening | School/Addition Opening | école/ajout ouverte
Project Reconciliation | Project Reconciliation | Réconciliation du projet
Funding Requested | Funding Requested | Financement demandé
Cost of Project (Excluding Site) | Cost of Project (Excluding Site) | Coût du projet (Excluant coût du site)
Total Cost of Project (Including Site) | Total Cost of Project (Including Site) | Coût total
Total CP Request | Total CP Request
Total Child Care Request | Total Child Care Request

## To-dos (hidden)
Does this need to be a .xlm file? I think that might cause problems | Done
When I open the file it says there is blocked content and links that can't be updated.
Phase
Nitpicky, but can we change the conditional formating so green is >=? | Done
Monthly Update
Freeze cells at top and left | Done
Can we discuss how the actuals vs estimates will work again? | Done
Can we discuss the project status? - is this a place to indicate projects that should be removed from further tracking? | yes
Some of the conditional formatting has #REF errors | Done
Col 32: The way you've spelled mobilisation is fun, but not correct. | lol corrected
Col 32: What are we looking for here? - Add pop up to explain | Done
Col 26: Why is the green/black thing mentioned here? Is this the only place we want that? | Added a note for the full sheet
How do you feel about conditional formatting (e.g. red highlight) for blanks where there should be data? | Done
Can we complete row 15 all the way acorss, just for now? | Done
Col 59: Risk type - is there realistically only going to be one risk/project? | No but it is a monthly update & I think they'll be dealing with 1 risk at a time? I did add a "Multiple" option
Col 46: What's the conditional formatting here? (Note in cell AT10)
We're missing "Building Costs - Other" - There are some other errors here - double check and fix | Done
Land cost = site purchase costs? | Updated
Total cost doesn't include building costs - school | fixed
Ad-Hoc Potential Projects
The tab name has an extra hypen | done - As discussed this sheet will be unlocked and fully maintained by analysts
Let's have a quick discussion about this tab | done - As discussed this sheet will be unlocked and fully maintained by analysts
Need a column to indicate that something should be removed | done - As discussed this sheet will be unlocked and fully maintained by analysts
Project Commitment
Tell me about the comment in column Z? | Done
The key milestones are all coming from the project commitments? | Yes
The last of these (project reconciliation) looks like it's being pulled from the monthly update. Is that correct? | Yes

## Phase (hidden)
Project Phase
Col1 | Col2 | Col3 | Col4 | Col5 | Col6 | Col7 | Col8 | Col9
Project ID | Project Name | Project Type | Project Category | Construction Status | Project Phase | Phase Start Date | Phase End Date | Expected Phase Completion - Date
project.id | project.name | project.type | project.category |  | project.phase | phase.start.date | phase.end.date | exp.phase.completion
11-137 | Churchill Public Elementary School | Addition | Consolidation | Pre-Procurement | 1 | 2024-04-01 | 2025-02-01 | 2025-03-01
11-139 | Levack Public Elementary School | Retrofit | Consolidation | Project Reconciliation | 4 | 2024-02-01 | 2024-03-01
11-138 | Sudbury Consolidation Public Elementary School | New Construction | Consolidation | Pre-Procurement | 1 | 2024-04-01 | 2025-02-01 | 2025-05-01
11-139 | Little Current Public Elementary School | Retrofit | Child Care | Substantial Completion | 3 | 2025-02-01 | 2025-02-01 | 2027-01-01

## Phase - E (hidden)
English
Output | English | French
Label Out | Label English | Label French
Project Phase | Project Phase
Project ID | Project ID
Project Name | Project Name
Project Type | Project Type
Project Category | Project Category
Construction Status | Construction Status
Project Phase | Project Phase
Phase Start Date | Phase Start Date
Phase End Date | Phase End Date
Expected Phase Completion - Date | Expected Phase Completion - Date

## Glossary
Section 1: Project Details | Definition | Legend
Project ID | Each project is assigned a unique ID for tracking throughout its lifecycle. Projects with a demolition component require a separate ID for the demolition | Date | Unbolded - Estimated dates Bolded - Actual Dates
Project Name | The official name or title of the project.
Address | The specific location or physical address where the project is situated or being carried out.
City | The city in which the project is located
Postal Code | A series of letters, numbers, or both, assigned to a specific geographic area by the postal service.
Project Type | A classification that describes the nature or scope of the project. Project types include: (1) New Construction, (2) Retrofit, (3) Addition, (4) Other, (5) Land Acquisition, (6) Demolition, (7) Purchase
Project Category | A broader classification that groups the project within a certain area or field. Project categories include: (1) Accommodation Pressure, (2) ASD Pilot Project, (3) Child Care, (4) Community Based CC, (5) Condition, (6) Consolidation, (7) FDK, (8) FL Capital Transitional, (9) Other
Project Status | The project status indicates where the project stands with the ministry. Project statuses include: "Under Ministry Review," "In Progress", "Removed from tracker (Cancelled)", "Removed from tracker (Complete)".
Construction Status | Construction status refers to the current stage or condition of a construction project. It provides an update on whete the project stands in its lifecycle includes stages such as "Planning," Pre-Procurement," "Completed," "On Hold," or "Cancelled
Planning | This stage of construction will encompass all the work required during the planning stage of a process. This planning process extends from the conception of the project to when the board hires the architect to desgin the project.
Pre-Procurement | This stage of the construction process encompasses all activities following the planning phase to get the project ready for tender. This stage includes sourcing and qualifying general contractors, site plan application process, addressing budget constraints, environmental assessments, and any legal/contractual issues.
Tender Issuance | This stage of construction process involves the formal process of inviting contractors to submit bids for a project. It includes the tender announcement, preparation of bids, submission of bids, and the boards evaluation of bids.
Tender Closed | This stage of the construction process occurs after the tender process has closed but before the school board has awarded the contract.
Contract Award | This stage of the construction process begins when the school board awards the contract to the selected contractor.
Site Prep./Mobilization | This stage of the construction process involves site preparation, including clearing the site, ensuring it is ready for construction, and moving equipment on site. At this stage the main construction activities have not yet begun.
Construction | This stage of the construction process will capture the main construction activities. This includes foundation, structural, mechanical, electrical, and plumbing work.
Substantial Completion | This stage of the construction signifies that the project is sufficiently complete to be used, even if minor work remains. At this point the project is functional, minor work like finishings remain, and inspections are still needed.
Completed | At this stage, the construction process is complete. Meaning the building is open, operating, and all inspections have been completed.
Project Reconciliation | Project reconciliation is the process that ensures all financial records and project activities align accurately at the end of the project. The school will be reviewing expenses, identifying discrepancies, settling change orders, and roviding the ministry with final reporting.
Section 2: Square Footage Specification
Anticipate Design Change? | Whether the school board anticipate needing to change the design of the project. This would required an approval from the ministry.
Square Footage of New Construction | The school board to confirm the size of the project
Square Footage of Renovation/Retrofit | The school board to confirm the size of the renovation/retrofit
Square Footage of Demolition | The school board to confirm the size of the demolition
Square Footage of New Child Care | The school board to confirm the size of the new child care
Square Footage of EarlyOn | The school board to confirm the size of the EarlyOn
Section 3: Phase 1- Pre-Tender
Site Ownership Status | The school board needs to confirm the status of the site ownership
Not Site Identified | The board requires a site but has not found one yet
Site Identified Only | The school has only identified the site
Site under option agreement | The site has been identified and is under contract (but not obligation) to sell/buy an asset at a predetermined price.
Site Purchased | The school board has purchased the site needed for the project
Not Applicable | Site requirements do not apply to the project
Site Purchase Date | This is the date the site ownership transfer has occurred.
Space Template Approval Date | This is the date the space template was approved by the Ministry. If the date is yet to be approved, please enter an estimated date.
Type of Designed Used | A drop down for CAs to select the type of design used for the project. Options include: "New", "Repeat" (short for another repeat design), "EDU Catalogue"
Design Status | A drop down for CAs to update the status of design completion
Class A/B Cost Estimate- Date | This is the date the board submitted their class A/B cost estimate to the ministry.
Child Care Floorplan Approval - Date | This is the date the board received their child care floor plan approval.
Site, Design and Child Care Related Comments | A general comment box for analysts to provide useful information regarding site, design and child care related items.
Section 4: Phase 2 - Tender
Site Plan Submisison Date | This is the date the school board started their site plan application with the municipality.
Site Plan Approval Date | This is the date the school board received their site plan approval.
Build Permit Obtained Date | This is the date the school board received their building permit which allows them to begin construction or renovation on a property.
Tender Issued Date | This is the date the school board formally invites contractors to submit bids or proposals for the construction project.
Tender Closed Date | This is the date the school board closes the bidding and proposals for the project has ended.
Section 5: Phase 3 - Construction
Contract Award Date | This is the date the board awards the contract to the suitable contractor. This happens after the board evaluates all the bids, selects the most suitable based on the project needs (includes consideration for lowest bid, the most qualified bid, or a combination of factors).
Site Prep./Mobilization Date | This phase involves preparing the construction site for building. It includes initial excavation to clear and level the ground, remove debris, and prepare the site for construction. Additionally, it involves mobilizing the site by bringing in necessary construction equipment and machinery, and setting up site offices and fences
Construction Start -Date | This is the official date that construction begins on a project. It includes extensive excavation for foundations, basements, or other substructures.
% Construction Progress | This is a metric used to quantify how much of a construction project has been completed. This can be calculated by the board by taking the Actual Costs to Date/Total Estimated Costs x 100
Substantial Completion Date | This marks the point when a project is sufficiently complete where final inspections can be done for school opening.
Section 6: Phase 4 - Project Completion
School Opening Date | This is the date the school opens for enrolment.
Child Care Opening Date | This is the date that the child care portion of the project opens.
Project Reconciliation Date | By this date the school board will identify any variances between the project’s incurred costs and the budget. If variances are found, the school board will request additional funding from the ministry. Once the project’s financial reconciliation is completed and confirmed by the Ministry, the project will be considered complete.
Section 7: Approved Project Funding
This section is populated based on the projects most recent approval.
Section 8: Projected Construction Cost
Basis of Cost Estimate | This column is intended to identiy the level of the cost estimate for the projected construction cost. The drop-down menu has been created in a hierarchical order, with the most accurate reports listed last.
In this section, the school board will estimate the cost of each construction
Section 9: Communication Protocol
Signage
Opening Ceremony - Date
Section 10: General Comments

## Board Contacts
Board | Name | Title | Email | Phone | Cell | Address

## Monthly Update
Monthly Project Updates
ALL ESTIMATED DATES = UNBOLDED ALL ACTUAL DATES = BOLDED | [18 empty] | All Fields Are Filled
Meeting Date |  | 2024-12-13
Section 1: Project Details | [11 empty] | Section 2: Square Footage Specification | [6 empty] | Section 3: Phase 1 - Pre-Tender | [7 empty] | Section 4: Phase 2 - Tender |  |  |  |  | Section 5: Phase 3 - Construction |  |  |  |  | Section 6: Phase 4 - Project Completion |  |  |  | Section 7: Approved Project Funding |  |  |  |  | Section 8: Projected Construction Cost | [17 empty] | Section 9: Communications Protocol |  | Section 10: Project Risks and Mitigation Stategies | [7 empty] | Section 10: General Comments
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8 | Col 9 | Col 10 | Col 11 | Col 12 | Col 13 | Col 14 | Col 15 | Col 16 | Col 17 | Col 18 | Col 19 | Col 20 | Col 21 | Col 22 | Col 23 | Col 24 | Col 25 | Col 26 | Col 27 | Col 28 | Col 29 | Col 30 | Col 31 | Col 32 | Col 33 | Col 34 | Col 35 | Col 36 | Col 37 | Col 38 |  | Col 40 | Col 41 | Col 42 | Col 43 | Col 44 | Col 45 | Col 46 | Col 47 | Col 48 | Col 49 | Col 50 | Col 51 | Col 52 | Col 53 | Col 54 | Col 55 | Col 56 | Col 57 | Col 58 | Col 59 | Col 60 | Col 61 | Col 62 | Col 63 | Col 64 | Col 65 | Col 66 | Col 67 | [6 empty] | Col 74 | Col 75
Project ID | Board Name | Project Name | Address | City | Postal Code | Funding Program | Funding Year | Project Type | Project Category | Project Status | Construction Status | Anticipate Design Change? | Square Footage of New Construction | Square Footage of Renovaton/Retrofit | Square Footage of Demolition | Square Footage of New Child Care | Square Footage of Community Space | Square Footage of EarlyOn | Site Ownership Status | Site Purchase Date | Space Template Approval Date | Type of Design Used | Design Status | Class A/B Cost Estimate -Date | Child Care Floorplan Approval - Date | Site, Design and Child Care Related Comments: Include details of scope change if applicable | Site Plan Submission Date | Site Plan Approval Date | Build Permit Obtained | Tender Issued Date | Tender Closed | Contract Awarded | Site Prep/Mobilization | Construction Start - Date | % Construction Progress | Substantial Completion | School Opening Date | Risk of Delay? | Child Care Opening Date | Project Reconciliation | LP/EDC | CP | CC | Other | Total Approved Funding | Basis of Cost Estimate | Site Acquisition Cost | Site Preparation Cost | Site Funding Source | Building Cost - School | Soft Costs - School | Unique Site Costs - School | Building Cost - Child Care | Soft Costs -Child Care | Unique Site Costs - Child Care | Building Cost - Other | Unique Site Costs - Other | Municipal/Extraordinary Cost - School | Municipal/Extraordinary Cost - Child Care | Municipal/Extraordinary Cost - Other | Total | Variance | Revised Funding Request | Signage | Opening Ceremony - Date | Risk Type | Risk Rating | Risk Exposure Start Date | Min Cost of Risk ($M) | Max Cost of Risk ($M) | Min Delay of Risk (Months) | Max Delay of Risk (Months) | Mitigation Stategies/Comments | CA Comments
Section 1: Project Details Col 1: No. de projet; Section 1: Project Details Col 3: Nom du projet; Section 1: Project Details Col 9: Type de projet; Section 1: Project Details Col 10: Catégorie de projet; Section 2: Square Footage Specification Col 13: Prévoyez-vous avoir besoin d'un changement de portée pour ce projet; Section 2: Square Footage Specification Col 14: Détails du Projet - Superficie de la Nouvelle Construction |  |  |  |  | IP | Service de garde | Autre | Financement total approuvé | Base de l'estimation des coûts |  |  |  | Coûts du site | Autre coût de construction | [5 empty] | Bâtiment |  | Coût unique du site
Section 1: Project Details Col 1: project.id; Section 1: Project Details Col 3: project.name; Section 1: Project Details Col 9: project.type; Section 1: Project Details Col 10: project.category; Section 2: Square Footage Specification Col 13: scope.change.needed; Section 2: Square Footage Specification Col 14: square.footage.new; Section 2: Square Footage Specification Col 15: square.footage.reno; Section 2: Square Footage Specification Col 17: square.footage.cc; Section 2: Square Footage Specification Col 19: square.footage.eo; Section 3: Phase 1 - Pre-Tender Col 26: cc.floorplan.approved; Section 3: Phase 1 - Pre-Tender Col 27: design.comments |  |  |  |  | lp.funding | cp.funding | fdk.funding | total.funding | cost.basis |  |  |  | site.cost | other.cost | [5 empty] | building.cost | [6 empty] | Signage | opening.ceremony | comments | [7 empty] | comments
11-137 | Rainbow DSB | Churchill Public Elementary School | Updated by CA | Updated by CA | Updated by CA | Standalone Child Care | 2023-24 | Addition | Consolidation | Under Ministry Review | Pre-Procurement |  |  |  |  | 400 |  |  | Site Purchased | 2024-04-01 | 2024-04-01 | New | 30%-80% Complete | 2024-05-01 | 2025-03-01 | CA to input | 2024-03-01 | 2024-08-01 | 2025-03-01 | 2025-06-01 | 2025-02-01 | 2024-04-01 | 2024-05-01 | 2025-05-01 | 20 | Aug 1 2025 | 2026-10-01 |  | 2025-10-01 | 2025-10-01 |  | 20000000 | 5000000 | 1000000 | 26000000 | Board Estimate | 3000000 | 500000 | EDC | 5000000 | 2000000 |  | 4000000 | 1000000 |  |  | 1000000 | 3000000 | 2000000 |  | 21500000 | 4500000 | CA Input | No/Non | CA to input | Delay | [6 empty] | Mitigate
11-139 | Rainbow DSB | Levack Public Elementary School |  |  |  | Capital Priorities | 2024-25 | Retrofit | Consolidation | Remove from tracker (Cancelled) | Project Reconciliation |  |  |  |  | 400 |  |  | Site Purchased | 2024-01-01 | 2024-02-01 | Repeat | >80% Complete | 2024-06-01 | 2025-04-01 |  | 2024-03-02 | 2024-09-01 | 2025-03-01 | May 1 2024 | March 15 2024 | 2024-04-01 | 2024-05-01 | May 1 2025 | 90 | 2024-02-01 | 2024-02-01 |  | 2025-03-01 | 2024-02-01 |  |  |  |  | 0 | Class D Estimate | [14 empty] | 0
11-138 | Rainbow DSB | Sudbury Consolidation Public Elementary School |  |  |  | Ad Hoc |  | New Construction | Consolidation | Remove from tracker (Complete) | Pre-Procurement | [7 empty] | Site Purchased | 2024-05-01 | 2024-06-01 | New | <30% Complete | 2024-07-01 | 2025-05-01 |  | 2024-03-03 | 2024-09-02 | 2025-03-01 | May 1 2025 | March 15 2025 | 2024-04-01 | 2024-05-01 | May 1 2026 | 60 | 2026-01-01 | 2024-02-02 |  | 2025-03-02 | 2027-01-01 |  |  |  |  | 0 | Tender Results | [14 empty] | 0
03-039 | Rainbow DSB | Little Current Public Elementary School |  |  |  | Third-Party Funded |  | Retrofit | Child Care | In Progress | Substantial Completion | [7 empty] | Site Purchased |  | 2024-07-01 | EDU Catalogue | 30%-80% Complete | 2024-08-01 | 2025-06-01 |  | 2024-03-04 | 2024-09-03 | 2025-03-01 | May 1 2026 | March 15 2026 | 2024-04-01 | 2024-05-01 | May 1 2027 |  | 2027-01-01 | 2024-02-03 |  | 2025-03-03 | 2028-01-01 |  |  |  |  | 0 | [15 empty] | 0
[45 empty] | 0 | [15 empty] | 0
0
Pulled | Pulled & Col Hidden | Pulled but unlocked and can be changed by CA | Pulled but unlocked and can be changed by CA | Pulled but unlocked and can be changed by CA | Pulled but unlocked and can be changed by CA |  |  | Pulled | Pulled | Drop down | Automatic | Drop Down | CA input | CA input | CA input | CA input | CA input | CA input | Drop Down | CA Input | CA Input | CA Input/Drop Down | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | Drop Down | CA input | CA input |  | CA input | CA Input | Pulled From Latest Approval | Pulled From Latest Approval | Pulled From Latest Approval | Pulled From Latest Approval | Calculated | Drop Down | CA Input | CA Input | Drop Down | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | CA Input | Calculated | Calculated | CA Input | Drop Down | CA to input | Drop Down | Drop Down | CA Input | CA Input |  | CA Input |  | Drop Down | CA Input
low
medium
high

## Sheet2 (hidden)
Notes
When we consolidate if we can just add the SB Name |  |  | Added | Col to be hidden
Move Funding Program |  |  | Added
Funding Program Year instead of approval period | Funding Year | Program | Added
| 2022-23 | Capital Priorities
| 2023-24 | Stand-A-Lone Child Care
Third-Party
Ad Hoc
reorganize the phase 2 because it's disorganized - should go from site plan to | DONE
Change section 7 to projected construction cost
Add colum 60 for forecasted variance | done | Hidden
colum 61 - forecasted submission | done

## Monthly Update - E (hidden)
English
Output | English | French
Monthly Update Sheet
Meeting Date | Meeting Date
Section 1: Project Details | Section 1: Project Details | Détails associés aux projets
Project ID | Project ID
Project Name | Project Name
Address | Address
City | City
Postal Code | Postal Code
Project Type | Project Type
Approval Period | Approval Period
Project Category | Project Category
Project Status | Project Status
Construction Status | Construction Status
Section 2: Square Footage Specification | Section 2: Square Footage Specification
Anticipate Design Change? | Anticipate Design Change?
Square Footage of New Construction | Square Footage of New Construction
Square Footage of Renovaton/Retrofit | Square Footage of Renovaton/Retrofit
Square Footage of Demolition | Square Footage of Demolition
Square Footage of New Child Care | Square Footage of New Child Care
Square Footage of Community Space | Square Footage of Community Space
Square Footage of EarlyOn | Square Footage of EarlyOn
Section 3: Phase 1 - Pre-Tender | Section 3: Phase 1 - Pre-Tender
Site Ownership Status | Site Ownership Status
Site Purchase Date | Site Purchase Date
Space Template Approval Date | Space Template Approval Date
Type of Design Used | Type of Design Used
Design Status | Design Status
Class A/B Cost Estimate -Date | Class A/B Cost Estimate -Date
Child Care Floorplan Approval - Date | Child Care Floorplan Approval - Date
Site, Design and Child Care Related Comments: Include details of scope change if applicable | Site, Design and Child Care Related Comments: Include details of scope change if applicable
Section 4: Phase 2 - Tender | Section 4: Phase 2 - Tender
Tender Issued Date | Tender Issued Date
Tender Closed | Tender Closed
Site Plan Submission Date | Site Plan Submission Date
Site Plan Approval Date | Site Plan Approval Date
Section 5: Phase 3 - Construction | Section 5: Phase 3 - Construction
Construction Start - Date | Construction Start - Date
% Construction Progress | % Construction Progress
Substantial Completion | Substantial Completion
Section 6: Phase 4 - Project Completion | Section 6: Phase 4 - Project Completion
School Opening Date | School Opening Date
Child Care Opening Date | Child Care Opening Date
Project Reconciliation | Project Reconciliation
Section 7: Approved Project Funding | Section 7: Approved Project Funding | Financement approuvé du projet
LP/EDC | LP/EDC
CP | CP
CC | CC
Other | Other
Total Approved Funding | Total Approved Funding
Section 8: Projected Construction Cost | Section 8: Projected Construction Cost | Coût prévu du projet
Basis of Cost Estimate | Basis of Cost Estimate
Land Cost | Land Cost
Building Cost - School | Building Cost - School
Soft Costs - School | Soft Costs - School
Building Cost - Child Care | Building Cost - Child Care
Soft Costs -Child Care | Soft Costs -Child Care
Unique Site Costs - School | Unique Site Costs - School
Unique Site Costs - Child Care | Unique Site Costs - Child Care
Unique Site Costs - Other | Unique Site Costs - Other
Municipal/Extraordinary Cost - School | Municipal/Extraordinary Cost - School
Municipal/Extraordinary Cost - Child Care | Municipal/Extraordinary Cost - Child Care
Municipal/Extraordinary Cost - Other | Municipal/Extraordinary Cost - Other
Total | Total
Variance | Variance
Revised Funding Request | Revised Funding Request
Section 9: Communications Protocol | Section 9: Communications Protocol
Signage | Signage
Opening Ceremony - Date | Opening Ceremony - Date
Section 10: General Comments | Section 10: General Comments | Commentaires
Section 10: Project Risks and Mitigation Stategies | Section 10: Project Risks and Mitigation Stategies
Risk Type | Risk Type
Risk Rating | Risk Rating
Risk Exposure Start Date | Risk Exposure Start Date
Min-Max Cost of Risk ($M) | Min-Max Cost of Risk ($M)
Min-Max Delay of Risk (Months) | Min-Max Delay of Risk (Months)
Mitigation Stategies/Comments | Mitigation Stategies/Comments
CA Comments | CA Comments
Contract Awarded | Contract Awarded
Build Permit Obtained | Build Permit Obtained
Site Preparation Cost | Site Preparation Cost
Site Funding Source | Site Funding Source
Site Prep/Mobilization | Site Prep/Mobilization
Building Cost - Other | Building Cost - Other
ALL ESTIMATED DATES = UNBOLDED ALL ACTUAL DATES = BOLDED | ALL ESTIMATED DATES = UNBOLDED ALL ACTUAL DATES = BOLDED
0
0
0

## Ad-Hoc or Potential Projects
Ad-hoc & Potential Projects
Parent ID | Project ID | Submission Type | Project Type | Year Open | Project Name | Project Category | Project Type | Timing | Cost | Funding Source | Comments
| 11-137 | CP | Addition | 2025 | Churchill Public Elementary School | Accommodation Pressure | Land
| 11-139 | CP | Demolition | 2026 | Levack Public Elementary School | School Consolidation | Demolition
| 11-138 | CP | Addition | 2027 | Sudbury Consolidation Public Elementary School | Accommodation Pressure | Purchase
| 11-140 | CP | Purchase | 2025 | Disposition of our Lady of Lavender | Accommodation Pressure | New School
| 11-141 | CP | Other | 2025 | Land Purchase | Accommodation Pressure | Addition
| not mandatory | drop down | drop down |  |  | drop down
This whole sheet will be updated/maitained by analysts

## Ad-Hoc-Potential Projects - E (hidden)
English
Output | English | French
Ad-Hoc Potential Projects
Parent ID | Parent ID
Project ID | Project ID
Submission Type | Submission Type
Project Type | Project Type
Year Open | Year Open
Project Name | Project Name
Project Category | Project Category
Comments | Comments

## Historical Notes
Project ID | Project Name | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01
11-137 | Churchill Public Elementary School | 2024-05-01: 0
11-139 | Levack Public Elementary School
11-138 | Sudbury Consolidation Public Elementary School
03-039 | Little Current Public Elementary School

## Project Commitment
Project Commitment
English | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Project Info |  |  | Phase Dates | [7 empty] | Key Milestones | [10 empty] | Funding Requested
Key | Project ID | Project Name | Phase 1 - Start | Phase 1 - End | Phase 2 - Start | Phase 2 - End | Phase 3 - Start | Phase 3 - End | Phase 4 - Start | Phase 4 - End | Site Purchase | Space Template Finalized | Signed Joint Use Agreement | 80% Design | Class A Cost Estimate | Site Plan Approval | Build Permit Obtained | Tender Issued | Construction Start | School/Addition Opening | Project Reconciliation | Cost of Project (Excluding Site) | Total Cost of Project (Including Site) | Total CP Request | Total Child Care Request
11¦1 | 11-137 | New West London PS | 2023-09-01 | 2024-04-01 | 2025-02-01 | 2025-03-31 | 2025-03-31 | 2025-02-01 | 2025-02-01 | 2025-10-01 | 2024-03-01 | 2023-09-01 | September 1 2023 | 2023-10-01 | 2024-04-01 | 2024-07-01 | 2025-03-01 | 2025-02-01 | 2025-03-31 | 2025-02-01 | 2025-10-01 | 30977807.23 | 39712487.23 | 26028749 | 4762940
11¦3 | 11-139 | New Southeast London Elementary School | 2023-09-02 | 2024-04-01 | 2025-02-01 | 2025-03-31 | 2025-03-31 | 2025-02-01 | 2025-02-01 | 2024-02-01 | 2024-03-01 | 2023-09-02 | September 1 2024 | 2023-10-01 | 2024-04-01 | 2024-07-01 | 2025-03-01 | 2025-02-01 | 2025-03-31 | 2025-02-01 | 2024-02-01 | 31769765.8461 | 40453365.8461 | 27498622 | 4086062
11¦2 | 11-138 | New Lucan Elementary School | 2023-09-03 | 2024-04-01 | 2025-02-01 | 2024-11-01 | 2024-11-01 | 2024-09-01 | 2024-09-01 | 2027-01-01 | 2024-03-01 | 2023-09-03 | September 1 2025 | 2023-10-01 | 2024-04-01 | 2024-07-01 | 2025-03-01 | 2025-02-01 | 2024-11-01 | 2024-09-01 | 2027-01-01 | 28125989.49 | 37565573.49 | 23999941 | 3954660
11¦3 | 11-139 | New Lilly Elementary School | 2023-09-04 | 2024-04-01 | 2025-02-01 | 2024-11-02 | 2024-11-02 | 2024-09-02 | 2024-09-02 | 2028-01-01 | March 1 2024 | 2023-09-04 | September 1 2026 | 2023-10-01 | 2024-04-01 | 2024-07-01 | 2025-03-01 | 2025-02-01 | 2024-11-02 | 2024-09-02 | 2028-01-01 | 31769765.8461 | 40453365.8461 | 27498622 | 4086062
The dates here will be based on the original project commitment
Note on W3: Mirzajani, Ghazal (EDU): Pulled from cost reasonableness sheet

## To Do (hidden)
Questions | To Do | Status
| update phases to MPIP | Done
| Add Date in title for columns needing dates | Done
| French Translation - Mimic CP Excel Book | Do we need this if its for internal use?
| Make drop downs | Done
| Add tab for project commitment | Done
Can I do this without each individual tracker made? | Conditional formating - color for when it's on mark or passed | Done
Questions
Highlighted Sections
Do we need french translation if its internal use

## Sheet1 (hidden)
PROJECT ID | PARENT ID | DSBID | CMSM/DSSAB # | DSB # | SCHOOL BOARD NAME | PROJECT NAME | PROJECT NAME LONG | OCCUPANT CODE | SFIS ID | CAMPUS ID | ASSET ID | ADDRESS | CITY | POSTAL CODE | MUNICIPALITY CODE | MUNICIPALITY LEGAL | MUNICIPALITY FOR MOI | UPPER TIER | AREA | SUBREGION | REGION | LATITUDE (Y) | LONGITUDE (X) | ORI-DATE (DD-Mmm-YY) | ORI-SY (YYYY-YY) | ORI-FY (YYYY-YY) | LP-DATE (DD-Mmm-YY) | LP-SY (YYYY-YY) | LP-FY (YYYY-YY) | CP-DATE (DD-Mmm-YY) | CP-SY (YYYY-YY) | CP-FY (YYYY-YY) | CC-DATE (DD-Mmm-YY) | CC-SY (YYYY-YY) | CC-FY (YYYY-YY) | EO-DATE (DD-Mmm-YY) | EO-SY (YYYY-YY) | EO-FY (YYYY-YY) | CHR-DATE (DD-Mmm-YY) | CHR-SY (YYYY-YY) | CHR-FY (YYYY-YY) | PP COUNT | CCC ROOM COUNT | CCC SPACE COUNT | COUNT TOWARDS 100K | EO ROOM COUNT | ATP STATUS | ATP DATE (DD-Mmm-YY) | ATP MAX AMOUNT | PROJECT STATUS | PROJECT TYPE | CATEGORY | COMPLETION SY (YYYY-YY) | OCCUPANCY DATE (DD-mmm-YY) | SRA | SCI | POD | AS | EDC | EER | CCSF | CHMRA | TA | MUN | REG | PROV | FED | PRI | OTHSB | TOTAL-SB | NPP+GPLC | GPLR | FDK | LP | CP | EEC | CC | EO | CHR | OTHMIN | TOTAL-MIN | TOTAL-SB+MIN | PROJECT COST | VARIANCE | EMBARGO END DATE (DD-Mmm-YY) | OB SIGN INSTALLED (Y/N or N/A) | Recurrent Report for BOSSB - Project to be COUNTED for CP - Y or N | Recurrent Report for BOSSB - Funding to be INCLUDED for CP - Y or N | Recurrent Report for BOSSB - Project to be counted for CC - (1 (Yes as part of CP), 2(NO) or 3 (Yes as part of CC only)) | Recurrent Report for BOSSB - Funding to be INCLUDED for CC - Y or N | Is the sum of CP, LP, CC, EO, CHR
01-001 | 01-001 | 1 | N/A | 28002 | DSB Ontario North East | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18280 | 19057 | 19057-B01 | 153 CROATIA AVE | SCHUMACHER | P0N1G0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4751 | -81.2885 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-002 | 01-002 | 1 | N/A | 28002 | DSB Ontario North East | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18280 | 19057 | 19057-B01 | 153 CROATIA AVE | SCHUMACHER | P0N1G0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4751 | -81.2885 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 680264 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981601 | 981601 | 981601 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-003 | 01-003 | 1 | N/A | 28002 | DSB Ontario North East | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18280 | 19057 | 19057-B01 | 153 CROATIA AVE | SCHUMACHER | P0N1G0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4751 | -81.2885 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 373692 | Construction Complete | Other | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373692 | 373692 | 373692 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-004 | 01-004 | 1 | N/A | 28002 | DSB Ontario North East | Bertha Shaw | Bertha Shaw Public Elementary School | ELE | 180 | 5413 | 5413-B01 | 109 POWELL AVE | SOUTH PORCUPINE | P0N1H0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4828 | -81.2095 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3341985 | Construction Complete | Addition | Other | 2006-07 | 38961 | 2993258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348727 | 3341985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3341985 | 3341985 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-006 | 01-006 | 1 | N/A | 28002 | DSB Ontario North East | Cochrane | Cochrane Public Elementary School | ELE | 10635 | 5004 | 5004-B01 | 453 CHALMERS AVE | COCHRANE | P0L1C0 | 35-13-81-407 | Cochrane | Cochrane T | Cochrane District | COCHRANE | Northeast | North | 49.0748 | -81.0189 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5566509 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 358955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754521 | 2113476 | 3453033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3453033 | 5566509 | 5566509 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-007 | 01-007 | 1 | N/A | 28002 | DSB Ontario North East | DSBONE Head Office | Administrative Office | OFF-ADM | 18280 | 19057 | 19057-B01 | 153 CROATIA AVE | SCHUMACHER | P0N1G0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4751 | -81.2885 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5124700 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5124700 | 5124700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5124700 | 5124700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-008 | 01-008 | 1 | N/A | 28002 | DSB Ontario North East | Iroquois Falls | Iroquois Falls Public Elementary School | ELE | 309 | 5490 | 5490-B01 | 900 CENTENNIAL ST | IROQUOIS FALLS | P0K1G0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7625 | -80.6898 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5224409 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946648 | 3946648 | 1277761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277761 | 5224409 | 5224409 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-009 | 01-009 | 1 | N/A | 28002 | DSB Ontario North East | Iroquois Falls | Iroquois Falls Public Elementary School | ELE | 309 | 5490 | 5490-L01 | 900 CENTENNIAL ST | IROQUOIS FALLS | P0K1G0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7625 | -80.6898 | 41304 | 2012-13 | 2012-13 | 41304 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5000 | Construction Complete | Land Acquisition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 5000
01-010 | 01-010 | 1 | N/A | 28002 | DSB Ontario North East | Kirkland Lake District | Kirkland Lake District Public Secondary School | SEC | 10825 | 12029 | 12029-B01 | 60 ALLEN ST | KIRKLAND LAKE | P2N3J5 | 35-13-90-405 | Kirkland Lake | Kirkland Lake T | Timiskaming District | TIMISKAMING | Northeast | North | 48.1492 | -80.0195 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24370665 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 6390975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111712 | 7502687 | 16867978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16867978 | 24370665 | 24370665 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-011 | 01-011 | 1 | N/A | 28002 | DSB Ontario North East | New Liskeard | New Liskeard Public Elementary School | ELE | 1620 | 6347 | 6347-B01 | 141 DYMOND ST | NEW LISKEARD | P0J1P0 | 35-13-90-101 | Temiskaming Shores | Temiskaming Shores C | Timiskaming District | TIMISKAMING | Northeast | North | 47.5051 | -79.6802 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2588353 | Construction Complete | Addition | Other | 2004-05 | 38231 | 2588353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2588353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2588353 | 2588353 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-012 | 01-012 | 1 | N/A | 28002 | DSB Ontario North East | Pinecrest | Pinecrest Public Elementary School | ELE | 1815 | 6462 | 6462-B01 | 542 TOKE ST | TIMMINS | P4N6W1 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4879 | -81.3175 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1575417 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575417 | 1575417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575417 | 1575417 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-014 | 01-014 | 1 | N/A | 28002 | DSB Ontario North East | Roland Michener | Roland Michener Public Secondary School | SEC | 5667 | 8378 | 8378-B01 | 155 LEGION DR | SOUTH PORCUPINE | P0N1H0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4826 | -81.2137 | 41824 | 2013-14 | 2014-15 | - | - | - | 41824 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41858 | 790000 | Construction Complete | Retrofit | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790000 | 0 | 0 | 0 | 0 | 0 | 790000 | 790000 | 790000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 790000
01-015 | 01-015 | 1 | N/A | 28002 | DSB Ontario North East | Smooth Rock Falls | Smooth Rock Falls Public Elementary School | ELE | 7624 | 5106 | 5106-B01 | 50 THIRD ST | SMOOTH ROCK FALLS | P0L2B0 | 35-13-81-406 | Smooth Rock Falls | Smooth Rock Falls T | Cochrane District | COCHRANE | Northeast | North | 49.2773 | -81.6342 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3238744 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356505 | 1356505 | 1882239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1882239 | 3238744 | 3238744 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-016 | 01-016 | 1 | N/A | 28002 | DSB Ontario North East | Smooth Rock Falls | Smooth Rock Falls Public Elementary School | ELE | 7624 | 5106 | 5106-B01 | 50 THIRD ST | SMOOTH ROCK FALLS | P0L2B0 | 35-13-81-406 | Smooth Rock Falls | Smooth Rock Falls T | Cochrane District | COCHRANE | Northeast | North | 49.2773 | -81.6342 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42117 | 715991 | Construction Complete | Retrofit | Consolidation | 2015-16 | 42400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715991 | 0 | 0 | 0 | 0 | 0 | 715991 | 715991 | 715991 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 715991
01-017 | 01-017 | 1 | N/A | 28002 | DSB Ontario North East | Timiskaming District | Timiskaming District Public Secondary School | SEC | 5692 | 8394 | 8394-B01 | 90 NIVEN ST N | NEW LISKEARD | P0J1P0 | 35-13-90-101 | Temiskaming Shores | Temiskaming Shores C | Timiskaming District | TIMISKAMING | Northeast | North | 47.5115 | -79.6796 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42117 | 870565 | Construction Complete | Retrofit | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 870565 | 0 | 0 | 0 | 0 | 0 | 870565 | 870565 | 870565 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 870565
01-018 | 01-018 | 1 | N/A | 28002 | DSB Ontario North East | Timmins Centennial | Timmins Centennial Public Elementary School | ELE | 15287 | 18047 | 18047-B01 | 545 WILCOX ST | TIMMINS | P4N3K5 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4643 | -81.3375 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13779114 | Construction Complete | New Construction | Consolidation | 2012-13 | 41153 | 0 | 0 | 949807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949807 | 11673401 | 0 | 1155906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12829307 | 13779114 | 13779114 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-019 | 01-019 | 1 | N/A | 28002 | DSB Ontario North East | W Earle Miller | W Earle Miller Public Elementary School | ELE | 1530 | 6283 | 6283-B01 | 200 VICTORIA AVE | TIMMINS | P4N8H3 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.492 | -81.3416 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1159861 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159861 | 1159861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159861 | 1159861 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
01-020 | 01-020 | 1 | 301 - DSSAB Cochrane | 28002 | DSB Ontario North East | Schumacher | Schumacher Public Elementary School | ELE | 2090 | 6647 | 6647-B01 | 64 CROATIA AVE | SCHUMACHER | P0N1G0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4747 | -81.2969 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2019-20 | 43711 | 0 | 0 | 0 | 369503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369503 | 0 | 0 | 0 | 0 | 0 | 0 | 1134384 | 0 | 0 | 0 | 1134384 | 1503887 | 1503887 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1134384
02-001 | 02-001 | 2 | N/A | 28010 | Algoma DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 24570 | 19576 | 19576-B01 | 644 ALBERT ST E | SAULT STE. MARIE | P6A2K7 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5096 | -84.3269 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21926 | 0 | 0 | 0 | 0 | 0 | 21926 | 21926 | 21926 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 21926
02-002 | 02-002 | 2 | N/A | 28010 | Algoma DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 24570 | 19576 | 19576-B01 | 644 ALBERT ST E | SAULT STE. MARIE | P6A2K7 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5096 | -84.3269 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5130885 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5712386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5712386 | 5712386 | 5712386 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-003 | 02-003 | 2 | 304 - DSSAB Sault Ste Marie | 28010 | Algoma DSB | Boreal | Boreal Public Elementary School | ELE | 24609 | 8115 | 8115-B01 | 232 NORTHERN AVE E | SAULT STE. MARIE | P6B4H6 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5353 | -84.3253 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43084 | 17873055 | Construction Complete | Retrofit | Condition | 2018-19 | 43344 | 0 | 3169773 | 0 | 2251545 | 0 | 0 | 0 | 713876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6135194 | 0 | 0 | 0 | 0 | 10800099 | 0 | 937758 | 0 | 0 | 0 | 11737857 | 17873051 | 17873051 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11737857
02-004 | 02-004 | 2 | N/A | 28010 | Algoma DSB | Arthur Henderson Annex | Arthur Henderson Annex Public Elementary School | ELE | 2930 | 5465 | 5465-B02 | 3 HENDERSON LANE RR 2 | BRUCE MINES | P0R1C0 | 35-13-80-402 | Bruce Mines | Bruce Mines T | Algoma District | ALGOMA | Northeast | North | 46.3028 | -83.7813 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 208787 | Construction Complete | Demolition | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208787 | 0 | 0 | 0 | 0 | 0 | 208787 | 208787 | 208787 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 208787
02-005-01 | 02-005 | 2 | N/A | 28010 | Algoma DSB | Central Algoma | Central Algoma Public Elementary and Secondary School | ELE/SEC | 5206 | 8118 | 8118-B01 | 32 KENSINGTON RD RR 1 | DESBARATS | P0R1E0 | 35-13-80-605 | Johnson | Johnson Tp | Algoma District | ALGOMA | Northeast | North | 46.3401 | -83.9369 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 125 | - | - | N | - | Approved | 42109 | 3331430 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605731 | 0 | 2463561 | 0 | 0 | 0 | 0 | 0 | 3069292 | 3069292 | 3069292 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2463561
02-005-02 | 02-005 | 2 | N/A | 28010 | Algoma DSB | Central Algoma | Central Algoma Public Elementary and Secondary School | ELE/SEC | 5206 | 8118 | 8118-L01 | 32 KENSINGTON RD RR 1 | DESBARATS | P0R1E0 | 35-13-80-605 | Johnson | Johnson Tp | Algoma District | ALGOMA | Northeast | North | 46.3401 | -83.9369 | 41858 | 2013-14 | 2014-15 | 41858 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41858 | 2187473 | Construction Complete | Land Acquisition | Consolidation | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2187473 | 0 | 0 | 0 | 0 | 0 | 0 | 2187473 | 2187473 | 2187473 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2187473
02-006 | 02-006 | 2 | N/A | 28010 | Algoma DSB | Central Algoma | Central Algoma Public Elementary and Secondary School | ELE/SEC | 5206 | 8118 | 8118-B01 | 32 KENSINGTON RD RR 1 | DESBARATS | P0R1E0 | 35-13-80-605 | Johnson | Johnson Tp | Algoma District | ALGOMA | Northeast | North | 46.3401 | -83.9369 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4679086 | Construction Complete | Addition | Consolidation | 2013-14 | 41518 | 2543000 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636086 | 4679086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4679086 | 4679086 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-007-01 | 02-007 | 2 | N/A | 28010 | Algoma DSB | Chapleau | Chapleau Public Elementary and Secondary School | ELE/SEC | 7609 | 5042 | 5042-B01 | 20 TEAK ST | CHAPLEAU | P0M1K0 | 35-13-88-606 | Chapleau | Chapleau Tp | Sudbury District | SUDBURY | Northeast | North | 47.8419 | -83.4113 | 40999 | 2011-12 | 2011-12 | - | - | - | TBD | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2609412 | Construction Complete | Retrofit | Condition | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109412 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 2609412 | 2609412 | 2609412 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2500000
02-007-03 | 02-007 | 2 | N/A | 28010 | Algoma DSB | Chapleau | Chapleau Public Elementary School | ELE | 7611 | 8833 | 8833-B01 | 24 PINE ST | CHAPLEAU | P0M1K0 | 35-13-88-606 | Chapleau | Chapleau Tp | Sudbury District | SUDBURY | Northeast | North | 47.8445 | -83.4047 | 41782 | 2013-14 | 2014-15 | - | - | - | 41782 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 483523 | Construction Complete | Demolition | Consolidation | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483523 | 0 | 0 | 0 | 0 | 0 | 483523 | 483523 | 397587 | -85936 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 483523
02-013-01 | 02-013 | 2 | N/A | 28010 | Algoma DSB | FH Clergue | FH Clergue Public Elementary School | ELE | 14222 | 12284 | 12284-B01 | 80 WELDON AVE | SAULT STE. MARIE | P6B3C6 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5182 | -84.3104 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15488607 | Construction Complete | New Construction | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15488607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15488607 | 15488607 | 15488607 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-013-03 | 02-013 | 2 | N/A | 28010 | Algoma DSB | FH Clergue | FH Clergue Public Elementary School | ELE | 848 | 5853 | 5853-B01 | 80 WELDON AVE | SAULT STE. MARIE | P6B3C6 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5178 | -84.3093 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 123000 | Construction Complete | Demolition | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123000 | 123000 | 123000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-014 | 02-014 | 2 | N/A | 28010 | Algoma DSB | Grandview | Grandview Public Elementary School | ELE | 955 | 5918 | 5918-B01 | 161 DENWOOD DR | SAULT STE. MARIE | P6A5R4 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5095 | -84.2659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 82000 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 | 82000 | 82000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-017 | 02-017 | 2 | N/A | 28010 | Algoma DSB | Hornepayne | Hornepayne Public Elementary and Secondary School | ELE/SEC | 17562 | 18016 | 18016-B01 | 162 FOURTH AVE | HORNEPAYNE | P0M1Z0 | 35-13-80-615 | Hornepayne | Hornepayne Tp | Algoma District | ALGOMA | Northeast | North | 49.2167 | -84.78 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 14753201 | Construction Complete | New Construction | Consolidation | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 13603201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13603201 | 14753201 | 14753201 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-019 | 02-019 | 2 | N/A | 28010 | Algoma DSB | Missarenda Consolidated | Missarenda Consolidated Teacherage | TEA | 11272 | 12215 | 12215-B01 | 1 SCHOOL ST | MISSANABIE | P0M2H0 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 48.3111 | -84.0802 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 30000 | Construction Complete | Retrofit | Consolidation | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-023 | 02-023 | 2 | N/A | 28010 | Algoma DSB | Sir James Dunn | Sir James Dunn Public Elementary School | ELE | 5645 | 5345 | 5345-B01 | 1601 WELLINGTON ST E | SAULT STE. MARIE | P6A2R8 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5076 | -84.2877 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 720228 | Construction Complete | Demolition | Other | 2016-17 | 42614 | 0 | 0 | 635000 | 85228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720228 | 720228 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-024 | 02-024 | 2 | N/A | 28010 | Algoma DSB | Superior Heights | Superior Heights Public Secondary School | SEC | 14496 | 8128 | 8128-B02 | 750 NORTH ST | SAULT STE. MARIE | P6B2C5 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5395 | -84.3349 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40044 | 46704290 | Construction Complete | New Construction | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46704290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46704290 | 46704290 | 46704290 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-025 | 02-025 | 2 | 300 - DSSAB Algoma | 28010 | Algoma DSB | Central Algoma | Central Algoma Public Elementary and Secondary School | ELE/SEC | 5206 | 8118 | 8118-B01 | 32 KENSINGTON RD RR 1 | DESBARATS | P0R1E0 | 35-13-80-605 | Johnson | Johnson Tp | Algoma District | ALGOMA | Northeast | North | 46.3401 | -83.9369 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 95 | 4 | 64 | Y | - | Approved | 43740 | 8642578 | Construction Complete | Addition | Consolidation | 2020-21 | 44286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327711 | 0 | 3699841 | 0 | 4615026 | 0 | 0 | 0 | 8642578 | 8642578 | 8642578 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 8314867
02-026 | 02-026 | 2 | 300 - DSSAB Algoma | 28010 | Algoma DSB | Echo Bay Central | Echo Bay Central Public Elementary School | ELE | 698 | 5760 | 5760-B01 | 290 CHURCH ST | ECHO BAY | P0S1C0 | 35-13-80-607 | Macdonald, Meredith and Aberdeen Add'l | Macdonald Meredith et al Tp | Algoma District | ALGOMA | Northeast | North | 46.4857 | -84.0637 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655422 | 0 | 0 | 0 | 655422 | 655422 | 655422 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 655422
02-027 | 02-027 | 2 | 304 - DSSAB Sault Ste Marie | 28010 | Algoma DSB | R M Moore | R M Moore Public Elementary School | ELE | 1946 | 6556 | 6556-B01 | 1272 BASE LINE | SAULT STE. MARIE | P6A5K6 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5218 | -84.4441 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875515 | 0 | 0 | 0 | 1875515 | 1875515 | 1875515 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1875515
02-028 | 02-028+57-016 | 2 | 300 - DSSAB Algoma | 28010 | Algoma DSB | Blind River | Blind River Public Elementary and Secondary School | ELE/SEC | 24831 | 19836 | 19836-B01 | 180 YOUNGFOX RD | BLIND RIVER | P0R1B0 | 35-13-80-401 | Blind River | Blind River T | Algoma District | ALGOMA | Northeast | North | 46.1833 | -82.9745 | 43131 | 2017-18 | 2017-18 | - | - | - | 43921 | 2019-20 | 2019-20 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 381 | 4 | 64 | Y | 2 | Approved | 45203 | 44597813 | Planned | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 32415507 | 0 | 7328604 | 1853702 | 0 | 0 | 41597813 | 44597813 | 44597813 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 41597813
02-029 | 02-029 | 2 | N/A | 28010 | Algoma DSB | Parkland | Parkland Public Elementary School | ELE | 1767 | 6430 | 6430-B01 | 54 AMBER ST | SAULT STE. MARIE | P6A5G1 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5151 | -84.2581 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
02-030 | 02-030 | 2 | N/A | 28010 | Algoma DSB | East View | East View Public Elementary School | ELE | 682 | 5748 | 5748-B01 | 75 ARIZONA AVE | SAULT STE. MARIE | P6A4L9 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5161 | -84.2787 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42327 | 1238281 | Construction Complete | FDK | FDK | 2016-17 | 42614 | 608311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608311 | 0 | 0 | 629970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629970 | 1238281 | 1238281 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
02-031 | 02-031 | 2 | 304 - DSSAB Sault Ste Marie | 28010 | Algoma DSB | Tarentorus | Tarentorus Public Elementary School | ELE | 2279 | 6759 | 6759-B01 | 96 NORTHWOOD ST | SAULT STE. MARIE | P6B4M4 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5458 | -84.308 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 92 | 3 | 49 | - | - | Approved | 44960 | 7952061 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 4486481 | 0 | 2965580 | 0 | 0 | 0 | 7452061 | 7952061 | 7952061 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7452061
02-032 | 02-028+57-016 | 2 | N/A | 28010 | Algoma DSB | Blind River | Blind River Public Elementary and Secondary School | ELE/SEC | 24831 | 19836 | 19836-L01 | 180 YOUNGFOX RD | BLIND RIVER | P0R1B0 | 35-13-80-401 | Blind River | Blind River T | Algoma District | ALGOMA | Northeast | North | 46.1833 | -82.9745 | 44186 | 2020-21 | 2020-21 | 44186 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44186 | 488000 | Construction Complete | Land Acquisition | Consolidation | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488000 | 0 | 0 | 0 | 0 | 0 | 0 | 488000 | 488000 | 488000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 488000
02-033 | 02-033 | 2 | 300 - DSSAB Algoma | 28010 | Algoma DSB | HM Robbins | HM Robbins Public Elementary School | ELE | 993 | 5946 | 5946-B01 | 83 EAST BALFOUR ST | SAULT STE. MARIE | P6C1X4 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5328 | -84.3895 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 26 | 4 | 64 | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1305072 | 0 | 3233668 | 0 | 0 | 0 | 4538740 | 4538740 | 4538740 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4538740
02-034 | 02-034 | 2 |  | 28010 | Algoma DSB | White Pine | White Pines Collegiate and Vocational School | ELE/SEC | 5758 |  |  | 1007 Trunk Rd. | Sault Ste. Marie | P6A 5K9 |  | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | [28 empty] | Planned | Land Acquisition | Consolidation | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-001 | 03-001 | 3 | N/A | 28029 | Rainbow DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15766 | 18083 | 18083-B01 | 69 YOUNG ST | SUDBURY | P3E3G5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4916 | -80.9909 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13417 | 0 | 0 | 0 | 0 | 0 | 13417 | 13417 | 0 | -13417 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 13417
03-002 | 03-002 | 3 | N/A | 28029 | Rainbow DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15766 | 18083 | 18083-B01 | 69 YOUNG ST | SUDBURY | P3E3G5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4916 | -80.9909 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3667576 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3670634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3670634 | 3670634 | 3667015 | -3619 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-005 | 03-005 | 3 | N/A | 28029 | Rainbow DSB | Alexander | Alexander Public Elementary School | ELE | 42 | 5324 | 5324-B01 | 39 ST. BRENDAN ST | SUDBURY | P3E1K3 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4852 | -80.9952 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1413977 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1413977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1413977 | 1413977 | 1413977 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-007 | 03-007 | 3 | N/A | 28029 | Rainbow DSB | Algonquin Road | Algonquin Road Public Elementary School | ELE | 5982 | 8516 | 8516-B01 | 2650 ALGONQUIN RD | SUDBURY | P3E4X6 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4362 | -80.9948 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 614851 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614851 | 614851 | 614851 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-008 | 03-008 | 3 | N/A | 28029 | Rainbow DSB | Algonquin Road | Algonquin Road Public Elementary School | ELE | 5982 | 8516 | 8516-B01 | 2650 ALGONQUIN RD | SUDBURY | P3E4X6 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4362 | -80.9948 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4369904 | Construction Complete | Addition | Other | 2012-13 | 41153 | 1000000 | 0 | 0 | 0 | 0 | 765000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765000 | 357904 | 1243000 | 1004000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604904 | 4369904 | 4369904 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-011 | 03-011 | 3 | N/A | 28029 | Rainbow DSB | Churchill | Churchill Public Elementary School | ELE | 448 | 5589 | 5589-B01 | 1722 FIELDING ST | SUDBURY | P3A1P1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5187 | -80.9343 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4348704 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 1800000 | 0 | 310000 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3810000 | 0 | 0 | 538704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538704 | 4348704 | 4348704 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-015 | 03-015 | 3 | N/A | 28029 | Rainbow DSB | AB Ellis-Espanola | AB Ellis-Espanola Public Elementary and Secondary School | ELE/SEC | 5357 | 5035 | 5035-B01 | 147 SPRUCE AVE | ESPANOLA | P5E1R7 | 35-13-88-405 | Espanola | Espanola T | Sudbury District | SUDBURY | Northeast | North | 46.2632 | -81.7702 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44603 | 9261143 | Construction Complete | Retrofit | Consolidation | 2016-17 | 42614 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 559136 | 0 | 6187720 | 0 | 0 | 0 | 0 | 0 | 6746856 | 8146856 | 8146856 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6187720
03-018 | 03-018 | 3 | N/A | 28029 | Rainbow DSB | Little Current | Little Current Public Elementary School | ELE | 1373 | 6175 | 6175-B01 | 18 DRAPER ST | LITTLE CURRENT | P0P1K0 | 35-13-83-403 | Northeastern Manitoulin and The Islands | Northeastern Manitoulin & The Isl. T | Manitoulin District | MANITOULIN | Northeast | North | 45.9763 | -81.9268 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 923535 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923535 | 923535 | 923535 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-019 | 03-019 | 3 | N/A | 28029 | Rainbow DSB | MacLeod | MacLeod Public Elementary School | ELE | 14407 | 3000 | 3000-B03 | 23 WALFORD RD | SUDBURY | P3E2H2 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.464 | -81.0059 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9250 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9250 | 9250 | 9250 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-020 | 03-020 | 3 | N/A | 28029 | Rainbow DSB | MacLeod | MacLeod Public Elementary School | ELE | 14407 | 3000 | 3000-B03 | 23 WALFORD RD | SUDBURY | P3E2H2 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.464 | -81.0059 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 600 | - | - | N | - | Not Required | - | 16893070 | Construction Complete | New Construction | Condition | 2013-14 | 41518 | 0 | 0 | 141000 | 711600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852600 | 0 | 0 | 1118273 | 0 | 14922197 | 0 | 0 | 0 | 0 | 0 | 16040470 | 16893070 | 16893070 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 14922197
03-022 | 03-022 | 3 | N/A | 28029 | Rainbow DSB | Markstay | Markstay Public Elementary School | ELE | 996 | 5215 | 5215-B01 | 7 PIONEER ST E | MARKSTAY | P0M1G0 | 35-13-88-412 | Markstay-Warren | Markstay-Warren M | Sudbury District | SUDBURY | Northeast | North | 46.4929 | -80.5401 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1090236 | Construction Complete | Addition | Condition | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090236 | 1090236 | 1090236 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-024 | 03-024 | 3 | N/A | 28029 | Rainbow DSB | Princess Anne | Princess Anne Public Elementary School | ELE | 1880 | 6510 | 6510-B01 | 500 DOUGLAS ST | SUDBURY | P3C1H7 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4864 | -81.013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9425143 | Construction Complete | Addition | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1305143 | 0 | 0 | 0 | 0 | 8120000 | 0 | 0 | 0 | 0 | 9425143 | 9425143 | 9425143 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-025 | 03-025 | 3 | N/A | 28029 | Rainbow DSB | Queen Elizabeth II | Queen Elizabeth II Public Elementary School | ELE | 1920 | 6541 | 6541-B01 | 32 DELL ST | SUDBURY | P3C2X8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5065 | -80.9953 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 138554 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138554 | 138554 | 138554 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-026 | 03-026 | 3 | N/A | 28029 | Rainbow DSB | Redwood Acres | Redwood Acres Public Elementary School | ELE | 1964 | 6567 | 6567-B01 | 4625 CARL ST | HANMER | P3P1X5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6544 | -80.9397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 749593 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749593 | 749593 | 749593 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-028 | 03-028 | 3 | N/A | 28029 | Rainbow DSB | RL Beattie | RL Beattie Public Elementary School | ELE | 1945 | 6555 | 6555-B01 | 102 LOACH'S RD |  | P3E2P7 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4501 | -80.9939 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2734518 | Construction Complete | Addition | Other | 2012-13 | 41153 | 500000 | 0 | 0 | 0 | 0 | 927000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427000 | 233078 | 277496 | 796944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307518 | 2734518 | 2734518 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-029 | 03-029 | 3 | N/A | 28029 | Rainbow DSB | Sudbury | Sudbury Public Secondary School | SEC | 5975 | 8512 | 8512-B01 | 154 COLLEGE ST | SUDBURY | P3C4Y2 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4971 | -80.9986 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 23587179 | Construction Complete | Addition | Condition | 2012-13 | 41153 | 0 | 0 | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 0 | 6487179 | 0 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 21487179 | 23587179 | 23587179 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-030 | 03-030 | 3 | N/A | 28029 | Rainbow DSB | Valley View | Valley View Public Elementary School | ELE | 11050 | 6812 | 6812-B01 | 1840 VALLEYVIEW RD | VAL CARON | P3N1S1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5953 | -81.0169 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17374591 | Construction Complete | New Construction | Condition | 2008-09 | 39692 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420819 | 6420819 | 10953772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10953772 | 17374591 | 17374591 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-031 | 03-031 | 3 | N/A | 28029 | Rainbow DSB | Walden | Walden Public Elementary School | ELE | 11335 | 8286 | 8286-B02 | 249 SIXTH AVE | LIVELY | P3Y1M4 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4388 | -81.1408 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13734680 | Construction Complete | New Construction | Condition | 2009-10 | 40057 | 441000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000559 | 1441559 | 12293121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12293121 | 13734680 | 13734680 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-032 | 03-032 | 3 | N/A | 28029 | Rainbow DSB | Wembley | Administrative Office | OFF-ADM | 2445 | 6877 | 6877-B01 | 408 WEMBLEY DR | SUDBURY | P3E1P2 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4806 | -81.0054 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6200000 | Construction Complete | Retrofit | Other | 2016-17 | 42614 | 2000000 | 0 | 0 | 4200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 6200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
03-033 | 03-033 | 3 | N/A | 28029 | Rainbow DSB | Chelmsford Valley District | Chelmsford Valley District Public Secondary School | SEC | 5853 | 5078 | 5078-B01 | 3594 HIGHWAY 144 E | CHELMSFORD | P0M1L0 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5699 | -81.1939 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43741 | 9095826 | Construction Complete | Retrofit | Consolidation | 2021-22 | 44440 | 682415 | 2530758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213173 | 0 | 0 | 0 | 0 | 5882653 | 0 | 0 | 0 | 0 | 0 | 5882653 | 9095826 | 9095826 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5882653
03-034 | 03-034 | 3 | 202 - CMSM Greater Sudbury | 28029 | Rainbow DSB | Churchill | Churchill Public Elementary School | ELE | 448 | 5589 | 5589-B01 | 1722 FIELDING ST | SUDBURY | P3A1P1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5187 | -80.9343 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44278 | 4266712 | Under Construction | Addition | Consolidation | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635574 | 0 | 2631138 | 0 | 0 | 0 | 4266712 | 4266712 | 4266712 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4266712
03-035 | 03-035 | 3 | N/A | 28029 | Rainbow DSB | Confederation | Confederation Public Secondary School | SEC | 5234 | 8134 | 8134-B01 | 1918 MAIN ST | VAL CARON | P3N1R8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6117 | -81.0201 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635590 | 0 | 0 | 0 | 0 | 0 | 1635590 | 1635590 | 1635590 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1635590
03-036 | 03-036 | 3 | 202 - CMSM Greater Sudbury | 28029 | Rainbow DSB | Levack | Levack Public Elementary School | ELE | 5483 | 8280 | 8280-B01 | 100 HIGH ST | LEVACK | P0M2C0 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6451 | -81.3967 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43740 | 1319879 | Under Construction | Retrofit | Consolidation | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730000 | 0 | 589879 | 0 | 0 | 0 | 1319879 | 1319879 | 1319879 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 1319879
03-037 | 03-037 | 3 | 202 - CMSM Greater Sudbury | 28029 | Rainbow DSB | Sudbury Consolidation | Sudbury Consolidation Public Elementary School | ELE | 24674 | 8271 | 8271-B02 | 1545 KENNEDY ST | SUDBURY | P3A2G1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5243 | -80.9399 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | 387 | 3 | 49 | Y | 1 | Approved | 44651 | 16264180 | Under Construction | New Construction | Consolidation | 2022-23 | 44805 | 0 | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 0 | 0 | 1134384 | 0 | 10527505 | 0 | 1912412 | 589879 | 0 | 0 | 14164180 | 16264180 | 16264180 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13029796
03-038 | 03-038 | 3 | 307 - DSSAB Manitoulin-Sudbury | 28029 | Rainbow DSB | Markstay | Markstay Public Elementary School | ELE | 996 | 5215 | 5215-B01 | 7 PIONEER ST E | MARKSTAY | P0M2G0 | 35-13-88-412 | Markstay-Warren | Markstay-Warren M | Sudbury District | SUDBURY | Northeast | North | 46.4929 | -80.5401 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 30 | Y | - | Approved | 43266 | 933171 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 429000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 429000 | 0 | 0 | 0 | 0 | 0 | 0 | 504171 | 0 | 0 | 0 | 504171 | 933171 | 933171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 504171
03-039 | 03-039 | 3 | 307 - DSSAB Manitoulin-Sudbury | 28029 | Rainbow DSB | Little Current | Little Current Public Elementary School | ELE | 1373 | 6175 | 6175-B01 | 18 DRAPER ST | LITTLE CURRENT | P0P1K0 | 35-13-83-403 | Northeastern Manitoulin and The Islands | Northeastern Manitoulin & The Isl. T | Manitoulin District | MANITOULIN | Northeast | North | 45.9763 | -81.9268 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Planned | - | 0 | Planned | Retrofit | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327711 | 0 | 0 | 0 | 327711 | 327711 | 327711 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 327711
03-040 | 03-040 | 3 | 307 - DSSAB Manitoulin-Sudbury | 28029 | Rainbow DSB | S Geiger | S Geiger Public Elementary School | ELE | 2075 | 6637 | 6637-B01 | 355 GOVERNMENT RD W | MASSEY | P0P1P0 | 35-13-88-621 | Sables-Spanish Rivers | Sables-Spanish Rivers Tp | Sudbury District | SUDBURY | Northeast | North | 46.2061 | -82.0819 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 30 | Y | - | Approved | 43266 | 605005 | Construction Complete | Retrofit | Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605005 | 0 | 0 | 0 | 605005 | 605005 | 603391 | -1614 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 605005
03-041 | 03-041 | 3 | 202 - CMSM Greater Sudbury | 28029 | Rainbow DSB | Algonquin Road | Algonquin Road Public Elementary School | ELE | 5982 | 8516 | 8516-B01 | 2650 ALGONQUIN RD | SUDBURY | P3E4X6 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4362 | -80.9948 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884820 | 0 | 0 | 0 | 884820 | 884820 | 0 | -884820 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 884820
03-042 | 03-042 | 3 | 307 - DSSAB Manitoulin-Sudbury | 28029 | Rainbow DSB | Assiginack | Assiginack Public Elementary School | ELE | 105 | 5360 | 5360-B01 | 134 MICHAELS BAY RD | MANITOWANING | P0P1N0 | 35-13-83-601 | Assiginack | Assiginack Tp | Manitoulin District | MANITOULIN | Northeast | North | 45.7462 | -81.8113 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | - | 1 | 15 | Y | 1 | Approved | 44235 | 1595635 | Construction Complete | Addition | Child Care | 2019-20 | 43709 | 0 | 0 | 284791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284791 | 0 | 0 | 0 | 0 | 0 | 0 | 655422 | 655422 | 0 | 0 | 1310844 | 1595635 | 1595635 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1310844
03-043 | 03-043 | 3 | 307 - DSSAB Manitoulin-Sudbury | 28029 | Rainbow DSB | Central Manitoulin | Central Manitoulin Public Elementary School | ELE | 331 | 5505 | 5505-B01 | 56 YONGE ST | MINDEMOYA | P0P1S0 | 35-13-83-613 | Central Manitoulin | Central Manitoulin M | Manitoulin District | MANITOULIN | Northeast | North | 45.7297 | -82.1666 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43266 | 1030422 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 0 | 702711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702711 | 0 | 0 | 0 | 0 | 0 | 0 | 327711 | 0 | 0 | 0 | 327711 | 1030422 | 1030422 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 327711
03-045 | 03-045 | 3 | 202 - CMSM Greater Sudbury | 28029 | Rainbow DSB | Larchwood | Larchwood Public Elementary School | ELE | 608 | 5694 | 5694-B01 | 43 MAIN ST | DOWLING | P0M1R0 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5857 | -81.3366 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294940 | 0 | 0 | 0 | 294940 | 294940 | 0 | -294940 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 294940
03-046 | 03-015 | 3 | N/A | 28029 | Rainbow DSB | AB Ellis | AB Ellis Public Elementary School | ELE | 759 | 5802 | 5802-B01 | 128 PARK ST | ESPANOLA | P5E1S7 | 35-13-88-405 | Espanola | Espanola T | Sudbury District | SUDBURY | Northeast | North | 46.2624 | -81.7683 | 44603 | 2021-22 | 2021-22 | - | - | - | 44603 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44603 | 2136802 | Construction Complete | Demolition | Consolidation | 2021-22 | 44804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2643743 | 0 | 607346 | 0 | 0 | 0 | 3251089 | 3251089 | 3251089 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3251089
04-001 | 04-001 | 4 | N/A | 28037 | Near North DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 2386 | 6832 | 6832-B01 | 963 AIRPORT RD | NORTH BAY | P1C1A5 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3466 | -79.4367 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-002 | 04-002 | 4 | N/A | 28037 | Near North DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 2386 | 6832 | 6832-B01 | 963 AIRPORT RD | NORTH BAY | P1C1A5 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3466 | -79.4367 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3288458 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3772465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3772465 | 3772465 | 2733981 | -1038484 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-004 | 04-004 | 4 | N/A | 28037 | Near North DSB | Almaguin Highlands | Almaguin Highlands Public Secondary School | SEC | 16843 | 19022 | 19022-B01 | 21 MOUNTAINVIEW RD | SOUTH RIVER | P0A1X0 | 35-13-86-504 | South River | South River V | Parry Sound District | PARRY SOUND | Northeast | North | 45.8173 | -79.3691 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 467 | - | - | N | - | Not Required | - | 28317686 | Construction Complete | New Construction | Condition | 2011-12 | 40787 | 2650975 | 0 | 950831 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3901806 | 24415880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24415880 | 28317686 | 28317686 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-008 | 04-008 | 4 | N/A | 28037 | Near North DSB | Land of Lakes Senior | Land of Lakes Senior Public Elementary School | ELE | 279 | 5469 | 5469-B01 | 92 ONTARIO ST | BURKS FALLS | P0A1C0 | 35-13-86-501 | Burk's Falls | Burk's Falls V | Parry Sound District | PARRY SOUND | Northeast | North | 45.6152 | -79.4058 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4660750 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1735474 | 1735474 | 2925276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2925276 | 4660750 | 4660750 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-009 | 04-009 | 4 | N/A | 28037 | Near North DSB | Land of Lakes Senior | Land of Lakes Senior Public Elementary School | ELE | 279 | 5469 | 5469-B01 | 92 ONTARIO ST | BURKS FALLS | P0A1C0 | 35-13-86-501 | Burk's Falls | Burk's Falls V | Parry Sound District | PARRY SOUND | Northeast | North | 45.6152 | -79.4058 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42570 | 2191130 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547065 | 0 | 1644065 | 0 | 0 | 0 | 0 | 0 | 2191130 | 2191130 | 2191130 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1644065
04-010 | 04-010 | 4 | N/A | 28037 | Near North DSB | Laurentian | Laurentian Public Secondary School | SEC | 1340 | 6155 | 6155-B01 | 647 MCKAY AVE | NORTH BAY | P1B7V7 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3237 | -79.4371 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 786536 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 0 | 786536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786536 | 786536 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-013-01 | 04-013 | 4 | N/A | 28037 | Near North DSB | Parry Sound | Parry Sound Public Elementary School | ELE | 24393 | 19394 | 19394-B01 | 21 BEATTY ST | PARRY SOUND | P2A2H5 | 35-13-86-402 | Parry Sound | Parry Sound T | Parry Sound District | PARRY SOUND | Northeast | North | 45.3575 | -80.0294 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 640 | - | - | N | - | Approved | 41599 | 12572291 | Construction Complete | New Construction | Condition | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510749 | 0 | 12061542 | 0 | 0 | 0 | 0 | 0 | 12572291 | 12572291 | 12572291 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 12061542
04-013-02 | 04-013 | 4 | N/A | 28037 | Near North DSB | Parry Sound | Parry Sound Public Elementary School | ELE | 24393 | 19394 | 19394-L01 | 21 BEATTY ST | PARRY SOUND | P2A2H5 | 35-13-86-402 | Parry Sound | Parry Sound T | Parry Sound District | PARRY SOUND | Northeast | North | 45.3575 | -80.0294 | 41038 | 2011-12 | 2012-13 | 41038 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41038 | 2495517 | Construction Complete | Land Acquisition | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495517 | 0 | 0 | 0 | 0 | 0 | 0 | 2495517 | 2495517 | 2495517 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2495517
04-014 | 04-014 | 4 | 303 - DSSAB Parry Sound | 28037 | Near North DSB | Parry Sound | Parry Sound Public Elementary and Secondary School | ELE/SEC | 24472-25150 | 8334 | 8334-B02 | 111 ISABELLA ST | PARRY SOUND | P2A1N2 | 35-13-86-402 | Parry Sound | Parry Sound T | Parry Sound District | PARRY SOUND | Northeast | North | 45.3545 | -80.0388 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | 42317 | 2015-16 | 2015-16 | 43090 | 2017-18 | 2017-18 | - | - | - | 815 | 3 | 49 | N | 1 | Approved | 45075 | 58562436 | Under Construction | New Construction | Consolidation | 2024-25 | 45536 | 0 | 0 | 1775000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3775000 | 0 | 0 | 1153330 | 0 | 44475281 | 0 | 4672909 | 554588 | 0 | 0 | 50856108 | 54631108 | 58562436 | 3931328 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 49702778
04-016 | 04-016 | 4 | N/A | 28037 | Near North DSB | Silver Birches | Silver Birches Public Elementary School | ELE | 6381 | 6243 | 6243-B02 | 65 MARSHALL AVE E | NORTH BAY | P1A3L4 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.2813 | -79.4394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1510749 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 510749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510749 | 1510749 | 1510749 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-019 | 04-019 | 4 | N/A | 28037 | Near North DSB | Vincent Massey | Vincent Massey Public Elementary School | ELE | 10061 | 10381 | 10381-B01 | 15 JANEY AVE | NORTH BAY | P1C1N1 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3371 | -79.4336 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6578752 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023267 | 3023267 | 3555485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3555485 | 6578752 | 6578752 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-021 | 04-021 | 4 | N/A | 28037 | Near North DSB | White Woods | White Woods Public Elementary School | ELE | 10695 | 5020 | 5020-B02 | 177 ETHEL ST | STURGEON FALLS | P2B2Z8 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3733 | -79.9198 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5420068 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559611 | 2559611 | 2860457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2860457 | 5420068 | 5420068 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
04-022-01 | 04-022 | 4 | N/A | 28037 | Near North DSB | Woodland | Woodland Public Elementary School | ELE | 24473 | 8708 | 8708-B02 | 1325 CEDARGROVE DR | NORTH BAY | P1B4S3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3298 | -79.4793 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 507 | - | - | N | - | Approved | 44414 | 11584628 | Construction Complete | New Construction | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663431 | 0 | 9921197 | 0 | 0 | 0 | 0 | 0 | 11584628 | 11584628 | 11584628 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9921197
04-022-03 | 04-022 | 4 | N/A | 28037 | Near North DSB | Pinewood | Pinewood Public Elementary School | ELE | 6380 | 8708 | 8708-B01 | 1325 CEDARGROVE DR | NORTH BAY | P1B4S3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3298 | -79.4791 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 507 | - | - | N | - | Not Required | - | 809546 | Construction Complete | Demolition | Condition | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809546 | 0 | 0 | 0 | 0 | 0 | 809546 | 809546 | 809546 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 809546
04-023 | 04-023 | 4 | 303 - DSSAB Parry Sound | 28037 | Near North DSB | Land of Lakes Senior | Land of Lakes Senior Public Elementary School | ELE | 279 | 5469 | 5469-B01 | 92 ONTARIO ST | BURKS FALLS | P0A1C0 | 35-13-86-501 | Burk's Falls | Burk's Falls V | Parry Sound District | PARRY SOUND | Northeast | North | 45.6152 | -79.4058 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | N | 1 | Approved | 42958 | 563923 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599963 | 0 | 0 | 599963 | 599963 | 563923 | -36040 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 599963
04-024 | 04-024 | 4 | 302 - DSSAB Nipissing | 28037 | Near North DSB | Woodland | Woodland Public Elementary School | ELE | 24473 | 8708 | 8708-B02 | 1325 CEDARGROVE DR | NORTH BAY | P1B4S3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3298 | -79.4793 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 4 | 73 | N | - | Approved | 42895 | 2704028 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2989389 | 0 | 0 | 0 | 2989389 | 2989389 | 2704028 | -285361 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2989389
04-025 | 04-025 | 4 | 302 - DSSAB Nipissing | 28037 | Near North DSB | Fricker | Fricker Public Elementary School | ELE | 24797 | 6844 | 6844-B02 | 790 NORMAN AVE | NORTH BAY | P1B8C4 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3294 | -79.4289 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 308 | 4 | 73 | Y | 1 | Approved | 44414 | 19363537 | Under Construction | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 3067960 | 664989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3732949 | 0 | 0 | 898174 | 0 | 11692571 | 0 | 2439880 | 599963 | 0 | 0 | 15630588 | 19363537 | 19363537 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14732414
04-026 | 04-025 | 4 | N/A | 28037 | Near North DSB | Fricker | Fricker Public Elementary School | ELE | 24797 | 6844 | 6844-B01 | 790 NORMAN AVE | NORTH BAY | P1B8C4 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3294 | -79.4289 | 44414 | 2020-21 | 2021-22 | - | - | - | 44414 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44414 | 408475 | Under Construction | Demolition | Consolidation | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408475 | 0 | 0 | 0 | 0 | 0 | 408475 | 408475 | 408475 | 0 | - | TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 408475
04-027 | 04-014 | 4 | 303 - DSSAB Parry Sound | 28037 | Near North DSB | Parry Sound | Parry Sound Public Elementary and Secondary School | ELE/SEC | 24472-25150 | 8334 | 8334-B02 | 111 ISABELLA ST | PARRY SOUND | P2A1N2 | 35-13-86-402 | Parry Sound | Parry Sound T | Parry Sound District | PARRY SOUND | Northeast | North | 45.3545 | -80.0388 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | 42317 | 2015-16 | 2015-16 | 43090 | 2017-18 | 2017-18 | - | - | - | 815 | 3 | 49 | N | 1 | Approved | 45075 |  | Under Construction | Demolition | Consolidation | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2429489 | 0 | 0 | 0 | 0 | 0 | 2429489 | 2429489 | 58562436 | 56132947 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 2429489
04-028 | 04-014 | 4 | 303 - DSSAB Parry Sound | 28037 | Near North DSB | Parry Sound | Parry Sound Public Elementary and Secondary School | ELE/SEC | 24472-25150 | 8334 | 8334-B02 | 111 ISABELLA ST | PARRY SOUND | P2A1N2 | 35-13-86-402 | Parry Sound | Parry Sound T | Parry Sound District | PARRY SOUND | Northeast | North | 45.3545 | -80.0388 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | 42317 | 2015-16 | 2015-16 | 43090 | 2017-18 | 2017-18 | - | - | - | 815 | 3 | 49 | N | 1 | Approved | 45075 |  | Under Construction | Portapak | Consolidation | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1501839 | 0 | 0 | 0 | 0 | 0 | 1501839 | 1501839 | 58562436 | 57060597 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 1501839
05.1-001 | 05.1-001 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 10911 | 12074 | 12074-B01 | 100 FIRST AVE W | KENORA | P9N3Z7 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7678 | -94.5242 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-002 | 05.1-002 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 10911 | 12074 | 12074-B01 | 100 FIRST AVE W | KENORA | P9N3Z7 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7678 | -94.5242 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 84509 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190236 | 190236 | 84509 | -105727 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-003 | 05.1-003 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Beaver Brae | Beaver Brae Public Secondary School | SEC | 7528 | 8768 | 8768-B01 | 1400 NINTH ST N | KENORA | P9N2T7 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7774 | -94.4619 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2397308 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2397308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2397308 | 2397308 | 2397308 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-004 | 05.1-004 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Beaver Brae | Beaver Brae Public Secondary School | SEC | 7528 | 8768 | 8768-B01 | 1400 NINTH ST N | KENORA | P9N2T7 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7774 | -94.4619 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1859346 | Construction Complete | Retrofit | Other | 2008-09 | 39692 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159346 | 1859346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1859346 | 1859346 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-005 | 05.1-005 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Dryden | Dryden Public Secondary School | SEC | 5316 | 8186 | 8186-B01 | 79 CASIMIR AVE | DRYDEN | P8N2H4 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.781 | -92.8323 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41774 | 590000 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 590000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590000 | 590000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-006 | 05.1-006 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Dryden Regional Training & Cultural Centre | Dryden Regional Training & Cultural Centre Public Secondary School | SEC | 10912 | 12075 | 12075-B01 | 100 CASIMIR AVE | DRYDEN | P8N3L4 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7805 | -92.8336 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7500136 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500136 | 7500136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500136 | 7500136 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-007 | 05.1-007 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Evergreen | Evergreen Public Elementary School | ELE | 7537 | 8773 | 8773-B01 | 675 BRINKMAN RD | KENORA | P9N2R5 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7728 | -94.4724 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3408414 | Construction Complete | Retrofit | Other | 2003-04 | 37865 | 1698844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908414 | 2607258 | 801156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801156 | 3408414 | 3408414 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-008 | 05.1-008 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | King George VI | King George VI Public Elementary School | ELE | 7539 | 8775 | 8775-B01 | 320 SIXTH AVE S | KENORA | P9N2C3 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7622 | -94.4819 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41774 | 986493 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 0 | 986493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986493 | 986493 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-009 | 05.1-009 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | KPDSB Head Office | Administrative Office | OFF-ADM | 10911 | 12074 | 12074-B01 | 100 FIRST AVE W | KENORA | P9N3Z7 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7678 | -94.5242 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41752 | 160398 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10398 | 160398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160398 | 160398 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-010 | 05.1-010 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | New Prospect | New Prospect Public Elementary School | ELE | 10179 | 10451 | 10451-B01 | 289 WICE RD | DRYDEN | P8N3H6 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7933 | -92.8375 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9639547 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139547 | 9639547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9639547 | 9639547 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-011-01 | 05.1-011 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Open Roads | Open Roads Public Elementary School | ELE | 17731 | 6589 | 6589-B02 | 20 DAVIS ST | DRYDEN | P8N1R4 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7736 | -92.8405 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 470 | - | - | N | - | Not Required | - | 14865098 | Construction Complete | New Construction | Condition | 2011-12 | 40787 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1488565 | 1688565 | 13176533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13176533 | 14865098 | 14865098 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-011-03 | 05.1-011 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Riverview | Riverview Public Elementary School | ELE | 2000 | 6589 | 6589-B01 | 20 DAVIS ST | DRYDEN | P8N1R4 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7742 | -92.8405 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 446000 | Construction Complete | Demolition | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446000 | 446000 | 446000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-012-01 | 05.1-012 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Sioux North | Sioux North Public Secondary School | SEC | 24468 | 10450 | 10450-B02 | 86 THIRD AVE N | SIOUX LOOKOUT | P8T1A9 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.1095 | -91.9115 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 513 | - | - | N | - | Approved | 42916 | 28866492 | Construction Complete | New Construction | Condition | 2018-19 | 43344 | 0 | 0 | 0 | 2316232 | 0 | 0 | 0 | 0 | 0 | 527024 | 0 | 2078332 | 0 | 150000 | 0 | 5071588 | 0 | 0 | 0 | 0 | 23794904 | 0 | 0 | 0 | 0 | 0 | 23794904 | 28866492 | 28866492 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 23794904
05.1-012-02 | 05.1-012 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Sioux North | Sioux North Public Secondary School | SEC | 24468 | 10450 | 10450-L02 | 86 THIRD AVE N | SIOUX LOOKOUT | P8T1A9 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.1095 | -91.9115 | 42296 | 2015-16 | 2015-16 | 42296 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42296 | 936833 | Construction Complete | Land Acquisition | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936833 | 0 | 0 | 0 | 0 | 0 | 0 | 936833 | 936833 | 936833 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 936833
05.1-013 | 05.1-013 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Red Lake District | Red Lake District Public Secondary School | SEC | 5610 | 8352 | 8352-B01 | 60C HWY 105 | RED LAKE | P0V2M0 | 35-14-82-406 | Red Lake | Red Lake M | Kenora District | KENORA | Northwest | North | 51.0141 | -93.8179 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6534178 | Construction Complete | Retrofit | Other | 2003-04 | 37865 | 4434178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 6534178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6534178 | 6534178 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-014 | 05.1-014 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Red Lake District | Red Lake District Public Secondary School | SEC | 5610 | 8352 | 8352-B01 | 60C HWY 105 | RED LAKE | P0V2M0 | 35-14-82-406 | Red Lake | Red Lake M | Kenora District | KENORA | Northwest | North | 51.0141 | -93.8179 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41774 | 339341 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 339341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339341 | 339341 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-016 | 05.1-016 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Sioux Lookout Access Centre | Sioux Lookout Access Centre Public Continued Education | SEC-CED | 2442 | 6874 | 6874-B01 | A-70 WELLINGTON ST | SIOUX LOOKOUT | P8T1E1 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.0935 | -91.9196 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 515774 | Construction Complete | Retrofit | Other | 2003-04 | 37865 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95774 | 515774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515774 | 515774 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-017 | 05.1-017 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Sioux Mountain | Sioux Mountain Public Elementary School | ELE | 10178 | 10450 | 10450-B01 | 89 FIRST AVE | SIOUX LOOKOUT | P8T1B5 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.1071 | -91.9099 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9115682 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 7568514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547168 | 9115682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9115682 | 9115682 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-018 | 05.1-018 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Upsala | Upsala Public Elementary School | ELE | 11286 | 12203 | 12203-B01 | 5006 HWY 17 | UPSALA | P0T2Y0 | 35-14-89-739 | Upsala | Upsala LSB | Thunder Bay District | THUNDER BAY | Northwest | North | 49.049 | -90.4716 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41774 | 52391 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 0 | 1567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50824 | 52391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52391 | 52391 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-019 | 05.1-019 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Valleyview | Valleyview Public Elementary School | ELE | 7532 | 8771 | 8771-B01 | 1529 VALLEY DR | KENORA | P9N4K3 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7831 | -94.4457 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41774 | 1518213 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 53974 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378974 | 0 | 0 | 1139239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139239 | 1518213 | 1518213 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-020 | 05.1-020 | 5.1 | 306 - DSSAB Kenora | 28045 | Keewatin-Patricia DSB | Evergreen | Evergreen Public Elementary School | ELE | 7537 | 8773 | 8773-B01 | 675 BRINKMAN RD | KENORA | P9N2R5 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7728 | -94.4724 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 15 | Y | - | Approved | 43966 | 1715836 | Construction Complete | Addition | Child Care | 2020-21 | 44287 | 0 | 909164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909164 | 0 | 0 | 0 | 0 | 0 | 0 | 806672 | 0 | 0 | 0 | 806672 | 1715836 | 1715836 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 806672
05.1-021 | 05.1-021 | 5.1 | 306 - DSSAB Kenora | 28045 | Keewatin-Patricia DSB | Keewatin | Keewatin Public Elementary School | ELE | 7538 | 8774 | 8774-B01 | 330 MILL ST | KEEWATIN | P0X1C0 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.76 | -94.561 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 44096 | 998244 | Construction Complete | Retrofit | Child Care | 2020-21 | 44286 | 0 | 496056 | 0 | 0 | 0 | 0 | 83703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579759 | 0 | 0 | 15149 | 0 | 0 | 0 | 403336 | 0 | 0 | 0 | 418485 | 998244 | 998244 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 403336
05.1-022 | 05.1-022 | 5.1 | 306 - DSSAB Kenora | 28045 | Keewatin-Patricia DSB | New Prospect | New Prospect Public Elementary School | ELE | 10179 | 10451 | 10451-B01 | 289 WICE RD | DRYDEN | P8N3H6 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7933 | -92.8375 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 31 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169358 | 0 | 0 | 0 | 169358 | 169358 | 806672 | 637314 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 169358
05.1-023 | 05.1-023 | 5.1 | 306 - DSSAB Kenora | 28045 | Keewatin-Patricia DSB | Open Roads | Open Roads Public Elementary School | ELE | 17731 | 6589 | 6589-B02 | 20 DAVIS ST | DRYDEN | P8N1R4 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7736 | -92.8405 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 42984 | 294695 | Construction Complete | Addition | Child Care | 2017-18 | 43131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361075 | 0 | 0 | 0 | 361075 | 361075 | 294695 | -66380 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 361075
05.1-024 | 05.1-024 | 5.1 | 306 - DSSAB Kenora | 28045 | Keewatin-Patricia DSB | Sioux Mountain | Sioux Mountain Public Elementary School | ELE | 10178 | 10450 | 10450-B01 | 89 FIRST AVE | SIOUX LOOKOUT | P8T1B5 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.1071 | -91.9099 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 2 | 39 | Y | 1 | Approved | 43287 | 1910008 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 806672 | 403336 | 0 | 0 | 1210008 | 1910008 | 1910008 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1210008
05.1-025 | 05.1-025 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Valleyview | Valleyview Public Elementary School | ELE | 7532 | 8771 | 8771-B01 | 1529 VALLEY DR | KENORA | P9N4K3 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7831 | -94.4457 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42443 | 1260000 | Construction Complete | Retrofit | Condition | 2016-17 | 42614 | 0 | 0 | 0 | 1140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260000 | 1260000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.1-026 | 05.1-026 | 5.1 | N/A | 28045 | Keewatin-Patricia DSB | Savant Lake | Savant Lake Public Elementary School | ELE | 25362 | 12202 | 12202-B01 | FIRST ST | SAVANT LAKE | POV2S0 | 35-14-89-000 | Thunder Bay District | Thunder Bay District | Thunder Bay District | THUNDER BAY | Northwest | North | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 95 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Condition | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750222 | 0 | 0 | 0 | 0 | 0 | 4750222 | 4750222 | 4750222 | 0 | - | No, Ministry is following up with the school board | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4750222
05.1-027 | 05.1-027 | 5.1 | 306 - DSSAB Kenora | 28045 | Keewatin-Patricia DSB | Lillian Berg | Lillian Berg Public Elementary School | ELE | 2364 | 6815 | 6815-B01 | 1 SCHOOL LANE | VERMILION BAY | P0V2V0 | 35-14-82-603 | Machin | Machin Tp | Kenora District | KENORA | Northwest | North | 49.8567 | -93.3849 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 1 | 15 | N | - | Approved | 45177 | 2175488 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 650000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 1225488 | 0 | 0 | 0 | 1225488 | 2175488 | 2175488 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1225488
05.1-028 | 05.1-028 | 5.1 | 306 - DSSAB Kenora | 28045 | Keewatin-Patricia DSB | Ignace | Ignace Public Elementary School | ELE | 9475 | 5121 | 5121-B01 | 194 DAVEY LAKE RD | IGNACE | P0T1T0 | 35-14-82-601 | Ignace | Ignace Tp | Kenora District | KENORA | Northwest | North | 49.4093 | -91.6609 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 1 | 15 | N | - | Approved | 45177 | 1917589 | Planned | Retrofit | Child Care | 2023-24 | 45174 | 50000 | 465633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515633 | 0 | 0 | 0 | 0 | 0 | 0 | 1401956 | 0 | 0 | 0 | 1401956 | 1917589 | 1917589 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1401956
05.2-001 | 05.2-001 | 5.2 | N/A | 28053 | Rainy River DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15775 | 10142 | 10142-B02 | 522 SECOND ST E | FORT FRANCES | P9A1N4 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6135 | -93.3871 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286700 | 0 | 0 | 0 | 0 | 0 | 286700 | 286700 | 0 | -286700 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 286700
05.2-002 | 05.2-002 | 5.2 | N/A | 28053 | Rainy River DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15775 | 10142 | 10142-B02 | 522 SECOND ST E | FORT FRANCES | P9A1N4 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6135 | -93.3871 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Board Wide Input Line | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12404 | 12404 | 0 | -12404 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-003-01 | 05.2-003 | 5.2 | N/A | 28053 | Rainy River DSB | Donald Young | Donald Young Public Elementary School | ELE | 9377 | 10136 | 10136-B01 | 9024 HIGHWAY 602 | EMO | P0W1E0 | 35-14-87-607 | Emo | Emo Tp | Rainy River District | RAINY RIVER | Northwest | North | 48.6308 | -93.8302 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42461 | 6832784 | Construction Complete | Retrofit | Condition | 2018-19 | 43344 | 304318 | 0 | 0 | 4394482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2133984 | 6832784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6832784 | 6832784 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-003-03 | 05.2-003 | 5.2 | N/A | 28053 | Rainy River DSB | Donald Young | Donald Young Public Elementary School | ELE | 9377 | 10136 | 10136-B01 | 9024 HIGHWAY 602 | EMO | P0W1E0 | 35-14-87-607 | Emo | Emo Tp | Rainy River District | RAINY RIVER | Northwest | North | 48.6308 | -93.8302 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 150000 | Construction Complete | Demolition | Other | 2016-17 | 42614 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7795 | 157795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157795 | 157795 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-004 | 05.2-004 | 5.2 | N/A | 28053 | Rainy River DSB | JW Walker | JW Walker Public Elementary School | ELE | 9380 | 10139 | 10139-B01 | 475 KEATING AVE | FORT FRANCES | P9A3K8 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6098 | -93.4207 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6229374 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614977 | 1614977 | 4614397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4614397 | 6229374 | 6229374 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-005 | 05.2-005 | 5.2 | N/A | 28053 | Rainy River DSB | JW Walker | JW Walker Public Elementary School | ELE | 9380 | 10139 | 10139-B01 | 475 KEATING AVE | FORT FRANCES | P9A3K8 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6098 | -93.4207 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2955907 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2955907 | 2955907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2955907 | 2955907 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-006 | 05.2-006 | 5.2 | N/A | 28053 | Rainy River DSB | JW Walker | JW Walker Public Elementary School | ELE | 9380 | 10139 | 10139-B01 | 475 KEATING AVE | FORT FRANCES | P9A3K8 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6098 | -93.4207 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1087095 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 243896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243896 | 0 | 0 | 843199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843199 | 1087095 | 1087095 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-007 | 05.2-007 | 5.2 | N/A | 28053 | Rainy River DSB | Mine Centre | Mine Centre Public Elementary School | ELE | 11676 | 12336 | 12336-B01 | 123 MINE CENTRE RD | MINE CENTRE | P0W1H0 | 35-14-87-000 | Rainy River District | Rainy River District | Rainy River District | RAINY RIVER | Northwest | North | 48.7594 | -92.6208 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 200 | - | - | N | - | Not Required | - | 6695151 | Construction Complete | New Construction | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6695151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6695151 | 6695151 | 6475507 | -219644 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-008 | 05.2-008 | 5.2 | N/A | 28053 | Rainy River DSB | Robert Moore | Robert Moore Public Elementary School | ELE | 11300 | 10142 | 10142-B01 | 528 SECOND ST E | FORT FRANCES | P9A1N4 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6135 | -93.3871 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 473 | - | - | N | - | Not Required | - | 14343309 | Construction Complete | New Construction | Condition | 2010-11 | 40422 | 0 | 0 | 133914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451079 | 584993 | 13758316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13758316 | 14343309 | 14343309 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
05.2-009 | 05.2-009 | 5.2 | 308 - DSSAB Rainy River | 28053 | Rainy River DSB | Rainy River | Rainy River Public Elementary and Secondary School | ELE/SEC | 25363-25364 | 20369 | 20369-B01 | 1-11 MILL AVENUE | RAINY RIVER | P0W1L0 | 35-14-87-402 | Rainy River | Rainy River T | Rainy River District | RAINY RIVER | Northwest | North | 48.7194 | -94.5617 | 42904 | 2016-17 | 2017-18 | - | - | - | 43921 | 2019-20 | 2019-20 | 43090 | 2017-18 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | 311 | 2 | 39 | Y | 1 | Approved | 45044 | 30173882 | Under Construction | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 304509 | 4386727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4691236 | 0 | 0 | 0 | 0 | 21950513 | 0 | 2725460 | 806673 | 0 | 0 | 25482646 | 30173882 | 30173882 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 25482646
05.2-010 | 05.2-010 | 5.2 | 308 - DSSAB Rainy River | 28053 | Rainy River DSB | Donald Young | Donald Young Public Elementary School | ELE | 9377 | 10136 | 10136-B01 | 9024 HIGHWAY 602 | EMO | P0W1E0 | 35-14-87-607 | Emo | Emo Tp | Rainy River District | RAINY RIVER | Northwest | North | 48.6308 | -93.8302 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44006 | 3016680 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 0 | 28799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28799 | 0 | 0 | 0 | 0 | 0 | 0 | 2987881 | 0 | 0 | 0 | 2987881 | 3016680 | 3016680 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2987881
05.2-012 | 05.2-012 | 5.2 | 308 - DSSAB Rainy River | 28053 | Rainy River DSB | Robert Moore | Robert Moore Public Elementary School | ELE | 11300 | 10142 | 10142-B01 | 528 SECOND ST E | FORT FRANCES | P9A1N4 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6135 | -93.3871 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43727 | 1210009 | Construction Complete | Addition | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210009 | 0 | 0 | 0 | 1210009 | 1210009 | 1210009 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1210009
05.2-013 | 05.2-013 | 5.2 | 308 - DSSAB Rainy River | 28053 | Rainy River DSB | Atikokan | Atikokan Public Elementary and Secondary School | ELE/SEC | 9390-9381 | 5122 | 5122-B01 | 324 MERCURY AVE | ATIKOKAN | P0T1C0 | 35-14-87-602 | Atikokan | Atikokan Tp | Rainy River District | RAINY RIVER | Northwest | North | 48.7625 | -91.6124 | 43131 | 2017-18 | 2017-18 | - | - | - | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 354 | 3 | 49 | Y | 1 | Approved | 43993 | 30949076 | Under Construction | Addition | Consolidation | 2022-23 | 44805 | 1474764 | 5024797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6499561 | 0 | 0 | 0 | 0 | 21021155 | 0 | 2571270 | 857090 | 0 | 0 | 24449515 | 30949076 | 30949076 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 24449515
05.2-014 | 02-033 | 5.2 | N/A | 28053 | Rainy River DSB | Nestor Falls | Nestor Falls Public Elementary School | ELE | TBD | TBD | TBD | TBD | KEEWATIN | P0X1K0 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Planned | - | - | Planned | New Construction | Condition | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2638903 | 0 | 0 | 0 | 0 | 0 | 2638903 | 2638903 | 2638903 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2638903
06.1-001 | 06.1-001 | 6.1 | N/A | 28061 | Lakehead DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16129 | 18104 | 18104-B01 | 2135 SILLS ST | THUNDER BAY | P7E5T2 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3821 | -89.2695 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318112 | 0 | 0 | 0 | 0 | 0 | 318112 | 318112 | 0 | -318112 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 318112
06.1-002 | 06.1-002 | 6.1 | N/A | 28061 | Lakehead DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16129 | 18104 | 18104-B01 | 2135 SILLS ST | THUNDER BAY | P7E5T2 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3821 | -89.2695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4688922 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688923 | 4688923 | 4688923 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.1-003 | 06.1-003 | 6.1 | N/A | 28061 | Lakehead DSB | Bernier-Stokes | Bernier-Stokes Facility Holding | HFA | 11284 | 12195 | 12195-B01 | 3 MAHEEGAN DR | COLLINS | P0V1M0 | 35-14-89-000 | Thunder Bay District | Thunder Bay District | Thunder Bay District | THUNDER BAY | Northwest | North | 50.2952 | -89.4464 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 374698 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374698 | 374698 | 374698 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.1-008 | 06.1-008 | 6.1 | 309 - DSSAB Thunder Bay | 28061 | Lakehead DSB | Kingsway Park | Kingsway Park Public Elementary School | ELE | 7563 | 8793 | 8793-B02 | 315 EMPIRE AVE | THUNDER BAY | P7E4R9 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3721 | -89.2667 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | 101 | 3 | 49 | N | - | Approved | 42828 | 6015680 | Construction Complete | Addition | Consolidation | 2018-19 | 43466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 963854 | 0 | 3124117 | 0 | 1927709 | 0 | 0 | 0 | 6015680 | 6015680 | 6015680 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5051826
06.1-009 | 06.1-009 | 6.1 | N/A | 28061 | Lakehead DSB | Superior | Superior Public Secondary School | SEC | 11101 | 12362 | 12362-B01 | 333 HIGH ST N | THUNDER BAY | P7A5S3 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4495 | -89.2275 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 31836503 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 1848023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848023 | 29988480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29988480 | 31836503 | 31836503 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.1-010 | 06.1-010 | 6.1 | N/A | 28061 | Lakehead DSB | Woodcrest | Woodcrest Public Elementary School | ELE | 11017 | 12146 | 12146-B01 | 867 WOODCREST RD | THUNDER BAY | P7G0A3 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4508 | -89.2856 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11195679 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 4025984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7169695 | 11195679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11195679 | 11195679 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.1-011 | 06.1-011 | 6.1 | N/A | 28061 | Lakehead DSB | Woodcrest | Woodcrest Public Elementary School | ELE | 11017 | 12146 | 12146-B01 | 867 WOODCREST RD | THUNDER BAY | P7G0A3 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4508 | -89.2856 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 98 | - | - | N | - | Not Required | - | 1678475 | Construction Complete | Addition | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 1628475 | 0 | 0 | 0 | 0 | 0 | 1678475 | 1678475 | 1678475 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1628475
06.1-012-01 | 06.1-012 | 6.1 | 309 - DSSAB Thunder Bay | 28061 | Lakehead DSB | École Elsie MacGill | École Elsie MacGill Public Elementary School | ELE | 24675 | 5228 | 5228-B02 | 130 CHURCHILL DR W | THUNDER BAY | P7C1V5 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3884 | -89.281 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 745 | 3 | 49 | Y | - | Approved | 43206 | 32180790 | Construction Complete | New Construction | Consolidation | 2020-21 | 44075 | 0 | 0 | 4000000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200000 | 0 | 0 | 2016682 | 0 | 23630918 | 0 | 2333190 | 0 | 0 | 0 | 27980790 | 32180790 | 32180790 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 25964108
06.1-012-03 | 06.1-012 | 6.1 | N/A | 28061 | Lakehead DSB | Sir Winston Churchill | Sir Winston Churchill Public Secondary School | SEC | 7567 | 5228 | 5228-B01 | 130 CHURCHILL DR W | THUNDER BAY | P7C1V5 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.389 | -89.2827 | 43206 | 2017-18 | 2018-19 | - | - | - | 43206 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43206 | 3491187 | Construction Complete | Demolition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3491187 | 0 | 0 | 0 | 0 | 0 | 3491187 | 3491187 | 3491187 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3491187
06.1-013 | 06.1-013 | 6.1 | N/A | 28061 | Lakehead DSB | Westgate | Westgate Public Secondary School | SEC | 7572 | 8802 | 8802-B01 | 707 JAMES ST S | THUNDER BAY | P7E2V9 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3732 | -89.291 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 79 | - | - | N | - | Approved | 43180 | 7164119 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 2414444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2414444 | 0 | 0 | 0 | 0 | 4749675 | 0 | 0 | 0 | 0 | 0 | 4749675 | 7164119 | 7164119 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4749675
06.2-001 | 06.2-001 | 6.2 | N/A | 28070 | Superior Greenstone DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16161 | 5013 | 5013-B02 | 12 HEMLO DR | MARATHON | P0T2E0 | 35-14-89-403 | Marathon | Marathon T | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7179 | -86.372 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-002 | 06.2-002 | 6.2 | N/A | 28070 | Superior Greenstone DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16161 | 5013 | 5013-B02 | 12 HEMLO DR | MARATHON | P0T2E0 | 35-14-89-403 | Marathon | Marathon T | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7179 | -86.372 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 61230 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59615 | 59615 | 61230 | 1615 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-004-01 | 06.2-004 | 6.2 | N/A | 28070 | Superior Greenstone DSB | BA Parker | BA Parker Public Elementary School | ELE | 17408 | 8223 | 8223-B01 | 500 SECOND ST W | GERALDTON | P0T1M0 | 35-14-89-404 | Greenstone | Greenstone M | Thunder Bay District | THUNDER BAY | Northwest | North | 49.7217 | -86.9554 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5505422 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715000 | 4790422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4790422 | 5505422 | 5505422 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-004-03 | 06.2-004 | 6.2 | N/A | 28070 | Superior Greenstone DSB | BA Parker | BA Parker Land Holding | HLA | 896 | 8223 | 8223-B0- | 501 HOGARTH AVE W | GERALDTON | P0T1M0 | 35-14-89-404 | Greenstone | Greenstone M | Thunder Bay District | THUNDER BAY | Northwest | North | 49.7221 | -86.9561 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 525425 | Construction Complete | Demolition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525425 | 525425 | 525425 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-005 | 06.2-005 | 6.2 | N/A | 28070 | Superior Greenstone DSB | Geraldton | Geraldton Public Secondary School | SEC | 5388 | 8223 | 8223-B01 | 500 SECOND ST W | GERALDTON | P0T1M0 | 35-14-89-404 | Greenstone | Greenstone M | Thunder Bay District | THUNDER BAY | Northwest | North | 49.7219 | -86.9538 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 156667 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 156667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156667 | 156667 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-007-01 | 06.2-007 | 6.2 | N/A | 28070 | Superior Greenstone DSB | Manitouwadge | Manitouwadge Public Secondary School | SEC | 9319 | 11050 | 11050-B01 | 200 MANITOU RD W | MANITOUWADGE | P0T2C0 | 35-14-89-614 | Manitouwadge | Manitouwadge Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 49.1175 | -85.8419 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6704488 | Construction Complete | New Construction | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495202 | 2495202 | 4209286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4209286 | 6704488 | 6704488 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-007-03 | 06.2-007 | 6.2 | N/A | 28070 | Superior Greenstone DSB | 1 Ohsweken Drive Site | 1 Ohsweken Drive Site Land Holding | HLA | 5504 | 5222 | 5222-B0- | 1 OHSWEKEN DR | MANITOUWADGE | P0T2C0 | 35-14-89-614 | Manitouwadge | Manitouwadge Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 49.13 | -85.84 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 399565 | Construction Complete | Demolition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399565 | 399565 | 399565 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-008 | 06.2-008 | 6.2 | N/A | 28070 | Superior Greenstone DSB | Marathon | Marathon Public Secondary School | SEC | 5507 | 5013 | 5013-B01 | 14 HEMLO DR | MARATHON | P0T2E0 | 35-14-89-403 | Marathon | Marathon T | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7179 | -86.372 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 156666 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 156666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156666 | 156666 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-009 | 06.2-009 | 6.2 | N/A | 28070 | Superior Greenstone DSB | Nipigon Red Rock District | Nipigon Red Rock District Public Secondary School | SEC | 5542 | 8315 | 8315-B01 | 20 FROST ST | RED ROCK | P0T2P0 | 35-14-89-617 | Red Rock | Red Rock Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.9378 | -88.2602 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 156667 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 156667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156667 | 156667 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
06.2-010 | 06.2-010 | 6.2 | 309 - DSSAB Thunder Bay | 28070 | Superior Greenstone DSB | BA Parker | BA Parker Public Elementary School | ELE | 17408 | 8223 | 8223-B01 | 500 SECOND ST W | GERALDTON | P0T1M0 | 35-14-89-404 | Greenstone | Greenstone M | Thunder Bay District | THUNDER BAY | Northwest | North | 49.7217 | -86.9554 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | Y | 1 | Approved | 43980 | 5206495 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 195771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195771 | 0 | 0 | 0 | 0 | 0 | 0 | 4204052 | 806672 | 0 | 0 | 5010724 | 5206495 | 5206495 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 5010724
06.2-011 | 06.2-011 | 6.2 | N/A | 28070 | Superior Greenstone DSB | Geraldton | Geraldton Public Secondary School | SEC | 5388 | 8223 | 8223-B01 | 500 SECOND ST W | GERALDTON | P0T1M0 | 35-14-89-404 | Greenstone | Greenstone M | Thunder Bay District | THUNDER BAY | Northwest | North | 49.7219 | -86.9538 | 43796 | 2019-20 | 2019-20 | - | - | - | 43796 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43980 | 5034654 | Construction Complete | Retrofit | Condition | 2021-22 | 44440 | 2161023 | 1860121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4021144 | 0 | 0 | 0 | 0 | 1013510 | 0 | 0 | 0 | 0 | 0 | 1013510 | 5034654 | 5034654 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1013510
07-001 | 07-001 | 7 | N/A | 66001 | Bluewater DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 10805 | 12045 | 12045-B01 | 351 1ST AVE N RR 2 | CHESLEY | N0G1L0 | 35-15-41-621 | Arran-Elderslie | Arran-Elderslie M | Bruce Co | BRUCE | Southwest | South | 44.3102 | -81.096 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-002 | 07-002 | 7 | N/A | 66001 | Bluewater DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 10805 | 12045 | 12045-B01 | 351 1ST AVE N RR 2 | CHESLEY | N0G1L0 | 35-15-41-621 | Arran-Elderslie | Arran-Elderslie M | Bruce Co | BRUCE | Southwest | South | 44.3102 | -81.096 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6862927 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6862927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6862927 | 6862927 | 6862927 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-003 | 07-003 | 7 | N/A | 66001 | Bluewater DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 10805 | 12045 | 12045-B01 | 351 1ST AVE N RR 2 | CHESLEY | N0G1L0 | 35-15-41-621 | Arran-Elderslie | Arran-Elderslie M | Bruce Co | BRUCE | Southwest | South | 44.3102 | -81.096 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 443039 | Construction Complete | Other | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443039 | 443039 | 443039 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-004 | 07-004 | 7 | N/A | 66001 | Bluewater DSB | Alexandra Community | Alexandra Community Public Elementary School | ELE | 11297 | 5328 | 5328-B02 | 1556 8TH AVE E | OWEN SOUND | N4K3B6 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.573 | -80.9294 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6455905 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 559000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256195 | 815195 | 5640710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5640710 | 6455905 | 6455905 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-005 | 07-005 | 7 | N/A | 66001 | Bluewater DSB | BDSB Chelsey Head Office | Administrative Office | OFF-ADM | 10805 | 12045 | 12045-B01 | 351 1ST AVE N RR 2 | CHESLEY | N0G1L0 | 35-15-41-621 | Arran-Elderslie | Arran-Elderslie M | Bruce Co | BRUCE | Southwest | South | 44.3102 | -81.096 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9480000 | Construction Complete | Retrofit | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9480000 | 9480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9480000 | 9480000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-007 | 07-007 | 7 | N/A | 66001 | Bluewater DSB | Chesley District | Chesley District Public Secondary School | SEC | 6083 | 8562 | 8562-B01 | 231 4TH AVE SE | CHESLEY | N0G1L0 | 35-15-41-621 | Arran-Elderslie | Arran-Elderslie M | Bruce Co | BRUCE | Southwest | South | 44.2945 | -81.0894 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 98 | - | - | N | - | Not Required | - | 2417264 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258906 | 0 | 1158358 | 0 | 0 | 0 | 0 | 0 | 2417264 | 2417264 | 2417264 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1158358
07-008 | 07-008 | 7 | N/A | 66001 | Bluewater DSB | Dawnview | Dawnview Public Elementary School | ELE | 565 | 5669 | 5669-B01 | 149 12TH AVE | HANOVER | N4N2S8 | 35-15-47-402 | Hanover | Hanover T | Grey Co | GREY | Southwest | South | 44.1446 | -81.021 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 45446 | Construction Complete | Retrofit | Other | 2003-04 | 37865 | 45446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45446 | 45446 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-009 | 07-009 | 7 | N/A | 66001 | Bluewater DSB | Dawnview | Dawnview Public Elementary School | ELE | 565 | 5669 | 5669-B01 | 149 12TH AVE | HANOVER | N4N2S8 | 35-15-47-402 | Hanover | Hanover T | Grey Co | GREY | Southwest | South | 44.1446 | -81.021 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1488654 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480920 | 480920 | 0 | 0 | 1007734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007734 | 1488654 | 1488654 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-011 | 07-011 | 7 | N/A | 66001 | Bluewater DSB | Dundalk Highpoint | Dundalk Highpoint Public Elementary School | ELE | 9315 | 10119 | 10119-B01 | 351 MAIN ST W | DUNDALK | N0C1B0 | 35-15-47-621 | Southgate | Southgate Tp | Grey Co | GREY | Southwest | South | 44.1639 | -80.3986 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2644337 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472789 | 472789 | 2171548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2171548 | 2644337 | 2644337 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-013 | 07-013 | 7 | N/A | 66001 | Bluewater DSB | Egremont Community | Egremont Community Public Elementary School | ELE | 710 | 5768 | 5768-B01 | 392141 GREY ROAD 109 RR 2 | HOLSTEIN | N0G2A0 | 35-15-47-621 | Southgate | Southgate Tp | Grey Co | GREY | Southwest | South | 44.0677 | -80.7605 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9277 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9277 | 9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9277 | 9277 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-016 | 07-016 | 7 | N/A | 66001 | Bluewater DSB | Grey Highlands | Grey Highlands Public Secondary School | SEC | 5404 | 8236 | 8236-B01 | 100 TORONTO RD S | FLESHERTON | N0C1E0 | 35-15-47-623 | Grey Highlands | Grey Highlands M | Grey Co | GREY | Southwest | South | 44.2571 | -80.5431 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4889839 | Construction Complete | Addition | Other | 2005-06 | 38596 | 1368908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502588 | 1871496 | 3018343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3018343 | 4889839 | 4889839 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-017 | 07-017 | 7 | N/A | 66001 | Bluewater DSB | Hanover Heights | Hanover Heights Public Elementary School | ELE | 11011 | 6052 | 6052-B01 | 524 13TH ST | HANOVER | N4N1Y4 | 35-15-47-402 | Hanover | Hanover T | Grey Co | GREY | Southwest | South | 44.1563 | -81.0223 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8519631 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1671868 | 1671868 | 6847763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6847763 | 8519631 | 8519631 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-019 | 07-019 | 7 | N/A | 66001 | Bluewater DSB | Holland-Chatsworth Central | Holland-Chatsworth Central Public Elementary School | ELE | 1099 | 6011 | 6011-B01 | 777346 10 HWY RR 3 | HOLLAND CENTRE | N0H1R0 | 35-15-47-619 | Chatsworth | Chatsworth Tp | Grey Co | GREY | Southwest | South | 44.4127 | -80.8278 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 42916 | Construction Complete | Retrofit | Other | 2003-04 | 37865 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 42916 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-021 | 07-021 | 7 | N/A | 66001 | Bluewater DSB | John Diefenbaker | John Diefenbaker Public Secondary School | SEC | 5411 | 8241 | 8241-L01 | 181 7TH ST | HANOVER | N4N1G7 | 35-15-47-402 | Hanover | Hanover T | Grey Co | GREY | Southwest | South | 44.1478 | -81.0309 | 41183 | 2012-13 | 2012-13 | 41183 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1040181 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10073 | 10073 | 0 | 0 | 0 | 1030108 | 0 | 0 | 0 | 0 | 0 | 0 | 1030108 | 1040181 | 1040181 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1030108
07-022 | 07-022 | 7 | N/A | 66001 | Bluewater DSB | John Diefenbaker | John Diefenbaker Public Secondary School | SEC | 24616 | 19622 | 19622-B01 | 201 18TH AVE | HANOVER | N4N3S5 | 35-15-47-402 | Hanover | Hanover T | Grey Co | GREY | Southwest | South | 44.1476 | -81.0123 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 737 | - | - | N | - | Approved | 42864 | 22934975 | Construction Complete | New Construction | Consolidation | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21734975 | 0 | 0 | 0 | 0 | 0 | 21734975 | 21734975 | 21734975 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 21734975
07-023 | 07-023 | 7 | N/A | 66001 | Bluewater DSB | Keppel-Sarawak | Keppel-Sarawak Public Elementary School | ELE | 1255 | 6096 | 6096-B01 | 937 24TH ST W RR 2 | OWEN SOUND | N4K5N4 | 35-15-47-622 | Georgian Bluffs | Georgian Bluffs Tp | Grey Co | GREY | Southwest | South | 44.589 | -80.9544 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Not Required | - | 1745694 | Construction Complete | Addition | Accommodation Pressure | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185740 | 0 | 1559954 | 0 | 0 | 0 | 0 | 0 | 1745694 | 1745694 | 1745694 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1559954
07-024 | 07-024 | 7 | N/A | 66001 | Bluewater DSB | Macphail Memorial | Macphail Memorial Public Elementary School | ELE | 10582 | 5836 | 5836-B01 | 49 CAMPBELL ST | FLESHERTON | N0C1E0 | 35-15-47-623 | Grey Highlands | Grey Highlands M | Grey Co | GREY | Southwest | South | 44.2575 | -80.5497 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8059509 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2684042 | 2684042 | 5375467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5375467 | 8059509 | 8059509 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-027-01 | 07-027 | 7 | 215 - CMSM Grey | 66001 | Bluewater DSB | Georgian Bay Community | Georgian Bay Community Public Elementary and Secondary School | ELE/SEC | 24605-24604 | 6725 | 6725-B02 | 519 ST VINCENT ST | MEAFORD | N4L1C6 | 35-15-47-406 | Meaford | Meaford M | Grey Co | GREY | Southwest | South | 44.5951 | -80.5836 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | 43073 | 2017-18 | 2017-18 | - | - | - | 1033 | - | - | N | 1 | Approved | 44385 | 27577965 | Construction Complete | New Construction | Consolidation | 2021-22 | 44440 | 0 | 0 | 636165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636165 | 0 | 0 | 1297496 | 0 | 25114925 | 0 | 0 | 529379 | 0 | 0 | 26941800 | 27577965 | 27577965 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 25644304
07-027-02 | 07-027 | 7 | N/A | 66001 | Bluewater DSB | Georgian Bay Community | Georgian Bay Community Public Elementary and Secondary School | ELE/SEC | 24605-24604 | 6725 | 6725-L02 | 519 ST VINCENT ST | MEAFORD | N4L1C6 | 35-15-47-406 | Meaford | Meaford M | Grey Co | GREY | Southwest | South | 44.5951 | -80.5836 | 43402 | 2018-19 | 2018-19 | 43402 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44385 | 2053830 | Construction Complete | Land Acquisition | Consolidation | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053830 | 0 | 0 | 0 | 0 | 0 | 0 | 2053830 | 2053830 | 2053830 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2053830
07-029 | 07-029 | 7 | N/A | 66001 | Bluewater DSB | Osprey Central | Osprey Central Public Elementary School | ELE | 385 | 5548 | 5548-B01 | 408053 GREY ROAD 4 | MAXWELL | N0C1J0 | 35-15-47-623 | Grey Highlands | Grey Highlands M | Grey Co | GREY | Southwest | South | 44.3111 | -80.3907 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 46779 | Construction Complete | Retrofit | Other | 2003-04 | 37865 | 46779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46779 | 46779 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-032 | 07-032 | 7 | N/A | 66001 | Bluewater DSB | Peninsula Shores District | Peninsula Shores District Public Secondary School | SEC | 10581 | 11292 | 11292-B01 | 115 GEORGE ST | WIARTON | N0H2T0 | 35-15-41-407 | South Bruce Peninsula | The South Bruce Peninsula T | Bruce Co | BRUCE | Southwest | South | 44.7407 | -81.1508 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16282637 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1698104 | 1698104 | 14584533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14584533 | 16282637 | 16282637 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-034 | 07-034 | 7 | N/A | 66001 | Bluewater DSB | Ripley Huron Community | Ripley Huron Community Public Elementary School | ELE | 9373 | 10132 | 10132-B01 | 2 QUEEN ST | RIPLEY | N0G2R0 | 35-15-41-624 | Huron-Kinloss | Huron-Kinloss Tp | Bruce Co | BRUCE | Southwest | South | 44.0732 | -81.5823 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2776685 | Construction Complete | Addition | Other | 2001-02 | 37135 | 2776685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2776685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2776685 | 2776685 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-035 | 07-035 | 7 | N/A | 66001 | Bluewater DSB | Saugeen District | Saugeen District Public Secondary School | SEC | 5626 | 8362 | 8362-B01 | 780 GUSTAVUS ST | PORT ELGIN | N0H2C4 | 35-15-41-408 | Saugeen Shores | Saugeen Shores T | Bruce Co | BRUCE | Southwest | South | 44.4329 | -81.3834 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9485136 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 1641074 | 0 | 823796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7020266 | 9485136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9485136 | 9485136 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-036 | 07-036 | 7 | N/A | 66001 | Bluewater DSB | Spruce Ridge | Spruce Ridge Public Elementary School | ELE | 653 | 5729 | 5729-B01 | 239 KINCARDINE ST | DURHAM | N0G1R0 | 35-15-47-624 | West Grey | West Grey M | Grey Co | GREY | Southwest | South | 44.1744 | -80.8128 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 87601 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87601 | 87601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87601 | 87601 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-037 | 07-037 | 7 | N/A | 66001 | Bluewater DSB | Spruce Ridge | Spruce Ridge Public Elementary School | ELE | 653 | 5729 | 5729-B01 | 239 KINCARDINE ST | DURHAM | N0G1R0 | 35-15-47-624 | West Grey | West Grey M | Grey Co | GREY | Southwest | South | 44.1744 | -80.8128 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5772568 | Construction Complete | Addition | Other | 2004-05 | 38231 | 119476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2567652 | 2687128 | 3085440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3085440 | 5772568 | 5772568 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-040 | 07-040 | 7 | N/A | 66001 | Bluewater DSB | Sydenham Community | Sydenham Community Public Elementary School | ELE | 2272 | 6755 | 6755-B01 | 1130 8TH ST E | OWEN SOUND | N4K1M7 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5671 | -80.921 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2231495 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 486000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486000 | 840483 | 0 | 905012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1745495 | 2231495 | 2231495 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-041 | 07-041 | 7 | N/A | 66001 | Bluewater DSB | Walkerton District Community | Walkerton District Community Public Elementary and Secondary School | ELE/SEC | 11301 | 8414 | 8414-B02 | 1320 YONGE ST S | WALKERTON | N0G2V0 | 35-15-41-622 | Brockton | Brockton M | Bruce Co | BRUCE | Southwest | South | 44.1173 | -81.1476 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 21146648 | Construction Complete | New Construction | Condition | 2012-13 | 41153 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36662 | 236662 | 20457480 | 0 | 452506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20909986 | 21146648 | 21146648 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-042-01 | 07-042 | 7 | 215 - CMSM Grey | 66001 | Bluewater DSB | East Ridge Community | East Ridge Community Public Elementary School | ELE | 24614 | 5124 | 5124-B01 | 1550 8TH ST E | OWEN SOUND | N4K0A2 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5671 | -80.9161 | 42685 | 2016-17 | 2016-17 | - | - | - | 42685 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 4 | 60 | Y | 2 | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946841 | 0 | 2077181 | 1038591 | 0 | 0 | 5062613 | 5062613 | 5062613 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5062613
07-042-03 | 07-042 | 7 | N/A | 66001 | Bluewater DSB | Owen Sound | Owen Sound Facility Holding | HFA | 5918 | 5124 | 5124-B01 | 1550 8TH ST E | OWEN SOUND | N4K0A2 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5679 | -80.9168 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1075000 | Construction Complete | Demolition | Other | 2003-04 | 37865 | 1075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075000 | 1075000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
07-043 | 07-043 | 7 | N/A | 66001 | Bluewater DSB | Owen Sound District | Owen Sound District Public Secondary School | SEC | 5740 | 8425 | 8425-B01 | 750 9TH ST W | OWEN SOUND | N4K3P6 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5651 | -80.9575 | 42685 | 2016-17 | 2016-17 | - | - | - | 42685 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6728750 | 0 | 0 | 0 | 0 | 0 | 6728750 | 6728750 | 6728750 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6728750
07-044 | 07-044 | 7 | N/A | 66001 | Bluewater DSB | Bruce Peninsula District | Bruce Peninsula District Public Elementary and Secondary School | ELE/SEC | 273 | 5105 | 5105-B01 | 5 MOORE ST RR 3 | LIONS HEAD | N0H1W0 | 35-15-41-623 | Northern Bruce Peninsula | Northern Bruce Peninsula M | Bruce Co | BRUCE | Southwest | South | 44.9851 | -81.2508 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326800 | 0 | 0 | 0 | 0 | 0 | 326800 | 326800 | 326800 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 326800
07-045 | 07-045 | 7 | 213 - CMSM Bruce | 66001 | Bluewater DSB | Amabel-Sauble Community | Amabel-Sauble Community Public Elementary School | ELE | 54 | 5331 | 5331-B01 | 555 SAUBLE FALLS PKY | SAUBLE BEACH | N0H2G0 | 35-15-41-407 | South Bruce Peninsula | The South Bruce Peninsula T | Bruce Co | BRUCE | Southwest | South | 44.6505 | -81.2568 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529380 | 0 | 0 | 0 | 529380 | 529380 | 514510 | -14870 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 529380
07-046 | 07-046 | 7 | 215 - CMSM Grey | 66001 | Bluewater DSB | Spruce Ridge | Spruce Ridge Public Elementary School | ELE | 653 | 5729 | 5729-B01 | 239 KINCARDINE ST | DURHAM | N0G1R0 | 35-15-47-624 | West Grey | West Grey M | Grey Co | GREY | Southwest | South | 44.1744 | -80.8128 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44356 | 2163227 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2163227 | 0 | 0 | 0 | 2163227 | 2163227 | 2163227 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2163227
07-047-01 | 07-047 | 7 | 215 - CMSM Grey | 66001 | Bluewater DSB | Beavercrest Community | Beavercrest Community Public Elementary School | ELE | 24793 | 19800 | 19800-B01 | TBD | GREY HIGHLANDS | TBD | 35-15-47-623 | Grey Highlands | Grey Highlands M | Grey Co | GREY | Southwest | South | TBD | TBD | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 236 | 2 | 39 | Y | 2 | Approved | 45076 | 19644390 | Planned | New Construction | Condition | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16672407 | 0 | 1913225 | 855555 | 0 | 0 | 19441187 | 19441187 | 19644390 | 203203 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19441187
07-047-02 | 07-047 | 7 | N/A | 66001 | Bluewater DSB | Beavercrest Community | Beavercrest Community Public Elementary School | ELE | 24793 | 19800 | 19800-L01 | TBD | GREY HIGHLANDS | TBD | 35-15-47-623 | Grey Highlands | Grey Highlands M | Grey Co | GREY | Southwest | South | TBD | TBD | 43837 | 2019-20 | 2019-20 | 43837 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43837 | 320254 | Construction Complete | Land Acquisition | Condition | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320254 | 0 | 0 | 0 | 0 | 0 | 0 | 320254 | 320254 | 320254 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 320254
07-048 | 07-048 | 7 | 215 - CMSM Grey | 66001 | Bluewater DSB | Egremont Community | Egremont Community Public Elementary School | ELE | 710 | 5768 | 5768-B01 | 392141 GREY ROAD 109 RR 2 | HOLSTEIN | N0G2A0 | 35-15-47-621 | Southgate | Southgate Tp | Grey Co | GREY | Southwest | South | 44.0677 | -80.7605 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | 43223 | 2017-18 | 2018-19 | - | - | - | - | 2 | 39 | Y | 2 | Approved | 44673 | 3929000 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 464005 | 236200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700205 | 0 | 0 | 0 | 0 | 0 | 0 | 1915295 | 1313500 | 0 | 0 | 3228795 | 3929000 | 3929000 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3228795
07-049 | 07-049 | 7 | 215 - CMSM Grey | 66001 | Bluewater DSB | Dundalk & Proton Community | Dundalk & Proton Community Public Elementary School | ELE | 1894 | 6519 | 6519-B01 | 251 YOUNG ST | DUNDALK | N0C1B0 | 35-15-47-621 | Southgate | Southgate Tp | Grey Co | GREY | Southwest | South | 44.165 | -80.3897 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Planned | - | 0 | Planned | Retrofit | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262500 | 0 | 0 | 262500 | 262500 | 262500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 262500
07-050 | 07-050 | 7 | N/A | 66001 | Bluewater DSB | Kincardine | Kincardine Public Secondary School | SEC | 25483-25484 | 20489 | 20489-B01 | TBD | KINCARDINE | TBD | 35-15-41-625 | Kincardine | Kincardine M | Bruce Co | BRUCE | Southwest | South | TBD | TBD | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 881 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26450989 | 0 | 0 | 0 | 0 | 0 | 26450989 | 26450989 | 26450989 | 0 | - | No, Site to be acquired. Sign installation planned for August 1, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 26450989
07-051 | 07-051 | 7 | 213 - CMSM Bruce | 66001 | Bluewater DSB | St. Edmunds | St. Edmunds Public Elementary School | ELE | 2214 | 6723 | 6723-B01 | 21 CENTENNIAL DR | TOBERMORY | N0H2R0 | 35-15-41-623 | Northern Bruce Peninsula | Northern Bruce Peninsula M | Bruce Co | BRUCE | Southwest | South | 45.2446 | -81.6506 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | 39 | N | - | Approved | 44918 | 2003980 | Planned | Retrofit | Child Care | 2022-23 | 44805 | 0 | 1064225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259398 | 1323623 | 0 | 0 | 0 | 0 | 0 | 0 | 680357 | 0 | 0 | 0 | 680357 | 2003980 | 2003980 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 680357
08-001 | 08-001 | 8 | N/A | 66010 | Avon Maitland DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 11311 | 8160 | 8160-B01 | 165 PRINCESS ST E | CLINTON | N0M1L0 | 35-15-52-617 | Central Huron | Central Huron M | Huron Co | HURON | Southwest | South | 43.6168 | -81.5337 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-002 | 08-002 | 8 | N/A | 66010 | Avon Maitland DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 11311 | 8160 | 8160-B01 | 165 PRINCESS ST E | CLINTON | N0M1L0 | 35-15-52-617 | Central Huron | Central Huron M | Huron Co | HURON | Southwest | South | 43.6168 | -81.5337 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5988067 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7381598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7381598 | 7381598 | 5988067 | -1393531 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-003 | 08-003 | 8 | N/A | 66010 | Avon Maitland DSB | Avon | Avon Public Elementary School | ELE | 1284 | 6116 | 6116-B01 | 31 HUNTINGDON AVE | STRATFORD | N5A6N7 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3744 | -80.9979 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1238005 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 1238005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238005 | 1238005 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-005 | 08-005 | 8 | N/A | 66010 | Avon Maitland DSB | Bedford | Bedford Public Elementary School | ELE | 161 | 5401 | 5401-B01 | 59 BEDFORD DR | STRATFORD | N5A5J7 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3824 | -80.9722 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 800422 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800422 | 800422 | 800422 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-006 | 08-006 | 8 | N/A | 66010 | Avon Maitland DSB | Bedford | Bedford Public Elementary School | ELE | 161 | 5401 | 5401-B01 | 59 BEDFORD DR | STRATFORD | N5A5J7 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3824 | -80.9722 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1266390 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 447091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447091 | 0 | 0 | 819299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 819299 | 1266390 | 1266390 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-007 | 08-007 | 8 | N/A | 66010 | Avon Maitland DSB | Bluewater Coast | Bluewater Coast Public Elementary School | ELE | 1048 | 5982 | 5982-B01 | 85 YORK ST | HENSALL | N0M1X0 | 35-15-52-406 | Bluewater | Bluewater M | Huron Co | HURON | Southwest | South | 43.4315 | -81.5015 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1010553 | Construction Complete | Addition | Other | 2011-12 | 40787 | 532527 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562527 | 0 | 0 | 448026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448026 | 1010553 | 1010553 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-012 | 08-012 | 8 | N/A | 66010 | Avon Maitland DSB | Goderich | Goderich Public Elementary School | ELE | 2013 | 6598 | 6598-B01 | 125 BLAKE ST W | GODERICH | N7A1Z1 | 35-15-52-403 | Goderich | Goderich T | Huron Co | HURON | Southwest | South | 43.7347 | -81.7164 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3008849 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854881 | 854881 | 2153968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2153968 | 3008849 | 3008849 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-014 | 08-014 | 8 | N/A | 66010 | Avon Maitland DSB | Goderich District | Goderich District Public Secondary School | SEC | 5398 | 8231 | 8231-B01 | 260 SOUTH ST | GODERICH | N7A3M5 | 35-15-52-403 | Goderich | Goderich T | Huron Co | HURON | Southwest | South | 43.7341 | -81.7112 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 905101 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 180160 | 0 | 0 | 724941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905101 | 905101 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-016 | 08-016 | 8 | N/A | 66010 | Avon Maitland DSB | Hullett Central | Hullett Central Public Elementary School | ELE | 1119 | 6025 | 6025-B01 | 269 KING ST | LONDESBOROUGH | N0M2H0 | 35-15-52-617 | Central Huron | Central Huron M | Huron Co | HURON | Southwest | South | 43.6976 | -81.4775 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1056814 | Construction Complete | Addition | Other | 2013-14 | 41518 | 174045 | 0 | 0 | 882769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056814 | 1056814 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-018 | 08-018 | 8 | N/A | 66010 | Avon Maitland DSB | Listowel District | Listowel District Public Secondary School | SEC | 5491 | 8285 | 8285-B01 | 155 MAITLAND AVE S | LISTOWEL | N4W2M4 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.7275 | -80.9467 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 743461 | Construction Complete | Retrofit | Other | 2004-05 | 38231 | 0 | 0 | 743461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743461 | 743461 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-019 | 08-019 | 8 | N/A | 66010 | Avon Maitland DSB | Listowel District | Listowel District Public Secondary School | SEC | 5491 | 8285 | 8285-B01 | 155 MAITLAND AVE S | LISTOWEL | N4W2M4 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.7275 | -80.9467 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4427937 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 545361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545361 | 3882576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3882576 | 4427937 | 4427937 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-020 | 08-020 | 8 | N/A | 66010 | Avon Maitland DSB | Listowel Eastdale | Listowel Eastdale Public Elementary School | ELE | 686 | 5752 | 5752-B01 | 365 NICHOL AVE S | LISTOWEL | N4W2M3 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.7268 | -80.9496 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1419885 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642620 | 642620 | 777265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 777265 | 1419885 | 1419885 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-021 | 08-021 | 8 | N/A | 66010 | Avon Maitland DSB | Listowel Eastdale | Listowel Eastdale Public Elementary School | ELE | 686 | 5752 | 5752-B01 | 365 NICHOL AVE S | LISTOWEL | N4W2M3 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.7268 | -80.9496 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 910214 | Construction Complete | Addition | Other | 2014-15 | 41883 | 28150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28150 | 0 | 0 | 882064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882064 | 910214 | 910214 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-022 | 08-022 | 8 | N/A | 66010 | Avon Maitland DSB | Little Falls | Little Falls Public Elementary School | ELE | 13309 | 12239 | 12239-B01 | 25 LINDSAY ATKINSON DR | ST MARYS | N4X1B6 | 35-15-65-301 | St. Marys | St. Marys ST | Perth Co | PERTH | Southwest | South | 43.2511 | -81.1319 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7937636 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 614918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307273 | 922191 | 7015445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7015445 | 7937636 | 7937636 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-023 | 08-023 | 8 | N/A | 66010 | Avon Maitland DSB | Maitland River | Maitland River Public Elementary School | ELE | 11327 | 8434 | 8434-B02 | 250 JOHN ST E | WINGHAM | N0G2W0 | 35-15-52-408 | Huron East | Huron East M | Huron Co | HURON | Southwest | South | 43.8822 | -81.3033 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10698569 | Construction Complete | New Construction | Condition | 2013-14 | 41518 | 0 | 0 | 750000 | 915131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 1815131 | 7987387 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8883438 | 10698569 | 10698569 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-024 | 08-024 | 8 | N/A | 66010 | Avon Maitland DSB | Milverton | Milverton Public Elementary School | ELE | 1549 | 6295 | 6295-B01 | 68 MILL ST E | MILVERTON | N0K1M0 | 35-15-65-612 | Perth East | Perth East Tp | Perth Co | PERTH | Southwest | South | 43.5629 | -80.915 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2272721 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 1462828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1462828 | 0 | 0 | 0 | 0 | 0 | 809893 | 0 | 0 | 0 | 0 | 809893 | 2272721 | 2272721 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-026 | 08-026 | 8 | N/A | 66010 | Avon Maitland DSB | Mornington Central | Mornington Central Public Elementary School | ELE | 1566 | 6306 | 6306-B01 | 7241 ROAD 131 RR 1 | NEWTON | N0K1R0 | 35-15-65-612 | Perth East | Perth East Tp | Perth Co | PERTH | Southwest | South | 43.6147 | -80.8846 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1071941 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 555833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555833 | 0 | 0 | 516108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516108 | 1071941 | 1071941 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-028-01 | 08-028 | 8 | N/A | 66010 | Avon Maitland DSB | North Perth Westfield | North Perth Westfield Public Elementary School | ELE | 24202 | 19194 | 19194-B01 | 955 BINNING ST W | LISTOWEL | N4W0G3 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.7401 | -80.9644 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 565 | - | - | N | - | Approved | 41792 | 13301499 | Construction Complete | New Construction | Consolidation | 2016-17 | 42614 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454280 | 2004280 | 0 | 0 | 978489 | 0 | 10318730 | 0 | 0 | 0 | 0 | 0 | 11297219 | 13301499 | 13301499 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10318730
08-028-02 | 08-028 | 8 | N/A | 66010 | Avon Maitland DSB | North Perth Westfield | North Perth Westfield Public Elementary School | ELE | 24202 | 19194 | 19194-L01 | 955 BINNING ST W | LISTOWEL | N4W0G3 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.7401 | -80.9644 | 41515 | 2012-13 | 2013-14 | 41515 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41515 | 1492750 | Construction Complete | Land Acquisition | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492750 | 0 | 0 | 0 | 0 | 0 | 0 | 1492750 | 1492750 | 1492750 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1492750
08-029 | 08-029 | 8 | N/A | 66010 | Avon Maitland DSB | Romeo | Romeo Public Elementary School | ELE | 2029 | 6610 | 6610-B01 | 49 REBECCA ST | STRATFORD | N5A3P2 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3691 | -80.9779 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1121604 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847282 | 847282 | 274322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274322 | 1121604 | 1121604 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-031 | 08-031 | 8 | N/A | 66010 | Avon Maitland DSB | South Huron District | South Huron District Public Secondary School | SEC | 5665 | 8376 | 8376-B01 | 92 GIDLEY ST E | EXETER | N0M1S6 | 35-15-52-407 | South Huron | South Huron M | Huron Co | HURON | Southwest | South | 43.3495 | -81.4774 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 174 | - | - | N | - | Not Required | - | 2500000 | Construction Complete | Addition | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000 | 2500000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2500000
08-034 | 08-034 | 8 | N/A | 66010 | Avon Maitland DSB | Upper Thames | Upper Thames Public Elementary School | ELE | 2346 | 6802 | 6802-B01 | 165 FRANCES ST E RR 5 | MITCHELL | N0K1N0 | 35-15-65-614 | West Perth | West Perth M | Perth Co | PERTH | Southwest | South | 43.4736 | -81.1857 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 921952 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 90080 | 0 | 192509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282589 | 0 | 0 | 639363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639363 | 921952 | 921952 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-035 | 08-035 | 8 | N/A | 66010 | Avon Maitland DSB | Mitchell District | Mitchell District Public Secondary School | SEC | 1555 | 6298 | 6298-B01 | 95 FRANCES ST E RR 5 | MITCHELL | N0K1N0 | 35-15-65-614 | West Perth | West Perth M | Perth Co | PERTH | Southwest | South | 43.4752 | -81.1895 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42221 | 1390844 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 270095 | 0 | 1120749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1390844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1390844 | 1390844 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
08-036 | 08-036 | 8 | 210 - CMSM Stratford | 66010 | Avon Maitland DSB | Anne Hathaway | Anne Hathaway Public Elementary School | ELE | 80 | 5347 | 5347-B01 | 77 BRUCE ST | STRATFORD | N5A4A2 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3579 | -80.972 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557887 | 0 | 0 | 0 | 1557887 | 1557887 | 0 | -1557887 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1557887
08-037 | 08-037 | 8 | 217 - CMSM Huron | 66010 | Avon Maitland DSB | Exeter | Exeter Public Elementary School | ELE | 771 | 5805 | 5805-B01 | 93 VICTORIA ST E SS 1 | EXETER | N0M1S1 | 35-15-52-407 | South Huron | South Huron M | Huron Co | HURON | Southwest | South | 43.3512 | -81.4776 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43699 | 567657 | Construction Complete | Addition | Child Care | 2020-21 | 44105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567657 | 0 | 0 | 0 | 567657 | 567657 | 567657 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 567657
08-038 | 08-038 | 8 | 210 - CMSM Stratford | 66010 | Avon Maitland DSB | Sprucedale | Sprucedale Public Elementary School | ELE | 2207 | 6720 | 6720-B01 | 2215 FRASER ST | SHAKESPEARE | N0B2P0 | 35-15-65-612 | Perth East | Perth East Tp | Perth Co | PERTH | Southwest | South | 43.3681 | -80.8394 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 44515 | 714301 | Construction Complete | Addition | Child Care | 2020-21 | 44287 | 43715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43715 | 0 | 0 | 0 | 0 | 0 | 0 | 670586 | 0 | 0 | 0 | 670586 | 714301 | 714301 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 670586
08-039 | 08-039 | 8 | 210 - CMSM Stratford | 66010 | Avon Maitland DSB | Upper Thames | Upper Thames Public Elementary School | ELE | 2346 | 6802 | 6802-B01 | 165 FRANCES ST E RR 5 | MITCHELL | N0K1N0 | 35-15-65-614 | West Perth | West Perth M | Perth Co | PERTH | Southwest | South | 43.4736 | -81.1857 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43756 | 2071196 | Construction Complete | Addition | Child Care | 2020-21 | 44316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2071196 | 0 | 0 | 0 | 2071196 | 2071196 | 2071196 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2071196
08-040 | 08-040 | 8 | 210 - CMSM Stratford | 66010 | Avon Maitland DSB | Stratford Northwestern | Stratford Northwestern Public Secondary School | SEC | 5683 | 8389 | 8389-B01 | 428 FORMAN AVE | STRATFORD | N5A6R7 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3843 | -80.9931 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43756 | 1794907 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557887 | 0 | 0 | 0 | 1557887 | 1557887 | 1557887 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1557887
08-041 | 08-041 | 8 | N/A | 66010 | Avon Maitland DSB | Stratford Central | Stratford Central Public Secondary School | SEC | 5682 | 8388 | 8388-B01 | 60 ST ANDREW ST | STRATFORD | N5A1A3 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3709 | -80.9865 | 43214 | 2017-18 | 2018-19 | - | - | - | 43214 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 168 | - | - | N | - | Approved | 44601 | 7742243 | Construction Complete | Addition | Condition | 2020-21 | 44256 | 242783 | 0 | 642289 | 0 | 0 | 0 | 0 | 321884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206956 | 0 | 0 | 0 | 0 | 6535287 | 0 | 0 | 0 | 0 | 0 | 6535287 | 7742243 | 7742243 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6535287
08-042 | 08-042 | 8 | 210 - CMSM Stratford | 66010 | Avon Maitland DSB | Milverton | Milverton Public Elementary School | ELE | 1549 | 6295 | 6295-B01 | 68 MILL ST E | MILVERTON | N0K1M0 | 35-15-65-612 | Perth East | Perth East Tp | Perth Co | PERTH | Southwest | South | 43.5629 | -80.915 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | 39 | N | - | Planned | 44909 | 2841430 | Planned | Addition | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841430 | 0 | 0 | 0 | 2841430 | 2841430 | 2841430 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 2841430
08-043 | 08-043 | 8 | 210 - CMSM Stratford | 66010 | Avon Maitland DSB | Listowel Eastdale | Listowel Eastdale Public Elementary School | ELE | 686 | 5752 | 5752-B01 | 365 NICHOL AVE S | LISTOWEL | N4W2M3 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.7268 | -80.9496 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 98 | 3 | 49 | N | - | Approved | 45121 | 8775600 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6461956 | 0 | 2313644 | 0 | 0 | 0 | 8775600 | 8775600 | 8775600 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 8775600
09-001 | 09-001 | 9 | N/A | 66028 | Greater Essex County DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16109 | 18100 | 18100-B01 | 451 PARK ST W | WINDSOR | N9A6K1 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3146 | -83.043 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1661390 | 0 | 0 | 0 | 0 | 0 | 1661390 | 1661390 | 0 | -1661390 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 1661390
09-002 | 09-002 | 9 | N/A | 66028 | Greater Essex County DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16109 | 18100 | 18100-B01 | 451 PARK ST W | WINDSOR | N9A6K1 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3146 | -83.043 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 23721438 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26075509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26075509 | 26075509 | 27511438 | 1435929 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-003 | 09-003 | 9 | N/A | 66028 | Greater Essex County DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 16109 | 18100 | 18100-B01 | 451 PARK ST W | WINDSOR | N9A6K1 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3146 | -83.043 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2097998 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2097998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2097998 | 2097998 | 2097998 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-006 | 09-006 | 9 | N/A | 66028 | Greater Essex County DSB | Belle River | Belle River Public Elementary School | ELE | 166 | 5404 | 5404-B01 | 370 ST PETER ST | BELLE RIVER | N0R1A0 | 35-15-45-412 | Lakeshore | Lakeshore T | Essex Co | ESSEX | Southwest | South | 42.29 | -82.7048 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 196 | - | - | N | - | Not Required | - | 2956857 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672386 | 672386 | 931794 | 0 | 484585 | 0 | 868092 | 0 | 0 | 0 | 0 | 0 | 2284471 | 2956857 | 2956857 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 868092
09-007 | 09-007 | 9 | N/A | 66028 | Greater Essex County DSB | Bellewood | Bellewood Public Elementary School | ELE | 171 | 5408 | 5408-B01 | 2500 LABELLE ST | WINDSOR | N9E1B6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2669 | -83.0407 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9636529 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 602226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602226 | 9034303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9034303 | 9636529 | 9636529 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-011-01 | 09-011 | 9 | 212 - CMSM Windsor | 66028 | Greater Essex County DSB | North Shore | North Shore Public Elementary School | ELE | 24552 | 19557 | 19557-B01 | AMY CROFT / COMMERCIAL | WINDSOR | TBD | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.307 | -82.861 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 651 | 4 | 73 | N | - | Approved | 44750 | 25728569 | Under Construction | New Construction | Condition | 2023-24 | 45174 | 0 | 0 | 1513285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513285 | 0 | 0 | 978489 | 0 | 20331968 | 0 | 2904827 | 0 | 0 | 0 | 24215284 | 25728569 | 25728569 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23236795
09-011-02 | 09-011 | 9 | N/A | 66028 | Greater Essex County DSB | North Shore | North Shore Public Elementary School | ELE | 24552 | 19557 | 19557-B01 | AMY CROFT / COMMERCIAL | WINDSOR | TBD | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.307 | -82.861 | 42621 | 2016-17 | 2016-17 | 42621 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled | - | 0 | Cancelled | Cancelled | Condition | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94384 | 0 | 0 | 0 | 0 | 0 | 0 | 94384 | 94384 | 94384 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 94384
09-012 | 09-012 | 9 | N/A | 66028 | Greater Essex County DSB | Dougall Avenue | Dougall Avenue Public Elementary School | ELE | 604 | 5691 | 5691-L01 | 811 DOUGALL AVE | WINDSOR | N9A4R2 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3106 | -83.0386 | 42447 | 2015-16 | 2015-16 | 42447 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 150000 | Construction Complete | Land Acquisition | Other | 2015-16 | 42255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 138702 | -11298 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 150000
09-013 | 09-013 | 9 | N/A | 66028 | Greater Essex County DSB | Dr. David Suzuki | Dr. David Suzuki Public Elementary School | ELE | 10944 | 6509 | 6509-B01 | 6320 RAYMOND AVE | WINDSOR | N8S1Z9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3266 | -82.9593 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 16982262 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16982262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16982262 | 16982262 | 16982262 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-015 | 09-015 | 9 | N/A | 66028 | Greater Essex County DSB | Essex | Essex Public Elementary School | ELE | 10945 | 12099 | 12099-B01 | 72 BRIEN AVE E | ESSEX | N8M2N8 | 35-15-45-410 | Essex | Essex T | Essex Co | ESSEX | Southwest | South | 42.1731 | -82.8155 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 14147818 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 3117023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3117023 | 11030795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11030795 | 14147818 | 14147818 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-017 | 09-017 | 9 | N/A | 66028 | Greater Essex County DSB | Essex District | Essex District Public Secondary School | SEC | 5358 | 8207 | 8207-B01 | 244 TALBOT ST N | ESSEX | N8M2E1 | 35-15-45-410 | Essex | Essex T | Essex Co | ESSEX | Southwest | South | 42.1793 | -82.8279 | 42310 | 2015-16 | 2015-16 | - | - | - | 42310 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 700 | - | - | N | - | Not Required | - | 21919757 | Construction Complete | Addition | Condition | 2015-16 | 42255 | 0 | 0 | 703000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674050 | 1377050 | 19652068 | 0 | 0 | 0 | 890639 | 0 | 0 | 0 | 0 | 0 | 20542707 | 21919757 | 21901386 | -18371 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 890639
09-020 | 09-020 | 9 | N/A | 66028 | Greater Essex County DSB | Forest Glade Primary Learning | Forest Glade Primary Learning Public Elementary School | ELE | 10540 | 8898 | 8898-B01 | 9367 ESPLANADE DR | WINDSOR | N8R1J3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3102 | -82.9257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 873000 | Construction Complete | Retrofit | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873000 | 873000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873000 | 873000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-021 | 09-021 | 9 | N/A | 66028 | Greater Essex County DSB | Frank W Begley | Frank W Begley Public Elementary School | ELE | 10656 | 5854 | 5854-B01 | 1093 ASSUMPTION ST | WINDSOR | N9A3C5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3208 | -83.022 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11885291 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11885291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11885291 | 11885291 | 11885291 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-023-01 | 09-023 | 9 | 212 - CMSM Windsor | 66028 | Greater Essex County DSB | James L Dunn | James L Dunn Public Elementary School | ELE | 24551 | 19556 | 19556-B01 | 1123 MERCER ST | WINDSOR | N9A1N8 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3111 | -83.0195 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 645 | 4 | 73 | N | - | Approved | 43837 | 15428988 | Under Construction | New Construction | Consolidation | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285139 | 0 | 12067856 | 0 | 2075994 | 0 | 0 | 0 | 15428989 | 15428989 | 15428988 | -1 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14143850
09-023-02 | 09-023 | 9 | N/A | 66028 | Greater Essex County DSB | James L Dunn | James L Dunn Public Elementary School | ELE | 24551 | 19556 | 19556-L01 | 1123 MERCER ST | WINDSOR | N9A1N8 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3111 | -83.0195 | 42705 | 2016-17 | 2016-17 | 42705 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42705 | 3965143 | Construction Complete | Land Acquisition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3965143 | 0 | 0 | 0 | 0 | 0 | 0 | 3965143 | 3965143 | 3965143 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3965143
09-026 | 09-026 | 9 | N/A | 66028 | Greater Essex County DSB | Harrow | Harrow Public Elementary School | ELE | 1026 | 5970 | 5970-B01 | 400 CENTRE ST E | HARROW | N0R1G0 | 35-15-45-410 | Essex | Essex T | Essex Co | ESSEX | Southwest | South | 42.0367 | -82.912 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1713394 | Construction Complete | Addition | Other | 2012-13 | 41153 | 986517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986517 | 0 | 0 | 726877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726877 | 1713394 | 1713394 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-030 | 09-030 | 9 | N/A | 66028 | Greater Essex County DSB | John Campbell | John Campbell Public Elementary School | ELE | 10800 | 6067 | 6067-B01 | 1255 TECUMSEH RD E | WINDSOR | N8W1B7 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3001 | -83.0062 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11176806 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 1200000 | 9976806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9976806 | 11176806 | 11176806 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-032-01 | 09-032 | 9 | 212 - CMSM Windsor | 66028 | Greater Essex County DSB | Kingsville | Kingsville Public Elementary and Secondary School | ELE/SEC | 24505-24658 | 19510 | 19510-B01 | 1620 JASPERSON LANE | KINGSVILLE | N9Y3J5 | 35-15-45-411 | Kingsville | Kingsville T | Essex Co | ESSEX | Southwest | South | 42.0466 | -82.7242 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | 42509 | 2015-16 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 1798 | 6 | 98 | N | 3 | Approved | 44385 | 59907386 | Under Construction | New Construction | Consolidation | 2023-24 | 45174 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116300 | 3816300 | 0 | 0 | 2075994 | 0 | 48199168 | 0 | 4258929 | 1556995 | 0 | 0 | 56091086 | 59907386 | 59907386 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 54015092
09-032-02 | 09-032 | 9 | N/A | 66028 | Greater Essex County DSB | Kingsville | Kingsville Public Elementary and Secondary School | ELE/SEC | 24505-24658 | 19510 | 19510-L01 | 1620 JASPERSON LANE | KINGSVILLE | N9Y3J5 | 35-15-45-411 | Kingsville | Kingsville T | Essex Co | ESSEX | Southwest | South | 42.0466 | -82.7242 | 43753 | 2019-20 | 2019-20 | 43753 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43753 | 2695700 | Construction Complete | Land Acquisition | Consolidation | 2019-20 | 43845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2695700 | 0 | 0 | 0 | 0 | 0 | 0 | 2695700 | 2695700 | 2695700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2695700
09-033 | 09-033 | 9 | N/A | 66028 | Greater Essex County DSB | Lakeshore Discovery | Lakeshore Discovery Public Elementary School | ELE | 10801 | 12005 | 12005-B01 | 376 IC ROY DR | BELLE RIVER | N0R1A0 | 35-15-45-412 | Lakeshore | Lakeshore T | Essex Co | ESSEX | Southwest | South | 42.2891 | -82.7305 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 18117537 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18117537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18117537 | 18117537 | 18117537 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-035 | 09-035 | 9 | N/A | 66028 | Greater Essex County DSB | LaSalle | LaSalle Public Elementary School | ELE | 9998 | 10358 | 10358-B01 | 1600 MAYFAIR AVE | WINDSOR | N9J3T3 | 35-15-45-408 | LaSalle | LaSalle T | Essex Co | ESSEX | Southwest | South | 42.2291 | -83.0877 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8994000 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8994000 | 8994000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8994000 | 8994000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-037-01 | 09-037 | 9 | N/A | 66028 | Greater Essex County DSB | Leamington District | Leamington District Public Secondary School | SEC | 24212 | 20098 | 20098-B01 | 80 OAK ST W | LEAMINGTON | N8H2B3 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0465 | -82.6085 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 1017 | - | - | N | - | Approved | 42429 | 26686228 | Construction Complete | New Construction | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26686228 | 0 | 0 | 0 | 0 | 0 | 26686228 | 26686228 | 26686228 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 26686228
09-037-02 | 09-037 | 9 | N/A | 66028 | Greater Essex County DSB | Leamington District | Leamington District Public Secondary School | SEC | 24212 | 20098 | 20098-L01 | 80 OAK ST W | LEAMINGTON | N8H2B3 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0465 | -82.6085 | 41380 | 2012-13 | 2013-14 | 41380 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41380 | 5395681 | Construction Complete | Land Acquisition | Condition | 2013-14 | 41758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5395681 | 0 | 0 | 0 | 0 | 0 | 0 | 5395681 | 5395681 | 5395681 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 5395681
09-039 | 09-039 | 9 | N/A | 66028 | Greater Essex County DSB | Mill Street | Mill Street Public Elementary School | ELE | 1541 | 6291 | 6291-B01 | 134 MILL ST E | LEAMINGTON | N8H1S6 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0515 | -82.588 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 591500 | Construction Complete | Addition | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591500 | 591500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591500 | 591500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-040 | 09-040 | 9 | N/A | 66028 | Greater Essex County DSB | Mount Carmel-Blytheswood | Mount Carmel-Blytheswood Public Elementary School | ELE | 1574 | 6312 | 6312-B01 | 622 MERSEA ROAD 5 RR 2 | LEAMINGTON | N8H3V5 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0855 | -82.6018 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2883000 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2883000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2883000 | 2883000 | 2883000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-043 | 09-043 | 9 | N/A | 66028 | Greater Essex County DSB | Northwood | Northwood Public Elementary School | ELE | 1674 | 6380 | 6380-B01 | 1100 NORTHWOOD ST | WINDSOR | N9E1A3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2778 | -83.0301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2155331 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2155331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2155331 | 2155331 | 2155331 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-044 | 09-044 | 9 | N/A | 66028 | Greater Essex County DSB | Northwood | Northwood Public Elementary School | ELE | 1674 | 6380 | 6380-B01 | 1100 NORTHWOOD ST | WINDSOR | N9E1A3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2778 | -83.0301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5604742 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 2231463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2231463 | 3373279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3373279 | 5604742 | 5604742 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-051 | 09-051 | 9 | N/A | 66028 | Greater Essex County DSB | Roseland | Roseland Public Elementary School | ELE | 2039 | 6617 | 6617-B01 | 620 CABANA RD E | WINDSOR | N9G1A4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2595 | -82.9925 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2057887 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057887 | 2057887 | 2057887 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-052 | 09-052 | 9 | N/A | 66028 | Greater Essex County DSB | Roseland | Roseland Public Elementary School | ELE | 2039 | 6617 | 6617-L01 | 620 CABANA RD E | WINDSOR | N9G1A4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2595 | -82.9925 | 41029 | 2011-12 | 2012-13 | 41029 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 105000 | Construction Complete | Land Acquisition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 105000 | 105000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 105000
09-057 | 09-057 | 9 | N/A | 66028 | Greater Essex County DSB | Talbot Trail | Talbot Trail Public Elementary School | ELE | 10802 | 12006 | 12006-B01 | 4000 DUCHARME ST | WINDSOR | N9G0A1 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2515 | -82.9716 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 14948081 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14948081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14948081 | 14948081 | 14948081 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-059 | 09-059 | 9 | N/A | 66028 | Greater Essex County DSB | Tecumseh Vista | Tecumseh Vista Public Elementary and Secondary School | ELE/SEC | 11076 | 12097 | 12097-B01 | 11555 SHIELDS ST | TECUMSEH | N8N0C1 | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.2781 | -82.8923 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 27784905 | Construction Complete | New Construction | Consolidation | 2011-12 | 40787 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 26284905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26284905 | 27784905 | 27784905 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-060 | 09-060 | 9 | N/A | 66028 | Greater Essex County DSB | Tecumseh Vista | Tecumseh Vista Public Elementary and Secondary School | ELE/SEC | 11076 | 12097 | 12097-B01 | 11555 SHIELDS ST | TECUMSEH | N8N0C1 | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.2781 | -82.8923 | 41765 | 2013-14 | 2014-15 | - | - | - | 41765 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 411 | - | - | N | - | Not Required | - | 10710439 | Construction Complete | Addition | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10710439 | 0 | 0 | 0 | 0 | 0 | 10710439 | 10710439 | 10710439 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10710439
09-061 | 09-061 | 9 | N/A | 66028 | Greater Essex County DSB | West Gate | West Gate Public Elementary School | ELE | 10799 | 5699 | 5699-B02 | 1275 CAMPBELL AVE | WINDSOR | N9B3M7 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3071 | -83.0536 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10991650 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 638456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638456 | 10353194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10353194 | 10991650 | 10991650 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-062 | 09-062 | 9 | N/A | 66028 | Greater Essex County DSB | Western | Western Public Secondary School | SEC | 7805 | 8894 | 8894-B01 | 5791 NORTH TOWN LINE RR 4 | AMHERSTBURG | N9V2Y9 | 35-15-45-409 | Amherstburg | Amherstburg T | Essex Co | ESSEX | Southwest | South | 42.1845 | -83.0208 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 243200 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243200 | 243200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243200 | 243200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-063 | 09-063 | 9 | N/A | 66028 | Greater Essex County DSB | Westview Freedom Academy | Westview Freedom Academy Public Secondary School | SEC | 5761 | 8433 | 8433-B01 | 1375 CALIFORNIA AVE | WINDSOR | N9B2Z8 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2924 | -83.0558 | 41765 | 2013-14 | 2014-15 | - | - | - | 41765 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 849 | - | - | N | - | Not Required | - | 2386818 | Construction Complete | Retrofit | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2386818 | 0 | 0 | 0 | 0 | 0 | 2386818 | 2386818 | 2386818 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2386818
09-064 | 09-064 | 9 | N/A | 66028 | Greater Essex County DSB | WF Herman Academy | WF Herman Academy Public Elementary and Secondary School | ELE/SEC | 5724 | 8413 | 8413-B01 | S-1905 BERNARD RD | WINDSOR | N8W0A8 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3072 | -82.9736 | 41877 | 2013-14 | 2014-15 | - | - | - | 41877 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 104 | - | - | N | - | Approved | 42374 | 6500000 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2284289 | 0 | 3980120 | 0 | 0 | 0 | 0 | 0 | 6264409 | 6264409 | 6264409 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3980120
09-066-01 | 09-066 | 9 | N/A | 66028 | Greater Essex County DSB | Amherstburg | Amherstburg Public Secondary School | SEC | 24506 | 19511 | 19511-B01 | 315 SIMCOE ST | AMHERSTBURG | N9V1N1 | 35-15-45-409 | Amherstburg | Amherstburg T | Essex Co | ESSEX | Southwest | South | 42.1066 | -83.111 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 819 | - | - | N | - | Approved | 43922 | 25985519 | Under Construction | New Construction | Consolidation | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25985519 | 0 | 0 | 0 | 0 | 0 | 25985519 | 25985519 | 25985519 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 25985519
09-066-02 | 09-066 | 9 | N/A | 66028 | Greater Essex County DSB | Amherstburg | Amherstburg Public Secondary School | SEC | 24506 | 19511 | 19511-L01 | 315 SIMCOE ST | AMHERSTBURG | N9V1N1 | 35-15-45-409 | Amherstburg | Amherstburg T | Essex Co | ESSEX | Southwest | South | 42.1066 | -83.111 | 43115 | 2017-18 | 2017-18 | 43115 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43115 | 3063224 | Construction Complete | Land Acquisition | Consolidation | 2017-18 | 43219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3063224 | 0 | 0 | 0 | 0 | 0 | 0 | 3063224 | 3063224 | 3063224 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3063224
09-067-01 | 09-067 | 9 | N/A | 66028 | Greater Essex County DSB | Prince Andrew | Prince Andrew Public Elementary School | ELE | 24568 | 19574 | 19574-B01 | LAURIER PKWY / DISPUTED RD | LASALLE | TBD | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2254 | -83.0309 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 423 | - | - | N | - | Approved | 43837 | 10313477 | Construction Complete | New Construction | Condition | 2021-22 | 44446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794068 | 0 | 9519409 | 0 | 0 | 0 | 0 | 0 | 10313477 | 10313477 | 10313477 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9519409
09-067-02 | 09-067 | 9 | N/A | 66028 | Greater Essex County DSB | Prince Andrew | Prince Andrew Public Elementary School | ELE | 24568 | 19574 | 19574-L01 | LAURIER PKWY / DISPUTED RD | LASALLE | TBD | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2254 | -83.0309 | 43181 | 2017-18 | 2017-18 | 43181 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43181 | 1977012 | Construction Complete | Land Acquisition | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977012 | 0 | 0 | 0 | 0 | 0 | 0 | 1977012 | 1977012 | 1977012 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1977012
09-068 | 09-068 | 9 | N/A | 66028 | Greater Essex County DSB | Roseland | Roseland Public Elementary School | ELE | 2039 | 6617 | 6617-B01 | 620 CABANA RD E | WINDSOR | N9G1A4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2595 | -82.9925 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42944 | 3988452 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3567547 | 0 | 0 | 0 | 0 | 0 | 3567547 | 3567547 | 3567547 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3567547
09-069 | 09-069 | 9 | 212 - CMSM Windsor | 66028 | Greater Essex County DSB | Essex | Essex Public Elementary School | ELE | 10945 | 12099 | 12099-B01 | 72 BRIEN AVE E | ESSEX | N8M2N8 | 35-15-45-410 | Essex | Essex T | Essex Co | ESSEX | Southwest | South | 42.1731 | -82.8155 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 7 | 122 | Y | - | Approved | 43836 | 3705653 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3705654 | 0 | 0 | 0 | 3705654 | 3705654 | 3705654 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 3705654
09-070 | 09-070 | 9 | 212 - CMSM Windsor | 66028 | Greater Essex County DSB | Eastwood Parkview | Eastwood Parkview Public Elementary School | ELE | 24833 | 19839 | 19839-B01 | 3070 STILLMEADOW RD | WINDSOR | N8R1N3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2999 | -82.9126 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 501 | 4 | 73 | Y | - | Approved | 44068 | 13913989 | Under Construction | New Construction | Consolidation | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11796473 | 0 | 2117517 | 0 | 0 | 0 | 13913990 | 13913990 | 13913990 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13913990
09-071 | 09-071 | 9 | 212 - CMSM Windsor | 66028 | Greater Essex County DSB | Queen Elizabeth | Queen Elizabeth Public Elementary School | ELE | 1903 | 6527 | 6527-B01 | 4 MAXON AVE | LEAMINGTON | N8H2E2 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0453 | -82.5953 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 78 | 4 | 73 | Y | 2 | Approved | 45118 | 8147057 | Planned | Addition | Consolidation | 2023-24 | 45170 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 1200000 | 0 | 2562895 | 0 | 2862642 | 521520 | 0 | 0 | 7147057 | 8147057 | 8147057 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5947057
09-072 | 09-072 | 9 | N/A | 66028 | Greater Essex County DSB | Lakeshore | Lakeshore Public Elementary School | ELE | 25367 | 20373 | 20373-B01 | TBD | LAKESHORE | TBD | 35-15-45-412 | Lakeshore | Lakeshore T | Essex Co | ESSEX | Southwest | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 582 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13023966 | 0 | 0 | 0 | 0 | 0 | 13023966 | 13023966 | 13023966 | 0 | - | No, Site to be acquired. Sign installation planned for December 1, 2021 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13023966
09-073 | 09-011 | 9 | N/A | 66028 | Greater Essex County DSB | North Shore | North Shore Public Elementary School | ELE | 24552 | 19557 | 19557-L01 | AMY CROFT / COMMERCIAL | WINDSOR | TBD | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.307 | -82.861 | 44039 | 2019-20 | 2020-21 | 44039 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44533 | 3588414 | Construction Complete | Land Acquisition | Condition | 2019-20 | 43920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3588414 | 0 | 0 | 0 | 0 | 0 | 0 | 3588414 | 3588414 | 3588414 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3588414
09-074 | 09-074 | 9 | N/A | 66028 | Greater Essex County DSB | Legacy Oak Trail | Legacy Oak Trail Public Elementary School | ELE | 24568 | 19574 | 19574-B01 | 2648 LEPTIS MAGNA DR | LASALLE | N9J0E4 | 35-15-45-408 | LaSalle | LaSalle T | Essex Co | ESSEX | Southwest | South | 42.2241 | -83.0447 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 167 | - | - | N | - | Approved | 45092 | 4901913 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4901913 | 0 | 0 | 0 | 0 | 0 | 4901913 | 4901913 | 4901913 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4901913
09-075 | 09-075 | 9 | N/A | 66028 | Greater Essex County DSB | Marlborough | Marlborough Public Elementary School | ELE | 1470 | 6241 | 6241-B01 | 3357 MELBOURNE RD | WINDSOR | N9C1Y6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2898 | -83.0646 | 44503 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44503 | 5001 | Construction Complete | Purchase | Other | 2021-22 | 44440 | 0 | 0 | 0 | 5001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5001 | 5001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
09-076 | 09-076 | 9 | N/A | 66028 | Greater Essex County DSB | Northwood | Northwood Public Elementary School | ELE | 1674 | 6380 | 6380-B01 | 1100 NORTHWOOD ST | WINDSOR | N9E1A3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2778 | -83.0301 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 184 | - | - | N | - | Approved | 45118 | 4854477 | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4854477 | 0 | 0 | 0 | 0 | 0 | 4854477 | 4854477 | 4854477 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4854477
10-001 | 10-001 | 10 | N/A | 66036 | Lambton Kent DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 14525 | 14525 | 14525-B01 | 200 WELLINGTON ST | SARNIA | N7T7L2 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9694 | -82.4048 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-002 | 10-002 | 10 | N/A | 66036 | Lambton Kent DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 14525 | 14525 | 14525-B01 | 200 WELLINGTON ST | SARNIA | N7T7L2 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9694 | -82.4048 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6057711 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6104494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6104494 | 6104494 | 5784563 | -319931 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-003 | 10-003 | 10 | N/A | 66036 | Lambton Kent DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 14525 | 14525 | 14525-B01 | 200 WELLINGTON ST | SARNIA | N7T7L2 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9694 | -82.4048 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 109962 | Construction Complete | Other | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109962 | 109962 | 109962 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-004 | 10-004 | 10 | N/A | 66036 | Lambton Kent DSB | AA Wright | AA Wright Public Elementary School | ELE | 1 | 5301 | 5301-B01 | 55 ELM DR S | WALLACEBURG | N8A3M7 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.5915 | -82.4041 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 452074 | Construction Complete | Addition | Other | 2012-13 | 41153 | 174552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35777 | 210329 | 0 | 0 | 241745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241745 | 452074 | 452074 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-006 | 10-006 | 10 | N/A | 66036 | Lambton Kent DSB | Alexander Mackenzie | Alexander Mackenzie Public Secondary School | SEC | 5204 | 8116 | 8116-B01 | 1257 MICHIGAN AVE | SARNIA | N7S3Y3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9995 | -82.3616 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 872602 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 872602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872602 | 872602 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-008 | 10-008 | 10 | N/A | 66036 | Lambton Kent DSB | Bright's Grove | Bright's Grove Public Elementary School | ELE | 251 | 5456 | 5456-B01 | 2612 HAMILTON AVE | BRIGHT'S GROVE | N0N1C0 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 43.0306 | -82.2631 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 649283 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 0 | 0 | 607283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607283 | 649283 | 649283 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-009 | 10-009 | 10 | N/A | 66036 | Lambton Kent DSB | Brooke Central | Brooke Central Public Elementary School | ELE | 261 | 5461 | 5461-B01 | 7989 BROOKE LINE RR 7 | ALVINSTON | N0N1A0 | 35-15-54-613 | Brooke-Alvinston | Brooke-Alvinston M | Lambton Co | LAMBTON | Southwest | South | 42.8419 | -81.871 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2600000 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1271890 | 1871890 | 728110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728110 | 2600000 | 2600000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-011 | 10-011 | 10 | N/A | 66036 | Lambton Kent DSB | Cathcart Boulevard | Cathcart Boulevard Public Elementary School | ELE | 341 | 5513 | 5513-B01 | 1219 CATHCART BLVD | SARNIA | N7S2H7 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 43.0101 | -82.3634 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2374071 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140661 | 1640661 | 733410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733410 | 2374071 | 2374071 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-012 | 10-012 | 10 | N/A | 66036 | Lambton Kent DSB | Cathcart Boulevard | Cathcart Boulevard Public Elementary School | ELE | 341 | 5513 | 5513-B01 | 1219 CATHCART BLVD | SARNIA | N7S2H7 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 43.0101 | -82.3634 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1092984 | Construction Complete | Addition | Other | 2014-15 | 41883 | 245960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54479 | 300439 | 0 | 0 | 792545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792545 | 1092984 | 1092984 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-014 | 10-014 | 10 | N/A | 66036 | Lambton Kent DSB | Dresden Area Central | Dresden Area Central Public Elementary School | ELE | 628 | 5711 | 5711-B01 | 941 NORTH ST RR 5 | DRESDEN | N0P1M0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.5856 | -82.179 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 364123 | Construction Complete | Addition | Other | 2012-13 | 41153 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 0 | 0 | 336523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336523 | 364123 | 364123 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-017 | 10-017 | 10 | N/A | 66036 | Lambton Kent DSB | Errol Village | Errol Village Public Elementary School | ELE | 756 | 5799 | 5799-B01 | 3568 EGREMONT RD RR 2 | CAMLACHIE | N0N1E0 | 35-15-54-405 | Plympton-Wyoming | Plympton-Wyoming T | Lambton Co | LAMBTON | Southwest | South | 43.043 | -82.1868 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1192703 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192703 | 1192703 | 1192703 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-018 | 10-018 | 10 | N/A | 66036 | Lambton Kent DSB | Grand Bend | Grand Bend Public Elementary School | ELE | 948 | 5911 | 5911-B01 | 15 GILL RD | GRAND BEND | N0M1T0 | 35-15-54-103 | Lambton Shores | Lambton Shores M | Lambton Co | LAMBTON | Southwest | South | 43.3099 | -81.7547 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1199932 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 698774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698774 | 0 | 0 | 501158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501158 | 1199932 | 1199932 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-020 | 10-020 | 10 | N/A | 66036 | Lambton Kent DSB | High Park | High Park Public Elementary School | ELE | 1061 | 5991 | 5991-B01 | 757 KEMBER AVE | SARNIA | N7S2T3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9822 | -82.3719 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1206443 | Construction Complete | Addition | Other | 2014-15 | 41883 | 576571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576571 | 0 | 0 | 629872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629872 | 1206443 | 1206443 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-023 | 10-023 | 10 | N/A | 66036 | Lambton Kent DSB | John N Given | John N Given Public Elementary School | ELE | 1212 | 6072 | 6072-B01 | 92 CHURCHILL ST | CHATHAM | N7L3T5 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4051 | -82.2066 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 641411 | Construction Complete | Addition | Other | 2014-15 | 41883 | 145378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145378 | 0 | 0 | 496033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496033 | 641411 | 641411 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-026 | 10-026 | 10 | N/A | 66036 | Lambton Kent DSB | Lambton Kent | Lambton Kent Public Secondary School | SEC | 5473 | 8274 | 8274-B01 | 231 ST. GEORGE ST RR 4 | DRESDEN | N0P1M0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.5958 | -82.1779 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1165384 | Construction Complete | Addition | Other | 2013-14 | 41518 | 250000 | 0 | 0 | 915384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165384 | 1165384 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-027 | 10-027 | 10 | N/A | 66036 | Lambton Kent DSB | Lansdowne | Lansdowne Public Elementary School | ELE | 1334 | 6152 | 6152-B01 | 95 LANSDOWNE AVE S | SARNIA | N7S1G7 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9651 | -82.3711 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1838410 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705000 | 1105000 | 733410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733410 | 1838410 | 1838410 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-028 | 10-028 | 10 | N/A | 66036 | Lambton Kent DSB | Lansdowne | Lansdowne Public Elementary School | ELE | 1334 | 6152 | 6152-B01 | 95 LANSDOWNE AVE S | SARNIA | N7S1G7 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9651 | -82.3711 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1432278 | Construction Complete | Addition | Other | 2012-13 | 41153 | 285231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259957 | 545188 | 0 | 0 | 887090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887090 | 1432278 | 1432278 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-029 | 10-029 | 10 | N/A | 66036 | Lambton Kent DSB | LKDSB Head Office | Administrative Office | OFF-ADM | 14525 | 14525 | 14525-B01 | 200 WELLINGTON ST | SARNIA | N7T7L2 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9694 | -82.4048 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 591278 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 0 | 591278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591278 | 591278 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-031 | 10-031 | 10 | N/A | 66036 | Lambton Kent DSB | McNaughton Avenue | McNaughton Avenue Public Elementary School | ELE | 1510 | 6269 | 6269-B01 | 480 MCNAUGHTON AVE E | CHATHAM | N7L2G9 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4269 | -82.1815 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3423107 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2239711 | 2689711 | 733396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733396 | 3423107 | 3423107 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-032 | 10-032 | 10 | N/A | 66036 | Lambton Kent DSB | McNaughton Avenue | McNaughton Avenue Public Elementary School | ELE | 1510 | 6269 | 6269-B01 | 480 MCNAUGHTON AVE E | CHATHAM | N7L2G9 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4269 | -82.1815 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1199302 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 102321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102321 | 0 | 0 | 1096981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096981 | 1199302 | 1199302 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-034 | 10-034 | 10 | N/A | 66036 | Lambton Kent DSB | Naahii Ridge | Naahii Ridge Public Elementary School | ELE | 1111 | 6019 | 6019-B01 | 20473 VICTORIA RD RR 3 | RIDGETOWN | N0P2C0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4473 | -81.8739 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2958359 | Construction Complete | Addition | Other | 2012-13 | 41153 | 556157 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15112 | 2071269 | 0 | 0 | 887090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887090 | 2958359 | 2958359 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-035 | 10-035 | 10 | N/A | 66036 | Lambton Kent DSB | PE McGibbon | PE McGibbon Public Elementary School | ELE | 12746 | 6077 | 6077-B01 | 217 RUSSELL ST S | SARNIA | N7T3L6 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.967 | -82.3923 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8798531 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8798531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8798531 | 8798531 | 8798531 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-037 | 10-037 | 10 | N/A | 66036 | Lambton Kent DSB | Queen Elizabeth II | Queen Elizabeth II Public Elementary School | ELE | 1911 | 6533 | 6533-B01 | 4079 MAPLE ST | PETROLIA | N0N1R0 | 35-15-54-402 | Petrolia | Petrolia T | Lambton Co | LAMBTON | Southwest | South | 42.8849 | -82.1532 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 144 | - | - | N | - | Not Required | - | 6232826 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 165487 | 3081125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3246612 | 0 | 0 | 978489 | 0 | 2007725 | 0 | 0 | 0 | 0 | 0 | 2986214 | 6232826 | 6232826 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2007725
10-038 | 10-038 | 10 | N/A | 66036 | Lambton Kent DSB | Ridgetown District | Ridgetown District Public Secondary School | SEC | 5618 | 8357 | 8357-B01 | 9 HAROLD ST N | RIDGETOWN | N0P2C0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4447 | -81.882 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2078414 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178414 | 178414 | 0 | 0 | 0 | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 1900000 | 2078414 | 2078414 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-039 | 10-039 | 10 | N/A | 66036 | Lambton Kent DSB | Rosedale | Rosedale Public Elementary School | ELE | 2037 | 6615 | 6615-B01 | 1018 INDIAN RD N | SARNIA | N7V4C5 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.993 | -82.3746 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2443545 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 1500000 | 0 | 443545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943545 | 2443545 | 2443545 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-040 | 10-040 | 10 | N/A | 66036 | Lambton Kent DSB | Sir John Moore | Sir John Moore Public Elementary School | ELE | 9872 | 10306 | 10306-B01 | 274 ST CLAIR BLVD RR 1 | CORUNNA | N0N1G0 | 35-15-54-614 | St. Clair | St. Clair Tp | Lambton Co | LAMBTON | Southwest | South | 42.8771 | -82.4458 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 813769 | Construction Complete | Addition | Other | 2014-15 | 41883 | 257352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257352 | 0 | 0 | 556417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556417 | 813769 | 813769 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-042 | 10-042 | 10 | N/A | 66036 | Lambton Kent DSB | Tilbury Area | Tilbury Area Public Elementary School | ELE | 2311 | 6781 | 6781-B01 | 5 MABLE ST | TILBURY | N0P2L0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.2593 | -82.4269 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2256161 | Construction Complete | Addition | Other | 2011-12 | 40787 | 12616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 312616 | 1500000 | 0 | 443545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1943545 | 2256161 | 2256161 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-043 | 10-043 | 10 | N/A | 66036 | Lambton Kent DSB | Wallaceburgh District | Wallaceburgh District Public Secondary School | SEC | 5728 | 8416 | 8416-B01 | 920 ELGIN ST | WALLACEBURG | N8A3E1 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.5964 | -82.3911 | 41877 | 2013-14 | 2014-15 | - | - | - | 41877 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42135 | 2432240 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 182240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182240 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2432240 | 2432240 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2250000
10-045 | 10-045 | 10 | N/A | 66036 | Lambton Kent DSB | Great Lakes | Great Lakes Public Secondary School | SEC | 5673 | 8382 | 8382-B01 | 340 MURPHY RD | SARNIA | N7S2X1 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9669 | -82.366 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43173 | 25242875 | Construction Complete | Retrofit | Consolidation | 2019-20 | 43709 | 155266 | 13452209 | 0 | 0 | 0 | 0 | 0 | 1131317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14738792 | 0 | 0 | 0 | 0 | 10504083 | 0 | 0 | 0 | 0 | 0 | 10504083 | 25242875 | 25242875 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10504083
10-046 | 10-046 | 10 | 218 - CMSM Lambton | 66036 | Lambton Kent DSB | Plympton-Wyoming | Plympton-Wyoming Public Elementary School | ELE | 2576 | 6949 | 6949-B01 | 606 THAMES ST | WYOMING | N0N1T0 | 35-15-54-405 | Plympton-Wyoming | Plympton-Wyoming T | Lambton Co | LAMBTON | Southwest | South | 42.9509 | -82.123 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 43 | 1 | 24 | Y | - | Approved | 42716 | 3700822 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3171443 | 0 | 529379 | 0 | 0 | 0 | 3700822 | 3700822 | 6103066 | 2402244 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3700822
10-047 | 10-047 | 10 | 227 - CMSM Chatham-Kent | 66036 | Lambton Kent DSB | Indian Creek Road | Indian Creek Road Public Elementary School | ELE | 1145 | 6034 | 6034-B01 | 511 INDIAN CREEK RD W | CHATHAM | N7M0P5 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.3785 | -82.1814 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43796 | 2244640 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 0 | 104092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104092 | 0 | 0 | 0 | 0 | 0 | 0 | 2831523 | 0 | 0 | 0 | 2831523 | 2935615 | 2935615 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2831523
10-048 | 10-048 | 10 | 227 - CMSM Chatham-Kent | 66036 | Lambton Kent DSB | Wheatley Area | Wheatley Area Public Elementary School | ELE | 2489 | 6897 | 6897-B01 | 226 ERIE ST N | WHEATLEY | N0P2P0 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.1016 | -82.4632 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43280 | 344893 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 80203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80203 | 0 | 0 | 0 | 0 | 0 | 0 | 264690 | 0 | 0 | 0 | 264690 | 344893 | 351593 | 6700 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 264690
10-049 | 10-049 | 10 | 218 - CMSM Lambton | 66036 | Lambton Kent DSB | Forest Area | Forest Area Public Elementary and Secondary School | ELE/SEC | 24843-24842 | 19848 | 19848-B01 | 105 BEECHWOOD AVE | FOREST | N0N1J0 | 35-15-54-103 | Lambton Shores | Lambton Shores M | Lambton Co | LAMBTON | Southwest | South | 43.1053 | -81.9913 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 1186 | 3 | 49 | Y | 2 | Planned | - | 0 | Planned | New Construction | Consolidation | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079932 | 0 | 35590979 | 0 | 2053641 | 1058758 | 0 | 0 | 39783310 | 39783310 | 39783310 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 38703378
10-050 | 10-050 | 10 | N/A | 66036 | Lambton Kent DSB | Tecumseh | Tecumseh Public Elementary School | ELE | 2282 | 6762 | 6762-B01 | 287 MCNAUGHTON AVE W | CHATHAM | N7L1R8 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.409 | -82.2101 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581110 | 0 | 0 | 0 | 0 | 0 | 2581110 | 2581110 | 2581110 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2581110
10-051 | 10-051 | 10 | N/A | 66036 | Lambton Kent DSB | HW Burgess | HW Burgess Public Elementary School | ELE | 994 | 5947 | 5947-B01 | 140 LAWRENCE AVE | WALLACEBURG | N8A2B3 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.597 | -82.3712 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Other | 2012-13 | 41153 | 174551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174551 | 0 | 0 | 98597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98597 | 273148 | 273148 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-052 | 10-052 | 10 | N/A | 66036 | Lambton Kent DSB | Chatham-Kent | Chatham-Kent Public Secondary School | SEC | 5455 | 8263 | 8263-B01 | 285 MCNAUGHTON AVE E | CHATHAM | N7L2G7 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4216 | -82.1913 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43732 | 3561911 | Construction Complete | Addition | Other | 2021-22 | 44440 | 398424 | 2555537 | 0 | 607950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3561911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3561911 | 3561911 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
10-053 | 10-049 | 10 | N/A | 66036 | Lambton Kent DSB | Forest Area | Forest Area Public Elementary and Secondary School | ELE/SEC | 24843-24842 | 19848 | 19848-L01 | 105 BEECHWOOD AVE | FOREST | N0N1J0 | 35-15-54-103 | Lambton Shores | Lambton Shores M | Lambton Co | LAMBTON | Southwest | South | 43.1053 | -81.9913 | 44477 | 2021-22 | 2021-22 | 44477 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44477 | 4698146 | Under Construction | Land Acquisition | Consolidation | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698146 | 0 | 0 | 0 | 0 | 0 | 0 | 4698146 | 4698146 | 4698146 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4698146
10-054 | 10-054 | 10 | 218 - CMSM Lambton | 66036 | Lambton Kent DSB | Errol Village | Errol Village Public Elementary School | ELE | 756 | 5799 | 5799-B01 | 3568 EGREMONT RD RR 2 | CAMLACHIE | N0N1E0 | 35-15-54-405 | Plympton-Wyoming | Plympton-Wyoming T | Lambton Co | LAMBTON | Southwest | South | 43.043 | -82.1868 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 46 | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1794861 | 0 | 2053640 | 0 | 0 | 0 | 3848501 | 3848501 | 3848501 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3848501
11-001 | 11-001 | 11 | N/A | 66044 | Thames Valley DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 7947 | 5177 | 5177-B01 | 1250 DUNDAS ST | LONDON | N5W5P2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9968 | -81.2072 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-002 | 11-002 | 11 | N/A | 66044 | Thames Valley DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 7947 | 5177 | 5177-B01 | 1250 DUNDAS ST | LONDON | N5W5P2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9968 | -81.2072 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 40371347 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40331350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40331350 | 40331350 | 40375447 | 44097 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-004 | 11-004 | 11 | N/A | 66044 | Thames Valley DSB | Algonquin | Algonquin Public Elementary School | ELE | 53 | 5330 | 5330-B01 | 59 ALGONQUIN RD | WOODSTOCK | N4T1R8 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1513 | -80.7335 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2077160 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2077160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2077160 | 2077160 | 2077160 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-006 | 11-006 | 11 | N/A | 66044 | Thames Valley DSB | Annandale | Annandale Public Elementary School | ELE | 55 | 3002 | 3002-B01 | 60 TILLSON AVE | TILLSONBURG | N4G3A1 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8647 | -80.7223 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 104 | - | - | N | - | Not Required | - | 4137770 | Construction Complete | Retrofit | Consolidation | 2014-15 | 41883 | 2065094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065094 | 0 | 0 | 988568 | 0 | 1084108 | 0 | 0 | 0 | 0 | 0 | 2072676 | 4137770 | 4137770 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1084108
11-008 | 11-008 | 11 | N/A | 66044 | Thames Valley DSB | East Carling | East Carling Public Elementary School | ELE | 7865 | 8946 | 8946-B01 | 814 QUEBEC ST | LONDON | N5Y1X4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0032 | -81.2235 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 190 | - | - | N | - | Approved | 42173 | 6040339 | Construction Complete | Addition | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494285 | 0 | 5546054 | 0 | 0 | 0 | 0 | 0 | 6040339 | 6040339 | 6040339 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5546054
11-009 | 11-009 | 11 | N/A | 66044 | Thames Valley DSB | Blenheim District | Blenheim District Public Elementary School | ELE | 11203 | 5712 | 5712-B01 | 32 WILMOT ST S RR 3 | DRUMBO | N0J1G0 | 35-15-37-601 | Blandford-Blenheim | Blandford - Blenheim Tp | Oxford Co | OXFORD | Southwest | South | 43.2362 | -80.5502 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8339533 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 493385 | 0 | 47181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570319 | 2110885 | 6228648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6228648 | 8339533 | 8339533 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-012 | 11-012 | 11 | N/A | 66044 | Thames Valley DSB | Caradoc | Caradoc Public Elementary School | ELE | 321 | 5498 | 5498-B01 | 714 BOWAN ST | MOUNT BRYDGES | N0L1W0 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.9102 | -81.4918 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6255202 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4175300 | 2079902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255202 | 6255202 | 6255202 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-015 | 11-015 | 11 | N/A | 66044 | Thames Valley DSB | Central | Central Public Elementary School | ELE | 408 | 5568 | 5568-B01 | 410 HUNTER ST | WOODSTOCK | N4S4G4 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.131 | -80.7597 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2746784 | Construction Complete | Addition | Other | 2001-02 | 37135 | 2746784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746784 | 2746784 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-016 | 11-016 | 11 | N/A | 66044 | Thames Valley DSB | Chippewa | Chippewa Public Elementary School | ELE | 7873 | 8954 | 8954-B01 | 1035 CHIPPEWA DR | LONDON | N5V2T6 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0286 | -81.1962 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 899280 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899280 | 899280 | 899280 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-017 | 11-017 | 11 | N/A | 66044 | Thames Valley DSB | Clara Brenton | Clara Brenton Public Elementary School | ELE | 7874 | 8955 | 8955-B01 | 1025 ST CROIX AVE | LONDON | N6H3X8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9801 | -81.3154 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3895069 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3895069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3895069 | 3895069 | 3895069 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-018 | 11-018 | 11 | N/A | 66044 | Thames Valley DSB | Clara Brenton | Clara Brenton Public Elementary School | ELE | 7874 | 8955 | 8955-B01 | 1025 ST CROIX AVE | LONDON | N6H3X8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9801 | -81.3154 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1074771 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074771 | 1074771 | 1074771 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-019 | 11-019 | 11 | N/A | 66044 | Thames Valley DSB | College Avenue | College Avenue Public Secondary School | SEC | 5291 | 3003 | 3003-B01 | 700 COLLEGE AVE | WOODSTOCK | N4S2C8 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1241 | -80.7453 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3236919 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370322 | 0 | 0 | 0 | 2866597 | 0 | 0 | 0 | 0 | 3236919 | 3236919 | 3236919 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-021 | 11-021 | 11 | N/A | 66044 | Thames Valley DSB | Eagle Heights | Eagle Heights Public Elementary School | ELE | 7920 | 9001 | 9001-B01 | 284 OXFORD ST W | LONDON | N6H1S9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9879 | -81.2754 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3098060 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3098060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3098060 | 3098060 | 3098060 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-022 | 11-022 | 11 | N/A | 66044 | Thames Valley DSB | Eagle Heights | Eagle Heights Public Elementary School | ELE | 7920 | 9001 | 9001-B01 | 284 OXFORD ST W | LONDON | N6H1S9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9879 | -81.2754 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 155022 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 155022 | 155022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-023 | 11-023 | 11 | N/A | 66044 | Thames Valley DSB | Eagle Heights | Eagle Heights Public Elementary School | ELE | 7920 | 9001 | 9001-B01 | 284 OXFORD ST W | LONDON | N6H1S9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9879 | -81.2754 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 265 | - | - | N | - | Not Required | - | 5214848 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2215315 | 0 | 2999533 | 0 | 0 | 0 | 0 | 0 | 5214848 | 5214848 | 5214848 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2999533
11-024 | 11-024 | 11 | N/A | 66044 | Thames Valley DSB | East Williams Memorial | East Williams Memorial Public Elementary School | ELE | 683 | 5749 | 5749-B01 | 4441 QUEENS AVE | AILSA CRAIG | N0M1A0 | 35-15-59-619 | North Middlesex | North Middlesex M | Middlesex Co | MIDDLESEX | Southwest | South | 43.1119 | -81.5566 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1433088 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204278 | 204278 | 1228810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228810 | 1433088 | 1433088 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-025 | 11-025 | 11 | N/A | 66044 | Thames Valley DSB | Eastdale | Eastdale Public Elementary School | ELE | 687 | 5753 | 5753-B01 | 65 AILEEN DR | WOODSTOCK | N4S4A2 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1253 | -80.7338 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 77511 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 77511 | 77511 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-027 | 11-027 | 11 | N/A | 66044 | Thames Valley DSB | Elgin Court | Elgin Court Public Elementary School | ELE | 716 | 5774 | 5774-B01 | 254 FIRST AVE | ST THOMAS | N5R4P5 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.762 | -81.1757 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 551122 | Construction Complete | Addition | Other | 2001-02 | 37135 | 551122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551122 | 551122 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-029 | 11-029 | 11 | N/A | 66044 | Thames Valley DSB | Emily Stowe | Emily Stowe Public Elementary School | ELE | 22459 | 8323 | 8323-B01 | 1 JERDON ST RR 1 | NORWICH | N0J1P0 | 35-15-37-603 | Norwich | Norwich Tp | Oxford Co | OXFORD | Southwest | South | 42.9802 | -80.5969 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 186 | - | - | N | - | Not Required | - | 6020751 | Construction Complete | Retrofit | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425798 | 0 | 4594953 | 0 | 0 | 0 | 0 | 0 | 6020751 | 6020751 | 6020751 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4594953
11-031 | 11-031 | 11 | N/A | 66044 | Thames Valley DSB | FD Roosevelt | FD Roosevelt Public Elementary School | ELE | 7881 | 8962 | 8962-B01 | 560 SECOND ST | LONDON | N5V2B7 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0101 | -81.1936 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2634606 | Construction Complete | Addition | Other | 2000-01 | 36770 | 2327171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307435 | 2634606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2634606 | 2634606 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-032 | 11-032 | 11 | N/A | 66044 | Thames Valley DSB | Forest Park | Forest Park Public Elementary School | ELE | 5862 | 8470 | 8470-B01 | 295 FOREST AVE | ST THOMAS | N5R2K5 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7727 | -81.1709 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3099232.38 | Construction Complete | Addition | Other | 2001-02 | 37135 | 2980694.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118538.05 | 3099232.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3099232.38 | 3099232.38 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-033 | 11-033 | 11 | N/A | 66044 | Thames Valley DSB | Forest Park | Forest Park Public Elementary School | ELE | 5862 | 8470 | 8470-B01 | 295 FOREST AVE | ST THOMAS | N5R2K5 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7727 | -81.1709 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 596632 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596632 | 596632 | 596632 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-034 | 11-034 | 11 | N/A | 66044 | Thames Valley DSB | Glendale | Glendale Public Secondary School | SEC | 5392 | 8227 | 8227-B01 | 37 GLENDALE DR | TILLSONBURG | N4G1J6 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8671 | -80.7416 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8969136 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 33374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944300 | 977674 | 0 | 997180 | 0 | 0 | 0 | 6994282 | 0 | 0 | 0 | 0 | 7991462 | 8969136 | 8969136 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-035 | 11-035 | 11 | N/A | 66044 | Thames Valley DSB | Harrisfield | Harrisfield Public Elementary School | ELE | 1021 | 5967 | 5967-B01 | 2 CAFFYN ST | INGERSOLL | N5C3M8 | 35-15-37-401 | Ingersoll | Ingersoll T | Oxford Co | OXFORD | Southwest | South | 43.0324 | -80.8693 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4291591 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567600 | 2420236 | 1303755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4291591 | 4291591 | 4291591 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-036 | 11-036 | 11 | N/A | 66044 | Thames Valley DSB | Hickson Central | Hickson Central Public Elementary School | ELE | 1059 | 5990 | 5990-B01 | 161 LOVEYS ST | HICKSON | N0J1L0 | 35-15-37-602 | East Zorra-Tavistock | East Zorra - Tavistock Tp | Oxford Co | OXFORD | Southwest | South | 43.2393 | -80.8 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 22823 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22823 | 22823 | 22823 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-038 | 11-038 | 11 | N/A | 66044 | Thames Valley DSB | Huron Heights | Huron Heights Public Elementary School | ELE | 7885 | 8966 | 8966-B01 | 1245 MICHAEL ST | LONDON | N5V2H4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0203 | -81.2071 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 155022 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 155022 | 155022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-039 | 11-039 | 11 | N/A | 66044 | Thames Valley DSB | Jack Chambers | Jack Chambers Public Elementary School | ELE | 7886 | 8967 | 8967-B01 | 1650 HASTINGS DR | LONDON | N5X3E3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0362 | -81.2696 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2246286 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1906080 | 340206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2246286 | 2246286 | 2246286 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-041 | 11-041 | 11 | N/A | 66044 | Thames Valley DSB | Jeanne Sauvé | Jeanne Sauvé Public Elementary School | ELE | 7878 | 8959 | 8959-B01 | 215 WHARNCLIFFE RD N | LONDON | N6H2B6 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9907 | -81.2637 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 63397 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63397 | 63397 | 63397 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-042 | 11-042 | 11 | N/A | 66044 | Thames Valley DSB | John Dearness | John Dearness Public Elementary School | ELE | 7887 | 8968 | 8968-B01 | 555 SANATORIUM RD | LONDON | N6H3W6 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9654 | -81.3304 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 77511 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 77511 | 77511 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-044 | 11-044 | 11 | N/A | 66044 | Thames Valley DSB | John Wise | John Wise Public Elementary School | ELE | 11205 | 8385 | 8385-B02 | 100 PARKSIDE DR | ST THOMAS | N5R3T9 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7577 | -81.1931 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11660700 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 182226 | 0 | 1875419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630214 | 2687859 | 8972841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8972841 | 11660700 | 11660700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-045 | 11-045 | 11 | N/A | 66044 | Thames Valley DSB | June Rose Callwood | June Rose Callwood Public Elementary School | ELE | 5877 | 8476 | 8476-B01 | 84 EDWARD ST | ST THOMAS | N5P1Y7 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7867 | -81.1797 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5302172 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 2555647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2555647 | 506770 | 936000 | 1303755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746525 | 5302172 | 5302172 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-046 | 11-046 | 11 | N/A | 66044 | Thames Valley DSB | Kensal Park | Kensal Park Public Elementary School | ELE | 7888 | 8969 | 8969-B01 | 328 SPRINGBANK DR | LONDON | N6J1G5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9696 | -81.2783 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1250659 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250659 | 1250659 | 1250659 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-048 | 11-048 | 11 | N/A | 66044 | Thames Valley DSB | Lambeth | Lambeth Public Elementary School | ELE | 7860 | 8941 | 8941-B01 | 6820 DUFFIELD ST | LONDON | N6P1A4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9135 | -81.2977 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 77511 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 77511 | 77511 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-049 | 11-049 | 11 | N/A | 66044 | Thames Valley DSB | Lambeth | Lambeth Public Elementary School | ELE | 7860 | 8941 | 8941-B01 | 6820 DUFFIELD ST | LONDON | N6P1A4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9135 | -81.2977 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8178957 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 158148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158148 | 5329425 | 1802214 | 889170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8020809 | 8178957 | 8178957 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-050 | 11-050 | 11 | N/A | 66044 | Thames Valley DSB | Laurie Hawkins | Laurie Hawkins Public Elementary School | ELE | 13969 | 12257 | 12257-B01 | 156 INNES ST | INGERSOLL | N5C2R8 | 35-15-37-401 | Ingersoll | Ingersoll T | Oxford Co | OXFORD | Southwest | South | 43.0425 | -80.8941 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11107617 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10218447 | 0 | 889170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11107617 | 11107617 | 11107617 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-051 | 11-051 | 11 | N/A | 66044 | Thames Valley DSB | Locke's | Locke's Public Elementary School | ELE | 1376 | 6177 | 6177-B01 | 20 SOUTH EDGEWARE RD | ST THOMAS | N5P2H2 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7939 | -81.1806 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5591378 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 1355216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1355216 | 0 | 2932407 | 1303755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4236162 | 5591378 | 5591378 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-052 | 11-052 | 11 | N/A | 66044 | Thames Valley DSB | Lord Roberts | Lord Roberts Public Elementary School | ELE | 7894 | 8975 | 8975-B01 | 440 PRINCESS AVE | LONDON | N6B2B3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9916 | -81.2398 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 155022 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 155022 | 155022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-054 | 11-054 | 11 | N/A | 66044 | Thames Valley DSB | Lucan | Lucan Public Elementary School | ELE | 1398 | 6192 | 6192-B01 | 270 Main St | Lucan | N0M2J0 | 35-15-59-617 | Lucan Biddulph | Lucan Biddulph Tp | Middlesex Co | MIDDLESEX | Southwest | South | 43.1925 | -81.4123 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 155022 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 155022 | 155022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-055 | 11-055 | 11 | N/A | 66044 | Thames Valley DSB | Mary Wright | Mary Wright Public Elementary School | ELE | 18630 | 19085 | 19085-L01 | 213 CARROLL ST W | STRATHROY | N7G1B1 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.9429 | -81.6166 | 40884 | 2011-12 | 2011-12 | 40884 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 879671 | Construction Complete | Land Acquisition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9671 | 9671 | 0 | 0 | 0 | 870000 | 0 | 0 | 0 | 0 | 0 | 0 | 870000 | 879671 | 879671 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 870000
11-056 | 11-056 | 11 | N/A | 66044 | Thames Valley DSB | Mary Wright | Mary Wright Public Elementary School | ELE | 18630 | 19085 | 19085-B01 | 213 CARROLL ST W | STRATHROY | N7G1B1 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.9429 | -81.6166 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 534 | - | - | N | - | Not Required | - | 10652400 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80525 | 0 | 0 | 0 | 0 | 0 | 80525 | 0 | 0 | 511936 | 0 | 10059939 | 0 | 0 | 0 | 0 | 0 | 10571875 | 10652400 | 10652400 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10059939
11-057 | 11-057 | 11 | N/A | 66044 | Thames Valley DSB | Masonville | Masonville Public Elementary School | ELE | 7897 | 8978 | 8978-B01 | 25 HILLVIEW BLVD | LONDON | N6G3A7 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0257 | -81.2844 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2951929 | Construction Complete | Addition | Other | 2000-01 | 36770 | 2705804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246125 | 2951929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2951929 | 2951929 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-059 | 11-059 | 11 | N/A | 66044 | Thames Valley DSB | Medway | Medway Public Secondary School | SEC | 5517 | 8301 | 8301-B01 | 14405 MEDWAY RD | ARVA | N0M1C0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 43.0512 | -81.2891 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 20779353 | Construction Complete | Addition | Other | 2009-10 | 40057 | 11848222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 12598222 | 0 | 8181131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8181131 | 20779353 | 20779353 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-060 | 11-060 | 11 | N/A | 66044 | Thames Valley DSB | Mitchell Hepburn | Mitchell Hepburn Public Elementary School | ELE | 11013 | 12145 | 12145-B01 | 95 RAVEN AVE | ST THOMAS | N5R0C2 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7582 | -81.1599 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9519450 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 652996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652996 | 8866454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8866454 | 9519450 | 9519450 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-061 | 11-061 | 11 | N/A | 66044 | Thames Valley DSB | Mitchell Hepburn | Mitchell Hepburn Public Elementary School | ELE | 11013 | 12145 | 12145-B01 | 95 RAVEN AVE | ST THOMAS | N5R0C2 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7582 | -81.1599 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 150 | - | - | N | - | Not Required | - | 1749951 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261719 | 0 | 1488232 | 0 | 0 | 0 | 0 | 0 | 1749951 | 1749951 | 1749951 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1488232
11-062 | 11-062 | 11 | N/A | 66044 | Thames Valley DSB | Mountsfield | Mountsfield Public Elementary School | ELE | 7898 | 8979 | 8979-B01 | 8 MOUNTSFIELD DR | LONDON | N6C2S4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9593 | -81.2434 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 70393 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70393 | 70393 | 70393 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-064-01 | 11-064 | 11 | 206 - CMSM London | 66044 | Thames Valley DSB | Cedar Hollow | Cedar Hollow Public Elementary School | ELE | 24592 | 19598 | 19598-B01 | 1800 CEDAR HOLLOW BLVD | LONDON | N5X0K3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0433 | -81.2128 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | 625 | 5 | 88 | N | 4 | Approved | 42559 | 15698729 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260424 | 0 | 11086883 | 0 | 2471422 | 880000 | 0 | 0 | 15698729 | 15698729 | 15698729 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14438305
11-064-02 | 11-064 | 11 | N/A | 66044 | Thames Valley DSB | Cedar Hollow | Cedar Hollow Public Elementary School | ELE | 24592 | 19598 | 19598-L01 | 1800 CEDAR HOLLOW BLVD | LONDON | N5X0K3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0433 | -81.2128 | 42352 | 2015-16 | 2015-16 | 42352 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42352 | 3844758 | Construction Complete | Land Acquisition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3844758 | 0 | 0 | 0 | 0 | 0 | 0 | 3844758 | 3844758 | 3844758 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3844758
11-065 | 11-065 | 11 | N/A | 66044 | Thames Valley DSB | New Sarum | New Sarum Public Elementary School | ELE | 2578 | 6951 | 6951-B01 | 9473 BELMONT RD RR 3 | ST THOMAS | N5P3S7 | 35-15-44-610 | Central Elgin | Central Elgin M | Elgin Co | ELGIN | Southwest | South | 42.7775 | -81.0836 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 70000 | Construction Complete | Demolition | Other | 2011-12 | 40787 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-066 | 11-066 | 11 | N/A | 66044 | Thames Valley DSB | North Meadows | North Meadows Public Elementary School | ELE | 5809 | 8452 | 8452-B01 | 82 MIDDLESEX DR | STRATHROY | N7G4G5 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.974 | -81.6253 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1294020 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1294020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1294020 | 1294020 | 1294020 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-067 | 11-067 | 11 | N/A | 66044 | Thames Valley DSB | North Meadows | North Meadows Public Elementary School | ELE | 5809 | 8452 | 8452-B01 | 82 MIDDLESEX DR | STRATHROY | N7G4G5 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.974 | -81.6253 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 77511 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77511 | 77511 | 77511 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-069 | 11-069 | 11 | N/A | 66044 | Thames Valley DSB | Northbrae | Northbrae Public Elementary School | ELE | 7900 | 3006 | 3006-B02 | 335 BELFIELD ST | LONDON | N5Y2K3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.016 | -81.2407 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1049814 | Construction Complete | Addition | Other | 2001-02 | 37135 | 970403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79411 | 1049814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049814 | 1049814 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-071 | 11-071 | 11 | N/A | 66044 | Thames Valley DSB | Northdale Central | Northdale Central Public Elementary School | ELE | 1664 | 6374 | 6374-B01 | 3860 CATHERINE ST | DORCHESTER | N0L1G0 | 35-15-59-622 | Thames Centre | Thames Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.9885 | -81.0743 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2656601 | Construction Complete | Addition | Other | 2001-02 | 37135 | 2535755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120846 | 2656601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2656601 | 2656601 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-072 | 11-072 | 11 | N/A | 66044 | Thames Valley DSB | Northridge | Northridge Public Elementary School | ELE | 7902 | 8983 | 8983-B01 | 25 MCLEAN DR | LONDON | N5X1Y2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.037 | -81.2348 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7366579 | Construction Complete | Addition | Other | 2010-11 | 40422 | 331566 | 0 | 0 | 0 | 0 | 468767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800333 | 1109218 | 4366737 | 0 | 0 | 0 | 1090291 | 0 | 0 | 0 | 0 | 6566246 | 7366579 | 7366579 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-073-01 | 11-073 | 11 | 206 - CMSM London | 66044 | Thames Valley DSB | Arthur Currie | Arthur Currie Public Elementary School | ELE | 24446 | 19449 | 19449-B01 | 2435 BUROAK DR | LONDON | N6G0L1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0246 | -81.3246 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | 533 | 5 | 88 | N | 4 | Approved | 42559 | 14025667 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260424 | 0 | 9373821 | 0 | 2471422 | 920000 | 0 | 0 | 14025667 | 14025667 | 14025667 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12765243
11-073-02 | 11-073 | 11 | N/A | 66044 | Thames Valley DSB | Arthur Currie | Arthur Currie Public Elementary School | ELE | 24446 | 19449 | 19449-L01 | 2435 BUROAK DR | LONDON | N6G0L1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0246 | -81.3246 | 41976 | 2014-15 | 2014-15 | 41976 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41976 | 2376475 | Construction Complete | Land Acquisition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2376475 | 0 | 0 | 0 | 0 | 0 | 0 | 2376475 | 2376475 | 2376475 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2376475
11-076 | 11-076 | 11 | N/A | 66044 | Thames Valley DSB | Oxbow | Oxbow Public Elementary School | ELE | 1738 | 6413 | 6413-B01 | 13624 ILDERTON RD | ILDERTON | N0M2A0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 43.0862 | -81.3603 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2687721 | Construction Complete | Addition | Other | 2000-01 | 36770 | 2456033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231688 | 2687721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2687721 | 2687721 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-077 | 11-077 | 11 | N/A | 66044 | Thames Valley DSB | Oxbow | Oxbow Public Elementary School | ELE | 1738 | 6413 | 6413-B01 | 13624 ILDERTON RD | ILDERTON | N0M2A0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 43.0862 | -81.3603 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 310044 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310044 | 310044 | 310044 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-078 | 11-078 | 11 | N/A | 66044 | Thames Valley DSB | Oxbow | Oxbow Public Elementary School | ELE | 1738 | 6413 | 6413-B01 | 13624 ILDERTON RD | ILDERTON | N0M2A0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 43.0862 | -81.3603 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2720789 | Construction Complete | Addition | Other | 2011-12 | 40787 | 267991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267991 | 1583629 | 0 | 869169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2452798 | 2720789 | 2720789 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-080 | 11-080 | 11 | N/A | 66044 | Thames Valley DSB | Parkview | Parkview Public Elementary School | ELE | 1770 | 6432 | 6432-B01 | 10008 OXBOW DR | KOMOKA | N0L1R0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.9568 | -81.4404 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1623779 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623779 | 1623779 | 1623779 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-081 | 11-081 | 11 | N/A | 66044 | Thames Valley DSB | Parkview | Parkview Public Elementary School | ELE | 1770 | 6432 | 6432-B01 | 10008 OXBOW DR | KOMOKA | N0L1R0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.9568 | -81.4404 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 274 | - | - | N | - | Not Required | - | 4493462 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999 | 0 | 4393463 | 0 | 0 | 0 | 0 | 0 | 4493462 | 4493462 | 4493462 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4393463
11-082 | 11-082 | 11 | N/A | 66044 | Thames Valley DSB | Pierre Elliott Trudeau | Pierre Elliott Trudeau Public Elementary School | ELE | 1104 | 6014 | 6014-B01 | 112 CHURCHILL CRES | ST THOMAS | N5R1R1 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7688 | -81.1796 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 465066 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465066 | 465066 | 465066 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-083 | 11-083 | 11 | N/A | 66044 | Thames Valley DSB | Pierre Elliott Trudeau | Pierre Elliott Trudeau Public Elementary School | ELE | 1104 | 6014 | 6014-B01 | 112 CHURCHILL CRES | ST THOMAS | N5R1R1 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7688 | -81.1796 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5568530 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 958930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510189 | 1469119 | 4099411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4099411 | 5568530 | 5568530 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-084 | 11-084 | 11 | N/A | 66044 | Thames Valley DSB | Plattsville & District | Plattsville & District Public Elementary School | ELE | 1826 | 6469 | 6469-B01 | 112 MILL ST E | PLATTSVILLE | N0J1S0 | 35-15-37-601 | Blandford-Blenheim | Blandford - Blenheim Tp | Oxford Co | OXFORD | Southwest | South | 43.3062 | -80.6137 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1379506 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1379506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1379506 | 1379506 | 1379506 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-086 | 11-086 | 11 | N/A | 66044 | Thames Valley DSB | Princess Anne | Princess Anne Public Elementary School | ELE | 7922 | 9003 | 9003-B01 | 191 DAWN DR | LONDON | N5W4W9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9918 | -81.1803 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1261885 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261885 | 1261885 | 1261885 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-089 | 11-089 | 11 | N/A | 66044 | Thames Valley DSB | River Heights | River Heights Public Elementary School | ELE | 1992 | 6583 | 6583-B01 | 4269 HAMILTON RD | DORCHESTER | N0L1G3 | 35-15-59-622 | Thames Centre | Thames Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.986 | -81.0514 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2430340 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692000 | 0 | 1738340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430340 | 2430340 | 2430340 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-090 | 11-090 | 11 | N/A | 66044 | Thames Valley DSB | Royal Roads | Royal Roads Public Elementary School | ELE | 1877 | 6508 | 6508-B01 | 210 KING ST E | INGERSOLL | N5C1H2 | 35-15-37-401 | Ingersoll | Ingersoll T | Oxford Co | OXFORD | Southwest | South | 43.0405 | -80.8728 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6162556 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 3570054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570054 | 439680 | 1718237 | 434585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592502 | 6162556 | 6162556 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-095 | 11-095 | 11 | N/A | 66044 | Thames Valley DSB | South Ridge | South Ridge Public Elementary School | ELE | 2195 | 6710 | 6710-B01 | 10 SOUTH RIDGE RD | TILLSONBURG | N4G0C1 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8838 | -80.7554 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 118 | - | - | N | - | Not Required | - | 4045000 | Construction Complete | Addition | Consolidation | 2014-15 | 41883 | 429415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 429415 | 0 | 0 | 1482852 | 0 | 2073733 | 0 | 0 | 0 | 0 | 0 | 3556585 | 3986000 | 3986000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2073733
11-096 | 11-096 | 11 | N/A | 66044 | Thames Valley DSB | Southeast London | Southeast London Land Holding | HLA | 24447 | 19450 | 19450-L0- | 2541 MEADOWGATE BLVD | LONDON | N6M1L8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9582 | -81.1794 | 41831 | 2013-14 | 2014-15 | 41831 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1826907 | Construction Complete | Land Acquisition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30907 | 30907 | 0 | 0 | 0 | 1796000 | 0 | 0 | 0 | 0 | 0 | 0 | 1796000 | 1826907 | 1826907 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1796000
11-100 | 11-100 | 11 | N/A | 66044 | Thames Valley DSB | Springbank | Springbank Public Elementary School | ELE | 2201 | 6715 | 6715-B01 | 1060 SPRUCEDALE RD | WOODSTOCK | N4S4Z9 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1415 | -80.7296 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3796359 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3579067 | 0 | 217292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3796359 | 3796359 | 3796359 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-101 | 11-101 | 11 | N/A | 66044 | Thames Valley DSB | Stoney Creek | Stoney Creek Public Elementary School | ELE | 11217 | 12226 | 12226-B01 | 1335 NICOLE AVE | LONDON | N5X4M7 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0466 | -81.2419 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13365596 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000 | 12071426 | 0 | 869170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12940596 | 13365596 | 13365596 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-103 | 11-103+38-006 | 11 | N/A | 66044 | Thames Valley DSB | Strathroy District | Strathroy District Public Secondary School | SEC | 10174 | 10446 | 10446-B01 | 361 SECOND ST | STRATHROY | N7G4J8 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.9808 | -81.6076 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17904331 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17904331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17904331 | 17904331 | 17904331 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-104 | 11-104 | 11 | N/A | 66044 | Thames Valley DSB | Strathroy District | Strathroy District Public Secondary School | SEC | 10174 | 10446 | 10446-B01 | 361 SECOND ST | STRATHROY | N7G4J8 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.9808 | -81.6076 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7674811 | Construction Complete | Addition | Other | 2007-08 | 39326 | 1500000 | 0 | 567689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49832 | 2117521 | 5557290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5557290 | 7674811 | 7674811 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-106 | 11-106 | 11 | N/A | 66044 | Thames Valley DSB | Tollgate Central | Tollgate Central Facility Holding | HFA | 2314 | 6783 | 6783-B01 | 744993 OXFORD ROAD 17 RR 6 | WOODSTOCK | N4S7W1 | 35-15-37-602 | East Zorra-Tavistock | East Zorra - Tavistock Tp | Oxford Co | OXFORD | Southwest | South | 43.1575 | -80.7752 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 155022 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155022 | 155022 | 155022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-108 | 11-108 | 11 | N/A | 66044 | Thames Valley DSB | West Nissouri | West Nissouri Public Elementary School | ELE | 11204 | 12170 | 12170-B01 | 37 ELLIOTT TRAIL RR 1 | THORNDALE | N0M2P0 | 35-15-59-622 | Thames Centre | Thames Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 43.104 | -81.1544 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8635409 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8635409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8635409 | 8635409 | 8635409 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-109 | 11-109 | 11 | N/A | 66044 | Thames Valley DSB | West Oaks | West Oaks Public Elementary School | ELE | 7932 | 9013 | 9013-B01 | 1050 PLANTATION RD | LONDON | N6H2Y5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.972 | -81.3136 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5499900 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 5024634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5024634 | 0 | 0 | 475266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475266 | 5499900 | 5499900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-110 | 11-110 | 11 | N/A | 66044 | Thames Valley DSB | Westfield | Westfield Public Elementary School | ELE | 14493 | 18014 | 18014-B01 | 102 DEREHAM DR | TILLSONBURG | N4G0G5 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8585 | -80.7488 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 602 | - | - | N | - | Not Required | - | 11350455 | Construction Complete | New Construction | Consolidation | 2015-16 | 42258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1359510 | 0 | 9917917 | 0 | 0 | 0 | 0 | 0 | 11277427 | 11277427 | 11277427 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9917917
11-111 | 11-111 | 11 | N/A | 66044 | Thames Valley DSB | Wilberforce | Wilberforce Public Elementary School | ELE | 11104 | 16802 | 16802-B01 | 340 BEECH ST | LUCAN | N0M2J0 | 35-15-59-617 | Lucan Biddulph | Lucan Biddulph Tp | Middlesex Co | MIDDLESEX | Southwest | South | 43.1944 | -81.4024 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9340494 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 1014693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270794 | 1285487 | 8055007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8055007 | 9340494 | 9340494 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-113 | 11-113 | 11 | N/A | 66044 | Thames Valley DSB | Winchester Street | Winchester Street Public Elementary School | ELE | 550 | 5661 | 5661-B01 | 110 WINCHESTER ST | WOODSTOCK | N4S7K5 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1369 | -80.7404 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4482950 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4048365 | 0 | 434585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482950 | 4482950 | 4482950 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-115 | 11-115 | 11 | 209 - CMSM St. Thomas | 66044 | Thames Valley DSB | Aldborough | Aldborough Public Elementary School | ELE | 38 | 5322 | 5322-B01 | 11443 FURNIVAL RD | RODNEY | N0L2C0 | 35-15-44-613 | West Elgin | West Elgin M | Elgin Co | ELGIN | Southwest | South | 42.5564 | -81.6692 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 4 | 64 | Y | 2 | Approved | 44314 | 3910174 | Under Construction | Addition | Child Care | 2022-23 | 44986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861501 | 1048673 | 0 | 0 | 3910174 | 3910174 | 3910174 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3910174
11-116 | 11-116 | 11 | 206 - CMSM London | 66044 | Thames Valley DSB | River Heights | River Heights Public Elementary School | ELE | 1992 | 6583 | 6583-B01 | 4269 HAMILTON RD | DORCHESTER | N0L1G3 | 35-15-59-622 | Thames Centre | Thames Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.986 | -81.0514 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 6 | 103 | Y | 1 | Approved | 44685 | 8394862 | Under Construction | Addition | Child Care | 2023-24 | 45170 | 1747547 | 0 | 373514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2121061 | 0 | 0 | 0 | 0 | 0 | 0 | 5657363 | 616438 | 0 | 0 | 6273801 | 8394862 | 8394862 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 6273801
11-117 | 11-117 | 11 | N/A | 66044 | Thames Valley DSB | Stoney Creek | Stoney Creek Public Elementary School | ELE | 11217 | 12226 | 12226-B01 | 1335 NICOLE AVE | LONDON | N5X4M7 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0466 | -81.2419 | 42461 | 2015-16 | 2016-17 | - | - | - | 42461 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | 173 | - | - | N | - | Not Required | - | 1957795 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1957795 | 0 | 0 | 0 | 0 | 0 | 1957795 | 1957795 | 1957795 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1957795
11-118 | 11-118 | 11 | N/A | 66044 | Thames Valley DSB | East Carling | East Carling Public Elementary School | ELE | 7865 | 8946 | 8946-L01 | 814 QUEBEC ST | LONDON | N5Y1X4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0032 | -81.2235 | 42866 | 2016-17 | 2017-18 | 42866 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42866 | 967680 | Construction Complete | Land Acquisition | Other | 2019-20 | 43711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967680 | 0 | 0 | 0 | 0 | 0 | 0 | 967680 | 967680 | 967680 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 967680
11-119 | 11-119 | 11 | 222 - CMSM Oxford | 66044 | Thames Valley DSB | Algonquin | Algonquin Public Elementary School | ELE | 53 | 5330 | 5330-B01 | 59 ALGONQUIN RD | WOODSTOCK | N4T1R8 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1513 | -80.7335 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 34 | Y | - | Approved | 44049 | 1516992 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1516992 | 0 | 0 | 0 | 1516992 | 1516992 | 1516992 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1516992
11-120 | 11-120 | 11 | 222 - CMSM Oxford | 66044 | Thames Valley DSB | Harrisfield | Harrisfield Public Elementary School | ELE | 1021 | 5967 | 5967-B01 | 2 CAFFYN ST | INGERSOLL | N5C3M8 | 35-15-37-401 | Ingersoll | Ingersoll T | Oxford Co | OXFORD | Southwest | South | 43.0324 | -80.8693 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557887 | 0 | 0 | 0 | 1557887 | 1557887 | 0 | -1557887 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1557887
11-121 | 11-121 | 11 | 206 - CMSM London | 66044 | Thames Valley DSB | Southeast London | Southeast London Public Elementary School | ELE | 24447 | 19450 | 19450-B0- | 2541 MEADOWGATE BLVD | LONDON | N6M1L8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9582 | -81.1794 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 556 | 5 | 88 | Y | - | Approved | 44168 | 16624053 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 556436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556436 | 0 | 0 | 1285632 | 0 | 12184535 | 0 | 2597450 | 0 | 0 | 0 | 16067617 | 16624053 | 16624053 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14781985
11-122 | 11-122 | 11 | N/A | 66044 | Thames Valley DSB | Masonville | Masonville Public Elementary School | ELE | 7897 | 8978 | 8978-B01 | 25 HILLVIEW BLVD | LONDON | N6G3A7 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0257 | -81.2844 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 253 | - | - | N | - | Approved | 43664 | 8384522 | Construction Complete | Addition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 2425564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2425564 | 0 | 0 | 0 | 0 | 5958958 | 0 | 0 | 0 | 0 | 0 | 5958958 | 8384522 | 8384522 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5958958
11-123 | 11-123 | 11 | N/A | 66044 | Thames Valley DSB | Tweedsmuir | Tweedsmuir Public Elementary School | ELE | 7928 | 9009 | 9009-B01 | 349 TWEEDSMUIR AVE | LONDON | N5W1L5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9808 | -81.1792 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43836 | 7485886 | Construction Complete | Addition | Consolidation | 2021-22 | 44562 | 1304650 | 2314350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3619000 | 0 | 0 | 0 | 0 | 3866886 | 0 | 0 | 0 | 0 | 0 | 3866886 | 7485886 | 7485886 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3866886
11-124 | 11-124 | 11 | N/A | 66044 | Thames Valley DSB | Kettle Creek | Kettle Creek Public Elementary School | ELE | 1847 | 6484 | 6484-B01 | 350 CARLOW RD | PORT STANLEY | N5L1B6 | 35-15-44-610 | Central Elgin | Central Elgin M | Elgin Co | ELGIN | Southwest | South | 42.6732 | -81.2222 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43497 | 5553309 | Construction Complete | Retrofit | Other | 2020-21 | 44075 | 256847 | 4418849 | 0 | 877613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5553309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5553309 | 5553309 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-125 | 11-125 | 11 | N/A | 66044 | Thames Valley DSB | Southside | Southside Public Elementary School | ELE | 2193 | 6708 | 6708-B01 | 360 ALBERT ST | WOODSTOCK | N4S2L4 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1185 | -80.758 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 5400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400000 | 5400000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-126 | 11-126 | 11 | N/A | 66044 | Thames Valley DSB | Belmont | Belmont Public Elementary School | ELE | 25368 | 20374 | 20374-B01 | TBD | CENTRAL ELGIN | TBD | 35-15-44-610 | Central Elgin | Central Elgin M | Elgin Co | ELGIN | Southwest | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 354 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Condition | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12172588 | 0 | 0 | 0 | 0 | 0 | 12172588 | 12172588 | 12172588 | 0 | - | No, Site to be acquired. Sign installation planned for July 1, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12172588
11-127 | 11-127 | 11 | 206 - CMSM London | 66044 | Thames Valley DSB | Northwest London | Northwest London Public Elementary School | ELE | 25498 | 20504 | 20504-B01 | TBD | LONDON | TBD | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | TBD | TBD | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 802 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16854386 | 0 | 2674120 | 0 | 0 | 0 | 19528506 | 19528506 | 19528506 | 0 | - | No, Site to be acquired. Sign installation planned for July 1, 2022 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19528506
11-128 | 11-128 | 11 | N/A | 66044 | Thames Valley DSB | Eagle Heights | Eagle Heights Public Elementary School | ELE | 7920 | 9001 | 9001-B01 | 284 OXFORD ST W | LONDON | N6H1S9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9887 | -81.2757 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 300 | - | - | N | - | Approved | 45030 | 9212657 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 1406305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1406305 | 0 | 0 | 0 | 0 | 7806352 | 0 | 0 | 0 | 0 | 0 | 7806352 | 9212657 | 9212657 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7806352
11-129 | 11-129 | 11 | 206 - CMSM London | 66044 | Thames Valley DSB | Southwest London | Southwest London Public Elementary School | ELE | 25508 | 20514 | 20514-B01 | PACK RD / BOSTWICK RD | LONDON | TBD | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9317 | -81.2913 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 804 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17892129 | 0 | 2834561 | 0 | 0 | 0 | 20726690 | 20726690 | 20726690 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 20726690
11-130 | 11-130 | 11 | 222 - CMSM Oxford | 66044 | Thames Valley DSB | North Woodstock | North Woodstock Public Elementary School | ELE | 25528 | 20534 | 20534-B01 | OXFORD RD 17 / 13TH LINE | WOODSTOCK | TBD | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1619 | -80.7587 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 856 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22277171 | 0 | 3324943 | 0 | 0 | 0 | 25602114 | 25602114 | 25602114 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 25602114
11-131 | 11-131 | 11 | N/A | 66044 | Thames Valley DSB | Education Centre | Education Centre | OFF-ADM | 7947 | 5177 | 5177-B01 | 1250 DUNDAS ST | LONDON | N5W5P2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9968 | -81.2072 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Planned | - | - | Planned | Retrofit | Other | 2022-23 | 45169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10184470 | 10184470 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
11-132 | 11-129 | 11 | N/A | 66044 | Thames Valley DSB | Southwest London | Southwest London Public Elementary School | ELE | 7865 | 8946 | 8946-L01 | 814 QUEBEC ST | LONDON | N5Y1X4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0032 | -81.2235 | 42866 | 2016-17 | 2017-18 | 42866 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - |  |  |  |  | Land Acquisition | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10184470 | 0 | 0 | 0 | 0 | 0 | 0 | 10184470 | 10184470 | 0 | -10184470 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 10184470
11-133 | 11-130 | 11 | 222 - CMSM Oxford | 66044 | Thames Valley DSB | North Woodstock | North Woodstock Public Elementary School | ELE | 25528 | 20534 | 20534-B01 | OXFORD RD 17 / 13TH LINE | WOODSTOCK | TBD | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1619 | -80.7587 |  |  |  | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - |  |  |  |  | - | Planned | - | - | Planned | New Construction | Accommodation Pressure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14686995 | 0 | 0 | 0 | 0 | 0 | 0 | 14686995 | 14686995 | 14686995 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14686995
12-001 | 12-001 | 12 | N/A | 66052 | Toronto DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39998 | 0 | 0 | 0 | 0 | 0 | 39998 | 39998 | 0 | -39998 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 39998
12-002 | 12-002 | 12 | N/A | 66052 | Toronto DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 179363081 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183420594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183420594 | 183420594 | 179363081 | -4057513 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-003 | 12-003 | 12 | N/A | 66052 | Toronto DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9820415 | Construction Complete | Other | Other | 2010-11 | 40422 | 0 | 0 | 9820415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9820415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9820415 | 9820415 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-004 | 12-004 | 12 | N/A | 66052 | Toronto DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13671507 | Construction Complete | Other | Other | 2011-12 | 40787 | 0 | 0 | 13554000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117507 | 13671507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13671507 | 13671507 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-005 | 12-005 | 12 | N/A | 66052 | Toronto DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4759001 | Construction Complete | Other | Other | 2012-13 | 41153 | 0 | 0 | 4759001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4759001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4759001 | 4759001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-006 | 12-006 | 12 | N/A | 66052 | Toronto DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4201930 | Construction Complete | Other | Other | 2013-14 | 41518 | 0 | 0 | 4201930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4201930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4201930 | 4201930 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-007 | 12-007 | 12 | N/A | 66052 | Toronto DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 20896660 | Construction Complete | Other | Other | 2014-15 | 41883 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5896660 | 20896660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20896660 | 20896660 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-008 | 12-008 | 12 | N/A | 66052 | Toronto DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 28798953 | Construction Complete | Other | Other | 2015-16 | 42248 | 0 | 0 | 28798953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28798953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28798953 | 28798953 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-009 | 12-009 | 12 | N/A | 66052 | Toronto DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 19195049 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19195049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19195049 | 19195049 | 19195049 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-010 | 12-010 | 12 | N/A | 66052 | Toronto DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1240000 | Construction Complete | Other | Other | 2013-14 | 41518 | 0 | 0 | 1240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240000 | 1240000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-011 | 12-011 | 12 | N/A | 66052 | Toronto DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2000000 | Construction Complete | Other | Other | 2015-16 | 42248 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-012 | 12-012 | 12 | N/A | 66052 | Toronto DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 8610 | 18601 | 18601-B01 | 1 CIVIC CENTRE CRT | ETOBICOKE | M9C2B3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6427 | -79.5639 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12000000 | Construction Complete | Other | Other | 2016-17 | 42614 | 0 | 0 | 11300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 12000000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-013 | 12-013 | 12 | N/A | 66052 | Toronto DSB | Agnes Macphail | Agnes Macphail Public Elementary School | ELE | 8835 | 9722 | 9722-B01 | 112 GOLDHAWK TRAIL | SCARBOROUGH | M1V1W5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8193 | -79.2784 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 301835 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101835 | 301835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301835 | 301835 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-015 | 12-015 | 12 | N/A | 66052 | Toronto DSB | Alderwood | Alderwood Public Secondary School | SEC | 3420 | 5053 | 5053-B01 | 300 VALERMO DR | ETOBICOKE | M8W2L1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6094 | -79.5337 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 267302 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 267302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267302 | 267302 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-016 | 12-016 | 12 | N/A | 66052 | Toronto DSB | Alexander Stirling | Alexander Stirling Public Elementary School | ELE | 8838 | 9724 | 9724-B01 | 70 FAWCETT TRAIL | SCARBOROUGH | M1B3A9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8117 | -79.2076 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2248048 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 1799086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799086 | 0 | 0 | 448962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448962 | 2248048 | 2248048 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-018 | 12-018 | 12 | N/A | 66052 | Toronto DSB | Alvin Curling | Alvin Curling Public Elementary School | ELE | 18577 | 19083 | 19083-B01 | 50 UPPER ROUGE TRAIL | SCARBOROUGH | M1B6K4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8086 | -79.1904 | 40716 | 2010-11 | 2011-12 | - | - | - | 40716 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 654 | - | - | N | - | Not Required | - | 15290729 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41627 | 0 | 0 | 2887821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2887821 | 0 | 0 | 959851 | 0 | 11352328 | 0 | 0 | 0 | 0 | 0 | 12312179 | 15200000 | 15200000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11352328
12-019 | 12-019 | 12 | N/A | 66052 | Toronto DSB | Appian | Appian Public Elementary School | ELE | 9044 | 9905 | 9905-B01 | 44 APPIAN DR | NORTH YORK | M2J2P9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7859 | -79.3714 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2722618 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 2722618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2722618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2722618 | 2722618 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-020 | 12-020 | 12 | N/A | 66052 | Toronto DSB | Arlington | Arlington Public Elementary School | ELE | 8714 | 9615 | 9615-B01 | 501 ARLINGTON AVE | YORK | M6C3A4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6924 | -79.4329 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 35708 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 35708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35708 | 35708 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-022-01 | 12-022 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Avondale | Avondale Public Elementary School | ELE | 24559 | 9908 | 9908-B02 | 171 AVONDALE AVE | NORTH YORK | M2N2V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7595 | -79.4004 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 875 | 5 | 88 | N | - | Approved | 43087 | 25845346 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 9514208 | 0 | 0 | 0 | 0 | 0 | 0 | 1428580 | 0 | 0 | 0 | 0 | 0 | 10942788 | 0 | 0 | 1497390 | 0 | 8519005 | 0 | 2471420 | 0 | 0 | 0 | 12487815 | 23430603 | 23430603 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10990425
12-022-02 | 12-022 | 12 | N/A | 66052 | Toronto DSB | Oakburn East | Oakburn East Public Administrative Facility | OFF-OPS | 9158 | 9908 | 9908-B01 | 171 AVONDALE AVE | NORTH YORK | M2N2V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7595 | -79.4004 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42440 | 1621950 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 1621950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1621950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1621950 | 1621950 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-022-03 | 12-022 | 12 | N/A | 66052 | Toronto DSB | Avondale | Avondale Public Elementary School | ELE | 10467 | 9908 | 9908-B01 | 171 AVONDALE AVE | NORTH YORK | M2N2V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7595 | -79.4004 | 42271 | 2015-16 | 2015-16 | - | - | - | 42271 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42440 | 956956 | Construction Complete | Demolition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 956956 | 0 | 0 | 0 | 0 | 0 | 956956 | 956956 | 956956 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 956956
12-022-04 | 12-022 | 12 | N/A | 66052 | Toronto DSB | Oakburn East | Oakburn East Public Administrative Facility | OFF-OPS | 9158 | 9908 | 9908-B01 | 171 AVONDALE AVE | NORTH YORK | M2N2V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7595 | -79.4004 | 42271 | 2015-16 | 2015-16 | - | - | - | 42271 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42440 | 1545796 | Construction Complete | Demolition | Accommodation Pressure | 2016-17 | 42727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545796 | 0 | 0 | 0 | 0 | 0 | 1545796 | 1545796 | 1545796 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1545796
12-026 | 12-026 | 12 | N/A | 66052 | Toronto DSB | Midland Lawrence | Midland Lawrence Public Secondary School | SEC | 24613 | 19620 | 19620-B01 | 125 BROCKLEY DR | SCARBOROUGH | M1P0E1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6667 | -79.3831 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 1509 | - | - | N | - | Approved | 42723 | 49406616 | Construction Complete | New Construction | Consolidation | 2019-20 | 43809 | 0 | 0 | 7205199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205199 | 0 | 0 | 0 | 0 | 42201417 | 0 | 0 | 0 | 0 | 0 | 42201417 | 49406616 | 49406616 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 42201417
12-029-01 | 12-029 | 12 | N/A | 66052 | Toronto DSB | Bloor | Bloor Public Secondary School | SEC | 24650 | 9387 | 9387-B04 | 1141 BLOOR ST W | TORONTO | M6H1M9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.659 | -79.4353 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 922 | - | - | N | - | Approved | 44432 | 52240129 | Under Construction | New Construction | Consolidation | 2023-24 | 45352 | 0 | 0 | 31891202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31891202 | 0 | 0 | 0 | 0 | 20348927 | 0 | 0 | 0 | 0 | 0 | 20348927 | 52240129 | 52240129 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 20348927
12-029-03 | 12-029 | 12 | N/A | 66052 | Toronto DSB | Brockton Learning Centre | Brockton Learning Centre | HFA | 8511 | 9387 | 9387-B02 | 90 CROATIA ST | TORONTO | M6H1K9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6582 | -79.438 | 43168 | 2017-18 | 2017-18 | - | - | - | 43168 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43168 | 5275587 | Construction Complete | Demolition | Consolidation | 2019-20 | 43817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5275587 | 0 | 0 | 0 | 0 | 0 | 5275587 | 5275587 | 5275587 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5275587
12-032 | 12-032 | 12 | N/A | 66052 | Toronto DSB | Briar Hill | Briar Hill Public Elementary School | ELE | 8716 | 9617 | 9617-B01 | 1100 BRIAR HILL AVE | YORK | M6B1M7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7031 | -79.4512 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 77862 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 77862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77862 | 77862 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-035 | 12-035 | 12 | N/A | 66052 | Toronto DSB | Brock | Brock Public Elementary School | ELE | 8364 | 9392 | 9392-B01 | 93 MARGUERETTA ST | TORONTO | M6H3S4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.653 | -79.4378 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1273406 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099849 | 0 | 173557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273406 | 1273406 | 1273406 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-036 | 12-036 | 12 | N/A | 66052 | Toronto DSB | Brock | Brock Public Elementary School | ELE | 8364 | 9392 | 9392-B01 | 93 MARGUERETTA ST | TORONTO | M6H3S4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.653 | -79.4378 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1273794 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 1273794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273794 | 1273794 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-038 | 12-038 | 12 | N/A | 66052 | Toronto DSB | Brookside | Brookside Public Elementary School | ELE | 10928 | 12065 | 12065-B01 | 75 OASIS BLVD | SCARBOROUGH | M1X0A3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8278 | -79.2345 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 15276706 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 15176949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99757 | 15276706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15276706 | 15276706 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-045 | 12-045 | 12 | N/A | 66052 | Toronto DSB | Cedarbrook | Cedarbrook Public Elementary School | ELE | 8821 | 9709 | 9709-B01 | 56 NELSON ST | SCARBOROUGH | M1J2V6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7477 | -79.23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1805797 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1585797 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1805797 | 1805797 | 1805797 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-046 | 12-046 | 12 | N/A | 66052 | Toronto DSB | Cedarvale | Cedarvale Public Elementary School | ELE | 8718 | 9619 | 9619-B01 | 145 AVA RD | YORK | M6C1W4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6959 | -79.4302 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1022788 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457048 | 0 | 565740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1022788 | 1022788 | 1022788 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-047 | 12-047 | 12 | N/A | 66052 | Toronto DSB | Cedarvale | Cedarvale Public Elementary School | ELE | 8718 | 9619 | 9619-B01 | 145 AVA RD | YORK | M6C1W4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6959 | -79.4302 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3936398 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 3936398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3936398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3936398 | 3936398 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-049 | 12-049 | 12 | N/A | 66052 | Toronto DSB | Charles E Webster | Charles E Webster Public Elementary School | ELE | 8719 | 9620 | 9620-B01 | 1900 KEELE ST | YORK | M6M3X7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6933 | -79.476 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4444061 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 4219308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4219308 | 114753 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224753 | 4444061 | 4444061 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-050 | 12-050 | 12 | N/A | 66052 | Toronto DSB | Charles Gordon Senior | Charles Gordon Senior Public Elementary School | ELE | 8824 | 9711 | 9711-B02 | 25 MARCOS BLVD | SCARBOROUGH | M1K5A7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7463 | -79.2604 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 280645 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280645 | 280645 | 280645 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-052 | 12-052 | 12 | N/A | 66052 | Toronto DSB | Chief Dan George | Chief Dan George Public Elementary School | ELE | 8828 | 9715 | 9715-B01 | 185 GENERATION BLVD | SCARBOROUGH | M1B2K5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8026 | -79.1644 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1485259 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 785258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785258 | 0 | 0 | 700001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700001 | 1485259 | 1485259 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-054 | 12-054 | 12 | N/A | 66052 | Toronto DSB | Churchill | Churchill Public Elementary School | ELE | 9082 | 9938 | 9938-B01 | 188 CHURCHILL AVE | NORTH YORK | M2N1Z5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7711 | -79.4266 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10286715 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 0 | 0 | 0 | 0 | 60105 | 2360105 | 7478584 | 0 | 448026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7926610 | 10286715 | 10286715 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-057 | 12-057 | 12 | N/A | 66052 | Toronto DSB | Claude Watson for the Arts | Claude Watson for the Arts Public Elementary School | ELE | 10905 | 9939 | 9939-B01 | 130 DORIS AVE | NORTH YORK | M2N0A8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7657 | -79.4094 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11207466 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 11101914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105552 | 11207466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11207466 | 11207466 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-061 | 12-061 | 12 | N/A | 66052 | Toronto DSB | Crescent Town | Crescent Town Public Elementary School | ELE | 9014 | 9882 | 9882-B01 | 4 MASSEY SQ | EAST YORK | M4C5M9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6969 | -79.292 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8754875 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 7353077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401798 | 8754875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8754875 | 8754875 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-062 | 12-062 | 12 | N/A | 66052 | Toronto DSB | Crescent Town | Crescent Town Public Elementary School | ELE | 9014 | 9882 | 9882-B01 | 4 MASSEY SQ | EAST YORK | M4C5M9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6969 | -79.292 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6154502 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 878599 | 878599 | 5000740 | 0 | 275163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5275903 | 6154502 | 6154502 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-065-01 | 12-065 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Davisville Junior | Davisville Junior Public Elementary School | ELE | 24637 | 5143 | 5143-B02 | 43 MILLWOOD RD | TORONTO | M4S1J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6992 | -79.3948 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 728 | 5 | 62 | N | - | Approved | 44503 |  | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44446 | 0 | 0 | 5392659 | 0 | 0 | 0 | 0 | 0 | 0 | 8335000 | 0 | 0 | 0 | 0 | 0 | 13727659 | 0 | 0 | 1272782 | 0 | 17335540 | 0 | 2594993 | 0 | 0 | 0 | 21203315 | 34930974 | 34930974 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19930533
12-065-03 | 12-065 | 12 | N/A | 66052 | Toronto DSB | Davisville Junior | Davisville Junior Public Elementary School | ELE | 8384 | 5143 | 5143-B01 | 43 MILLWOOD RD | TORONTO | M4S1J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6994 | -79.3948 | 43157 | 2017-18 | 2017-18 | - | - | - | 43157 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43157 | 3032638 | Construction Complete | Demolition | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3032638 | 0 | 0 | 0 | 0 | 0 | 3032638 | 3032638 | 3032638 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3032638
12-066 | 12-066 | 12 | N/A | 66052 | Toronto DSB | Davisville Junior | Davisville Junior Public Elementary School | ELE | 8384 | 5143 | 5143-B01 | 43 MILLWOOD RD | TORONTO | M4S1J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6994 | -79.3948 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 210516 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210516 | 210516 | 210516 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-071 | 12-071 | 12 | N/A | 66052 | Toronto DSB | Dovercourt | Dovercourt Public Elementary School | ELE | 8389 | 9410 | 9410-B01 | 228 BARTLETT AVE | TORONTO | M6H3G4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.667 | -79.4361 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1813804 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534664 | 0 | 279140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813804 | 1813804 | 1813804 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-072 | 12-072 | 12 | N/A | 66052 | Toronto DSB | Dovercourt | Dovercourt Public Elementary School | ELE | 8389 | 9410 | 9410-B01 | 228 BARTLETT AVE | TORONTO | M6H3G4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.667 | -79.4361 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1386808 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386808 | 1386808 | 1386808 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-077 | 12-077 | 12 | N/A | 66052 | Toronto DSB | Earl Haig | Earl Haig Public Secondary School | SEC | 9107 | 9958 | 9958-B01 | 100 PRINCESS AVE | NORTH YORK | M2N3R7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7698 | -79.4064 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 168 | - | - | N | - | Approved | 42828 | 1765593 | Construction Complete | Retrofit | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765593 | 0 | 0 | 0 | 0 | 0 | 1765593 | 1765593 | 1765593 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1765593
12-078 | 12-078 | 12 | N/A | 66052 | Toronto DSB | Eastview | Eastview Public Elementary School | ELE | 8874 | 9758 | 9758-B01 | 20 WALDOCK ST | SCARBOROUGH | M1E2E5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7591 | -79.191 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3374910 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 2001622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001622 | 716658 | 0 | 656630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373288 | 3374910 | 3374910 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-083 | 12-083 | 12 | N/A | 66052 | Toronto DSB | Essex Junior & Senior | Essex Junior & Senior Public Elementary School | ELE | 8402 | 9421 | 9421-B01 | 50 ESSEX ST | TORONTO | M6G1T3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6683 | -79.4223 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 700130 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100130 | 700130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700130 | 700130 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-084 | 12-084 | 12 | N/A | 66052 | Toronto DSB | Fairbank | Fairbank Public Elementary School | ELE | 8726 | 9627 | 9627-B01 | 2335 DUFFERIN ST | YORK | M6E3S5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6944 | -79.4492 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2575714 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 2575714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575714 | 2575714 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-085 | 12-085 | 12 | N/A | 66052 | Toronto DSB | Fairmeadow | Operational Office | OFF-OPS | 9114 | 9964 | 9964-B01 | 17 FAIRMEADOW AVE | NORTH YORK | M2P1W6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.755 | -79.3968 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 131990 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 131990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131990 | 131990 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-090 | 12-090 | 12 | N/A | 66052 | Toronto DSB | Forest Manor | Forest Manor Public Elementary School | ELE | 9122 | 9970 | 9970-B01 | 25 FOREST MANOR RD | NORTH YORK | M2J1M4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7714 | -79.3432 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2240422 | Construction Complete | Addition | Other | 2009-10 | 40057 | 59418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084961 | 1144379 | 1096043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096043 | 2240422 | 2240422 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-092 | 12-092 | 12 | N/A | 66052 | Toronto DSB | Fraser Mustard Early Learning | Fraser Mustard Early Learning Public Elementary School | ELE | 13991 | 9889 | 9889-B02 | 82 THORNCLIFFE PARK DR | EAST YORK | M4H0A2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7065 | -79.3432 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 24538176 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4077906 | 4077906 | 14187910 | 0 | 6272360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20460270 | 24538176 | 24538176 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-098 | 12-098 | 12 | N/A | 66052 | Toronto DSB | George Webster | George Webster Public Elementary School | ELE | 24679 | 9897 | 9897-B02 | 50 CHAPMAN AVE | EAST YORK | M4B1C5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6888 | -79.5183 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 848 | - | - | N | - | Approved | 42445 | 21086846 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 14567201 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 16967201 | 0 | 0 | 2869701 | 0 | 3649944 | 0 | 0 | 0 | 0 | 0 | 6519645 | 23486846 | 23486846 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3649944
12-099 | 12-099 | 12 | N/A | 66052 | Toronto DSB | Givins/Shaw Junior | Givins/Shaw Junior Public Elementary School | ELE | 8450 | 9460 | 9460-B01 | 49 GIVINS ST | TORONTO | M6J2X5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6463 | -79.4177 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 80696 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 80696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80696 | 80696 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-105 | 12-105 | 12 | N/A | 66052 | Toronto DSB | Heron Park Junior | Heron Park Junior Public Elementary School | ELE | 8893 | 9776 | 9776-B01 | 280 MANSE RD | SCARBOROUGH | M1E3V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7681 | -79.1764 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 45152 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 45152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45152 | 45152 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-106 | 12-106 | 12 | N/A | 66052 | Toronto DSB | Highcastle | Highcastle Public Elementary School | ELE | 8894 | 9777 | 9777-B01 | 370 MILITARY TRAIL | SCARBOROUGH | M1E4E6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7867 | -79.2125 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1496887 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 1228500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 | 0 | 0 | 268387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268387 | 1496887 | 1496887 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-107 | 12-107 | 12 | N/A | 66052 | Toronto DSB | Highfield Junior | Highfield Junior Public Elementary School | ELE | 8623 | 9551 | 9551-B01 | 85 MOUNT OLIVE DR | ETOBICOKE | M9V2C9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7455 | -79.5893 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8359557 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506257 | 1506257 | 5350999 | 1502301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6853300 | 8359557 | 8359557 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-110 | 12-110 | 12 | N/A | 66052 | Toronto DSB | Hodgson Middle | Hodgson Middle Public Elementary School | ELE | 8462 | 9470 | 9470-B01 | 282 DAVISVILLE AVE | TORONTO | M4S1H2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7011 | -79.3849 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1200352 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200352 | 1200352 | 1200352 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-115 | 12-115 | 12 | N/A | 66052 | Toronto DSB | Humewood | Humewood Public Elementary School | ELE | 8734 | 9635 | 9635-B01 | 15 CHERRYWOOD AVE | YORK | M6C2X4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6865 | -79.428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2988024 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742979 | 0 | 1245045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2988024 | 2988024 | 2988024 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-119 | 12-119 | 12 | N/A | 66052 | Toronto DSB | John McCrae | John McCrae Public Elementary School | ELE | 8956 | 9833 | 9833-B01 | 431 MCCOWAN RD | SCARBOROUGH | M1J1J1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.744 | -79.2399 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 714311 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714311 | 714311 | 714311 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-120 | 12-120 | 12 | N/A | 66052 | Toronto DSB | John McCrae | John McCrae Public Elementary School | ELE | 8956 | 9833 | 9833-B01 | 431 MCCOWAN RD | SCARBOROUGH | M1J1J1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.744 | -79.2399 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7789000 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 5699735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5699735 | 0 | 0 | 2089265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2089265 | 7789000 | 7789000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-122 | 12-122 | 12 | N/A | 66052 | Toronto DSB | Joseph Brant | Joseph Brant Public Elementary School | ELE | 8957 | 9776 | 9776-B02 | 270 MANSE RD | SCARBOROUGH | M1E3V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7668 | -79.1763 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8385369 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 6467104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6467104 | 850294 | 0 | 1067971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918265 | 8385369 | 8385369 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-123 | 12-123 | 12 | N/A | 66052 | Toronto DSB | JR Wilcox | JR Wilcox Public Elementary School | ELE | 8736 | 9637 | 9637-B01 | 231 AVA RD | YORK | M6C1X3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6947 | -79.4363 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1533562 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849802 | 0 | 683760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533562 | 1533562 | 1533562 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-124 | 12-124 | 12 | N/A | 66052 | Toronto DSB | JR Wilcox | JR Wilcox Public Elementary School | ELE | 8736 | 9637 | 9637-B01 | 231 AVA RD | YORK | M6C1X3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6947 | -79.4363 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3582028 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 3582028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3582028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3582028 | 3582028 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-125 | 12-125 | 12 | N/A | 66052 | Toronto DSB | Keele Street | Keele Street Public Elementary School | ELE | 8480 | 9502 | 9502-B01 | 99 MOUNTVIEW AVE | TORONTO | M6P2L5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6572 | -79.4616 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 253 | - | - | N | - | Approved | 42828 | 7662045 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 0 | 0 | 956418 | 0 | 0 | 0 | 0 | 0 | 0 | 545453 | 0 | 0 | 0 | 0 | 0 | 1501871 | 0 | 0 | 1552834 | 0 | 4593782 | 0 | 0 | 0 | 0 | 0 | 6146616 | 7648487 | 7648487 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4593782
12-126 | 12-126 | 12 | N/A | 66052 | Toronto DSB | Keelesdale Junior | Keelesdale Junior Public Elementary School | ELE | 8738 | 9639 | 9639-B01 | 200 BICKNELL AVE | YORK | M6M4G9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.687 | -79.4779 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 226323 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226323 | 226323 | 226323 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-127 | 12-127 | 12 | N/A | 66052 | Toronto DSB | Kennedy | Kennedy Public Elementary School | ELE | 8963 | 9836 | 9836-B01 | 20 ELMFIELD CRES | SCARBOROUGH | M1V2Y6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8186 | -79.3085 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5576036 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101052 | 101052 | 4264673 | 1210311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5474984 | 5576036 | 5576036 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-128 | 12-128 | 12 | N/A | 66052 | Toronto DSB | Kent Senior | Kent Senior Facility Holding | HFA | 8482 | 9387 | 9387-B01 | 980 DUFFERIN ST | TORONTO | M6H4B4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6586 | -79.435 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 175718 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 175718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175718 | 175718 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-129 | 12-129 | 12 | N/A | 66052 | Toronto DSB | Kenton | Kenton Public Care & Treatment | ELE-CTF | 9138 | 9986 | 9986-B01 | 34 KENTON DR | NORTH YORK | M2R2H8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7795 | -79.4402 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 152305 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 152305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152305 | 152305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-133 | 12-133 | 12 | N/A | 66052 | Toronto DSB | Knob Hill | Knob Hill Public Elementary School | ELE | 8964 | 9837 | 9837-B01 | 25 SEMINOLE AVE | SCARBOROUGH | M1J1M8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7449 | -79.2498 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2629456 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2480461 | 0 | 148995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2629456 | 2629456 | 2629456 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-138 | 12-138 | 12 | N/A | 66052 | Toronto DSB | Maurice Cody Junior | Maurice Cody Junior Public Elementary School | ELE | 8495 | 9497 | 9497-B01 | 364 BELSIZE DR | TORONTO | M4S1N2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7046 | -79.3779 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4941441 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 4141456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4141456 | 0 | 0 | 799985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799985 | 4941441 | 4941441 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-139 | 12-139 | 12 | N/A | 66052 | Toronto DSB | McCowan Road Junior | McCowan Road Junior Child Care | EYC | 8978 | 9851 | 9851-B01 | 425 MCCOWAN RD | SCARBOROUGH | M1J1J1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7438 | -79.2388 | 41708 | 2013-14 | 2013-14 | - | - | - | 41708 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42156 | 738826 | Construction Complete | Retrofit | Child Care | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 153883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153883 | 0 | 0 | 0 | 0 | 584943 | 0 | 0 | 0 | 0 | 0 | 584943 | 738826 | 738826 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 584943
12-141 | 12-141 | 12 | N/A | 66052 | Toronto DSB | McNicoll | McNicoll Facility Holding | HFA | 9149 | 9997 | 9997-B01 | 155 MCNICOLL AVE | NORTH YORK | M2H2C1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7991 | -79.358 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 952200 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 952200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952200 | 952200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-145 | 12-145 | 12 | N/A | 66052 | Toronto DSB | Nelson Mandela Park | Nelson Mandela Park Public Elementary School | ELE | 8416 | 9433 | 9433-B01 | 440 SHUTER ST | TORONTO | M5A1X6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6585 | -79.361 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 30760547 | Construction Complete | Retrofit | Condition | 2013-14 | 41518 | 0 | 0 | 9450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4358600 | 13808600 | 8251947 | 0 | 0 | 0 | 0 | 8700000 | 0 | 0 | 0 | 0 | 16951947 | 30760547 | 30760547 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-147 | 12-147 | 12 | N/A | 66052 | Toronto DSB | Norseman Junior & Middle | Norseman Junior & Middle Public Elementary School | ELE | 8660 | 9578 | 9578-B01 | 105 NORSEMAN ST | ETOBICOKE | M8Z2R1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6342 | -79.5162 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 322 | - | - | N | - | Approved | 43227 | 6515961 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6515961 | 0 | 0 | 0 | 0 | 0 | 6515961 | 6515961 | 6515961 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6515961
12-148 | 12-148 | 12 | N/A | 66052 | Toronto DSB | North Toronto | North Toronto Public Secondary School | SEC | 14016 | 12259 | 12259-B01 | 17 BROADWAY AVE | TORONTO | M4P1T7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7099 | -79.3961 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 52265115 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 3931126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48333989 | 52265115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52265115 | 52265115 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-155 | 12-155 | 12 | N/A | 66052 | Toronto DSB | Pauline Junior | Pauline Junior Public Elementary School | ELE | 8419 | 5030 | 5030-B01 | 100 PAULINE AVE | TORONTO | M6H3M8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6625 | -79.4395 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 298211 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90042 | 0 | 208169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298211 | 298211 | 298211 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-156 | 12-156 | 12 | N/A | 66052 | Toronto DSB | Peckham Centre | Administrative Office | OFF-ADM | 9165 | 10012 | 10012-B02 | 296 PLEASANT AVE | NORTH YORK | M2R2R1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7903 | -79.4343 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 981905 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181905 | 981905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981905 | 981905 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-158 | 12-158 | 12 | N/A | 66052 | Toronto DSB | Peter Secor Junior | Peter Secor Junior Public Elementary School | ELE | 8992 | 9864 | 9864-B02 | 255 CORONATION DR | SCARBOROUGH | M1E2J3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7626 | -79.1797 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 102580 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 102580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102580 | 102580 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-160 | 12-160 | 12 | N/A | 66052 | Toronto DSB | Rawlinson | Rawlinson Public Elementary School | ELE | 8743 | 9642 | 9642-B01 | 231 GLENHOLME AVE | YORK | M6E3C7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6841 | -79.4394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1318321 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121000 | 0 | 197321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318321 | 1318321 | 1318321 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-163 | 12-163 | 12 | N/A | 66052 | Toronto DSB | Regent Park/Duke of York Junior | Regent Park/Duke of York Junior Public Elementary School | ELE | 8426 | 9440 | 9440-B01 | 20 REGENT ST | TORONTO | M5A3N6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6581 | -79.3642 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 324805 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 201600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123205 | 324805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324805 | 324805 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-164 | 12-164 | 12 | N/A | 66052 | Toronto DSB | RH McGregor | RH McGregor Public Elementary School | ELE | 9034 | 9879 | 9879-B01 | 555 MORTIMER AVE | EAST YORK | M4J2G9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.69 | -79.3271 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1610624 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 805312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805312 | 0 | 0 | 805312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805312 | 1610624 | 1610624 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-172 | 12-172 | 12 | N/A | 66052 | Toronto DSB | SCAS | SCAS Public Secondary School | SEC | 8981 | 9754 | 9754-B01 | 720 MIDLAND AVE | SCARBOROUGH | M1K4C9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7281 | -79.2573 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2097104 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 2083038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2083038 | 0 | 0 | 14066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14066 | 2097104 | 2097104 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-174 | 12-174 | 12 | N/A | 66052 | Toronto DSB | Silverthon Community | Silverthon Community Public Elementary School | ELE | 8737 | 9638 | 9638-B02 | 300 KANE AVE | YORK | M6M3P1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6872 | -79.4699 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3922854 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3276909 | 0 | 645945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3922854 | 3922854 | 3922854 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-175 | 12-175 | 12 | N/A | 66052 | Toronto DSB | Silverthon Community | Silverthon Community Public Elementary School | ELE | 8737 | 9638 | 9638-B02 | 300 KANE AVE | YORK | M6M3P1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6872 | -79.4699 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 221961 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 221961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221961 | 221961 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-177-1 | 12-177-1 | 12 | N/A | 66052 | Toronto DSB | West Hill | West Hill Public Secondary School | SEC | 8926 | 9808 | 9808-B01 | 350 MORNINGSIDE AVE | SCARBOROUGH | M1E3G3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7757 | -79.191 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42559 | 1873390 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873390 | 0 | 0 | 0 | 0 | 0 | 1873390 | 1873390 | 1881053 | 7663 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1873390
12-177-2 | 12-177-2 | 12 | N/A | 66052 | Toronto DSB | Sir Wilfrid Laurier | Sir Wilfrid Laurier Public Secondary School | SEC | 8901 | 9784 | 9784-B01 | 145 GUILDWOOD PKY | SCARBOROUGH | M1E1P5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7466 | -79.1967 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42559 | 266390 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266390 | 0 | 0 | 0 | 0 | 0 | 266390 | 266390 | 258727 | -7663 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 266390
12-178 | 12-178 | 12 | N/A | 66052 | Toronto DSB | Sprucecourt | Sprucecourt Public Elementary School | ELE | 8440 | 9452 | 9452-B01 | 70 SPRUCE ST | TORONTO | M5A2J1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6646 | -79.364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3860000 | Construction Complete | Addition | Other | 2016-17 | 42614 | 0 | 0 | 3860000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3860000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3860000 | 3860000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-181 | 12-181 | 12 | N/A | 66052 | Toronto DSB | Swansea Junior & Senior | Swansea Junior & Senior Public Elementary School | ELE | 8508 | 9507 | 9507-B01 | 207 WINDERMERE AVE | TORONTO | M6S3J9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6437 | -79.4757 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 340 | - | - | N | - | Approved | 41768 | 11083169 | Construction Complete | Addition | Condition | 2016-17 | 42614 | 0 | 0 | 212274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212274 | 0 | 0 | 1359045 | 0 | 7297699 | 0 | 0 | 0 | 0 | 0 | 8656744 | 8869018 | 8869018 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7297699
12-183 | 12-183 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Terry Fox | Terry Fox Public Elementary School | ELE | 8910 | 9792 | 9792-B01 | 185 WINTERMUTE BLVD | SCARBOROUGH | M1W3M9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8158 | -79.319 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 276 | 5 | 88 | N | - | Approved | 44376 | 12396337 | Under Construction | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 1751060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1751060 | 0 | 0 | 0 | 0 | 7656043 | 0 | 2989234 | 0 | 0 | 0 | 10645277 | 12396337 | 12396337 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10645277
12-184 | 12-184 | 12 | N/A | 66052 | Toronto DSB | Thomas L Wells | Thomas L Wells Public Elementary School | ELE | 10711 | 11186 | 11186-B01 | 69 NIGHTSTAR RD | SCARBOROUGH | M1X1V6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8244 | -79.2263 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16032877 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 13740261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2292616 | 16032877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16032877 | 16032877 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-186 | 12-186 | 12 | N/A | 66052 | Toronto DSB | Thorncliffe Park | Thorncliffe Park Public Elementary School | ELE | 9023 | 9889 | 9889-B01 | 80 THORNCLIFFE PARK DR | EAST YORK | M4H1K3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7052 | -79.3434 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 15004093 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 12569321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2434772 | 15004093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15004093 | 15004093 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-191 | 12-191 | 12 | N/A | 66052 | Toronto DSB | Valley Park Middle | Valley Park Middle Public Elementary School | ELE | 9024 | 9890 | 9890-B01 | 130 OVERLEA BLVD | NORTH YORK | M3C1B2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7102 | -79.3354 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7648349 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 7571766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76583 | 7648349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7648349 | 7648349 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-199 | 12-199 | 12 | N/A | 66052 | Toronto DSB | West Preparatory Junior | West Preparatory Junior Public Elementary School | ELE | 8515 | 9510 | 9510-B01 | 70 RIDGE HILL DR | TORONTO | M6C2J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7028 | -79.4332 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1688688 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585000 | 0 | 0 | 1103688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1103688 | 1688688 | 1688688 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-200 | 12-200 | 12 | N/A | 66052 | Toronto DSB | West Toronto | West Toronto Public Secondary School | SEC | 8516 | 9511 | 9511-B01 | 330 LANSDOWNE AVE | TORONTO | M6H3Y1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6524 | -79.4411 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 300940 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940 | 300940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300940 | 300940 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-201 | 12-201 | 12 | N/A | 66052 | Toronto DSB | William G Miller | William G Miller Public Elementary School | ELE | 8933 | 9815 | 9815-B01 | 60 BENNETT RD | SCARBOROUGH | M1E3Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7686 | -79.165 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5427017 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 4158818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4158818 | 0 | 128599 | 1139600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268199 | 5427017 | 5427017 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-202 | 12-202 | 12 | N/A | 66052 | Toronto DSB | William G Miller | William G Miller Public Elementary School | ELE | 8933 | 9815 | 9815-B01 | 60 BENNETT RD | SCARBOROUGH | M1E3Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7686 | -79.165 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 149885 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 149885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149885 | 149885 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-210 | 12-210 | 12 | N/A | 66052 | Toronto DSB | Hodgson | Hodgson Public Middle School | ELE | 8462 | 9470 | 9470-B01 | 282 DAVISVILLE AVE | TORONTO | M4S1H2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7011 | -79.3849 | 42695 | 2016-17 | 2016-17 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 391 | - | - | N | - | Planned | - | 0 | Planned | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18286235 | 0 | 0 | 0 | 0 | 0 | 18286235 | 18286235 | 18286235 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 18286235
12-211 | 12-211 | 12 | N/A | 66052 | Toronto DSB | Courcelette | Courcelette Public Elementary School | ELE | 8857 | 9743 | 9743-B01 | 100 FALLINGBROOK RD | SCARBOROUGH | M1N2T6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6791 | -79.2785 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Planned | - | 0 | Planned | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3221934 | 0 | 0 | 0 | 0 | 0 | 3221934 | 3221934 | 3221934 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3221934
12-212-1 | 12-212-1 | 12 | N/A | 66052 | Toronto DSB | Danforth | Danforth Public Secondary School | SEC | 8383 | 9406 | 9406-B02 | 800 GREENWOOD AVE | TORONTO | M4J4B7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6828 | -79.3341 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42803 | 3783266 | Construction Complete | Retrofit | Consolidation | 2017-18 | 43101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3783266 | 0 | 0 | 0 | 0 | 0 | 3783266 | 3783266 | 3021574 | -761692 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3783266
12-212-2 | 12-212-2 | 12 | N/A | 66052 | Toronto DSB | Monarch Park | Monarch Park Public Secondary School | SEC | 8500 | 9499 | 9499-B01 | 1 HANSON ST | TORONTO | M4J1G6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6786 | -79.3231 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42803 | 845508 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845508 | 0 | 0 | 0 | 0 | 0 | 845508 | 845508 | 1414317 | 568809 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 845508
12-213 | 12-213 | 12 | N/A | 66052 | Toronto DSB | Castlebar | Castlebar Public Elementary School | ELE | 8600 | 9535 | 9535-B01 | 70 CHARTWELL RD | ETOBICOKE | M8Z4G6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6306 | -79.5138 | 42510 | 2015-16 | 2016-17 | - | - | - | 42510 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42773 | 1044187 | Construction Complete | Retrofit | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1044187 | 0 | 0 | 0 | 0 | 0 | 1044187 | 1044187 | 1044187 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1044187
12-214 | 12-214 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Bala Avenue | Bala Avenue Public Elementary School | ELE | 8715 | 9616 | 9616-B01 | 6 BALA AVE | YORK | M6M2E1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6894 | -79.4994 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542761 | 0 | 0 | 0 | 1542761 | 1542761 | 1542761 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542761
12-215 | 12-215 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Chalkfarm | Chalkfarm Public Elementary School | ELE | 9077 | 9933 | 9933-B01 | 100 CHALKFARM DR | NORTH YORK | M3L1L4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7273 | -79.5146 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542761 | 0 | 0 | 0 | 1542761 | 1542761 | 1542761 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542761
12-216 | 12-216 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Gracedale | Gracedale Public Elementary School | ELE | 9131 | 9979 | 9979-B01 | 186 GRACEDALE BLVD | NORTH YORK | M9L2C1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7533 | -79.5622 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44579 | 3466800 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 831080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 831080 | 0 | 0 | 0 | 0 | 0 | 0 | 2635720 | 0 | 0 | 0 | 2635720 | 3466800 | 3466800 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2635720
12-217 | 12-217 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Macklin | Macklin Public Elementary School | ELE | 8971 | 9844 | 9844-B01 | 136 INGLETON BLVD | SCARBOROUGH | M1V2Y4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8221 | -79.2675 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44579 | 2981075 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 912338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912338 | 0 | 0 | 0 | 0 | 0 | 0 | 2068737 | 0 | 0 | 0 | 2068737 | 2981075 | 2981075 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2068737
12-218 | 12-218 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Miliken | Miliken Public Elementary School | ELE | 8983 | 9855 | 9855-B01 | 130 PORT ROYAL TRAIL | SCARBOROUGH | M1V2T4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8166 | -79.2885 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44579 | 2587049 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 695361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695361 | 0 | 0 | 0 | 0 | 0 | 0 | 1891688 | 0 | 0 | 0 | 1891688 | 2587049 | 2587049 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1891688
12-219 | 12-219 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Pelmo Park | Pelmo Park Public Elementary School | ELE | 9166 | 10013 | 10013-B01 | 180 GARY DR | NORTH YORK | M9N2M1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7124 | -79.5176 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542761 | 0 | 0 | 0 | 1542761 | 1542761 | 1542761 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542761
12-220 | 12-220+40-134 | 12 | N/A | 66052 | Toronto DSB | Jean Lumb | Jean Lumb Public Elementary School | ELE | 24655 | 19639 | 19639-B01 | 20 BRUNEL CRT | TORONTO | M5V0R5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.639 | -79.3945 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 545 | - | - | N | - | Approved | 42912 | 20854151 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20854151 | 20854151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20854151 | 20854151 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-223 | 12-223 | 12 | N/A | 66052 | Toronto DSB | Fisherville Senior | Fisherville Senior Public Elementary School | ELE | 9119 | 5067 | 5067-B01 | 425 PATRICIA AVE | NORTH YORK | M2R2N1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7843 | -79.4418 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 543103 | Construction Complete | Retrofit | Other | 2016-17 | 42614 | 0 | 0 | 543103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543103 | 543103 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-224 | 12-224 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Birch Cliff | Birch Cliff Public Elementary School | ELE | 8851 | 9737 | 9737-B01 | 1650 KINGSTON RD | SCARBOROUGH | M1N1S2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.692 | -79.2656 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44579 | 3583904 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 1111203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111203 | 0 | 0 | 0 | 0 | 0 | 0 | 2472701 | 0 | 0 | 0 | 2472701 | 3583904 | 3583904 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2472701
12-225 | 12-225 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Dixon Grove | Dixon Grove Public Elementary School | ELE | 8607 | 9541 | 9541-B01 | 315 THE WESTWAY | ETOBICOKE | M9R1H1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6849 | -79.5561 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 4518639 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 910641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910641 | 0 | 0 | 0 | 0 | 0 | 0 | 3607998 | 0 | 0 | 0 | 3607998 | 4518639 | 4518639 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3607998
12-226 | 12-226 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Elmbank | Elmbank Public Elementary School | ELE | 8611 | 9544 | 9544-B01 | 10 PITTSBORO DR | ETOBICOKE | M9V3R4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.736 | -79.59 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Retrofit | Child Care | 2023-24 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285635 | 0 | 0 | 0 | 1285635 | 1285635 | 1285635 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1285635
12-227 | 12-227 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Kingsview Village Junior | Kingsview Village Junior Public Elementary School | ELE | 8635 | 9562 | 9562-B01 | 1 YORK RD | ETOBICOKE | M9R3C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6978 | -79.5506 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 5065910 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 869720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869720 | 0 | 0 | 0 | 0 | 0 | 0 | 4196190 | 0 | 0 | 0 | 4196190 | 5065910 | 5065910 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 4196190
12-228 | 12-228 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Valleyfield Junior | Valleyfield Junior Public Elementary School | ELE | 8690 | 9604 | 9604-B01 | 35 SASKATOON DR | ETOBICOKE | M9P2E8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6938 | -79.5381 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571270 | 0 | 0 | 0 | 2571270 | 2571270 | 2571270 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2571270
12-229 | 12-229 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Weston Memorial Junior | Weston Memorial Junior Public Elementary School | ELE | 8751 | 9650 | 9650-B01 | 200 JOHN ST | YORK | M9N1K2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7061 | -79.5091 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
12-230 | 12-230 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Alexander Stirling | Alexander Stirling Public Elementary School | ELE | 8838 | 9724 | 9724-B01 | 70 FAWCETT TRAIL | SCARBOROUGH | M1B3A9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8117 | -79.2076 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 5267063 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 804645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 804645 | 0 | 0 | 0 | 0 | 0 | 0 | 4462418 | 0 | 0 | 0 | 4462418 | 5267063 | 5267063 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 4462418
12-231 | 12-231 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Dorset Park | Dorset Park Public Elementary School | ELE | 8864 | 9748 | 9748-B01 | 28 BLAISDALE RD | SCARBOROUGH | M1P1V6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7502 | -79.2787 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44579 | 2936947 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 898046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898046 | 0 | 0 | 0 | 0 | 0 | 0 | 2038901 | 0 | 0 | 0 | 2038901 | 2936947 | 2936947 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2038901
12-232 | 12-232 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Ellesmere-Statton | Ellesmere-Statton Public Elementary School | ELE | 8878 | 9761 | 9761-B01 | 739 ELLESMERE RD | SCARBOROUGH | M1P2W1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7632 | -79.2872 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 3952825 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 184017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184017 | 0 | 0 | 0 | 0 | 0 | 0 | 3768808 | 0 | 0 | 0 | 3768808 | 3952825 | 3952825 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3768808
12-233 | 12-233 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Glen Ravine Junior | Glen Ravine Junior Public Elementary School | ELE | 8882 | 9765 | 9765-B01 | 11 GADSBY DR | SCARBOROUGH | M1K4V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.738 | -79.2544 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44579 | 3535911 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 1043277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043277 | 0 | 0 | 0 | 0 | 0 | 0 | 2492634 | 0 | 0 | 0 | 2492634 | 3535911 | 3535911 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2492634
12-234 | 12-234 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Grey Owl Junior | Grey Owl Junior Public Elementary School | ELE | 8885 | 9768 | 9768-B01 | 150 WICKSON TRAIL | SCARBOROUGH | M1B1M4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.804 | -79.2133 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 4456270 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 879224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879224 | 0 | 0 | 0 | 0 | 0 | 0 | 3577046 | 0 | 0 | 0 | 3577046 | 4456270 | 4456270 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3577046
12-235 | 12-235 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Emily Carr | Emily Carr Public Elementary School | ELE | 8918 | 9800 | 9800-B01 | 90 JOHN TABOR TRAIL | SCARBOROUGH | M1B2V2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.805 | -79.2069 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 5298528 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 1324658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1324658 | 0 | 0 | 0 | 0 | 0 | 0 | 3973870 | 0 | 0 | 0 | 3973870 | 5298528 | 5298528 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3973870
12-236 | 12-236 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | General Crerar | General Crerar Public Elementary School | ELE | 8924 | 9806 | 9806-B02 | 30 MCGREGOR RD | SCARBOROUGH | M1P1C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7458 | -79.28 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571270 | 0 | 0 | 0 | 2571270 | 2571270 | 2571270 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2571270
12-237 | 12-237 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Willow Park Junior | Willow Park Junior Public Elementary School | ELE | 8935 | 9817 | 9817-B01 | 45 WINDOVER DR | SCARBOROUGH | M1G1P1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7611 | -79.2093 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2314143 | 0 | 0 | 0 | 2314143 | 2314143 | 2314143 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2314143
12-238 | 12-238 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Ionview | Ionview Public Elementary School | ELE | 8947 | 9825 | 9825-B01 | 90 IONVIEW RD | SCARBOROUGH | M1K2Z9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7378 | -79.2748 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 3798309 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 643467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643467 | 0 | 0 | 0 | 0 | 0 | 0 | 3154842 | 0 | 0 | 0 | 3154842 | 3798309 | 3798309 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3154842
12-239 | 12-239 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | J G Workman | J G Workman Public Elementary School | ELE | 8950 | 9828 | 9828-B01 | 487 BIRCHMOUNT RD | SCARBOROUGH | M1K1N7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7075 | -79.2665 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 3667953 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 644319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644319 | 0 | 0 | 0 | 0 | 0 | 0 | 3023634 | 0 | 0 | 0 | 3023634 | 3667953 | 3667953 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3023634
12-240 | 12-240 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Lord Roberts Junior | Lord Roberts Junior Public Elementary School | ELE | 8967 | 9840 | 9840-B01 | 165 LORD ROBERTS DR | SCARBOROUGH | M1K3W5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7417 | -79.2638 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44579 | 3062246 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 871364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 871364 | 0 | 0 | 0 | 0 | 0 | 0 | 2190882 | 0 | 0 | 0 | 2190882 | 3062246 | 3062246 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2190882
12-241 | 12-241 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Malvern Junior | Malvern Junior Public Elementary School | ELE | 8972 | 9845 | 9845-B01 | 70 MAMMOTH HALL TRAIL | SCARBOROUGH | M1B1P6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7978 | -79.2332 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 4324790 | Under Construction | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 838672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838672 | 0 | 0 | 0 | 0 | 0 | 0 | 3486118 | 0 | 0 | 0 | 3486118 | 4324790 | 4324790 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3486118
12-242 | 12-242 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Military Trail | Military Trail Public Elementary School | ELE | 8982 | 9854 | 9854-B01 | 701 MILITARY TRAIL | SCARBOROUGH | M1E4P6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7891 | -79.1971 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571270 | 0 | 0 | 0 | 2571270 | 2571270 | 2571270 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2571270
12-243 | 12-243 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Daystrom | Daystrom Public Elementary School | ELE | 9091 | 9945 | 9945-B01 | 25 DAYSTROM DR | NORTH YORK | M9M2A8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7478 | -79.5472 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571270 | 0 | 0 | 0 | 2571270 | 2571270 | 2571270 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2571270
12-244 | 12-244 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Dennis Avenue | Dennis Avenue Public Elementary School | ELE | 24790 | 9624 | 9624-B02 | 17 DENNIS AVE | YORK | M6N2T7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6843 | -79.4874 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 358 | 5 | 88 | Y | - | Approved | 44916 | 24127463 | Under Construction | New Construction | Consolidation | 2023-24 | 45383 | 0 | 0 | 11358982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11358982 | 0 | 0 | 0 | 0 | 9698908 | 0 | 3069573 | 0 | 0 | 0 | 12768481 | 24127463 | 24127463 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12768481
12-245 | 12-245 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Kapapamahchakwew - Wandering Spirit | Kapapamahchakwew - Wandering Spirit Public Elementary and Secondary School | ELE/SEC | 24617 | 9419 | 9419-B01 | 16 PHIN AVE | TORONTO | M4J3T2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6791 | -79.337 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 304 | 4 | 64 | Y | 1 | Planned | - | 0 | Planned | Addition | Consolidation | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8866411 | 0 | 2117516 | 529380 | 0 | 0 | 11513307 | 11513307 | 11513307 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11513307
12-246 | 12-246 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | George Syme | George Syme Public Elementary School | ELE | 8729 | 9630 | 9630-B01 | 69 PRITCHARD AVE | YORK | M6N1T6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6688 | -79.4909 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 92 | 5 | 88 | Y | - | Approved | 44951 | 10888378 | Under Construction | Addition | Consolidation | 2023-24 | 45292 | 0 | 0 | 5397371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5397371 | 0 | 0 | 0 | 0 | 2842625 | 0 | 2648382 | 0 | 0 | 0 | 5491007 | 10888378 | 10888378 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5491007
12-247 | 12-247 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Hollywood | Hollywood Public Elementary School | ELE | 9072 | 9928 | 9928-B01 | 360 HOLLYWOOD AVE | NORTH YORK | M2N3L4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7708 | -79.3925 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 190 | 5 | 88 | Y | - | Approved | 44987 | 18869567 | Planned | Addition | Accommodation Pressure | 2023-24 | 45383 | 0 | 0 | 4874574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4874574 | 0 | 0 | 0 | 0 | 9912149 | 0 | 4082844 | 0 | 0 | 0 | 13994993 | 18869567 | 18869567 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13994993
12-248 | 12-248 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Sir Sandford Fleming | Sir Sandford Fleming Public Elementary School | HFA | 9185 | 10029 | 10029-B01 | 50 AMEER AVE | NORTH YORK | M6A2L3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7283 | -79.4428 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44124 | 7468658 | Construction Complete | Retrofit | Consolidation | 2021-22 | 44621 | 0 | 2444023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2444023 | 0 | 0 | 0 | 0 | 3570000 | 0 | 1454635 | 0 | 0 | 0 | 5024635 | 7468658 | 7468658 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5024635
12-249 | 12-249 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Kipling | Kipling Public Secondary School | SEC | 8649 | 9568 | 9568-B01 | 380 THE WESTWAY | ETOBICOKE | M9R1H4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6853 | -79.5623 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44579 | 3470432 | Under Construction | Retrofit | Consolidation | 2023-24 | 45292 | 0 | 0 | 858176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 858176 | 0 | 0 | 0 | 0 | 1326621 | 0 | 1285635 | 0 | 0 | 0 | 2612256 | 3470432 | 3470432 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 2612256
12-252 | 12-252 | 12 | N/A | 66052 | Toronto DSB | Canadian Tire | Canadian Tire Land | HLA | 24834 | 19840 | 19840-L0- | 50 WOODSY PARK LANE | NORTH YORK | TBD | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7671 | -79.3752 | 43227 | 2017-18 | 2018-19 | 43227 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43227 | 24000000 | Construction Complete | Land Acquisition | Accommodation Pressure | 2018-19 | 43555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000000 | 0 | 0 | 0 | 0 | 0 | 0 | 24000000 | 24000000 | 24000000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 24000000
12-253 | 12-253 | 12 | N/A | 66052 | Toronto DSB | West Glen Junior | West Glen Junior Public Elementary School | ELE | 8696 | 9608 | 9608-B01 | 47 COWLEY AVE | ETOBICOKE | M9B2E4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6501 | -79.5605 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
12-254 | 12-254 | 12 | N/A | 66052 | Toronto DSB | Stanley | Stanley Public Elementary School | ELE | 9191 | 10032 | 10032-B01 | 75 STANLEY RD | NORTH YORK | M3N1C2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7416 | -79.5171 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43717 | 3900000 | Construction Complete | Retrofit | Child Care | 2021-22 | 44531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 3900000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-255 | 12-255 | 12 | N/A | 66052 | Toronto DSB | McKee | McKee Public Elementary School | ELE | 9148 | 9996 | 9996-B01 | 35 CHURCH AVE | NORTH YORK | M2N6X6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7743 | -79.4105 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 69 | - | - | - | - | Approved | 45183 | 4423735 | Planned | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4423735 | 0 | 0 | 0 | 0 | 0 | 4423735 | 4423735 | 4423735 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4423735
12-256 | 12-256 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | David Lewis | David Lewis Public Elementary School | ELE | 8860 | 9746 | 9746-B01 | 130 FUNDY BAY BLVD | SCARBOROUGH | M1W3G1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8096 | -79.3179 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 184 | 5 | 88 | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2024-25 | 45658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3121011 | 0 | 2727597 | 0 | 0 | 0 | 5848608 | 5848608 | 5848608 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5848608
12-257 | 12-183 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Terry Fox | Terry Fox Public Elementary School | ELE | 8910 | 9792 | 9792-L01 | 185 WINTERMUTE BLVD | SCARBOROUGH | M1W3M9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8158 | -79.319 | 44222 | 2020-21 | 2020-21 | 44222 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44376 | 1915037 | Construction Complete | Land Acquisition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1915037 | 0 | 0 | 0 | 0 | 0 | 0 | 1915037 | 1915037 | 1915037 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1915037
12-258 | 12-258 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Elmlea | Elmlea Junior Public Elementary School | ELE | 8612 | 9545 | 9545-B01 | 50 HADRIAN DR | ETOBICOKE | M9W1V4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7162 | -79.5502 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 5 | 88 | N | - | Planned | - | - | Planned | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2727603 | 0 | 0 | 0 | 2727603 | 2727603 | 2727603 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 2727603
12-259 | 12-244 | 12 | 999 | 66052 | Toronto DSB | Dennis Avenue | Dennis Avenue Public Elementary School | ELE | 24790 | 9624 | 9624-B01 | 17 DENNIS AVE | YORK | M6N2T7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6843 | -79.4874 | 44404 | 2020-21 | 2021-22 | - | - | - | 44404 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44404 | 1867708 | Under Construction | Demolition | Consolidation | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1867708 | 0 | 0 | 0 | 0 | 0 | 1867708 | 1867708 | 1867708 | 0 | - | TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1867708
12-260 | 12-260 | 12 | N/A | 66052 | Toronto DSB | Toronto | Toronto Public Elementary School | ELE | TBD | TBD | TBD | YONGE ST / QUEENS QUAY W | TORONTO | TBD | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | TBD | TBD | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 455 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000000 | 0 | 0 | 0 | 0 | 0 | 44000000 | 44000000 | 44000000 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 44000000
12-261 | 12-261 | 12 | N/A | 66052 | Toronto DSB | York Memorial | York Memorial Public Secondary School | SEC | 8753 | 9652 | 9652-B01 | 2690 EGLINTON AVE W | YORK | M6M1T9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6906 | -79.4762 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 368 | - | - | N | - | Planned | - | - | Planned | Addition | Consolidation | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11045702 | 0 | 0 | 0 | 0 | 0 | 11045702 | 11045702 | 11045702 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11045702
12-265 | 12-065 | 12 | N/A | 66052 | Toronto DSB | Davisville Junior | Davisville Junior Public Elementary School | ELE | 24637 | 5143 | 5143-L02 | 43 MILLWOOD RD | TORONTO | M4S1J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6992 | -79.3948 | 44503 | 2021-22 | 2021-22 | 44503 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44503 |  | Construction Complete | Land Acquisition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614599 | 0 | 0 | 0 | 0 | 0 | 0 | 1614599 | 1614599 | 1614599 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1614599
12-266 | 12-266 | 12 | N/A | 66052 | Toronto DSB | Jones Avenue | Jones Avenue Public Elementary School | ELE | TBD | 9375 | 9375-B01 | 540 JONES AVE | TORONTO | M4J3G9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6774 | -79.3396 | 44651 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44651 | 9140212 | Under Construction | Retrofit | Condition |  | 45170 | 954890 | 5885322 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9140212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9140212 | 9140212 | 0 | - |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
12-267 | 12-267 | 12 | N/A | 66052 | Toronto DSB | Elizabeth Simcoe Jr. | Elizabeth Simcoe Jr. Public Elementary School | ELE | 8877 | 9760 | 9760-B01 | 166 SYLVAN AVE | SCARBOROUGH | M1E1A3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7385 | -79.2062 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Planned | - | - | Planned | Addition | Consolidation | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2532250 | 0 | 0 | 0 | 0 | 0 | 2532250 | 2532250 | 2532250 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2532250
12-268 | 12-268 | 12 | 211 - CMSM Toronto | 66052 | Toronto DSB | Poplar Road Jr. | Poplar Road Jr. Public Elementary School | ELE | TBD | TBD | TBD | TBD | SCARBOROUGH | M1E1S4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 341 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Consolidation | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10115229 | 0 | 3324941 | 0 | 0 | 0 | 13440170 | 13440170 | 13440170 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13440170
13-001 | 13-001 | 13 | N/A | 66060 | Durham DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 6113 | 8367 | 8367-B01 | 400 TAUNTON RD E | WHITBY | L1R2K6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9198 | -78.9394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-002 | 13-002 | 13 | N/A | 66060 | Durham DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 6113 | 8367 | 8367-B01 | 400 TAUNTON RD E | WHITBY | L1R2K6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9198 | -78.9394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 28486736 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30201975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30201975 | 30201975 | 28486736 | -1715239 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-003 | 13-003 | 13 | N/A | 66060 | Durham DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6113 | 8367 | 8367-B01 | 400 TAUNTON RD E | WHITBY | L1R2K6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9198 | -78.9394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2961687 | Construction Complete | Other | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2961687 | 2961687 | 2961687 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-004 | 13-004 | 13 | N/A | 66060 | Durham DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6113 | 8367 | 8367-B01 | 400 TAUNTON RD E | WHITBY | L1R2K6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9198 | -78.9394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5168625 | Construction Complete | Other | Other | 2014-15 | 41883 | 0 | 0 | 2753625 | 0 | 0 | 0 | 0 | 0 | 2415000 | 0 | 0 | 0 | 0 | 0 | 0 | 5168625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5168625 | 5168625 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-005 | 13-005 | 13 | N/A | 66060 | Durham DSB | ACEC - EA Lovell | ACEC - EA Lovell Public Secondary School | SEC | 660 | 5734 | 5734-B01 | 120 CENTRE ST S | OSHAWA | L1H4A3 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8939 | -78.8645 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1256470 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 1256470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1256470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1256470 | 1256470 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-007 | 13-007 | 13 | N/A | 66060 | Durham DSB | Ajax | Ajax Public Secondary School | SEC | 5197 | 8111 | 8111-B01 | 105 BAYLY ST E | AJAX | L1S1P2 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8444 | -79.0138 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8504583 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8504583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8504583 | 8504583 | 8504583 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-008 | 13-008 | 13 | N/A | 66060 | Durham DSB | Alexander Graham Bell | Alexander Graham Bell Public Elementary School | ELE | 9760 | 10250 | 10250-B01 | 25 HARKINS DR | AJAX | L1T3T6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8695 | -79.0565 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5178571 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5178571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5178571 | 5178571 | 5178571 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-009 | 13-009 | 13 | N/A | 66060 | Durham DSB | Alexander Graham Bell | Alexander Graham Bell Public Elementary School | ELE | 9760 | 10250 | 10250-B01 | 25 HARKINS DR | AJAX | L1T3T6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8695 | -79.0565 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1335911 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1335911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1335911 | 1335911 | 1335911 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-011 | 13-011 | 13 | N/A | 66060 | Durham DSB | Altona Forest | Altona Forest Public Elementary School | ELE | 9761 | 10251 | 10251-B01 | 405 WOODSMERE CRES | PICKERING | L1V7A3 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8279 | -79.1318 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5284272 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5284272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5284272 | 5284272 | 5284272 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-012 | 13-012 | 13 | N/A | 66060 | Durham DSB | Altona Forest | Altona Forest Public Elementary School | ELE | 9761 | 10251 | 10251-B01 | 405 WOODSMERE CRES | PICKERING | L1V7A3 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8279 | -79.1318 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1348402 | Construction Complete | Addition | Other | 2009-10 | 40057 | 116550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116550 | 1231852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231852 | 1348402 | 1348402 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-016 | 13-016 | 13 | N/A | 66060 | Durham DSB | Bellwood | Bellwood Public Elementary School | ELE | 173 | 5410 | 5410-B01 | 30 BELLWOOD DR | WHITBY | L1N8M4 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8798 | -78.9061 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1840072 | Construction Complete | Addition | Other | 2009-10 | 40057 | 27769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27769 | 1812303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1812303 | 1840072 | 1840072 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-017 | 13-017 | 13 | N/A | 66060 | Durham DSB | Blair Ridge | Blair Ridge Public Elementary School | ELE | 11118 | 12175 | 12175-B01 | 100 BLACKFRIAR AVE | WHITBY | L1M0E8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9632 | -78.941 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9611749 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9611749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9611749 | 9611749 | 9611749 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-019 | 13-019 | 13 | N/A | 66060 | Durham DSB | Bobby Orr | Bobby Orr Public Elementary School | ELE | 10470 | 11117 | 11117-B01 | 7 WATERLOO ST | OSHAWA | L1H8V9 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8729 | -78.8409 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7591615 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7591615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7591615 | 7591615 | 7591615 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-020 | 13-020 | 13 | N/A | 66060 | Durham DSB | Brooklin | Brooklin Public Secondary School | SEC | 24307 | 19299 | 19299-B01 | 20 CARNWITH DR W | WHITBY | L1M0K7 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9658 | -78.9627 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 1101 | - | - | N | - | Approved | 41688 | 33155562 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 3021453 | 0 | 1536562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4558015 | 0 | 0 | 0 | 0 | 27774060 | 0 | 0 | 0 | 0 | 0 | 27774060 | 32332075 | 32332075 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 27774060
13-021 | 13-021 | 13 | N/A | 66060 | Durham DSB | Brooklin Village | Brooklin Village Public Elementary School | ELE | 10741 | 11190 | 11190-B01 | 25 SELKIRK DR | WHITBY | L1M2L5 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9702 | -78.9521 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8310656 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8310656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8310656 | 8310656 | 8310656 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-022 | 13-022 | 13 | N/A | 66060 | Durham DSB | Brooklin Village | Brooklin Village Public Elementary School | ELE | 10741 | 11190 | 11190-B01 | 25 SELKIRK DR | WHITBY | L1M2L5 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9702 | -78.9521 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 674 | - | - | N | - | Approved | 41316 | 3642789 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 0 | 0 | 31640 | 0 | 2811149 | 0 | 0 | 0 | 0 | 0 | 2842789 | 3642789 | 3642789 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2811149
13-024 | 13-024 | 13 | N/A | 66060 | Durham DSB | Cadarackque | Cadarackque Public Elementary School | ELE | 299 | 5481 | 5481-B01 | 15 MILES DR | AJAX | L1Z1C7 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8615 | -79.0092 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3362649 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3362649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3362649 | 3362649 | 3362649 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-025 | 13-025 | 13 | N/A | 66060 | Durham DSB | Captain Michael Vandenbos | Captain Michael Vandenbos Public Elementary School | ELE | 10114 | 10399 | 10399-B01 | 3121 COUNTRY LANE | WHITBY | L1P1N3 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9 | -78.9692 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6555343 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6555343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6555343 | 6555343 | 6555343 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-026 | 13-026 | 13 | N/A | 66060 | Durham DSB | Captain Michael Vandenbos | Captain Michael Vandenbos Public Elementary School | ELE | 10114 | 10399 | 10399-B01 | 3121 COUNTRY LANE | WHITBY | L1P1N3 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9 | -78.9692 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1596813 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596813 | 1596813 | 1596813 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-027 | 13-027 | 13 | N/A | 66060 | Durham DSB | Carruthers Creek | Carruthers Creek Public Elementary School | ELE | 10447 | 11107 | 11107-B01 | 1 GREENHALF DR | AJAX | L1S7N6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8398 | -79.0047 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8167835 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8167835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8167835 | 8167835 | 8167835 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-028 | 13-028 | 13 | N/A | 66060 | Durham DSB | Carruthers Creek | Carruthers Creek Public Elementary School | ELE | 10447 | 11107 | 11107-B01 | 1 GREENHALF DR | AJAX | L1S7N6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8398 | -79.0047 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2565886 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565886 | 2565886 | 2565886 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-029 | 13-029 | 13 | N/A | 66060 | Durham DSB | Cartwright Central | Cartwright Central Public Elementary School | ELE | 387 | 5550 | 5550-B01 | 10 ALEXANDER ST | BLACKSTOCK | L0B1B0 | 35-11-10-602 | Scugog | Scugog Tp | Durham R | DURHAM | GTA | South | 44.1122 | -78.8225 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4157392 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3826170 | 331222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4157392 | 4157392 | 4157392 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-030 | 13-030 | 13 | N/A | 66060 | Durham DSB | Chris Hadfield | Chris Hadfield Public Elementary School | ELE | 17264 | 19027 | 19027-B01 | 160 CARNWITH DR W | WHITBY | L1M0A5 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9627 | -78.9703 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11289708 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10357814 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11289708 | 11289708 | 11289708 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-031 | 13-031 | 13 | N/A | 66060 | Durham DSB | Clara Hughes | Clara Hughes Public Elementary School | ELE | 19890 | 5719 | 5719-B02 | 610 TAYLOR AVE | OSHAWA | L1H2E7 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8965 | -78.8385 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12115599 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 10383705 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11315599 | 12115599 | 12115599 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-032 | 13-032 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Claremont | Claremont Public Elementary School | ELE | 1805 | 6456 | 6456-B01 | 1675 CENTRAL ST | CLAREMONT | L1Y1A8 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.9709 | -79.1338 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 28 | 3 | 49 | N | - | Approved | 42727 | 5551448 | Construction Complete | Addition | Condition | 2017-18 | 43145 | 330000 | 405500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735500 | 0 | 0 | 0 | 0 | 3307702 | 0 | 1482853 | 0 | 0 | 0 | 4790555 | 5526055 | 5551448 | 25393 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4790555
13-034 | 13-034 | 13 | N/A | 66060 | Durham DSB | Colonel JE Farewell | Colonel JE Farewell Public Elementary School | ELE | 480 | 5610 | 5610-B01 | 810 MCQUAY BLVD | WHITBY | L1P1J1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8865 | -78.9705 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3577394 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3577394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3577394 | 3577394 | 3577394 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-036 | 13-036 | 13 | N/A | 66060 | Durham DSB | da Vinci | da Vinci Public Elementary School | ELE | 15601 | 18071 | 18071-B01 | 61 WILLIAMSON DR E | AJAX | L1T0A9 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8931 | -79.029 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9714247 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8836117 | 0 | 878130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9714247 | 9714247 | 9714247 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-037 | 13-037 | 13 | N/A | 66060 | Durham DSB | David Bouchard | David Bouchard Public Elementary School | ELE | 24220 | 5226 | 5226-B02 | 460 WILSON RD S | OSHAWA | L1H6C9 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8903 | -78.8386 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13313309 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12381415 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13313309 | 13313309 | 13313309 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-038 | 13-038 | 13 | N/A | 66060 | Durham DSB | Donald A Wilson | Donald A Wilson Public Secondary School | SEC | 10456 | 11113 | 11113-B01 | 681 ROSSLAND RD W | WHITBY | L1P1Y1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8933 | -78.9651 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 28333513 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28333513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28333513 | 28333513 | 28333513 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-039 | 13-039 | 13 | N/A | 66060 | Durham DSB | Dr. CF Cannon | Dr. CF Cannon Public Elementary School | ELE | 1308 | 6133 | 6133-B01 | 1196 CEDAR ST | OSHAWA | L1J3S2 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.866 | -78.8503 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4874525 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4874525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4874525 | 4874525 | 4874525 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-042 | 13-042 | 13 | N/A | 66060 | Durham DSB | Dunbarton | Dunbarton Public Secondary School | SEC | 2557 | 6938 | 6938-B02 | 1464 WHITES RD | PICKERING | L1V1R4 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8195 | -79.1177 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2059209 | Construction Complete | Retrofit | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059209 | 2059209 | 2059209 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-043 | 13-043 | 13 | N/A | 66060 | Durham DSB | Eagle Ridge | Eagle Ridge Public Elementary School | ELE | 10471 | 11118 | 11118-B01 | 425 DELANEY DR | AJAX | L1T4N1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8632 | -79.0664 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8017232 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8017232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8017232 | 8017232 | 8017232 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-044 | 13-044 | 13 | N/A | 66060 | Durham DSB | Eastdale | Eastdale Public Secondary School | SEC | 5324 | 5186 | 5186-B02 | 265 HARMONY RD N | OSHAWA | L1G6L4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9118 | -78.8357 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Approved | 43115 | 8573068 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 3417780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3417780 | 0 | 0 | 0 | 0 | 5155288 | 0 | 0 | 0 | 0 | 0 | 5155288 | 8573068 | 8573068 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5155288
13-045 | 13-045 | 13 | N/A | 66060 | Durham DSB | Elizabeth B Phin | Elizabeth B Phin Public Elementary School | ELE | 10367 | 6624 | 6624-B01 | 1500 ROUGEMOUNT DR | PICKERING | L1V1N1 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8155 | -79.1348 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5978929 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 3734889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3734889 | 2244040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2244040 | 5978929 | 5978929 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-047 | 13-047 | 13 | N/A | 66060 | Durham DSB | Fallingbrook | Fallingbrook Public Elementary School | ELE | 9772 | 10256 | 10256-B01 | 155 FALLINGBROOK ST | WHITBY | L1R2G2 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9137 | -78.9415 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4883332 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4883332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4883332 | 4883332 | 4883332 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-048 | 13-048 | 13 | N/A | 66060 | Durham DSB | Fallingbrook | Fallingbrook Public Elementary School | ELE | 9772 | 10256 | 10256-B01 | 155 FALLINGBROOK ST | WHITBY | L1R2G2 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9137 | -78.9415 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1454376 | Construction Complete | Addition | Other | 2009-10 | 40057 | 124253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124253 | 1330123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1330123 | 1454376 | 1454376 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-049 | 13-049 | 13 | N/A | 66060 | Durham DSB | Forestview | Forestview Public Elementary School | ELE | 24330 | 5916 | 5916-B01 | 285 GRANDVIEW ST S | OSHAWA | L1H7C6 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.898 | -78.8205 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 553 | - | - | N | - | Approved | 42440 | 10809241 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 0 | 8906357 | 0 | 0 | 0 | 0 | 0 | 10806357 | 10806357 | 10806357 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 8906357
13-050 | 13-050 | 13 | N/A | 66060 | Durham DSB | Frenchmans Bay | Frenchmans Bay Public Elementary School | ELE | 860 | 5859 | 5859-B01 | 920 OKLAHOMA DR | PICKERING | L1W2H7 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8145 | -79.1013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6477573 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 2375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375000 | 3636626 | 0 | 465947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4102573 | 6477573 | 6477573 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-052 | 13-052 | 13 | N/A | 66060 | Durham DSB | Glen Dhu | Glen Dhu Public Elementary School | ELE | 894 | 5877 | 5877-B01 | 29 FALLINGBROOK ST | WHITBY | L1R1M7 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9048 | -78.9344 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2173237 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173237 | 2173237 | 2173237 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-054 | 13-054 | 13 | N/A | 66060 | Durham DSB | Glen Street | Glen Street Public Elementary School | ELE | 916 | 5889 | 5889-B01 | 929 GLEN ST | OSHAWA | L1J3T9 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8723 | -78.8548 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4044337 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4044337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4044337 | 4044337 | 4044337 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-056 | 13-056 | 13 | N/A | 66060 | Durham DSB | Goodwood | Goodwood Public Elementary School | ELE | 2349 | 6805 | 6805-B01 | 4340 FRONT ST | GOODWOOD | L0C1A0 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.0403 | -79.1978 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1325047 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 1290047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1290047 | 1325047 | 1325047 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-057 | 13-057 | 13 | N/A | 66060 | Durham DSB | Gordon B Attersley | Gordon B Attersley Public Elementary School | ELE | 9773 | 10257 | 10257-B01 | 1110 ATTERSLEY DR | OSHAWA | L1K1X8 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9271 | -78.8502 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5938732 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5938732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5938732 | 5938732 | 5938732 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-059 | 13-059 | 13 | N/A | 66060 | Durham DSB | Harmony Heights | Harmony Heights Public Elementary School | ELE | 1017 | 5964 | 5964-B01 | 590 GALAHAD DR | OSHAWA | L1K1M2 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9194 | -78.8428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1958981 | Construction Complete | Addition | Other | 2009-10 | 40057 | 50499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50499 | 1558945 | 251748 | 97789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1908482 | 1958981 | 1958981 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-060 | 13-060 | 13 | N/A | 66060 | Durham DSB | J Clarke Richardson | J Clarke Richardson Public Secondary School | SEC | 10278 | 10322 | 10322-B01 | 1355 HARWOOD AVE N | AJAX | L1T4G8 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8838 | -79.027 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 30482577 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30482577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30482577 | 30482577 | 30482577 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-061 | 13-061 | 13 | N/A | 66060 | Durham DSB | Jack Miner | Jack Miner Public Elementary School | ELE | 10112 | 10397 | 10397-B01 | 144 WHITBURN ST | WHITBY | L1R2N1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9078 | -78.9604 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6126396 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6126396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6126396 | 6126396 | 6126396 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-063 | 13-063 | 13 | N/A | 66060 | Durham DSB | Jeanne Sauvé | Jeanne Sauvé Public Elementary School | ELE | 24477 | 19481 | 19481-B01 | 950 COLDSTREAM DR | OSHAWA | L1K0X1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9455 | -78.8575 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 533 | - | - | N | - | Approved | 42440 | 10795685 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 2597258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2597258 | 0 | 0 | 465947 | 0 | 7152738 | 0 | 0 | 0 | 0 | 0 | 7618685 | 10215943 | 10215943 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7152738
13-064 | 13-064 | 13 | N/A | 66060 | Durham DSB | John Dryden | John Dryden Public Elementary School | ELE | 1205 | 6068 | 6068-B01 | 40 ROLLING ACRES DR | WHITBY | L1R2A1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9137 | -78.9177 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2427502 | Construction Complete | Addition | Other | 2010-11 | 40422 | 235881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235881 | 2191621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2191621 | 2427502 | 2427502 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-065 | 13-065 | 13 | N/A | 66060 | Durham DSB | Joseph Gould | Joseph Gould Public Elementary School | ELE | 1227 | 6082 | 6082-B01 | 144 PLANKS LANE | UXBRIDGE | L9P1K6 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.1086 | -79.1124 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3702547 | Construction Complete | Addition | Other | 2010-11 | 40422 | 196654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196654 | 3075893 | 430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3505893 | 3702547 | 3702547 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-067 | 13-067 | 13 | N/A | 66060 | Durham DSB | Julie Payette | Julie Payette Public Elementary School | ELE | 11122 | 12261 | 12261-B01 | 300 GARDEN ST | WHITBY | L1N3W4 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8856 | -78.9357 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12032782 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12032782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12032782 | 12032782 | 12032782 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-069 | 13-069 | 13 | N/A | 66060 | Durham DSB | Lakeside | Lakeside Public Elementary School | ELE | 1315 | 6139 | 6139-B01 | 4 PARKES DR | AJAX | L1S4X1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8234 | -79.0278 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2356230 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2356230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2356230 | 2356230 | 2356230 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-070 | 13-070 | 13 | N/A | 66060 | Durham DSB | Lakewoods | Lakewoods Public Elementary School | ELE | 415 | 5574 | 5574-B01 | 323 CHALEUR AVE | OSHAWA | L1J1G5 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8618 | -78.8434 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5138956 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5138956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5138956 | 5138956 | 5138956 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-071 | 13-071 | 13 | N/A | 66060 | Durham DSB | Lester B Pearson | Lester B Pearson Public Elementary School | ELE | 1352 | 6161 | 6161-B01 | 21 COUGHLEN ST | AJAX | L1T2M9 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8712 | -79.0434 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2320014 | Construction Complete | Addition | Other | 2010-11 | 40422 | 132673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132673 | 2162341 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2187341 | 2320014 | 2320014 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-073 | 13-073 | 13 | N/A | 66060 | Durham DSB | Lord Elgin | Lord Elgin Public Elementary School | ELE | 1386 | 6185 | 6185-B01 | 24 ONTARIO ST | AJAX | L1S1T6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8568 | -79.0264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2588237 | Construction Complete | Addition | Other | 2010-11 | 40422 | 101401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101401 | 2051836 | 435000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2486836 | 2588237 | 2588237 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-074 | 13-074 | 13 | N/A | 66060 | Durham DSB | Maxwell Heights | Maxwell Heights Public Secondary School | SEC | 10982 | 12126 | 12126-B01 | 1100 COLDSTREAM DR | OSHAWA | L1K0N1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9466 | -78.852 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 31100640 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31100640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31100640 | 31100640 | 31100640 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-075 | 13-075 | 13 | N/A | 66060 | Durham DSB | McCaskill's Mills | McCaskill's Mills Public Elementary School | ELE | 10808 | 12047 | 12047-B01 | 85 ALBERT ST | CANNINGTON | L0E1E0 | 35-11-10-601 | Brock | Brock Tp | Durham R | DURHAM | GTA | South | 44.3468 | -79.0454 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5070207 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070207 | 5070207 | 5070207 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-076 | 13-076 | 13 | N/A | 66060 | Durham DSB | McCaskill's Mills | McCaskill's Mills Public Elementary School | ELE | 10808 | 12047 | 12047-B01 | 85 ALBERT ST | CANNINGTON | L0E1E0 | 35-11-10-601 | Brock | Brock Tp | Durham R | DURHAM | GTA | South | 44.3468 | -79.0454 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2234310 | Construction Complete | Addition | Other | 2010-11 | 40422 | 142675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142675 | 2091635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2091635 | 2234310 | 2234310 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-078 | 13-078 | 13 | N/A | 66060 | Durham DSB | Michaëlle-Jean | Michaëlle-Jean Public Elementary School | ELE | 24308 | 19300 | 19300-B01 | 180 WILLIAMSON DR E | AJAX | L1Z0G7 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8963 | -79.0248 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 553 | - | - | N | - | Approved | 41782 | 11145000 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 171475 | 0 | 435286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606761 | 0 | 0 | 931893 | 0 | 9444414 | 0 | 0 | 0 | 0 | 0 | 10376307 | 10983068 | 10983068 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9444414
13-079 | 13-079 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Viola Desmond | Viola Desmond Public Elementary School | ELE | 24571 | 19577 | 19577-B01 | 39 FORMOSA AVE | AJAX | L1Z0M6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8823 | -79.0058 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 663 | 4 | 73 | N | - | Approved | 42850 | 15049173 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977136 | 0 | 10687057 | 0 | 1977138 | 0 | 0 | 0 | 14641331 | 14641331 | 14899173 | 257842 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12664195
13-080 | 13-080 | 13 | N/A | 66060 | Durham DSB | Norman G Powers | Norman G Powers Public Elementary School | ELE | 10727 | 11192 | 11192-B01 | 1555 COLDSTREAM DR | OSHAWA | L1K3B5 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9476 | -78.836 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8360357 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8360357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8360357 | 8360357 | 8360357 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-081 | 13-081 | 13 | N/A | 66060 | Durham DSB | Nottingham | Nottingham Public Elementary School | ELE | 10728 | 11191 | 11191-B01 | 50 SEGGAR AVE | AJAX | L1T4Y4 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8817 | -79.0441 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8557501 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8557501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8557501 | 8557501 | 8557501 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-082 | 13-082 | 13 | N/A | 66060 | Durham DSB | Pickering | Pickering Public Secondary School | SEC | 5587 | 8338 | 8338-B01 | 180 CHURCH ST N | AJAX | L1T2W7 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8575 | -79.0574 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21562161 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21562161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21562161 | 21562161 | 21562161 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-083 | 13-083 | 13 | N/A | 66060 | Durham DSB | Pierre Elliot Trudeau | Pierre Elliot Trudeau Public Elementary School | ELE | 10275 | 10477 | 10477-B01 | 1111 BEATRICE ST E | OSHAWA | L1K2S7 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9326 | -78.8343 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7146068 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7146068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7146068 | 7146068 | 7146068 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-085 | 13-085 | 13 | N/A | 66060 | Durham DSB | Pine Ridge | Pine Ridge Public Secondary School | SEC | 5588 | 8339 | 8339-B01 | 2155 LIVERPOOL RD | PICKERING | L1X1V4 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8518 | -79.0965 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3677245 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677245 | 3677245 | 3677245 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-086 | 13-086 | 13 | N/A | 66060 | Durham DSB | Port Perry | Port Perry Public Secondary School | SEC | 5596 | 8344 | 8344-B01 | 160 ROSA ST | PORT PERRY | L9L1L7 | 35-11-10-602 | Scugog | Scugog Tp | Durham R | DURHAM | GTA | South | 44.1023 | -78.9517 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3102115 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3102115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3102115 | 3102115 | 3102115 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-087 | 13-087 | 13 | N/A | 66060 | Durham DSB | Port Perry | Port Perry Public Secondary School | SEC | 5596 | 8344 | 8344-B01 | 160 ROSA ST | PORT PERRY | L9L1L7 | 35-11-10-602 | Scugog | Scugog Tp | Durham R | DURHAM | GTA | South | 44.1023 | -78.9517 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4409138 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 470000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470000 | 3939138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3939138 | 4409138 | 4409138 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-088 | 13-088 | 13 | N/A | 66060 | Durham DSB | Pringle Creek | Pringle Creek Public Elementary School | ELE | 1895 | 6520 | 6520-B01 | 80 RIBBLESDALE DR | WHITBY | L1N8M1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8926 | -78.9301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2851079 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2851079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2851079 | 2851079 | 2851079 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-089 | 13-089 | 13 | N/A | 66060 | Durham DSB | Quaker Village | Quaker Village Public Elementary School | ELE | 9774 | 10258 | 10258-B01 | 295 BROCK ST W | UXBRIDGE | L9P1A1 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.106 | -79.138 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5895889 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5895889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5895889 | 5895889 | 5895889 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-090 | 13-090 | 13 | N/A | 66060 | Durham DSB | Queen Elizabeth | Queen Elizabeth Public Elementary School | ELE | 1915 | 6537 | 6537-B01 | 1205 SIMCOE ST N | OSHAWA | L1G4X1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9296 | -78.8768 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8268821 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 4743245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4743245 | 3525576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3525576 | 8268821 | 8268821 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-092 | 13-092 | 13 | N/A | 66060 | Durham DSB | Robert Munsch | Robert Munsch Public Elementary School | ELE | 11120 | 12177 | 12177-B01 | 20 NORISTA ST | WHITBY | L1R0J2 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9227 | -78.963 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9377305 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9377305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9377305 | 9377305 | 9377305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-093 | 13-093 | 13 | N/A | 66060 | Durham DSB | Roméo Dallaire | Roméo Dallaire Public Elementary School | ELE | 11117 | 12174 | 12174-B01 | 300 WILLIAMSON DR E | AJAX | L1Z0H6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8982 | -79.0147 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9828566 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9828566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9828566 | 9828566 | 9828566 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-094 | 13-094 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | RS McLaughlin | RS McLaughlin Public Secondary School | SEC | 5606 | 5314 | 5314-B02 | 570 STEVENSON RD N | OSHAWA | L1J5P1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9076 | -78.8908 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | 60 | 4 | 73 | N | - | Approved | 44181 | 5048534 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 176596 | 0 | 0 | 436821 | 15719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629136 | 0 | 0 | 0 | 0 | 2402861 | 0 | 2016537 | 0 | 0 | 0 | 4419398 | 5048534 | 5048534 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4419398
13-095 | 13-095 | 13 | N/A | 66060 | Durham DSB | SA Cawker | SA Cawker Public Elementary School | ELE | 2126 | 6669 | 6669-B01 | 16200 OLD SIMCOE RD | PORT PERRY | L9L1P3 | 35-11-10-602 | Scugog | Scugog Tp | Durham R | DURHAM | GTA | South | 44.1132 | -78.9577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2515462 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2515462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2515462 | 2515462 | 2515462 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-096 | 13-096 | 13 | N/A | 66060 | Durham DSB | Seneca Trail | Seneca Trail Public Elementary School | ELE | 17265 | 19028 | 19028-B01 | 1915 QUEENSBURY DR | OSHAWA | L1K0S1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9575 | -78.8425 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11034446 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10102552 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11034446 | 11034446 | 11034446 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-097 | 13-097 | 13 | N/A | 66060 | Durham DSB | Sherwood | Sherwood Public Elementary School | ELE | 10304 | 11012 | 11012-B01 | 633 ORMOND DR | OSHAWA | L1K2W6 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9426 | -78.8637 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8765559 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8765559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8765559 | 8765559 | 8765559 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-100 | 13-100 | 13 | N/A | 66060 | Durham DSB | Sir Samuel Steele | Sir Samuel Steele Public Elementary School | ELE | 10113 | 10398 | 10398-B01 | 55 BAKERVILLE ST | WHITBY | L1R2S6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9184 | -78.9197 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6655920 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6655920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6655920 | 6655920 | 6655920 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-102 | 13-102 | 13 | N/A | 66060 | Durham DSB | Sir William Stephenson | Sir William Stephenson Public Elementary School | ELE | 10655 | 11189 | 11189-B01 | 1125 ATHOL ST | WHITBY | L1N4A6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8692 | -78.9335 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6071055 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6071055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6071055 | 6071055 | 6071055 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-103 | 13-103 | 13 | N/A | 66060 | Durham DSB | Southwood Park | Southwood Park Public Elementary School | ELE | 2196 | 6711 | 6711-B01 | 28 LAMBARD CRES | AJAX | L1S1M5 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8341 | -79.0086 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3377819 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 2577819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2577819 | 3377819 | 3377819 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-104 | 13-104 | 13 | N/A | 66060 | Durham DSB | Stephen G Saywell | Stephen G Saywell Public Elementary School | ELE | 2234 | 6732 | 6732-B01 | 855 ROUNDELAY DR | OSHAWA | L1J7V1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9002 | -78.9007 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1568194 | Construction Complete | Addition | Other | 2009-10 | 40057 | 125965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125965 | 1400229 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442229 | 1568194 | 1568194 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-106 | 13-106 | 13 | N/A | 66060 | Durham DSB | Terry Fox | Terry Fox Public Elementary School | ELE | 10276 | 10478 | 10478-B01 | 30 KERRISON DR W | AJAX | L1Z1K1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.871 | -79.0274 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7462219 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7462219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7462219 | 7462219 | 7462219 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-109 | 13-109 | 13 | N/A | 66060 | Durham DSB | Uxbridge | Uxbridge Public Secondary School | SEC | 5713 | 8408 | 8408-B01 | 127 PLANKS LANE | UXBRIDGE | L9P1K5 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.1095 | -79.1139 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 14729991 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14729991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14729991 | 14729991 | 14729991 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-110 | 13-110 | 13 | N/A | 66060 | Durham DSB | Uxbridge | Uxbridge Public Secondary School | SEC | 5713 | 8408 | 8408-B01 | 127 PLANKS LANE | UXBRIDGE | L9P1K5 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.1095 | -79.1139 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5860126 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 5760126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760126 | 5860126 | 5860126 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-111 | 13-111 | 13 | N/A | 66060 | Durham DSB | Valley Farm | Valley Farm Public Elementary School | ELE | 2359 | 6811 | 6811-B01 | 1615 PEPPERWOOD GATE | PICKERING | L1X2K5 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8584 | -79.0872 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2639089 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2639089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2639089 | 2639089 | 2639089 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-113 | 13-113 | 13 | N/A | 66060 | Durham DSB | Vaughan Willard | Vaughan Willard Public Elementary School | ELE | 2363 | 6814 | 6814-B01 | 1911 DIXIE RD | PICKERING | L1V1V4 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8374 | -79.1012 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3257129 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435750 | 435750 | 2821379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2821379 | 3257129 | 3257129 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-115 | 13-115 | 13 | N/A | 66060 | Durham DSB | Village Union | Village Union Public Elementary School | ELE | 6133 | 8577 | 8577-B01 | 240 SIMCOE ST S | OSHAWA | L1H4H4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8906 | -78.8615 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3740031 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 3740031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3740031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3740031 | 3740031 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-116 | 13-116 | 13 | N/A | 66060 | Durham DSB | Vimy Ridge | Vimy Ridge Public Elementary School | ELE | 11119 | 12176 | 12176-B01 | 40 TELFORD ST | AJAX | L1T4Z4 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8785 | -79.0485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9882500 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9882500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9882500 | 9882500 | 9882500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-118 | 13-118 | 13 | N/A | 66060 | Durham DSB | Vincent Massey | Vincent Massey Public Elementary School | ELE | 2387 | 5186 | 5186-B01 | 211 HARMONY RD N | OSHAWA | L1G6L4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9105 | -78.836 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 166 | - | - | N | - | Not Required | - | 5200000 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 0 | 0 | 0 | 0 | 0 | 5200000 | 5200000 | 5209212 | 9212 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 5200000
13-119 | 13-119 | 13 | N/A | 66060 | Durham DSB | Walter E Harris | Walter E Harris Public Elementary School | ELE | 383 | 5546 | 5546-B01 | 495 CENTRAL PARK BLVD N | OSHAWA | L1G6A2 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9145 | -78.8547 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2731356 | Construction Complete | Addition | Other | 2010-11 | 40422 | 147399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147399 | 2583957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2583957 | 2731356 | 2731356 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-121 | 13-121 | 13 | N/A | 66060 | Durham DSB | West Lynde | West Lynde Public Elementary School | ELE | 1404 | 6197 | 6197-B01 | 270 MICHAEL BLVD | WHITBY | L1N6B1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8727 | -78.9526 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3116818 | Construction Complete | Addition | Other | 2011-12 | 40787 | 638226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638226 | 722331 | 0 | 1756261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2478592 | 3116818 | 3116818 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-122 | 13-122 | 13 | N/A | 66060 | Durham DSB | Westcreek | Westcreek Public Elementary School | ELE | 9775 | 10259 | 10259-B01 | 1779 WESTCREEK DR | PICKERING | L1V6M9 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8233 | -79.1428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5105012 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5105012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5105012 | 5105012 | 5105012 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-123 | 13-123 | 13 | N/A | 66060 | Durham DSB | Westcreek | Westcreek Public Elementary School | ELE | 9775 | 10259 | 10259-B01 | 1779 WESTCREEK DR | PICKERING | L1V6M9 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8233 | -79.1428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1395624 | Construction Complete | Addition | Other | 2009-10 | 40057 | 118552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118552 | 1277072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277072 | 1395624 | 1395624 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-124 | 13-124 | 13 | N/A | 66060 | Durham DSB | Westney Heights | Westney Heights Public Elementary School | ELE | 2452 | 6881 | 6881-B01 | 45 BRENNAN RD | AJAX | L1T1X5 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8651 | -79.046 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2477749 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477749 | 2477749 | 2477749 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-125 | 13-125 | 13 | N/A | 66060 | Durham DSB | Whitby Shores | Whitby Shores Public Elementary School | ELE | 11121 | 12238 | 12238-B01 | 485 WHITBY SHORES GREENWAY | WHITBY | L1N0G8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8554 | -78.9505 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11389505 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11389505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11389505 | 11389505 | 11389505 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-127 | 13-127 | 13 | N/A | 66060 | Durham DSB | Williamsburg | Williamsburg Public Elementary School | ELE | 10848 | 12020 | 12020-B01 | 20 KIRKLAND PL | WHITBY | L1P1W7 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9036 | -78.9757 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9221323 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9221323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9221323 | 9221323 | 9221323 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-128 | 13-128 | 13 | N/A | 66060 | Durham DSB | Winchester | Winchester Public Elementary School | ELE | 9776 | 10260 | 10260-B01 | 70 WATFORD ST | WHITBY | L1M1E8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9611 | -78.951 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5983073 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5983073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5983073 | 5983073 | 5983073 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-129 | 13-129 | 13 | N/A | 66060 | Durham DSB | Winchester | Winchester Public Elementary School | ELE | 9776 | 10260 | 10260-B01 | 70 WATFORD ST | WHITBY | L1M1E8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9611 | -78.951 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2745752 | Construction Complete | Addition | Other | 2009-10 | 40057 | 242801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242801 | 2502951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502951 | 2745752 | 2745752 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-130 | 13-130 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Northern Dancer | Northern Dancer Public Elementary School | ELE | 24572 | 19578 | 19578-B01 | 2200 BRIDLE RD | OSHAWA | L1L0L5 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9526 | -78.8927 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 513 | 4 | 73 | N | - | Approved | 42850 | 12242513 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988569 | 0 | 9243156 | 0 | 1977138 | 0 | 0 | 0 | 12208863 | 12208863 | 12242513 | 33650 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11220294
13-131 | 13-131 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Elsie MacGill | Elsie MacGill Public Elementary School | ELE | 24573 | 19579 | 19579-B01 | 800 GREENHILL AVE | OSHAWA | L1K0C8 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9512 | -78.8575 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 519 | 4 | 73 | Y | - | Approved | 42970 | 12734329 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512510 | 0 | 9137098 | 0 | 2016680 | 0 | 0 | 0 | 12666288 | 12666288 | 12734329 | 68041 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11153778
13-132 | 13-132 | 13 | N/A | 66060 | Durham DSB | Florence M Heard | Florence M Heard Facility Holding | HFA | 645 | 5723 | 5723-B0- | 100 GARDEN ST | WHITBY | L1N3W2 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8826 | -78.934 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42727 | 227306 | Construction Complete | Demolition | Other | 2017-18 | 42979 | 0 | 0 | 0 | 227306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227306 | 227306 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-133 | 13-133 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Altona Forest | Altona Forest Public Elementary School | ELE | 9761 | 10251 | 10251-B01 | 405 WOODSMERE CRES | PICKERING | L1V7A3 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8279 | -79.1318 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43250 | 756255 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756255 | 0 | 0 | 0 | 756255 | 756255 | 756255 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 756255
13-134 | 13-134 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Queen Elizabeth | Queen Elizabeth Public Elementary School | ELE | 1915 | 6537 | 6537-B01 | 1205 SIMCOE ST N | OSHAWA | L1G4X1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9296 | -78.8768 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | Y | 1 | Approved | 42958 | 1008340 | Construction Complete | Retrofit | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756255 | 252085 | 0 | 0 | 1008340 | 1008340 | 1008340 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1008340
13-135 | 13-135 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Roméo Dallaire | Roméo Dallaire Public Elementary School | ELE | 11117 | 12174 | 12174-B01 | 300 WILLIAMSON DR E | AJAX | L1Z0H6 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8982 | -79.0147 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43266 | 1953948 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 945608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945608 | 0 | 0 | 0 | 0 | 0 | 0 | 1008340 | 0 | 0 | 0 | 1008340 | 1953948 | 1953948 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1008340
13-136 | 13-136 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Scott Central | Scott Central Public Elementary School | ELE | 2094 | 6651 | 6651-B01 | 421 SANDFORD RD | SANDFORD | L0C1E0 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.1357 | -79.2062 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 45057 | 3261108 | Under Construction | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3261108 | 0 | 0 | 0 | 3261108 | 3261108 | 3261108 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 3261108
13-137 | 13-137 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Waverly | Waverly Public Elementary School | ELE | 2435 | 6869 | 6869-B01 | 100 WAVERLY ST S | OSHAWA | L1J5V1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8885 | -78.887 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | Y | 1 | Approved | 42958 | 1008340 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756255 | 252085 | 0 | 0 | 1008340 | 1008340 | 1008340 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1008340
13-138 | 13-138 | 13 | N/A | 66060 | Durham DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6113 | 8367 | 8367-B01 | 400 TAUNTON RD E | WHITBY | L1R2K6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9198 | -78.9394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42874 | 3570000 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 2896000 | 0 | 0 | 0 | 0 | 0 | 674000 | 0 | 0 | 0 | 0 | 0 | 0 | 3570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570000 | 3570000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-139 | 13-139 | 13 | N/A | 66060 | Durham DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6113 | 8367 | 8367-B01 | 400 TAUNTON RD E | WHITBY | L1R2K6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9198 | -78.9394 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42559 | 2296431 | Construction Complete | Other | Other | 2016-17 | 42614 | 0 | 0 | 1586431 | 0 | 0 | 0 | 0 | 0 | 710000 | 0 | 0 | 0 | 0 | 0 | 0 | 2296431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2296431 | 2296431 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
13-140 | 13-140 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Bayview Heights | Bayview Heights Public Elementary School | ELE | 147 | 5392 | 5392-B01 | 1400 GARVOLIN AVE | PICKERING | L1W1J6 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8272 | -79.0799 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44215 | 1095247 | Construction Complete | Retrofit | Child Care | 2021-22 | 44531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095247 | 0 | 0 | 0 | 1095247 | 1095247 | 1095247 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1095247
13-141 | 13-141 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Cartwright Central | Cartwright Central Public Elementary School | ELE | 387 | 5550 | 5550-B01 | 10 ALEXANDER ST | BLACKSTOCK | L0B1B0 | 35-11-10-602 | Scugog | Scugog Tp | Durham R | DURHAM | GTA | South | 44.1122 | -78.8225 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252086 | 0 | 0 | 0 | 252086 | 252086 | 0 | -252086 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 252086
13-142 | 13-142 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Dr Roberta Bondar | Dr Roberta Bondar Public Elementary School | ELE | 624 | 5707 | 5707-B01 | 25 SULLIVAN DR | AJAX | L1T3L3 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8711 | -79.0333 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43949 | 878164 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898164 | 0 | 0 | 0 | 898164 | 898164 | 878164 | -20000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 898164
13-143 | 13-143 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Glengrove | Glengrove Public Elementary School | ELE | 922 | 5894 | 5894-B01 | 1934 GLENGROVE RD | PICKERING | L1V1X2 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8426 | -79.0869 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 44168 | 504170 | Construction Complete | Retrofit | Child Care | 2021-22 | 44470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504171 | 0 | 0 | 0 | 504171 | 504171 | 504171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 504171
13-144 | 13-144 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Lakeside | Lakeside Public Elementary School | ELE | 1315 | 6139 | 6139-B01 | 4 PARKES DR | AJAX | L1S4X1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8234 | -79.0278 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 48 | Y | - | Approved | 44285 | 680339 | Construction Complete | Retrofit | Child Care | 2021-22 | 44621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908212 | 0 | 0 | 0 | 908212 | 908212 | 908212 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 908212
13-145 | 13-145 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Roland Michener | Roland Michener Public Elementary School | ELE | 2023 | 6605 | 6605-B01 | 95 RITCHIE AVE | AJAX | L1S6S2 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8541 | -79.0382 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43796 | 252085 | Construction Complete | Retrofit | Child Care | 2020-21 | 44105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252086 | 0 | 0 | 0 | 252086 | 252086 | 252086 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 252086
13-146 | 13-146 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Vaughan Willard | Vaughan Willard Public Elementary School | ELE | 2363 | 6814 | 6814-B01 | 1911 DIXIE RD | PICKERING | L1V1V4 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8374 | -79.1012 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Approved | 45051 | 2574882 | Planned | Retrofit | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574882 | 0 | 0 | 0 | 2574882 | 2574882 | 2574882 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2574882
13-147 | 13-147 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Winchester | Winchester Public Elementary School | ELE | 9776 | 10260 | 10260-B01 | 70 WATFORD ST | WHITBY | L1M1E8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9611 | -78.951 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43949 | 883341 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883341 | 0 | 0 | 0 | 883341 | 883341 | 883341 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 883341
13-148 | 13-148 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Bobby Orr | Bobby Orr Public Elementary School | ELE | 10470 | 11117 | 11117-B01 | 7 WATERLOO ST | OSHAWA | L1H8V9 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8729 | -78.8409 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43949 | 1121101 | Construction Complete | Retrofit | Child Care | 2021-22 | 44531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121101 | 0 | 0 | 0 | 1121101 | 1121101 | 1121101 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1121101
13-149 | 13-149 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | McCaskill's Mills | McCaskill's Mills Public Elementary School | ELE | 10808 | 12047 | 12047-B01 | 85 ALBERT ST | CANNINGTON | L0E1E0 | 35-11-10-601 | Brock | Brock Tp | Durham R | DURHAM | GTA | South | 44.3468 | -79.0454 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43777 | 504170 | Construction Complete | Retrofit | Child Care | 2020-21 | 44197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504171 | 0 | 0 | 0 | 504171 | 504171 | 504171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 504171
13-151 | 13-151 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Beaverton Thorah | Beaverton Thorah Public Elementary School | ELE | 24767 | 5399 | 5399-B02 | 270 KING ST | BEAVERTON | L0K1A0 | 35-11-10-601 | Brock | Brock Tp | Durham R | DURHAM | GTA | South | 44.4331 | -79.1552 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 418 | 3 | 49 | Y | 1 | Approved | Novermber 23, 2022 | 22309064 | Planned | New Construction | Consolidation | 2023-24 | 45174 | 0 |  | 8826759 | 0 | 658292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9485051 | 0 | 0 | 0 | 0 | 10294495 | 0 | 2025348 | 504170 | 0 | 0 | 12824013 | 22309064 | 22309064 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12824013
13-152 | 13-152 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Meadows North | Meadows North Public Elementary School | ELE | 24768 | 19775 | 19775-B01 | 270 WILLIAMSON DR W | AJAX | L1T0H7 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.882 | -79.0512 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | 43172 | 2017-18 | 2017-18 | - | - | - | 558 | - | - | N | 1 | Approved | 43728 | 12698463 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44446 | 0 | 0 | 592010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592010 | 0 | 0 | 0 | 0 | 11602283 | 0 | 0 | 504171 | 0 | 0 | 12106454 | 12698464 | 12698464 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12106454
13-153 | 13-153 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Willows Walk | Willows Walk Public Elementary School | ELE | 24769 | 19776 | 19776-B01 | 51 LAZIO ST | WHITBY | L1R3A1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.925 | -78.9378 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 490 | 4 | 73 | Y | 1 | Approved | 43728 | 13293815 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44446 | 0 | 0 | 432620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432620 | 0 | 0 | 1028507 | 0 | 9311837 | 0 | 2016682 | 504170 | 0 | 0 | 12861196 | 13293816 | 13293816 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11832689
13-154-01 | 13-154-01 | 13 | N/A | 66060 | Durham DSB | Walter E Harris | Walter E Harris Public Elementary School | ELE | 383 | 5546 | 5546-B01 | 495 CENTRAL PARK BLVD N | OSHAWA | L1G6A2 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9145 | -78.8547 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 116200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-02 | 13-154-02 | 13 | N/A | 66060 | Durham DSB | Glen Dhu | Glen Dhu Public Elementary School | ELE | 894 | 5877 | 5877-B01 | 29 FALLINGBROOK ST | WHITBY | L1R1M7 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9048 | -78.9344 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 106988 | -9212 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-03 | 13-154-03 | 13 | N/A | 66060 | Durham DSB | Glengrove | Glengrove Public Elementary School | ELE | 922 | 5894 | 5894-B01 | 1934 GLENGROVE RD | PICKERING | L1V1X2 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8426 | -79.0869 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 126200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126200 | 0 | 0 | 0 | 0 | 0 | 126200 | 126200 | 126200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 126200
13-154-04 | 13-154-04 | 13 | N/A | 66060 | Durham DSB | Lincoln Alexander | Lincoln Alexander Public Elementary School | ELE | 1362 | 6168 | 6168-B01 | 95 CHURCH ST N | AJAX | L1T2W4 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8574 | -79.056 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 232400 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232400 | 0 | 0 | 0 | 0 | 0 | 232400 | 232400 | 232400 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 232400
13-154-05 | 13-154-05 | 13 | N/A | 66060 | Durham DSB | West Lynde | West Lynde Public Elementary School | ELE | 1404 | 6197 | 6197-B01 | 270 MICHAEL BLVD | WHITBY | L1N6B1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8727 | -78.9526 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 116200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-06 | 13-154-06 | 13 | N/A | 66060 | Durham DSB | Stephen Saywell | Stephen Saywell Public Elementary School | ELE | 2234 | 6732 | 6732-B01 | 855 ROUNDELAY DR | OSHAWA | L1J7V1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9002 | -78.9007 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 116200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-07 | 13-154-07 | 13 | N/A | 66060 | Durham DSB | Goodwood | Goodwood Public Elementary School | ELE | 2349 | 6805 | 6805-B01 | 4340 FRONT ST | GOODWOOD | L0C1A0 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.0403 | -79.1978 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 126200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126200 | 0 | 0 | 0 | 0 | 0 | 126200 | 126200 | 126200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 126200
13-154-08 | 13-154-08 | 13 | N/A | 66060 | Durham DSB | Valley View | Valley View Public Elementary School | ELE | 2354 | 6808 | 6808-B01 | 3530 WESTNEY RD | GREENWOOD | L0H1H0 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.9265 | -79.0658 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 116200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-09 | 13-154-09 | 13 | N/A | 66060 | Durham DSB | Vincent Massey | Vincent Massey Public Elementary School | ELE | 2387 | 5186 | 5186-B01 | 211 HARMONY RD N | OSHAWA | L1G6L4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9105 | -78.836 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 232400 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232400 | 0 | 0 | 0 | 0 | 0 | 232400 | 232400 | 232400 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 232400
13-154-10 | 13-154-10 | 13 | N/A | 66060 | Durham DSB | Waverly | Waverly Public Elementary School | ELE | 2435 | 6869 | 6869-B01 | 100 WAVERLY ST S | OSHAWA | L1J5V1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8885 | -78.887 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 116200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-11 | 13-154-11 | 13 | N/A | 66060 | Durham DSB | Sir Samuel Steele | Sir Samuel Steele Public Elementary School | ELE | 10113 | 10398 | 10398-B01 | 55 BAKERVILLE ST | WHITBY | L1R2S6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9184 | -78.9197 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 242400 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242400 | 0 | 0 | 0 | 0 | 0 | 242400 | 242400 | 242400 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 242400
13-154-12 | 13-154-12 | 13 | N/A | 66060 | Durham DSB | Eagle Ridge | Eagle Ridge Public Elementary School | ELE | 10471 | 11118 | 11118-B01 | 425 DELANEY DR | AJAX | L1T4N1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8632 | -79.0664 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 116200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-13 | 13-154-13 | 13 | N/A | 66060 | Durham DSB | Julie Payette | Julie Payette Public Elementary School | ELE | 11122 | 12261 | 12261-B01 | 300 GARDEN ST | WHITBY | L1N3W4 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8856 | -78.9357 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 480885 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480885 | 0 | 0 | 0 | 0 | 0 | 480885 | 480885 | 480885 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 480885
13-154-14 | 13-154-14 | 13 | N/A | 66060 | Durham DSB | Clara Hughes | Clara Hughes Public Elementary School | ELE | 19890 | 5719 | 5719-B02 | 610 TAYLOR AVE | OSHAWA | L1H2E7 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8965 | -78.8385 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 116200 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116200 | 0 | 0 | 0 | 0 | 0 | 116200 | 116200 | 116200 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 116200
13-154-15 | 13-154-15 | 13 | N/A | 66060 | Durham DSB | Michaëlle Jean | Michaëlle Jean Public Elementary School | ELE | 24308 | 19300 | 19300-B01 | 180 WILLIAMSON DR E | AJAX | L1Z0G7 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8963 | -79.0248 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 232400 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232400 | 0 | 0 | 0 | 0 | 0 | 232400 | 232400 | 232400 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 232400
13-154-16 | 13-154-16 | 13 | N/A | 66060 | Durham DSB | Jeanne Sauvé | Jeanne Sauvé Public Elementary School | ELE | 24477 | 19481 | 19481-B01 | 950 COLDSTREAM DR | OSHAWA | L1K0X1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9455 | -78.8575 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 232400 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232400 | 0 | 0 | 0 | 0 | 0 | 232400 | 232400 | 232400 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 232400
13-154-17 | 13-154-17 | 13 | N/A | 66060 | Durham DSB | Northern Dancer | Northern Dancer Public Elementary School | ELE | 24572 | 19578 | 19578-B01 | 2200 BRIDLE RD | OSHAWA | L1L0L5 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9526 | -78.8927 | 43342 | 2017-18 | 2018-19 | - | - | - | 43342 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43342 | 358600 | Construction Complete | Other | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358600 | 0 | 0 | 0 | 0 | 0 | 358600 | 358600 | 358600 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 358600
13-155 | 13-155 | 13 | N/A | 66060 | Durham DSB | Mary Street | Mary Street Public Elementary School | ELE | 1487 | 6254 | 6254-B01 | 110 MARY ST N | OSHAWA | L1G7S2 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9014 | -78.8624 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 190 | - | - | - | - | Approved | 45036 | 8763038 | Planned | Addition | Condition | 2023-24 | 45174 | 0 | 694688 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1444688 | 0 | 0 | 0 | 0 | 7318350 | 0 | 0 | 0 | 0 | 0 | 7318350 | 8763038 | 8763038 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7318350
13-156 | 13-156 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Pickering Creekwood | Pickering Creekwood Public Elementary School | ELE | 25369 | 20375 | 20375-B01 | TILLINGS RD / SCENIC LANE DR | PICKERING | TBD | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8749 | -79.0913 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 536 | 4 | 73 | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11537075 | 0 | 2139296 | 0 | 0 | 0 | 13676371 | 13676371 | 13676371 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13676371
13-157 | 13-157 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | North Oshawa | North Oshawa Public Elementary School | ELE | 25491 | 20497 | 20497-B01 | WINDFIELDS FARM DR W / WINTERGRACE AVE | OSHAWA | TBD | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9572 | -78.9149 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 536 | 4 | 73 | N | - | Approved | 44902 | 22247107 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 1898100 | 0 | 630937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2529037 | 0 | 0 | 0 | 0 | 17280939 | 0 | 2437131 | 0 | 0 | 0 | 19718070 | 22247107 | 22247107 | 0 | - | No, Site to be acquired. Sign installation planned for October 1, 2021 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19718070
13-158 | 13-094 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | RS McLaughlin | RS McLaughlin Public Secondary School | SEC | 5606 | 5314 | 5314-L02 | 570 STEVENSON RD N | OSHAWA | L1J5P1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9076 | -78.8908 | 44181 | 2020-21 | 2020-21 | 44181 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | 60 | - | - | N | - | Approved | 44181 | 311321 | Construction Complete | Land Acquisition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311321 | 0 | 0 | 0 | 0 | 0 | 0 | 311321 | 311321 | 311321 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 311321
13-159 | 13-159 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Sunderland | Sunderland Public Elementary School | ELE | 2257 | 6747 | 6747-B01 | 41 ALBERT ST | SUNDERLAND | L0C1H0 | 35-11-10-601 | Brock | Brock Tp | Durham R | DURHAM | GTA | South | 44.2599 | -79.0655 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604472 | 0 | 0 | 0 | 1604472 | 1604472 | 1604472 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1604472
13-160 | 13-160 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Rosebank Road | Rosebank Road Public Elementary School | ELE | 2033 | 6613 | 6613-B01 | 591 ROSEBANK RD | PICKERING | L1W2N6 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8074 | -79.1205 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604472 | 0 | 0 | 0 | 1604472 | 1604472 | 1604472 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1604472
13-161 | 13-161 | 13 | N/A | 66060 | Durham DSB | North Oshawa | North Oshawa Public Secondary School | SEC | TBD | TBD | TBD | TBD | OSHAWA | L1L0J9 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 1387 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46389932 | 0 | 0 | 0 | 0 | 0 | 46389932 | 46389932 | 46389932 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 46389932
13-162 | 13-162 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Pickering Seaton | Pickering Seaton Public Elementary School | ELE | TBD | TBD | TBD | TBD | PICKERING | L1X0G2 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 634 | 4 | 73 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16389205 | 0 | 2607797 | 0 | 0 | 0 | 18997002 | 18997002 | 18997002 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 18997002
13-164 | 13-151 | 13 | N/A | 66060 | Durham DSB | Beaverton Thorah | Beaverton Thorah Public Elementary School | ELE | 24767 | 5399 | 5399-B01 | 270 KING ST | BEAVERTON | L0K1A0 | 35-11-10-601 | Brock | Brock Tp | Durham R | DURHAM | GTA | South | 44.4331 | -79.1552 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | Novermber 23, 2022 | 620000 | Planned | Demolition | Consolidation |  |  | 0 | 0 | 0 | 0 | 136400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136400 | 0 | 0 | 0 | 0 | 483600 | 0 | 0 | 0 | 0 | 0 | 483600 | 620000 | 620000 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 483600
14-001 | 14-001 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15353 | 18048 | 18048-B01 | 1994 FISHER DR | PETERBOROUGH | K9J6X6 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2599 | -78.3518 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709658 | 0 | 10649 | 0 | 0 | 0 | 720307 | 720307 | 0 | -720307 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | NO | YES | 720307
14-002 | 14-002 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15353 | 18048 | 18048-B01 | 1994 FISHER DR | PETERBOROUGH | K9J6X6 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2599 | -78.3518 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 14757570 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830432 | 14830432 | 14712869 | -117563 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-003 | 14-003 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 15353 | 18048 | 18048-B01 | 1994 FISHER DR | PETERBOROUGH | K9J6X6 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2599 | -78.3518 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 464175 | Construction Complete | Other | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464175 | 464175 | 464175 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-004 | 14-004 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Apsley Central | Apsley Central Public Elementary School | ELE | 11009 | 5350 | 5350-B02 | 238 BURLEIGH ST | APSLEY | K0L1A0 | 35-12-66-616 | North Kawartha | North Kawartha Tp | Peterborough Co | PETERBOROUGH | East | South | 44.7592 | -78.0889 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6767315 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 237948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237948 | 6529367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6529367 | 6767315 | 6767315 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-005 | 14-005 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Brighton | Brighton Public Elementary School | ELE | 248 | 5453 | 5453-B01 | 24 ELIZABETH ST | BRIGHTON | K0K1H0 | 35-12-61-407 | Brighton | Brighton M | Northumberland Co | NORTHUMBERLAND | East | South | 44.043 | -77.7328 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8956289 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 229205 | 0 | 0 | 0 | 0 | 1104017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1333222 | 6957749 | 0 | 665318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7623067 | 8956289 | 8956289 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-007 | 14-007 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Charles Bowman | Charles Bowman Public Elementary School | ELE | 11010 | 12143 | 12143-B01 | 195 BONS AVE | BOWMANVILLE | L1C0L3 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.931 | -78.6974 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8386976 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83041 | 83041 | 7416844 | 0 | 887091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303935 | 8386976 | 8386976 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-008 | 14-008 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Charles Bowman | Charles Bowman Public Elementary School | ELE | 11010 | 12143 | 12143-B01 | 195 BONS AVE | BOWMANVILLE | L1C0L3 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.931 | -78.6974 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 170 | - | - | N | - | Not Required | - | 2108182 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007952 | 0 | 1100230 | 0 | 0 | 0 | 0 | 0 | 2108182 | 2108182 | 2108182 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1100230
14-009 | 14-009 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Chemong | Chemong Public Elementary School | ELE | 434 | 5585 | 5585-B01 | 1029 GORE ST | BRIDGENORTH | K0L1H0 | 35-12-66-623 | Selwyn | Selwyn Tp | Peterborough Co | PETERBOROUGH | East | South | 44.3797 | -78.3815 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1502067 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1502067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1502067 | 1502067 | 1502067 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-011 | 14-011 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Clarington Central | Clarington Central Public Secondary School | SEC | 10486 | 11127 | 11127-B01 | 200 CLARINGTON BLVD | BOWMANVILLE | L1C5N8 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9131 | -78.7095 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21616421 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 259226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259226 | 21357195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21357195 | 21616421 | 21616421 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-012 | 14-012 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Cobourg | Cobourg Public Secondary School | SEC | 5288 | 8170 | 8170-B01 | 335 KING ST E | COBOURG | K9A1M2 | 35-12-61-403 | Cobourg | Cobourg T | Northumberland Co | NORTHUMBERLAND | East | South | 43.9622 | -78.1522 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 84 | - | - | N | - | Not Required | - | 12371807 | Construction Complete | Addition | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12371807 | 0 | 0 | 0 | 0 | 0 | 12371807 | 12371807 | 12371807 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12371807
14-015-01 | 14-015 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | CR Gummow | CR Gummow Public Elementary School | ELE | 24227 | 5583 | 5583-B02 | 311 COTTESMORE AVE | COBOURG | K9A4E3 | 35-12-61-403 | Cobourg | Cobourg T | Northumberland Co | NORTHUMBERLAND | East | South | 43.9657 | -78.1536 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 678 | - | - | N | - | Not Required | - | 11778498 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453754 | 0 | 11370875 | 0 | 0 | 0 | 0 | 0 | 12824629 | 12824629 | 12079457 | -745172 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11370875
14-015-03 | 14-015 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | CR Gummow | CR Gummow Public Elementary School | ELE | 431 | 5583 | 5583-B01 | 287 GRAVELY ST | COBOURG | K9A1H8 | 35-12-61-403 | Cobourg | Cobourg T | Northumberland Co | NORTHUMBERLAND | East | South | 43.9649 | -78.1557 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 452600 | Construction Complete | Demolition | Other | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452600 | 0 | 0 | 0 | 0 | 0 | 452600 | 452600 | 197629 | -254971 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 452600
14-016 | 14-016 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Dr. GJ MacGillivray | Dr. GJ MacGillivray Public Elementary School | ELE | 10056 | 10380 | 10380-B01 | 75 MEADOWGLADE RD | COURTICE | L1E3G7 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.8943 | -78.7964 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7988981 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7988981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7988981 | 7988981 | 7988981 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-017 | 14-017 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Dr. GJ MacGillivray | Dr. GJ MacGillivray Public Elementary School | ELE | 10056 | 10380 | 10380-B01 | 75 MEADOWGLADE RD | COURTICE | L1E3G7 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.8943 | -78.7964 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 179 | - | - | N | - | Not Required | - | 2044215 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007952 | 0 | 1036263 | 0 | 0 | 0 | 0 | 0 | 2044215 | 2044215 | 2044215 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1036263
14-018 | 14-018 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Dr. MS Hawkins Senior | Dr. MS Hawkins Senior Public Elementary School | ELE | 10230 | 8343 | 8343-B01 | 130 HIGHLAND DR | PORT HOPE | L1A2A3 | 35-12-61-409 | Port Hope | Port Hope M | Northumberland Co | NORTHUMBERLAND | East | South | 43.9577 | -78.3102 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1601880 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601880 | 1601880 | 1601880 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-020 | 14-020 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Duke of Cambridge | Duke of Cambridge Public Elementary School | ELE | 18392 | 6834 | 6834-B03 | 47 LIBERTY ST N | BOWMANVILLE | L1C2L8 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9139 | -78.6797 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 703 | - | - | N | - | Not Required | - | 12245117 | Construction Complete | New Construction | Other | 2013-14 | 41520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11373609 | 0 | 871508 | 0 | 336473 | 0 | 0 | 0 | 0 | 0 | 12581590 | 12581590 | 12245117 | -336473 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 336473
14-022 | 14-022 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Ganaraska Trail | Ganaraska Trail Public Elementary School | ELE | 11008 | 6020 | 6020-B01 | 34 PERCIVAL ST | PORT HOPE | L1A2B7 | 35-12-61-409 | Port Hope | Port Hope M | Northumberland Co | NORTHUMBERLAND | East | South | 43.9568 | -78.3153 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8747411 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 46433 | 0 | 0 | 0 | 186278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232711 | 8514700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8514700 | 8747411 | 8747411 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-023 | 14-023 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Ganaraska Trail | Ganaraska Trail Public Elementary School | ELE | 11008 | 6020 | 6020-B01 | 34 PERCIVAL ST | PORT HOPE | L1A2B7 | 35-12-61-409 | Port Hope | Port Hope M | Northumberland Co | NORTHUMBERLAND | East | South | 43.9568 | -78.3153 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Approved | 42846 | 2061064 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254556 | 0 | 1806508 | 0 | 0 | 0 | 0 | 0 | 2061064 | 2061064 | 2061064 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1806508
14-026 | 14-026 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Harold Longworth | Harold Longworth Public Elementary School | ELE | 10387 | 11092 | 11092-B01 | 350 LONGWORTH AVE | BOWMANVILLE | L1C5J5 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9325 | -78.6825 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8073124 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8073124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8073124 | 8073124 | 8073124 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-031 | 14-031 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | John M James | John M James Public Elementary School | ELE | 10055 | 10379 | 10379-B01 | 175 MEARNS AVE | BOWMANVILLE | L1C5C6 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9242 | -78.6741 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6969472 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6969472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6969472 | 6969472 | 6969472 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-035 | 14-035 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Kenner | Kenner Public Elementary School | ELE | 10601 | 8262 | 8262-B01 | 633 MONAGHAN RD | PETERBOROUGH | K9J5J2 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2784 | -78.3269 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1584337 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584337 | 1584337 | 1584337 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-038 | 14-038 | 14 | 208 - CMSM Peterborough | 66079 | Kawartha Pine Ridge DSB | Lakefield | Lakefield Public Elementary School | ELE | 24641 | 6135 | 6135-B01 | 71 BRIDGE ST | LAKEFIELD | K0L2H0 | 35-12-66-623 | Selwyn | Selwyn Tp | Peterborough Co | PETERBOROUGH | East | South | 44.4198 | -78.2784 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | N | 1 | Approved | 42864 | 7264442 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942315 | 0 | 0 | 0 | 0 | 4408417 | 0 | 1705281 | 568427 | 0 | 0 | 6682125 | 7624440 | 7624440 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 6682125
14-039 | 14-039 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Millbrook-South Cavan | Millbrook-South Cavan Public Elementary School | ELE | 1538 | 3012 | 3012-B01 | 47 TUPPER ST | MILLBROOK | L0A1G0 | 35-12-66-617 | Cavan-Monaghan | Cavan Monaghan Tp | Peterborough Co | PETERBOROUGH | East | South | 44.1555 | -78.4497 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2577956 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 152956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152956 | 2425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2425000 | 2577956 | 2577956 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-040 | 14-040 | 14 | 208 - CMSM Peterborough | 66079 | Kawartha Pine Ridge DSB | Millbrook-South Cavan | Millbrook-South Cavan Public Elementary School | ELE | 1538 | 3012 | 3012-B01 | 47 TUPPER ST | MILLBROOK | L0A1G0 | 35-12-66-617 | Cavan-Monaghan | Cavan Monaghan Tp | Peterborough Co | PETERBOROUGH | East | South | 44.1555 | -78.4497 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 92 | 3 | 49 | N | - | Approved | 42600 | 3501764 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1974425 | 0 | 1527339 | 0 | 0 | 0 | 3501764 | 3501764 | 3501764 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3501764
14-044 | 14-044 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Northumberland Hills | Northumberland Hills Public Elementary School | ELE | 11107 | 12237 | 12237-B01 | 2246 SPRING ST | CASTLETON | K0K1M0 | 35-12-61-617 | Cramahe | Cramahe Tp | Northumberland Co | NORTHUMBERLAND | East | South | 44.0969 | -77.9333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7592817 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 197612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197612 | 7395205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7395205 | 7592817 | 7592817 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-050 | 14-050 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Ridpath | Ridpath Public Elementary School | ELE | 1312 | 6136 | 6136-B01 | 39 ERMATINGER ST | LAKEFIELD | K0L2H0 | 35-12-66-623 | Selwyn | Selwyn Tp | Peterborough Co | PETERBOROUGH | East | South | 44.4257 | -78.2651 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1369289 | Construction Complete | Addition | Other | 2009-10 | 40057 | 4308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4308 | 1364981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1364981 | 1369289 | 1369289 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-052 | 14-052 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Roger Neilson | Roger Neilson Public Elementary School | ELE | 10525 | 5935 | 5935-B01 | 550 ERSKINE AVE | PETERBOROUGH | K9J5T4 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2744 | -78.3312 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6023774 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6023774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6023774 | 6023774 | 6023774 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-056 | 14-056 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Thomas A Stewart | Thomas A Stewart Public Secondary School | SEC | 5702 | 8399 | 8399-B01 | 1009 ARMOUR RD | PETERBOROUGH | K9H7H2 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3309 | -78.3099 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42548 | 2732958 | Construction Complete | Retrofit | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2732958 | 0 | 0 | 0 | 0 | 0 | 2732958 | 2732958 | 2732958 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2732958
14-057 | 14-057 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Waverley | Waverley Public Elementary School | ELE | 2426 | 6861 | 6861-B01 | 168 WAVERLEY RD | BOWMANVILLE | L1C3Y8 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.902 | -78.6918 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1692041 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1692041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1692041 | 1692041 | 1692041 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-059 | 14-059 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Westmount | Westmount Public Elementary School | ELE | 2475 | 6891 | 6891-B01 | 1520 SHERWOOD CRES | PETERBOROUGH | K9J6T8 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3045 | -78.3527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1336421 | Construction Complete | Addition | Other | 2014-15 | 41883 | 123634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123634 | 0 | 0 | 1212787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212787 | 1336421 | 1336421 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-060-01 | 14-060 | 14 | 208 - CMSM Peterborough | 66079 | Kawartha Pine Ridge DSB | East City | East City Public Elementary School | ELE | 24597 | 6110 | 6110-B02 | 220 HUNTER ST | PETERBOROUGH | K9H1H1 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3086 | -78.3039 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 674 | 3 | 49 | Y | - | Approved | 43584 | 19664319 | Construction Complete | New Construction | Consolidation | 2021-22 | 44440 | 0 | 0 | 0 | 1131600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1131600 | 0 | 0 | 1298237 | 0 | 15676596 | 0 | 1557886 | 0 | 0 | 0 | 18532719 | 19664319 | 19664319 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 17234482
14-060-02 | 14-060 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | East City | East City Public Elementary School | ELE | 24597 | 6110 | 6110-L02 | 220 HUNTER ST | PETERBOROUGH | K9H1H1 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3086 | -78.3039 | 43213 | 2017-18 | 2018-19 | 43213 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43213 | 300000 | Construction Complete | Land Acquisition | Consolidation | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 300000
14-061 | 14-061 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Orono | Orono Public Elementary School | ELE | 457 | 5594 | 5594-B01 | 171 CHURCH ST | ORONO | L0B1M0 | 35-11-10-402 | Clarington | Clarington M | Durham R | PETERBOROUGH | GTA | South | 43.9798 | -78.6159 | 43019 | 2017-18 | 2017-18 | - | - | - | 43019 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 69 | - | - | N | - | Approved | 43101 | 3350132 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 678588 | 0 | 0 | 1862467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2541055 | 0 | 0 | 0 | 0 | 745172 | 0 | 0 | 0 | 0 | 0 | 745172 | 3286227 | 3286227 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 745172
14-062 | 14-062 | 14 | 221 - CMSM Northumberland | 66079 | Kawartha Pine Ridge DSB | Brighton | Brighton Public Elementary School | ELE | 248 | 5453 | 5453-B01 | 24 ELIZABETH ST | BRIGHTON | K0K1H0 | 35-12-61-407 | Brighton | Brighton M | Northumberland Co | NORTHUMBERLAND | East | South | 44.043 | -77.7328 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 44385 | 1186906 | Under Construction | Addition | Child Care | 2022-23 | 44835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 836906 | 0 | 0 | 0 | 836906 | 1186906 | 1186906 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 836906
14-063 | 14-063 | 14 | 208 - CMSM Peterborough | 66079 | Kawartha Pine Ridge DSB | Havelock-Belmont | Havelock-Belmont Public Elementary School | ELE | 1033 | 5976 | 5976-B01 | 55 MATHISON ST E | HAVELOCK | K0L1Z0 | 35-12-66-620 | Havelock-Belmont-Methuen | Havelock-Belmont-Methuen Tp | Peterborough Co | PETERBOROUGH | East | South | 44.4365 | -77.8794 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44386 | 771457 | Construction Complete | Retrofit | Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771457 | 0 | 0 | 0 | 771457 | 771457 | 771457 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 771457
14-064 | 14-064 | 14 | 208 - CMSM Peterborough | 66079 | Kawartha Pine Ridge DSB | Crestwood | Crestwood Public Secondary School | SEC | 5301 | 8178 | 8178-B01 | 1885 SHERBROOKE ST W | CAVAN MONAGHAN | K9J0E5 | 35-12-66-617 | Cavan-Monaghan | Cavan Monaghan Tp | Peterborough Co | PETERBOROUGH | East | South | 44.2867 | -78.3816 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502881 | 0 | 0 | 0 | 502881 | 502881 | 502881 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 502881
14-065 | 14-065 | 14 | 208 - CMSM Peterborough | 66079 | Kawartha Pine Ridge DSB | Norwood District | Norwood District Public Secondary School | SEC | 5558 | 5221 | 5221-B01 | 44 ELM ST | NORWOOD | K0L2V0 | 35-12-66-615 | Asphodel-Norwood | Asphodel-Norwood Tp | Peterborough Co | PETERBOROUGH | East | South | 44.3828 | -77.9725 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44328 | 3374309 | Construction Complete | Retrofit | Child Care | 2021-22 | 44652 | 757655 | 757655 | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 2424310 | 0 | 0 | 0 | 0 | 0 | 0 | 949999 | 0 | 0 | 0 | 949999 | 3374309 | 3374309 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 949999
14-066 | 14-066 | 14 | 229 - CMSM Durham | 66079 | Kawartha Pine Ridge DSB | John M James | John M James Public Elementary School | ELE | 10055 | 10379 | 10379-B01 | 175 MEARNS AVE | BOWMANVILLE | L1C5C6 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9242 | -78.6741 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293068 | 0 | 0 | 0 | 293068 | 293068 | 293068 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 293068
14-067 | 14-067 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Newcastle | Newcastle Public Elementary School | ELE | 1626 | 6351 | 6351-B01 | 50 GLASS CRT | NEWCASTLE | L1B1M5 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9127 | -78.5827 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
14-068 | 14-068 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | 1211 Brealey Drive | 1211 Brealey Drive Land Holding | HFA | 1186 | 6058 | 6058-L01 | 1211 BREALEY DR | PETERBOROUGH | TBD | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2883 | -78.3772 | 44285 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44285 | 1570199 | Construction Complete | Land Acquisition | Other | 2021-22 | 44440 | 0 | 0 | 397423 | 1172776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570199 | 1570199 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
14-069 | 14-069 | 14 | 229 - CMSM Durham | 66079 | Kawartha Pine Ridge DSB | Northglen | Northglen Public Elementary School | ELE | TBD | TBD | TBD | NORTHGLEN BLVD / EDWIN CARR ST | BOWMANVILLE | TBD | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9373 | -78.7088 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 769 | 4 | 73 | N | - | Approved | 45184 | 36790281 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33120321 | 0 | 3669960 | 0 | 0 | 0 | 36790281 | 36790281 | 36790281 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 36790281
14-070 | 14-070 | 14 | N/A | 66079 | Kawartha Pine Ridge DSB | Murray Centennial | Murray Centennial Public Elementary School | ELE | 1592 | 6322 | 6322-B01 | 654 COUNTY RD 40 | TRENTON | K8V5P4 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.0973 | -77.6162 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 170 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4561225 | 0 | 0 | 0 | 0 | 0 | 4561225 | 4561225 | 4561225 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4561225
15-001 | 15-001 | 15 | N/A | 66087 | Trillium Lakelands DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-OPS | 18113 | 8253 | 8253-B02 | 300 HWY 36 | LINDSAY | K9V4S4 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.3597 | -78.7161 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-002 | 15-002 | 15 | N/A | 66087 | Trillium Lakelands DSB | FDK Projects | Full Day Kindergarten Projects | OFF-OPS | 18113 | 8253 | 8253-B02 | 300 HWY 36 | LINDSAY | K9V4S4 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.3597 | -78.7161 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10178904 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10647721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10647721 | 10647721 | 10178904 | -468817 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-003 | 15-003 | 15 | N/A | 66087 | Trillium Lakelands DSB | Alexandra | Alexandra Public Elementary School | ELE | 46 | 5327 | 5327-B01 | 65 SUSSEX ST N | LINDSAY | K9V4H9 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.3588 | -78.7453 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1361122 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361122 | 1361122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1361122 | 1361122 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-006 | 15-006 | 15 | N/A | 66087 | Trillium Lakelands DSB | Bracebridge and Muskoka Lakes | Bracebridge and Muskoka Lakes Public Secondary School | SEC | 10829 | 12008 | 12008-B01 | 100 CLEARBROOK TRAIL | BRACEBRIDGE | P1L0A3 | 35-11-33-401 | Bracebridge | Bracebridge T | Muskoka D | MUSKOKA | Central | South | 45.0644 | -79.3196 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 27853562 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27853562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27853562 | 27853562 | 27853562 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-010 | 15-010 | 15 | N/A | 66087 | Trillium Lakelands DSB | King Albert | King Albert Public Elementary School | ELE | 1267 | 6105 | 6105-B01 | 49 GLENELG ST W | LINDSAY | K9V2T9 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.3518 | -78.7377 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1233093 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1233093 | 1233093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1233093 | 1233093 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-016 | 15-016 | 15 | N/A | 66087 | Trillium Lakelands DSB | Monck | Monck Public Elementary School | ELE | 1558 | 6301 | 6301-B01 | 250 WELLINGTON ST | BRACEBRIDGE | P1L1C1 | 35-11-33-401 | Bracebridge | Bracebridge T | Muskoka D | MUSKOKA | Central | South | 45.0408 | -79.321 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2443040 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443040 | 2443040 | 2443040 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-018 | 15-018 | 15 | N/A | 66087 | Trillium Lakelands DSB | Muskoka Falls | Muskoka Falls Public Elementary School | ELE | 10908 | 6327 | 6327-B01 | 42 MORROW DR | BRACEBRIDGE | P1L0A1 | 35-11-33-401 | Bracebridge | Bracebridge T | Muskoka D | MUSKOKA | Central | South | 44.9949 | -79.299 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5958301 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2479745 | 2479745 | 3478556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3478556 | 5958301 | 5958301 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-023 | 15-023 | 15 | N/A | 66087 | Trillium Lakelands DSB | TLDSB Head Office | Operational Office | OFF-OPS | 18113 | 8253 | 8253-B02 | 300 HWY 36 | LINDSAY | K9V4S4 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.3597 | -78.7161 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6150000 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6150000 | 6150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6150000 | 6150000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
15-024 | 15-024 | 15 | 226 - CMSM Muskoka | 66087 | Trillium Lakelands DSB | Gravenhurst | Gravenhurst Public Elementary School | ELE | 960 | 5923 | 5923-B02 | 301 MARY ST S | GRAVENHURST | P1P1X6 | 35-11-33-402 | Gravenhurst | Gravenhurst T | Muskoka D | MUSKOKA | Central | South | 44.9181 | -79.3772 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2022-23 | 44928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663763 | 0 | 0 | 0 | 1663763 | 1663763 | 1663763 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1663763
15-025 | 15-025 | 15 | 204 - CMSM Kawartha Lakes | 66087 | Trillium Lakelands DSB | Scott Young | Scott Young Public Elementary School | ELE | 6372 | 8702 | 8702-B01 | 27 WALNUT ST | OMEMEE | K0L2W0 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.2993 | -78.5655 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 52 | 3 | 49 | Y | 1 | Approved | 44987 | 5908455 | Planned | Addition | Consolidation | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364454 | 0 | 3019664 | 524337 | 0 | 0 | 5908455 | 5908455 | 5908455 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5908455
15-026 | 15-026 | 15 | 226 - CMSM Muskoka | 66087 | Trillium Lakelands DSB | Glen Orchard | Glen Orchard Public Elementary School | ELE | 1522 | 6278 | 6278-B01 | 3954 MUSKOKA RD 169 RR 1 | PORT CARLING | P0B1J0 | 35-11-33-603 | Muskoka Lakes | Muskoka Lakes Tp | Muskoka D | MUSKOKA | Central | South | 45.0856 | -79.633 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 54 | Y | - | Approved | 44685 | 1706384 | Under Construction | Retrofit | Consolidation | 2023-24 | 45170 | 100000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 1516384 | 0 | 0 | 0 | 1516384 | 1706384 | 1706384 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CP (CP+CC) | YES | 1516384
15-027-01 | 15-027 | 15 | N/A | 66087 | Trillium Lakelands DSB | Honey Harbour | Honey Harbour Public Elementary School | ELE | 24719 | 9342 | 9342-B01 | 2586 HONEY HARBOUR RD | HONEY HARBOUR | P0E1E0 | 35-11-33-601 | Georgian Bay | Georgian Bay Tp | Muskoka D | MUSKOKA | Central | South | 44.8674 | -79.8186 | 43390 | 2018-19 | 2018-19 | - | - | - | 43390 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43390 | 351250 | Construction Complete | Purchase | Consolidation | 2019-20 | 43710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351250 | 0 | 0 | 0 | 0 | 0 | 351250 | 351250 | 351250 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 351250
15-027-02 | 15-027 | 15 | N/A | 66087 | Trillium Lakelands DSB | Honey Harbour | Honey Harbour Public Elementary School | ELE | 24719 | 9342 | 9342-L01 | 2586 HONEY HARBOUR RD | HONEY HARBOUR | P0E1E0 | 35-11-33-601 | Georgian Bay | Georgian Bay Tp | Muskoka D | MUSKOKA | Central | South | 44.8674 | -79.8186 | 43390 | 2018-19 | 2018-19 | 43390 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43390 | 240750 | Construction Complete | Land Acquisition | Consolidation | 2019-20 | 43710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240750 | 0 | 0 | 0 | 0 | 0 | 0 | 240750 | 240750 | 240750 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 240750
16-001 | 16-001 | 16 | N/A | 66095 | York Region DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 6482 | 19052 | 19052-B01 | 60 WELLINGTON ST W | AURORA | L4G3H2 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9994 | -79.4724 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-002 | 16-002 | 16 | N/A | 66095 | York Region DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 6482 | 19052 | 19052-B01 | 60 WELLINGTON ST W | AURORA | L4G3H2 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9994 | -79.4724 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 58867352 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59717344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59717344 | 59717344 | 58464190 | -1253154 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-003 | 16-003 | 16 | N/A | 66095 | York Region DSB | Adrienne Clarkson | Adrienne Clarkson Public Elementary School | ELE | 10535 | 11156 | 11156-B01 | 68 QUEENS COLLEGE DR | RICHMOND HILL | L4B1X3 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8465 | -79.4017 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6641037 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6641037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6641037 | 6641037 | 6641037 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-004 | 16-004 | 16 | N/A | 66095 | York Region DSB | Adrienne Clarkson | Adrienne Clarkson Public Elementary School | ELE | 10535 | 11156 | 11156-B01 | 68 QUEENS COLLEGE DR | RICHMOND HILL | L4B1X3 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8465 | -79.4017 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 110000 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 110000 | 110000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-005 | 16-005 | 16 | N/A | 66095 | York Region DSB | Aldergrove | Aldergrove Public Elementary School | ELE | 71 | 5339 | 5339-B01 | 150 ALDERGROVE DR | MARKHAM | L3R6Z8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8297 | -79.2951 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1081638 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1081638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1081638 | 1081638 | 1081638 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-007 | 16-007 | 16 | N/A | 66095 | York Region DSB | Alexander MacKenzie | Alexander MacKenzie Public Secondary School | SEC | 5306 | 8180 | 8180-B01 | 300 MAJOR MACKENZIE DR W | RICHMOND HILL | L4C3S3 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.87 | -79.4468 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4592805 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204805 | 204805 | 4388000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4388000 | 4592805 | 4592805 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-008 | 16-008 | 16 | N/A | 66095 | York Region DSB | Alexander Muir | Alexander Muir Public Elementary School | ELE | 10999 | 12135 | 12135-B01 | 75 FORD WILSON BLVD | NEWMARKET | L3X3G1 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0557 | -79.4994 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8986658 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8986658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8986658 | 8986658 | 8986658 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-010 | 16-010 | 16 | N/A | 66095 | York Region DSB | Anne Frank | Anne Frank Public Elementary School | ELE | 24234 | 19226 | 19226-B01 | 431 ILAN RAMON BLVD | MAPLE | L6A0X2 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8594 | -79.4652 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Not Required | - | 10443386 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931895 | 0 | 9511491 | 0 | 0 | 0 | 0 | 0 | 10443386 | 10443386 | 10443386 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9511491
16-011 | 16-011 | 16 | N/A | 66095 | York Region DSB | Armadale | Armadale Public Elementary School | ELE | 8 | 5307 | 5307-B01 | 11 COPPARD AVE | MARKHAM | L3S2J4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.837 | -79.2727 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3394494 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3394494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3394494 | 3394494 | 3394494 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-012 | 16-012 | 16 | N/A | 66095 | York Region DSB | Armadale | Armadale Public Elementary School | ELE | 8 | 5307 | 5307-B01 | 11 COPPARD AVE | MARKHAM | L3S2J4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.837 | -79.2727 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 540975 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540975 | 540975 | 540975 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-014 | 16-014 | 16 | N/A | 66095 | York Region DSB | Aurora Grove | Aurora Grove Public Elementary School | ELE | 9746 | 10245 | 10245-B01 | 415 STONE RD | AURORA | L4G6Z5 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9937 | -79.4467 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6087075 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12519 | 12519 | 6074556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6074556 | 6087075 | 6087075 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-015 | 16-015 | 16 | N/A | 66095 | York Region DSB | Aurora Heights | Aurora Heights Public Elementary School | ELE | 109 | 5364 | 5364-B01 | 85 TECUMSEH DR | AURORA | L4G2X5 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.0038 | -79.4743 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4625622 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4625622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4625622 | 4625622 | 4625622 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-017 | 16-017 | 16 | N/A | 66095 | York Region DSB | Bakersfield | Bakersfield Public Elementary School | ELE | 10155 | 10431 | 10431-B01 | 121 MISTYSUGAR TRAIL | THORNHILL | L4J8T6 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8279 | -79.4695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6915927 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6915927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6915927 | 6915927 | 6915927 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-019 | 16-019 | 16 | N/A | 66095 | York Region DSB | Bayview | Bayview Public Secondary School | SEC | 5226 | 8131 | 8131-B01 | 10077 BAYVIEW AVE | RICHMOND HILL | L4C2L4 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8782 | -79.4149 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2959183 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623199 | 623199 | 2335984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2335984 | 2959183 | 2959183 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-020 | 16-020 | 16 | N/A | 66095 | York Region DSB | Bayview Fairways | Bayview Fairways Public Elementary School | ELE | 145 | 5390 | 5390-B01 | 255 BAYVIEW FAIRWAYS DR | THORNHILL | L3T2Z6 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8186 | -79.3834 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 204000 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000 | 204000 | 204000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-021 | 16-021 | 16 | N/A | 66095 | York Region DSB | Bayview Hill | Bayview Hill Public Elementary School | ELE | 133 | 5381 | 5381-B01 | 81 STRATHEARN AVE | RICHMOND HILL | L4B2J5 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8629 | -79.4053 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2264088 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264088 | 2264088 | 2264088 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-022 | 16-022 | 16 | N/A | 66095 | York Region DSB | Beckett Farm | Beckett Farm Public Elementary School | ELE | 20281 | 19131 | 19131-B01 | 78 BECKETT AVE | MARKHAM | L6C0T3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8839 | -79.3096 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Not Required | - | 10253050 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 0 | 9321157 | 0 | 0 | 0 | 0 | 0 | 10253051 | 10253051 | 10253051 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9321157
16-023 | 16-023 | 16 | N/A | 66095 | York Region DSB | Beynon Fields | Beynon Fields Public Elementary School | ELE | 14835 | 18044 | 18044-B01 | 258 SELWYN RD | RICHMOND HILL | L4E0R9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.916 | -79.471 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11175998 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11175998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11175998 | 11175998 | 11175998 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-024 | 16-024 | 16 | N/A | 66095 | York Region DSB | Bill Crothers | Bill Crothers Public Secondary School | SEC | 10159 | 10435 | 10435-B01 | 44 MAIN ST | UNIONVILLE | L3R2E4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8583 | -79.31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 41162674 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277500 | 277500 | 40885174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40885174 | 41162674 | 41162674 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-025 | 16-025 | 16 | N/A | 66095 | York Region DSB | Black Walnut | Black Walnut Public Elementary School | ELE | 14831 | 18040 | 18040-B01 | 30 JOHN ALLAN CAMERON ST | MARKHAM | L6B0P4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8942 | -79.2221 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9734865 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8390788 | 0 | 1344077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9734865 | 9734865 | 9734865 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-026 | 16-026 | 16 | N/A | 66095 | York Region DSB | Blue Willow | Blue Willow Public Elementary School | ELE | 9742 | 10241 | 10241-B01 | 250 BLUE WILLOW DR | WOODBRIDGE | L4L9E1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.792 | -79.5577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7700191 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7700191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7700191 | 7700191 | 7700191 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-027 | 16-027 | 16 | N/A | 66095 | York Region DSB | Blue Willow | Blue Willow Public Elementary School | ELE | 9742 | 10241 | 10241-B01 | 250 BLUE WILLOW DR | WOODBRIDGE | L4L9E1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.792 | -79.5577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1906594 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1906594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1906594 | 1906594 | 1906594 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-028 | 16-028 | 16 | N/A | 66095 | York Region DSB | Bond Lake | Bond Lake Public Elementary School | ELE | 11232 | 12233 | 12233-B01 | 245 OLD COLONY RD | RICHMOND HILL | L4E5B9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9387 | -79.4397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9120615 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9120615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9120615 | 9120615 | 9120615 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-029 | 16-029 | 16 | N/A | 66095 | York Region DSB | Boxwood | Boxwood Public Elementary School | ELE | 9744 | 10243 | 10243-B01 | 30 BOXWOOD CRES | MARKHAM | L3S3P7 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8557 | -79.244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6876671 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6876671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6876671 | 6876671 | 6876671 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-030 | 16-030 | 16 | N/A | 66095 | York Region DSB | Bur Oak | Bur Oak Public Secondary School | SEC | 10759 | 11974 | 11974-B01 | 933 BUR OAK AVE | MARKHAM | L6E1G4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8973 | -79.2787 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 27021258 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27021258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27021258 | 27021258 | 27021258 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-031 | 16-031 | 16 | N/A | 66095 | York Region DSB | Carrville Mills | Carrville Mills Public Elementary School | ELE | 10791 | 11996 | 11996-B01 | 270 APPLE BLOSSOM DR | THORNHILL | L4J8W5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8407 | -79.4727 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8996590 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8996590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8996590 | 8996590 | 8996590 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-032 | 16-032 | 16 | N/A | 66095 | York Region DSB | Carrville Mills | Carrville Mills Public Elementary School | ELE | 10791 | 11996 | 11996-B01 | 270 APPLE BLOSSOM DR | THORNHILL | L4J8W5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8407 | -79.4727 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1578397 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613617 | 0 | 964780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1578397 | 1578397 | 1578397 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-033 | 16-033 | 16 | N/A | 66095 | York Region DSB | Castlemore | Castlemore Public Elementary School | ELE | 9922 | 10330 | 10330-B01 | 256 RIDGECREST RD | MARKHAM | L6C2R5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8979 | -79.3037 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7100182 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7100182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7100182 | 7100182 | 7100182 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-034 | 16-034 | 16 | N/A | 66095 | York Region DSB | Castlemore | Castlemore Public Elementary School | ELE | 9922 | 10330 | 10330-B01 | 256 RIDGECREST RD | MARKHAM | L6C2R5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8979 | -79.3037 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1439748 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439748 | 1439748 | 1439748 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-036 | 16-036 | 16 | N/A | 66095 | York Region DSB | Cedarwood | Cedarwood Public Elementary School | ELE | 10152 | 10428 | 10428-B01 | 399 ELSON ST | MARKHAM | L3S4R8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8448 | -79.2447 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7225854 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7225854 | 7225854 | 7225854 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-039 | 16-039 | 16 | N/A | 66095 | York Region DSB | Charles Howitt | Charles Howitt Public Elementary School | ELE | 427 | 5581 | 5581-B01 | 30 PEARSON AVE | RICHMOND HILL | L4C6T7 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8439 | -79.4383 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 207 | - | - | N | - | Approved | 42773 | 4186795 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 931487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931487 | 0 | 0 | 0 | 0 | 3255308 | 0 | 0 | 0 | 0 | 0 | 3255308 | 4186795 | 4186795 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 3255308
16-041 | 16-041 | 16 | N/A | 66095 | York Region DSB | Charlton | Charlton Public Elementary School | ELE | 476 | 5607 | 5607-B01 | 121 JOSEPH AARON BLVD | THORNHILL | L4J6J5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7963 | -79.4641 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1060881 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060881 | 1060881 | 1060881 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-042 | 16-042 | 16 | N/A | 66095 | York Region DSB | Clearmeadow | Clearmeadow Public Elementary School | ELE | 9745 | 10244 | 10244-B01 | 200 CLEARMEADOW BLVD | NEWMARKET | L3X2E4 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0371 | -79.4879 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6888399 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6888399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6888399 | 6888399 | 6888399 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-043 | 16-043 | 16 | N/A | 66095 | York Region DSB | Clearmeadow | Clearmeadow Public Elementary School | ELE | 9745 | 10244 | 10244-B01 | 200 CLEARMEADOW BLVD | NEWMARKET | L3X2E4 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0371 | -79.4879 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1073363 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073363 | 1073363 | 1073363 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-045 | 16-045 | 16 | N/A | 66095 | York Region DSB | Coppard Glen | Coppard Glen Public Elementary School | ELE | 503 | 5631 | 5631-B01 | 131 COPPARD AVE | MARKHAM | L3S2T5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8456 | -79.2737 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1420455 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420455 | 1420455 | 1420455 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-046 | 16-046 | 16 | N/A | 66095 | York Region DSB | Bill Hogarth | Bill Hogarth Public Secondary School | SEC | 24346 | 19344 | 19344-B01 | 100 DONALD SIM AVE | MARKHAM | L6B0R4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8929 | -79.2304 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 1500 | - | - | N | - | Approved | 42296 | 35203463 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 3325502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3325502 | 0 | 0 | 0 | 0 | 29738092 | 0 | 0 | 0 | 0 | 0 | 29738092 | 33063594 | 33063594 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 29738092
16-047 | 16-047 | 16 | N/A | 66095 | York Region DSB | Cornell Village | Cornell Village Public Elementary School | ELE | 10169 | 10442 | 10442-B01 | 186 COUNTRY GLEN RD | MARKHAM | L6B1B5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8912 | -79.235 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6624614 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6624614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6624614 | 6624614 | 6624614 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-049 | 16-049 | 16 | N/A | 66095 | York Region DSB | Crosby Heights | Crosby Heights Public Elementary School | ELE | 537 | 5651 | 5651-B01 | 190 NEAL DR | RICHMOND HILL | L4C3K7 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8846 | -79.4255 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 942764 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942764 | 942764 | 942764 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-050 | 16-050 | 16 | N/A | 66095 | York Region DSB | David Suzuki | David Suzuki Public Elementary School | ELE | 11124 | 12184 | 12184-B01 | 45 RIVERWALK DR | MARKHAM | L6B0L9 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.856 | -79.2252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10091827 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 9091827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9091827 | 10091827 | 10091827 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-051 | 16-051 | 16 | N/A | 66095 | York Region DSB | David Suzuki | David Suzuki Public Elementary School | ELE | 11124 | 12184 | 12184-B01 | 45 RIVERWALK DR | MARKHAM | L6B0L9 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.856 | -79.2252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3236208 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3236208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3236208 | 3236208 | 3236208 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-052 | 16-052 | 16 | N/A | 66095 | York Region DSB | David Suzuki | David Suzuki Public Elementary School | ELE | 11124 | 12184 | 12184-B01 | 45 RIVERWALK DR | MARKHAM | L6B0L9 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.856 | -79.2252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1422483 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469856 | 0 | 952627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422483 | 1422483 | 1422483 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-054 | 16-054 | 16 | N/A | 66095 | York Region DSB | Discovery | Discovery Public Elementary School | ELE | 10093 | 10390 | 10390-B01 | 120 DISCOVERY TRAIL | MAPLE | L6A2Z2 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8583 | -79.5429 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7110817 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7110817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7110817 | 7110817 | 7110817 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-056 | 16-056 | 16 | N/A | 66095 | York Region DSB | Donald Cousens | Donald Cousens Public Elementary School | ELE | 11002 | 12138 | 12138-B01 | 315 MINGAY AVE | MARKHAM | L6E1T5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9046 | -79.2767 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9628377 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9628377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9628377 | 9628377 | 9628377 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-058 | 16-058 | 16 | N/A | 66095 | York Region DSB | Dr. John M Denison | Dr. John M Denison Public Secondary School | SEC | 5314 | 8184 | 8184-B01 | 135 BRISTOL RD | NEWMARKET | L3Y8J7 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.069 | -79.4771 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4882551 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4882551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4882551 | 4882551 | 4882551 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-059 | 16-059 | 16 | N/A | 66095 | York Region DSB | Dr. Roberta Bondar | Dr. Roberta Bondar Public Elementary School | ELE | 10793 | 11998 | 11998-B01 | 401 AV GRAND TRUNK | MAPLE | L6A0T4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8525 | -79.4894 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9067157 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9067157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9067157 | 9067157 | 9067157 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-060 | 16-060 | 16 | N/A | 66095 | York Region DSB | Dr. Roberta Bondar | Dr. Roberta Bondar Public Elementary School | ELE | 10793 | 11998 | 11998-B01 | 401 AV GRAND TRUNK | MAPLE | L6A0T4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8525 | -79.4894 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2405299 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 1427347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427347 | 0 | 0 | 977952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977952 | 2405299 | 2405299 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-061-01 | 16-061 | 16 | 234 - CMSM York | 66095 | York Region DSB | EJ Sand | EJ Sand Public Elementary School | ELE | 24718 | 6940 | 6940-B04 | 160 HENDERSON AVE | THORNHILL | L3T2L5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8118 | -79.4133 | 42317 | 2015-16 | 2015-16 | - | - | - | 44186 | 2020-21 | 2020-21 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 409 | 2 | 39 | N | - | Approved | 44537 | 19153400 | Under Construction | New Construction | Condition | 2023-24 | 45170 | 0 | 0 | 10122180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10122180 | 0 | 0 | 0 | 0 | 8042652 | 0 | 988568 | 0 | 0 | 0 | 9031220 | 19153400 | 19153400 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9031220
16-061-02 | 16-061 | 16 | N/A | 66095 | York Region DSB | EJ Sand | EJ Sand Public Elementary School | ELE | 2560 | 6940 | 6940-B02 | 160 HENDERSON AVE | THORNHILL | L3T2L5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8117 | -79.4126 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43185 | 728056 | Construction Complete | Demolition | Condition | 2018-19 | 43556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289785 | 0 | 0 | 0 | 0 | 0 | 289785 | 289785 | 289785 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 289785
16-061-03 | 16-061 | 16 | N/A | 66095 | York Region DSB | Woodland Building | Woodland Building | HFA | 2558 | 6939 | 6939-B03 | 150 HENDERSON AVE | THORNHILL | L3T2L5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8112 | -79.4112 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43185 | 728056 | Construction Complete | Demolition | Condition | 2018-19 | 43556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289785 | 0 | 0 | 0 | 0 | 0 | 289785 | 289785 | 289785 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 289785
16-061-04 | 16-061 | 16 | N/A | 66095 | York Region DSB | EJ Sand | EJ Sand Public Elementary School | ELE | 24718 | 6940 | 6940-L04 | 160 HENDERSON AVE | THORNHILL | L3T2L5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8118 | -79.4133 | 43705 | 2018-19 | 2019-20 | 43705 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43705 | 592624 | Construction Complete | Land Acquisition | Condition | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 100746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100746 | 0 | 0 | 0 | 491878 | 0 | 0 | 0 | 0 | 0 | 0 | 491878 | 592624 | 592624 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 491878
16-062 | 16-062 | 16 | N/A | 66095 | York Region DSB | Elder's Mills | Elder's Mills Public Elementary School | ELE | 10532 | 11153 | 11153-B01 | 120 NAPA VALLEY AVE | WOODBRIDGE | L4H1L1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8141 | -79.6202 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6926647 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6926647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6926647 | 6926647 | 6926647 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-063 | 16-063 | 16 | N/A | 66095 | York Region DSB | Ellen Fairclough | Ellen Fairclough Public Elementary School | ELE | 10677 | 11195 | 11195-B01 | 33 BRANDO AVE | MARKHAM | L3S4K9 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8485 | -79.2565 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7239410 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277788 | 277788 | 6961622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6961622 | 7239410 | 7239410 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-064 | 16-064 | 16 | N/A | 66095 | York Region DSB | Emily Carr | Emily Carr Public Secondary School | SEC | 10157 | 10433 | 10433-B01 | 4901 RUTHERFORD RD | WOODBRIDGE | L4H3C2 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8173 | -79.5935 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 20965413 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21443 | 21443 | 20943970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20943970 | 20965413 | 20965413 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-065 | 16-065 | 16 | N/A | 66095 | York Region DSB | Fairwood | Fairwood Public Elementary School | ELE | 9928 | 10356 | 10356-B01 | 201 FAIRWOOD DR | KESWICK | L4P3Y5 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.222 | -79.4492 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7218812 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7218812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7218812 | 7218812 | 7218812 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-067 | 16-067 | 16 | N/A | 66095 | York Region DSB | Forest Run | Forest Run Public Elementary School | ELE | 10099 | 10392 | 10392-B01 | 200 FOREST RUN BLVD | CONCORD | L4K5H3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.836 | -79.4859 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7521621 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7521621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7521621 | 7521621 | 7521621 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-069 | 16-069 | 16 | N/A | 66095 | York Region DSB | Fossil Hill | Fossil Hill Public Elementary School | ELE | 10156 | 10432 | 10432-B01 | 2 FIRENZA RD | WOODBRIDGE | L4H2P5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8368 | -79.5651 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7008792 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7008792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7008792 | 7008792 | 7008792 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-072 | 16-072 | 16 | N/A | 66095 | York Region DSB | Fred Varley | Fred Varley Public Elementary School | ELE | 24345 | 19343 | 19343-B01 | 81 ALEXANDER LAWRIE AVE | MARKHAM | L6E0J8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8912 | -79.2853 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Not Required | - | 10863190 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453777 | 0 | 9010283 | 0 | 0 | 0 | 0 | 0 | 10464060 | 10464060 | 10464060 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9010283
16-073 | 16-073 | 16 | N/A | 66095 | York Region DSB | Glad Park | Glad Park Public Elementary School | ELE | 6359 | 8691 | 8691-B01 | 300 GLAD PARK AVE | STOUFFVILLE | L4A1E5 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9742 | -79.2588 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1528462 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528462 | 1528462 | 1528462 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-074 | 16-074 | 16 | N/A | 66095 | York Region DSB | Glen Shields | Glen Shields Public Elementary School | ELE | 895 | 5878 | 5878-B01 | 158 GLEN SHIELDS AVE | CONCORD | L4K1T8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.792 | -79.4818 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1585353 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1585353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1585353 | 1585353 | 1585353 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-076 | 16-076 | 16 | N/A | 66095 | York Region DSB | Glenn Gould | Glenn Gould Public Elementary School | ELE | 11234 | 12236 | 12236-B01 | 675 VELLORE PARK AVE | WOODBRIDGE | L4H0G5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8605 | -79.5574 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9317692 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8421641 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317692 | 9317692 | 9317692 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-077 | 16-077 | 16 | N/A | 66095 | York Region DSB | Greensborough | Greensborough Public Elementary School | ELE | 10531 | 11152 | 11152-B01 | 80 ALFRED PATERSON DR | MARKHAM | L6E1J5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9014 | -79.2447 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6547418 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6547418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6547418 | 6547418 | 6547418 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-079 | 16-079 | 16 | N/A | 66095 | York Region DSB | Harry Bowes | Harry Bowes Public Elementary School | ELE | 10794 | 11999 | 11999-B01 | 90 GREENWOOD RD | STOUFFVILLE | L4A0N8 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9807 | -79.2424 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9490761 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9490761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9490761 | 9490761 | 9490761 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-081 | 16-081 | 16 | N/A | 66095 | York Region DSB | Hartman | Hartman Public Elementary School | ELE | 10792 | 11997 | 11997-B01 | 130 RIVER RIDGE BLVD | AURORA | L4G7T7 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.0111 | -79.4404 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9259655 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9259655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9259655 | 9259655 | 9259655 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-082 | 16-082 | 16 | N/A | 66095 | York Region DSB | Henderson Avenue | Henderson Avenue Public Elementary School | ELE | 9747 | 5214 | 5214-B01 | 66 HENDERSON AVE | THORNHILL | L3T2K7 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8051 | -79.4085 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5062905 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5062905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5062905 | 5062905 | 5062905 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-084 | 16-084 | 16 | N/A | 66095 | York Region DSB | Herbert H Carnegie | Herbert H Carnegie Public Elementary School | ELE | 11000 | 12136 | 12136-B01 | 575 VIA ROMANO BLVD | MAPLE | L6A0G1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8765 | -79.4771 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9704000 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9704000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9704000 | 9704000 | 9704000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-085 | 16-085 | 16 | N/A | 66095 | York Region DSB | Herbert H Carnegie | Herbert H Carnegie Public Elementary School | ELE | 11000 | 12136 | 12136-B01 | 575 VIA ROMANO BLVD | MAPLE | L6A0G1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8765 | -79.4771 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1710697 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765243 | 0 | 945454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710697 | 1710697 | 1710697 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-086 | 16-086 | 16 | N/A | 66095 | York Region DSB | Highgate | Highgate Public Elementary School | ELE | 1070 | 5994 | 5994-B01 | 35 HIGHGATE DR | MARKHAM | L3R3R5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8269 | -79.315 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1431685 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1431685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1431685 | 1431685 | 1431685 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-088 | 16-088 | 16 | N/A | 66095 | York Region DSB | Holland Landing | Holland Landing Public Elementary School | ELE | 981 | 5937 | 5937-B01 | 16 HOLLAND RIVER BLVD | HOLLAND LANDING | L9N1C4 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.096 | -79.4777 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1332522 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332522 | 1332522 | 1332522 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-089 | 16-089 | 16 | N/A | 66095 | York Region DSB | Jersey | Jersey Public Elementary School | ELE | 10756 | 11971 | 11971-B01 | 176 GLENWOODS AVE | KESWICK | L4P3E9 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.2143 | -79.4576 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8188498 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8188498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8188498 | 8188498 | 8188498 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-090 | 16-090 | 16 | N/A | 66095 | York Region DSB | John McCrae | John McCrae Public Elementary School | ELE | 10675 | 11197 | 11197-B01 | 565 FRED MCLAREN BLVD | MARKHAM | L6E1N7 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9019 | -79.2874 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7310820 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113506 | 113506 | 7197314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7197314 | 7310820 | 7310820 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-091 | 16-091 | 16 | N/A | 66095 | York Region DSB | Johnny Lombardi | Johnny Lombardi Public Elementary School | ELE | 24387 | 19388 | 19388-B01 | 350 LAWFORD RD | WOODBRIDGE | L4H4C3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8519 | -79.5705 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Approved | 42135 | 11034530 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969184 | 0 | 9830247 | 0 | 0 | 0 | 0 | 0 | 10799431 | 10799431 | 10799431 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9830247
16-092 | 16-092 | 16 | N/A | 66095 | York Region DSB | Julliard | Julliard Public Elementary School | ELE | 10534 | 11155 | 11155-B01 | 61 JULLIARD DR | MAPLE | L6A3W7 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8322 | -79.5356 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6946712 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60709 | 60709 | 6886003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6886003 | 6946712 | 6946712 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-093 | 16-093 | 16 | N/A | 66095 | York Region DSB | Julliard | Julliard Public Elementary School | ELE | 10534 | 11155 | 11155-B01 | 61 JULLIARD DR | MAPLE | L6A3W7 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8322 | -79.5356 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 678075 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678075 | 678075 | 678075 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-094 | 16-094 | 16 | N/A | 66095 | York Region DSB | Julliard | Julliard Public Elementary School | ELE | 10534 | 11155 | 11155-B01 | 61 JULLIARD DR | MAPLE | L6A3W7 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8322 | -79.5356 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1006088 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006088 | 1006088 | 1006088 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-095 | 16-095 | 16 | N/A | 66095 | York Region DSB | Keswick | Keswick Public Secondary School | SEC | 9750 | 6560 | 6560-B02 | 100 BISCAYNE BLVD | KESWICK | L4P3S2 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.2228 | -79.4579 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 22863598 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 52000 | 22811598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22811598 | 22863598 | 22863598 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-096 | 16-096 | 16 | N/A | 66095 | York Region DSB | Kettle Lakes | Kettle Lakes Public Elementary School | ELE | 11123 | 12178 | 12178-B01 | 62 KINGSHILL RD | RICHMOND HILL | L4E4X5 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.936 | -79.4728 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10244377 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 9244377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9244377 | 10244377 | 10244377 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-097 | 16-097 | 16 | N/A | 66095 | York Region DSB | King City | King City Public Secondary School | SEC | 5458 | 8266 | 8266-B01 | 2001 KING RD | KING CITY | L7B1K2 | 35-11-27-603 | King | King Tp | York R | YORK | GTA | South | 43.9302 | -79.5174 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3487604 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304362 | 304362 | 3183242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3183242 | 3487604 | 3487604 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-098 | 16-098 | 16 | N/A | 66095 | York Region DSB | King City | King City Public Elementary School | ELE | 11163 | 6117 | 6117-B02 | 25 KING BLVD | KING CITY | L7B1K9 | 35-11-27-603 | King | King Tp | York R | YORK | GTA | South | 43.9322 | -79.5185 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8682558 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8682558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8682558 | 8682558 | 8682558 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-099 | 16-099 | 16 | N/A | 66095 | York Region DSB | Kleinburg | Kleinburg Public Elementary School | ELE | 11235 | 6129 | 6129-B02 | 10391 ISLINGTON AVE | KLEINBURG | L0J1C0 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8415 | -79.6252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10860512 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 9860512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9860512 | 10860512 | 10860512 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-100 | 16-100 | 16 | N/A | 66095 | York Region DSB | Kleinburg | Kleinburg Public Elementary School | ELE | 11235 | 6129 | 6129-B02 | 10391 ISLINGTON AVE | KLEINBURG | L0J1C0 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8415 | -79.6252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1457925 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 991978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991978 | 0 | 0 | 465947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465947 | 1457925 | 1457925 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-101 | 16-101 | 16 | N/A | 66095 | York Region DSB | Lake Simcoe | Lake Simcoe Public Elementary School | ELE | 9743 | 10242 | 10242-B01 | 38 THORNLODGE DR | KESWICK | L4P4A3 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.1974 | -79.4578 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5990379 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990379 | 5990379 | 5990379 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-103 | 16-103 | 16 | N/A | 66095 | York Region DSB | Lake Wilcox | Lake Wilcox Public Elementary School | ELE | 9749 | 5110 | 5110-B01 | 80 WILDWOOD AVE | RICHMOND HILL | L4E3B5 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9539 | -79.4372 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7194662 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11051 | 11051 | 7183611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7183611 | 7194662 | 7194662 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-104 | 16-104 | 16 | N/A | 66095 | York Region DSB | Langstaff | Langstaff Public Secondary School | SEC | 5474 | 8275 | 8275-B01 | 106 GARDEN AVE | RICHMOND HILL | L4C6M1 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8386 | -79.4399 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 18441808 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1321845 | 1321845 | 17119963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17119963 | 18441808 | 18441808 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-105 | 16-105 | 16 | N/A | 66095 | York Region DSB | Legacy | Legacy Public Elementary School | ELE | 10754 | 11969 | 11969-B01 | 61 RUSSELL JARVIS DR | MARKHAM | L3S4B1 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8647 | -79.2338 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8498322 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8498322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8498322 | 8498322 | 8498322 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-106 | 16-106 | 16 | N/A | 66095 | York Region DSB | Lester B Pearson | Lester B Pearson Public Elementary School | ELE | 1330 | 6149 | 6149-B01 | 15 ODIN CRES | AURORA | L4G3T3 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.007 | -79.465 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2642266 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2642266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2642266 | 2642266 | 2642266 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-107 | 16-107 | 16 | N/A | 66095 | York Region DSB | Lincoln Alexander | Lincoln Alexander Public Elementary School | ELE | 10530 | 11151 | 11151-B01 | 38 HILLMOUNT RD | MARKHAM | L6C2H4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.877 | -79.3684 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8197772 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8197772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8197772 | 8197772 | 8197772 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-108 | 16-108 | 16 | N/A | 66095 | York Region DSB | Little Rouge | Little Rouge Public Elementary School | ELE | 10790 | 11995 | 11995-B01 | 571 COUNTRY GLEN RD | MARKHAM | L6B1E8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9017 | -79.2351 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8501584 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8501584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8501584 | 8501584 | 8501584 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-110 | 16-110 | 16 | N/A | 66095 | York Region DSB | Lorna Jackson | Lorna Jackson Public Elementary School | ELE | 10100 | 10393 | 10393-B01 | 589 NAPA VALLEY AVE | WOODBRIDGE | L4H1R1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8225 | -79.6207 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7763319 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763319 | 7763319 | 7763319 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-111 | 16-111 | 16 | N/A | 66095 | York Region DSB | Louis-Honoré Fréchette | Louis-Honoré Fréchette Public Elementary School | ELE | 1397 | 6191 | 6191-B01 | 40 NEW WESTMINSTER DR | THORNHILL | L4J7Z8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7912 | -79.4587 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 604000 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604000 | 604000 | 604000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-112 | 16-112 | 16 | N/A | 66095 | York Region DSB | Mackenzie Glen | Mackenzie Glen Public Elementary School | ELE | 10171 | 10444 | 10444-B01 | 575 MELVILLE AVE | MAPLE | L6A2M4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8648 | -79.5308 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6922868 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6922868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6922868 | 6922868 | 6922868 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-114 | 16-114 | 16 | N/A | 66095 | York Region DSB | MacLeod’s Landing | MacLeod’s Landing Public Elementary School | ELE | 10753 | 11968 | 11968-B01 | 195 SILVER MAPLE RD | RICHMOND HILL | L4E4Z1 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9243 | -79.4552 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8259674 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8259674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8259674 | 8259674 | 8259674 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-116 | 16-116 | 16 | N/A | 66095 | York Region DSB | Maple | Maple Public Secondary School | SEC | 9929 | 10333 | 10333-B01 | 50 SPRINGSIDE RD | MAPLE | L6A2W5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8394 | -79.5306 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 25324402 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25324402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25324402 | 25324402 | 25324402 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-117 | 16-117 | 16 | N/A | 66095 | York Region DSB | Maple Creek | Maple Creek Public Elementary School | ELE | 10172 | 10445 | 10445-B01 | 210 HAWKER RD | MAPLE | L6A2J8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.843 | -79.5258 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7935453 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7935453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7935453 | 7935453 | 7935453 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-119 | 16-119 | 16 | N/A | 66095 | York Region DSB | Markham District | Markham District Public Secondary School | SEC | 11161 | 8295 | 8295-B02 | 89 CHURCH ST | MARKHAM | L3P2M3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8804 | -79.2508 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 32748054 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32748054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32748054 | 32748054 | 32748054 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-120 | 16-120 | 16 | N/A | 66095 | York Region DSB | Markham Gateway | Markham Gateway Public Elementary School | ELE | 9923 | 10331 | 10331-B01 | 30 FONDA RD | MARKHAM | L3S3X3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8449 | -79.2591 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6669878 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6669878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6669878 | 6669878 | 6669878 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-122 | 16-122 | 16 | N/A | 66095 | York Region DSB | Michael Cranny | Michael Cranny Public Elementary School | ELE | 9741 | 10240 | 10240-B01 | 155 MELVILLE AVE | MAPLE | L6A1Y9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8552 | -79.5332 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7446855 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252645 | 252645 | 7194210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7194210 | 7446855 | 7446855 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-123 | 16-123 | 16 | N/A | 66095 | York Region DSB | Michaëlle Jean | Michaëlle Jean Public Elementary School | ELE | 10788 | 11993 | 11993-B01 | 320 SHIRLEY DR | RICHMOND HILL | L4S2P1 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8911 | -79.4124 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8316644 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8316644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8316644 | 8316644 | 8316644 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-124 | 16-124 | 16 | N/A | 66095 | York Region DSB | Michaëlle Jean | Michaëlle Jean Public Elementary School | ELE | 10788 | 11993 | 11993-B01 | 320 SHIRLEY DR | RICHMOND HILL | L4S2P1 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8911 | -79.4124 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 204000 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000 | 204000 | 204000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-125 | 16-125 | 16 | N/A | 66095 | York Region DSB | Middlefield | Middlefield Public Secondary School | SEC | 5521 | 8304 | 8304-B01 | 525 HIGHGLEN AVE | MARKHAM | L3S3L5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8474 | -79.2678 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3613538 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3613538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3613538 | 3613538 | 3613538 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-126 | 16-126 | 16 | N/A | 66095 | York Region DSB | Middlefield | Middlefield Public Secondary School | SEC | 5521 | 8304 | 8304-B01 | 525 HIGHGLEN AVE | MARKHAM | L3S3L5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8474 | -79.2678 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3520000 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3520000 | 3520000 | 3520000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-127 | 16-127 | 16 | N/A | 66095 | York Region DSB | Milliken Mills | Milliken Mills Public Elementary School | ELE | 1544 | 6293 | 6293-B01 | 289 RISEBROUGH CIRCT | MARKHAM | L3R3J3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8265 | -79.3178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2380096 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96896 | 96896 | 2283200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283200 | 2380096 | 2380096 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-128 | 16-128 | 16 | N/A | 66095 | York Region DSB | Milliken Mills | Milliken Mills Public Secondary School | SEC | 5525 | 8306 | 8306-B01 | 7522 KENNEDY RD | MARKHAM | L3R9S5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8377 | -79.3052 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4297093 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425093 | 425093 | 3872000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3872000 | 4297093 | 4297093 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-129 | 16-129 | 16 | N/A | 66095 | York Region DSB | Moraine Hills | Moraine Hills Public Elementary School | ELE | 10752 | 11967 | 11967-B01 | 85 ROLLINGHILL RD | RICHMOND HILL | L4E4C7 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9103 | -79.4556 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8274127 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8274127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8274127 | 8274127 | 8274127 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-131 | 16-131 | 16 | N/A | 66095 | York Region DSB | Morning Glory | Morning Glory Public Elementary School | ELE | 1565 | 6305 | 6305-B01 | 29478 HIGHWAY 48 | PEFFERLAW | L0E1N0 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.3252 | -79.241 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4642173 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4642173 | 4642173 | 4642173 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-132 | 16-132 | 16 | N/A | 66095 | York Region DSB | Mount Albert | Mount Albert Public Elementary School | ELE | 1572 | 6310 | 6310-B01 | 5488 MOUNT ALBERT RD | MOUNT ALBERT | L0G1M0 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.1325 | -79.3114 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3101428 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3101428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3101428 | 3101428 | 3101428 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-133 | 16-133 | 16 | N/A | 66095 | York Region DSB | Mount Joy | Mount Joy Public Elementary School | ELE | 10755 | 11970 | 11970-B01 | 281 WILLIAMSON RD | MARKHAM | L6E1X1 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9026 | -79.2585 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7832610 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7832610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7832610 | 7832610 | 7832610 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-135 | 16-135 | 16 | N/A | 66095 | York Region DSB | Nellie McClung | Nellie McClung Public Elementary School | ELE | 11225 | 12269 | 12269-B01 | 360 AV THOMAS COOK | MAPLE | L6A4M1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.855 | -79.471 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9274401 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8378350 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9274401 | 9274401 | 9274401 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-137 | 16-137 | 16 | N/A | 66095 | York Region DSB | Northern Lights | Northern Lights Public Elementary School | ELE | 10149 | 10425 | 10425-B01 | 40 BRIDGENORTH DR | AURORA | L4G7S6 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.0156 | -79.4539 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7114047 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 7064047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7064047 | 7114047 | 7114047 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-139 | 16-139 | 16 | N/A | 66095 | York Region DSB | Oak Ridges | Oak Ridges Public Elementary School | ELE | 9748 | 10246 | 10246-B01 | 160 COON'S RD | RICHMOND HILL | L4E2P7 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9519 | -79.4689 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6934334 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6934334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6934334 | 6934334 | 6934334 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-140 | 16-140 | 16 | N/A | 66095 | York Region DSB | Oscar Peterson | Oscar Peterson Public Elementary School | ELE | 11001 | 12137 | 12137-B01 | 850 HOOVER PARK DR | STOUFFVILLE | L4A0E7 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9597 | -79.2648 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9053284 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9053284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9053284 | 9053284 | 9053284 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-142 | 16-142 | 16 | N/A | 66095 | York Region DSB | Parkland | Parkland Public Elementary School | ELE | 1747 | 6420 | 6420-B01 | 18 COXWORTH AVE | MARKHAM | L3S3B8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8399 | -79.2594 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2672000 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2672000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2672000 | 2672000 | 2672000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-144 | 16-144 | 16 | N/A | 66095 | York Region DSB | Phoebe Gilman | Phoebe Gilman Public Elementary School | ELE | 20280 | 19130 | 19130-B01 | 145 HARVEST HILLS BLVD | EAST GWILLIMBURY | L9N0C1 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.0677 | -79.4962 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 567 | - | - | N | - | Not Required | - | 10517911 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795735 | 0 | 9722176 | 0 | 0 | 0 | 0 | 0 | 10517911 | 10517911 | 10517911 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9722176
16-145 | 16-145 | 16 | N/A | 66095 | York Region DSB | Pierre Berton | Pierre Berton Public Elementary School | ELE | 11226 | 12270 | 12270-B01 | 470 VIA CAMPANILE | WOODBRIDGE | L4H0X9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8352 | -79.5775 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9324305 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8428254 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9324305 | 9324305 | 9324305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-146 | 16-146 | 16 | N/A | 66095 | York Region DSB | Pierre Elliott Trudeau | Pierre Elliott Trudeau Public Secondary School | SEC | 10098 | 10391 | 10391-B01 | 90 BUR OAK AVE | MARKHAM | L6C2E6 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8898 | -79.3131 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 22272495 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50350 | 50350 | 22222145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22222145 | 22272495 | 22272495 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-147 | 16-147 | 16 | N/A | 66095 | York Region DSB | Pierre Elliott Trudeau | Pierre Elliott Trudeau Public Secondary School | SEC | 10098 | 10391 | 10391-B01 | 90 BUR OAK AVE | MARKHAM | L6C2E6 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8898 | -79.3131 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5508594 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 5508594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5508594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5508594 | 5508594 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-148 | 16-148 | 16 | N/A | 66095 | York Region DSB | Pine Grove | Pine Grove Public Elementary School | ELE | 1810 | 6458 | 6458-B01 | 86 GAMBLE ST | WOODBRIDGE | L4L1R2 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7978 | -79.5879 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 720000 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 720000 | 720000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-149 | 16-149 | 16 | N/A | 66095 | York Region DSB | Pleasantville | Pleasantville Public Elementary School | ELE | 1832 | 6472 | 6472-B01 | 400 MILL ST | RICHMOND HILL | L4C4B9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8744 | -79.4573 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4068033 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96212 | 96212 | 3971821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3971821 | 4068033 | 4068033 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-150 | 16-150 | 16 | N/A | 66095 | York Region DSB | Poplar Bank | Poplar Bank Public Elementary School | ELE | 10153 | 10429 | 10429-B01 | 400 WOODSPRING AVE | NEWMARKET | L3X2X1 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0627 | -79.4918 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6851304 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6851304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6851304 | 6851304 | 6851304 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-151 | 16-151 | 16 | N/A | 66095 | York Region DSB | Randall | Randall Public Elementary School | ELE | 2065 | 6632 | 6632-B01 | 50 RANDALL AVE | MARKHAM | L3S1E2 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8415 | -79.2867 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3360320 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3360320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3360320 | 3360320 | 3360320 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-154 | 16-154 | 16 | N/A | 66095 | York Region DSB | Red Maple | Red Maple Public Elementary School | ELE | 10090 | 10387 | 10387-B01 | 155 RED MAPLE RD | RICHMOND HILL | L4B4P9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8451 | -79.4241 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7660364 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129531 | 129531 | 7530833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7530833 | 7660364 | 7660364 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-155 | 16-155 | 16 | N/A | 66095 | York Region DSB | Red Maple | Red Maple Public Elementary School | ELE | 10090 | 10387 | 10387-B01 | 155 RED MAPLE RD | RICHMOND HILL | L4B4P9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8451 | -79.4241 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1504269 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 572375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572375 | 0 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 1504269 | 1504269 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-156 | 16-156 | 16 | N/A | 66095 | York Region DSB | Redstone | Redstone Public Elementary School | ELE | 10676 | 11193 | 11193-B01 | 235 REDSTONE RD | RICHMOND HILL | L4S2E2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8901 | -79.3991 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7330491 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348588 | 348588 | 6981903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6981903 | 7330491 | 7330491 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-157 | 16-157 | 16 | N/A | 66095 | York Region DSB | Richmond Green | Richmond Green Public Secondary School | SEC | 10158 | 10434 | 10434-B01 | 1 WILLIAM F BELL PKY | RICHMOND HILL | L4S2T9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9033 | -79.3978 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 22879623 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22879623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22879623 | 22879623 | 22879623 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-158 | 16-158 | 16 | N/A | 66095 | York Region DSB | Richmond Hill | Richmond Hill Public Secondary School | SEC | 9752 | 10249 | 10249-B01 | 201 YORKLAND ST | RICHMOND HILL | L4S1A2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9028 | -79.4397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17355346 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 52000 | 17303346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17303346 | 17355346 | 17355346 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-159 | 16-159 | 16 | N/A | 66095 | York Region DSB | Richmond Rose | Richmond Rose Public Elementary School | ELE | 9739 | 10238 | 10238-B01 | 160 FRANK ENDEAN RD | RICHMOND HILL | L4S1S7 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8843 | -79.4127 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6832415 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6832415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6832415 | 6832415 | 6832415 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-160 | 16-160 | 16 | N/A | 66095 | York Region DSB | Rick Hansen | Rick Hansen Public Elementary School | ELE | 14834 | 18043 | 18043-B01 | 490 MAVRINAC BLVD | AURORA | L4G0J6 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.021 | -79.4416 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10288205 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9392154 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10288205 | 10288205 | 10288205 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-161-01 | 16-161 | 16 | N/A | 66095 | York Region DSB | Robert Munsch | Robert Munsch Public Elementary School | ELE | 24233 | 19225 | 19225-B01 | 395 KING ST E | MOUNT ALBERT | L0G1M0 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.1406 | -79.3037 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 488 | - | - | N | - | Not Required | - | 9344252 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 1388677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388677 | 0 | 0 | 1863788 | 0 | 6091787 | 0 | 0 | 0 | 0 | 0 | 7955575 | 9344252 | 9344252 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6091787
16-161-02 | 16-161 | 16 | N/A | 66095 | York Region DSB | Robert Munsch | Robert Munsch Public Elementary School | ELE | 24233 | 19225 | 19225-L01 | 395 KING ST E | MOUNT ALBERT | L0G1M0 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.1406 | -79.3037 | 41122 | 2011-12 | 2012-13 | 41122 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41122 | 1739485 | Construction Complete | Land Acquisition | Accommodation Pressure | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1739485 | 0 | 0 | 0 | 0 | 0 | 0 | 1739485 | 1739485 | 1739485 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1739485
16-162 | 16-162 | 16 | N/A | 66095 | York Region DSB | Rogers | Rogers Public Elementary School | ELE | 10757 | 6604 | 6604-B01 | 256 ROGERS RD | NEWMARKET | L3Y1G6 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0458 | -79.4659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7515986 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7515986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7515986 | 7515986 | 7515986 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-163 | 16-163 | 16 | N/A | 66095 | York Region DSB | Roméo Dallaire | Roméo Dallaire Public Elementary School | ELE | 24235 | 19227 | 19227-B01 | 550 PETER RUPERT AVE | MAPLE | L6A0S1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8554 | -79.4984 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Not Required | - | 11156721 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 0 | 9878318 | 0 | 0 | 0 | 0 | 0 | 10810212 | 10810212 | 10810212 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9878318
16-164 | 16-164 | 16 | N/A | 66095 | York Region DSB | Ross Doan | Ross Doan Public Elementary School | ELE | 2046 | 6622 | 6622-B01 | 101 WELDRICK RD W | RICHMOND HILL | L4C3T9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.858 | -79.4438 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3807492 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46117 | 46117 | 3761375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3761375 | 3807492 | 3807492 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-165 | 16-165 | 16 | N/A | 66095 | York Region DSB | Sam Chapman | Sam Chapman Public Elementary School | ELE | 11231 | 12232 | 12232-B01 | 270 ALFRED PATERSON DR | MARKHAM | L6E2G1 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9092 | -79.252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8930445 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8930445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8930445 | 8930445 | 8930445 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-167 | 16-167 | 16 | N/A | 66095 | York Region DSB | Sharon | Sharon Public Elementary School | ELE | 984 | 5940 | 5940-B01 | 18532 LESLIE ST | SHARON | L0G1V0 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.0909 | -79.4389 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1450488 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450488 | 1450488 | 1450488 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-168 | 16-168 | 16 | N/A | 66095 | York Region DSB | Silver Stream | Silver Stream Public Elementary School | ELE | 10091 | 10388 | 10388-B01 | 180 FARMSTEAD RD | RICHMOND HILL | L4S2K9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8819 | -79.4029 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7190155 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7190155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7190155 | 7190155 | 7190155 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-169 | 16-169 | 16 | N/A | 66095 | York Region DSB | Sir John A Macdonald | Sir John A Macdonald Public Elementary School | ELE | 14832 | 18041 | 18041-B01 | 45 MURISON DR | MARKHAM | L6C0J4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8906 | -79.3722 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9480113 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8584062 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9480113 | 9480113 | 9480113 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-170 | 16-170 | 16 | N/A | 66095 | York Region DSB | Sir Wilfrid Laurier | Sir Wilfrid Laurier Public Elementary School | ELE | 10789 | 11994 | 11994-B01 | 160 HAZELTON AVE | MARKHAM | L6C3H6 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8963 | -79.3682 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8186405 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8186405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8186405 | 8186405 | 8186405 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-171 | 16-171 | 16 | N/A | 66095 | York Region DSB | Sir Wilfrid Laurier | Sir Wilfrid Laurier Public Elementary School | ELE | 10789 | 11994 | 11994-B01 | 160 HAZELTON AVE | MARKHAM | L6C3H6 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8963 | -79.3682 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1779472 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 1779472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1779472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1779472 | 1779472 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-172 | 16-172 | 16 | N/A | 66095 | York Region DSB | Sir William Mulock | Sir William Mulock Public Secondary School | SEC | 9751 | 10248 | 10248-B01 | 705 COLUMBUS WAY | NEWMARKET | L3X2M7 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0322 | -79.4798 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24171984 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566271 | 566271 | 23605713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23605713 | 24171984 | 24171984 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-173 | 16-173 | 16 | N/A | 66095 | York Region DSB | Stephen Lewis | Stephen Lewis Public Secondary School | SEC | 10680 | 11198 | 11198-B01 | 555 AUTUMN HILL BLVD | THORNHILL | L4J8X2 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.836 | -79.4751 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24204661 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24204661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24204661 | 24204661 | 24204661 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-174 | 16-174 | 16 | N/A | 66095 | York Region DSB | Stonebridge | Stonebridge Public Elementary School | ELE | 10162 | 10437 | 10437-B01 | 168 STONEBRIDGE DR | MARKHAM | L6C2Z8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8908 | -79.2962 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7179090 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7179090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7179090 | 7179090 | 7179090 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-175 | 16-175 | 16 | N/A | 66095 | York Region DSB | Stonebridge | Stonebridge Public Elementary School | ELE | 10162 | 10437 | 10437-B01 | 168 STONEBRIDGE DR | MARKHAM | L6C2Z8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8908 | -79.2962 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 616867 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616867 | 616867 | 616867 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-177 | 16-177 | 16 | N/A | 66095 | York Region DSB | Stouffville District | Stouffville District Public Secondary School | SEC | 10758 | 11973 | 11973-B01 | 801 HOOVER PARK DR | STOUFFVILLE | L4A0A4 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9623 | -79.26 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 26747282 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26747282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26747282 | 26747282 | 26747282 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-178 | 16-178 | 16 | N/A | 66095 | York Region DSB | Barbara Reid | Barbara Reid Public Elementary School | ELE | 24504 | 19509 | 19509-B01 | 130 HOOVER PARK DR | STOUFFVILLE | L4A1S5 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9687 | -79.2252 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Approved | 44679 | 11144865 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482853 | 0 | 9662016 | 0 | 0 | 0 | 0 | 0 | 11144869 | 11144869 | 11144869 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9662016
16-179 | 16-179 | 16 | N/A | 66095 | York Region DSB | Sutton | Sutton Public Elementary School | ELE | 11521 | 5071 | 5071-B03 | 5147 BASELINE RD | SUTTON WEST | L0E1R0 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.3021 | -79.3676 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9381962 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 4500000 | 4881962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4881962 | 9381962 | 9381962 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-180 | 16-180 | 16 | N/A | 66095 | York Region DSB | Terry Fox | Terry Fox Public Elementary School | ELE | 10678 | 11196 | 11196-B01 | 161 SAWMILL VALLEY DR | NEWMARKET | L3X2T1 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.031 | -79.485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7418948 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372627 | 372627 | 7046321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7046321 | 7418948 | 7418948 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-181 | 16-181 | 16 | N/A | 66095 | York Region DSB | Teston Village | Teston Village Public Elementary School | ELE | 10795 | 12000 | 12000-B01 | 80 MURRAY FARM LANE | MAPLE | L6A3G1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8627 | -79.5464 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8250687 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250687 | 8250687 | 8250687 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-183 | 16-183 | 16 | N/A | 66095 | York Region DSB | Thornhill Woods | Thornhill Woods Public Elementary School | ELE | 10679 | 11194 | 11194-B01 | 341 THORNHILL WOODS DR | THORNHILL | L4J8V6 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.835 | -79.4671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7549523 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7549523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7549523 | 7549523 | 7549523 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-184 | 16-184 | 16 | N/A | 66095 | York Region DSB | Thornhill Woods | Thornhill Woods Public Elementary School | ELE | 10679 | 11194 | 11194-B01 | 341 THORNHILL WOODS DR | THORNHILL | L4J8V6 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.835 | -79.4671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 673000 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 673000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 673000 | 673000 | 673000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-186 | 16-186 | 16 | N/A | 66095 | York Region DSB | Thornlea | Thornlea Public Secondary School | SEC | 5704 | 8401 | 8401-B01 | 8075 BAYVIEW AVE | THORNHILL | L3T4N4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8295 | -79.4029 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3271094 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3271094 | 3271094 | 3271094 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-187 | 16-187 | 16 | N/A | 66095 | York Region DSB | Tommy Douglas | Tommy Douglas Public Secondary School | SEC | 16462 | 17109 | 17109-B01 | 4020 MAJOR MACKENZIE DR | WOODBRIDGE | L4H4E9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8445 | -79.5675 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 32501634 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 2666503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2666503 | 29371588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29371588 | 32038091 | 32038091 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-188 | 16-188 | 16 | N/A | 66095 | York Region DSB | Trillium Woods | Trillium Woods Public Elementary School | ELE | 10154 | 10430 | 10430-B01 | 18 ALAMO HEIGHTS DR | RICHMOND HILL | L4S2P3 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9028 | -79.4572 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7004070 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7004070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7004070 | 7004070 | 7004070 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-190 | 16-190 | 16 | N/A | 66095 | York Region DSB | Unionville | Unionville Public Secondary School | SEC | 5717 | 8410 | 8410-B01 | 201 TOWN CENTRE BLVD | MARKHAM | L3R8G5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8586 | -79.3367 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5260849 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5260849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5260849 | 5260849 | 5260849 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-192 | 16-192 | 16 | N/A | 66095 | York Region DSB | Unionville Meadows | Unionville Meadows Public Elementary School | ELE | 10529 | 11150 | 11150-B01 | 355 SOUTH UNIONVILLE AVE | UNIONVILLE | L3R5C8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8565 | -79.2939 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6702379 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6702379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6702379 | 6702379 | 6702379 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-193 | 16-193 | 16 | N/A | 66095 | York Region DSB | Unionville Meadows | Unionville Meadows Public Elementary School | ELE | 10529 | 11150 | 11150-B01 | 355 SOUTH UNIONVILLE AVE | UNIONVILLE | L3R5C8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8565 | -79.2939 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 115 | - | - | N | - | Not Required | - | 2131033 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896051 | 0 | 1234982 | 0 | 0 | 0 | 0 | 0 | 2131033 | 2131033 | 2131033 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1234982
16-194 | 16-194 | 16 | N/A | 66095 | York Region DSB | Vellore Woods | Vellore Woods Public Elementary School | ELE | 10170 | 10443 | 10443-B01 | 115 STARLING BLVD | WOODBRIDGE | L4H2T9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8381 | -79.5561 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7417660 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7417660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7417660 | 7417660 | 7417660 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-195 | 16-195 | 16 | N/A | 66095 | York Region DSB | Ventura Park | Ventura Park Public Elementary School | ELE | 9740 | 10239 | 10239-B01 | 121 WORTH BLVD | THORNHILL | L4J7V5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8166 | -79.4646 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6919821 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6919821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6919821 | 6919821 | 6919821 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-198 | 16-198 | 16 | N/A | 66095 | York Region DSB | Wendat Village | Wendat Village Public Elementary School | ELE | 14833 | 18042 | 18042-B01 | 99 REEVES WAY BLVD | STOUFFVILLE | L4A0J8 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9632 | -79.2422 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10119906 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9223855 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10119906 | 10119906 | 10119906 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-199 | 16-199 | 16 | N/A | 66095 | York Region DSB | Whitchurch Highlands | Whitchurch Highlands Public Elementary School | ELE | 11296 | 6898 | 6898-B02 | 13812 WARDEN AVE | STOUFFVILLE | L4A4L5 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9857 | -79.3627 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8603147 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 4500000 | 4103147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4103147 | 8603147 | 8603147 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-200 | 16-200 | 16 | N/A | 66095 | York Region DSB | Wilclay | Wilclay Public Elementary School | ELE | 2510 | 6907 | 6907-B01 | 60 WILCLAY AVE | MARKHAM | L3S1R4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8327 | -79.2824 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5044871 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5044871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5044871 | 5044871 | 5044871 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-202 | 16-202 | 16 | N/A | 66095 | York Region DSB | William Berczy | William Berczy Public Elementary School | ELE | 1465 | 6239 | 6239-B01 | 120 CARLTON RD | UNIONVILLE | L3R1Z9 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8717 | -79.3257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2169273 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169273 | 2169273 | 2169273 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-203 | 16-203 | 16 | N/A | 66095 | York Region DSB | Windham Ridge | Windham Ridge Public Elementary School | ELE | 10533 | 11154 | 11154-B01 | 32 RED CARDINAL TRAIL | RICHMOND HILL | L4E3Y4 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.953 | -79.4735 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8108299 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8108299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8108299 | 8108299 | 8108299 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-204 | 16-204 | 16 | N/A | 66095 | York Region DSB | Wismer | Wismer Public Elementary School | ELE | 10151 | 10427 | 10427-B01 | 171 MINGAY AVE | MARKHAM | L6E1H8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8984 | -79.2746 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7230058 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230058 | 7230058 | 7230058 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-205 | 16-205 | 16 | N/A | 66095 | York Region DSB | Wismer | Wismer Public Elementary School | ELE | 10151 | 10427 | 10427-B01 | 171 MINGAY AVE | MARKHAM | L6E1H8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8984 | -79.2746 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 370219 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370219 | 370219 | 370219 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-207 | 16-207 | 16 | N/A | 66095 | York Region DSB | Woodbridge | Woodbridge Public Elementary School | ELE | 10742 | 11960 | 11960-B01 | 60 BURWICK AVE | WOODBRIDGE | L4L1J7 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7806 | -79.5956 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8166759 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418215 | 418215 | 7748544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7748544 | 8166759 | 8166759 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-209 | 16-209 | 16 | N/A | 66095 | York Region DSB | Woodbridge | Woodbridge Public Secondary School | SEC | 5767 | 5072 | 5072-B01 | 71 BRUCE ST | WOODBRIDGE | L4L1J3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7799 | -79.5828 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12678982 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419446 | 419446 | 12259536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12259536 | 12678982 | 12678982 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-210 | 16-210 | 16 | N/A | 66095 | York Region DSB | Woodland | Woodland Public Elementary School | ELE | 11162 | 12179 | 12179-B01 | 120 ROYAL ORCHARD BLVD | THORNHILL | L3T3C9 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.825 | -79.4135 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8452786 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8452786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8452786 | 8452786 | 8452786 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-211 | 16-211 | 16 | N/A | 66095 | York Region DSB | Victoria Square | Victoria Square Public Elementary School | ELE | 24576 | 19582 | 19582-B01 | 50 PRINCE OF WALES DR | MARKHAM | L6C0K2 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9067 | -79.3759 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Approved | 44679 | 12181059 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512510 | 0 | 10668549 | 0 | 0 | 0 | 0 | 0 | 12181059 | 12181059 | 12181059 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10668549
16-212 | 16-212 | 16 | 234 - CMSM York | 66095 | York Region DSB | Wilclay | Wilclay Public Elementary School | ELE | 2510 | 6907 | 6907-B01 | 60 WILCLAY AVE | MARKHAM | L3S1R4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8327 | -79.2824 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43980 | 896094 | Construction Complete | Retrofit | Child Care | 2020-21 | 44196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896094 | 0 | 0 | 0 | 896094 | 896094 | 896094 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 896094
16-213 | 16-213 | 16 | 234 - CMSM York | 66095 | York Region DSB | Viola Desmond | Viola Desmond Public Elementary School | ELE | 24795 | 19802 | 19802-B01 | 25 FARRELL RD | MAPLE | L6A4W7 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8713 | -79.4716 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 638 | 2 | 39 | Y | - | Approved | 44679 | 13696144 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542760 | 0 | 11145042 | 0 | 1008341 | 0 | 0 | 0 | 13696143 | 13696143 | 13696143 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12153383
16-214 | 16-214 | 16 | 234 - CMSM York | 66095 | York Region DSB | Rouge Park | Rouge Park Public Elementary School | ELE | 24796 | 19803 | 19803-B01 | 568 RIVERLANDS AVE | MARKHAM | L6B0Y1 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8888 | -79.2164 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 638 | 2 | 39 | Y | - | Approved | 44679 | 13759396 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542760 | 0 | 11208294 | 0 | 1008341 | 0 | 0 | 0 | 13759395 | 13759395 | 13759395 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12216635
16-215 | 16-215 | 16 | 234 - CMSM York | 66095 | York Region DSB | Aurora 2C | Aurora 2C Public Elementary School | ELE | 25371 | 20377 | 20377-B01 | HARTWELL WAY/ WILLIAM GRAHAM DR | AURORA | TBD | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.0221 | -79.4297 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 638 | 2 | 39 | - | - | Approved | 44896 | 23845280 | Under Construction | New Construction | Accommodation Pressure | 2024-25 | 45538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22120349 | 0 | 1724931 | 0 | 0 | 0 | 23845280 | 23845280 | 23845280 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23845280
16-216 | 16-216 | 16 | 234 - CMSM York | 66095 | York Region DSB | Sharon | Sharon Public Elementary School | ELE | 25523 | 20530 | 20530-B01 | MURREL BLVD / CHARLESWHITE COURT | SHARON | TBD | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.0958 | -79.4491 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 638 | 2 | 39 | N | - | Approved | 44600 | 28824870 | Under Construction | New Construction | Accommodation Pressure | 2024-25 | 45538 | 0 | 0 | 0 | 0 | 5108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5108000 | 0 | 0 | 0 | 0 | 22355688 | 0 | 1361182 | 0 | 0 | 0 | 23716870 | 28824870 | 28824870 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23716870
16-217 | 16-217 | 16 | N/A | 66095 | York Region DSB | Stouffville | Stouffville Public Elementary School | ELE | 25520 | 20526 | 20526-B01 | EDWARD ST / MILLARD ST | STOUFFVILLE | TBD | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9764 | -79.2532 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 638 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45538 | 0 | 0 | 0 | 0 | 1969000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969000 | 0 | 0 | 0 | 0 | 25221700 | 0 | 0 | 0 | 0 | 0 | 25221700 | 27190700 | 27190700 | 0 | - | No, Site to be acquired. Sign installation planned for June 1, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 25221700
16-218 | 16-218 | 16 | 234 - CMSM York | 66095 | York Region DSB | Kleinburg Nashville | Kleinburg Nashville Public Elementary School | ELE | 25518 | 20524 | 20524-B01 | BARON ST / ALGOMA DR | VAUGHAN | TBD | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8345 | -79.6581 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 638 | 2 | 39 | N | - | Approved | 44893 | 22555780 | Under Construction | New Construction | Accommodation Pressure | 2024-25 | 45538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20950661 | 0 | 1605119 | 0 | 0 | 0 | 22555780 | 22555780 | 22555780 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 22555780
16-219 | 16-219 | 16 | N/A | 66095 | York Region DSB | Dr. GW Williams | Dr. GW Williams Public Secondary School | SEC | 25666 | 20672 | 20672-B01 | 200 CONOVER AVE | AURORA | L4G 7W1 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.0143 | -79.4443 | 44365 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 1212 | - | - | N | - | Approved | 45128 | 67536900 | Planned | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 36666499 | 23948530 | 4497471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2424400 | 67536900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67536900 | 67536900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-220 | 16-220 | 16 | N/A | 66095 | York Region DSB | Eva L. Dennis Building | Eva L. Dennis Building | HUB | 6351 | 8687 | 8687-B01 | 95 KINGSLYNN DR | KING CITY | L7B1H1 | 35-11-27-603 | King | King Tp | York R | YORK | GTA | South | 43.9127 | -78.5827 | 44365 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Construction Complete | Demolition | Condition | - | - | 0 | 0 | 416519 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416519 | 416519 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
16-221 | 16-221 | 16 | N/A | 66095 | York Region DSB | Markham Centre | Markham Centre Public Elementary School | ELE | TBD | TBD | TBD | ROUGESIDE PROM / WARDEN AVE | MARKHAM | TBD | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8536 | -79.3329 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 638 | 2 | 39 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14513493 | 0 | 1303899 | 0 | 0 | 0 | 15817392 | 15817392 | 15817392 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 15817392
16-222 | 16-222 | 16 | N/A | 66095 | York Region DSB | Oak Ridges | Oak Ridges Public Secondary School | SEC | TBD | TBD | TBD | 36 REGATTA AVE | RICHMOND HILL | TBD | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9526 | -79.4576 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 1250 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24438597 | 0 | 0 | 0 | 0 | 0 | 24438597 | 24438597 | 24438597 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 24438597
16-223 | 16-223 | 16 | N/A | 66095 | York Region DSB | Blue Willow | Blue Willow Public Elementary School | ELE | 9742 | 10241 | 10241-B01 | 250 BLUE WILLOW DR | WOODBRIDGE | L4L9E1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.792 | -79.5577 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 52 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342883 | 0 | 0 | 0 | 0 | 0 | 1342883 | 1342883 | 1342883 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1342883
16-224 | 16-224 | 16 | 234 - CMSM York | 66095 | York Region DSB | Queensville | Queensville Public Elementary School | ELE | TBD | TBD | TBD | TBD | EAST GWILLIMBURY | L9N0R8 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 638 | 2 | 39 | N | - | Approved | 45183 | 28368055 | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 1230892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230892 | 0 | 0 | 0 | 0 | 25609558 | 0 | 1527605 | 0 | 0 | 0 | 27137163 | 28368055 | 28368055 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 27137163
17-001 | 17-001 | 17 | N/A | 66109 | Simcoe County DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15823 | 18093 | 18093-B01 | 1170 HWY 26 | MIDHURST | L0L1X0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.446 | -79.7485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-002 | 17-002 | 17 | N/A | 66109 | Simcoe County DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15823 | 18093 | 18093-B01 | 1170 HWY 26 | MIDHURST | L0L1X0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.446 | -79.7485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 20973548 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21251921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21251921 | 21251921 | 20973548 | -278373 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-003 | 17-003 | 17 | N/A | 66109 | Simcoe County DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 15823 | 18093 | 18093-B01 | 1170 HWY 26 | MIDHURST | L0L1X0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.446 | -79.7485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 244773 | Construction Complete | Other | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244773 | 244773 | 244773 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-004 | 17-004 | 17 | N/A | 66109 | Simcoe County DSB | Admiral Collingwood | Admiral Collingwood Public Elementary School | ELE | 10166 | 10440 | 10440-B01 | 15 DEY DR | COLLINGWOOD | L9Y4N9 | 35-11-70-403 | Collingwood | Collingwood T | Simcoe Co | SIMCOE | Central | South | 44.4868 | -80.2032 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7665615 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 595251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595251 | 1190502 | 6475113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475113 | 7665615 | 7665615 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-005 | 17-005 | 17 | N/A | 66109 | Simcoe County DSB | Alcona Glen | Alcona Glen Public Elementary School | ELE | 8265 | 9317 | 9317-B01 | 1310 INNISFIL BEACH RD | INNISFIL | L9S4B7 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.3115 | -79.5655 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9250305 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8054446 | 8054446 | 1195859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1195859 | 9250305 | 9250305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-007 | 17-007 | 17 | N/A | 66109 | Simcoe County DSB | Algonquin Ridge | Algonquin Ridge Public Elementary School | ELE | 9811 | 10281 | 10281-B01 | 191 GOLDEN MEADOW RD | BARRIE | L4N9R6 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3686 | -79.644 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6702685 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259175 | 259175 | 6443510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6443510 | 6702685 | 6702685 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-009 | 17-009 | 17 | N/A | 66109 | Simcoe County DSB | Allandale Heights | Allandale Heights Public Elementary School | ELE | 8185 | 9248 | 9248-B01 | 124 BAYVIEW DR | BARRIE | L4N3P4 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3644 | -79.6852 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2304526 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613903 | 1613903 | 690623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690623 | 2304526 | 2304526 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-010-01 | 17-010 | 17 | N/A | 66109 | Simcoe County DSB | Alliston Union | Alliston Union Public Elementary School | ELE | 11086 | 12274 | 12274-B01 | 211 CHURCH ST N | ALLISTON | L9R0G3 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.1621 | -79.8715 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 507 | - | - | N | - | Not Required | - | 10272385 | Construction Complete | New Construction | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 221509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221509 | 0 | 0 | 919166 | 0 | 9131710 | 0 | 0 | 0 | 0 | 0 | 10050876 | 10272385 | 10272385 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9131710
17-010-02 | 17-010 | 17 | N/A | 66109 | Simcoe County DSB | Alliston Union | Alliston Union Public Elementary School | ELE | 11086 | 12274 | 12274-L01 | 211 CHURCH ST N | ALLISTON | L9R0G3 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.1621 | -79.8715 | 40970 | 2011-12 | 2011-12 | 40970 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 40970 | 1600000 | Construction Complete | Land Acquisition | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 1600000 | 1600000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1600000
17-011 | 17-011 | 17 | N/A | 66109 | Simcoe County DSB | Andrew Hunter | Andrew Hunter Public Elementary School | ELE | 8187 | 9250 | 9250-B01 | 59 LAMPMAN LANE | BARRIE | L4N5G4 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3912 | -79.7262 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2441585 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2441585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2441585 | 2441585 | 2441585 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-012 | 17-012 | 17 | N/A | 66109 | Simcoe County DSB | Angus Morrison | Angus Morrison Public Elementary School | ELE | 8188 | 9251 | 9251-B01 | 91 SIMCOE ST | ANGUS | L0M1B5 | 35-11-70-602 | Essa | Essa Tp | Simcoe Co | SIMCOE | Central | South | 44.3213 | -79.8786 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4217388 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1499604 | 0 | 497718 | 0 | 0 | 2220066 | 0 | 0 | 0 | 0 | 4217388 | 4217388 | 4217388 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-013 | 17-013 | 17 | N/A | 66109 | Simcoe County DSB | Ardagh Bluffs | Ardagh Bluffs Public Elementary School | ELE | 13190 | 12234 | 12234-B01 | 159 SUMMERSET DR | BARRIE | L4N6H2 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3547 | -79.7271 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10549598 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 425962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425962 | 10123636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10123636 | 10549598 | 10549598 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-014 | 17-014 | 17 | N/A | 66109 | Simcoe County DSB | Assikinack | Assikinack Public Elementary School | ELE | 8192 | 9255 | 9255-B01 | 226 LITTLE AVE | BARRIE | L4N6L3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.365 | -79.673 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3323866 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419626 | 419626 | 2904240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2904240 | 3323866 | 3323866 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-015 | 17-015 | 17 | N/A | 66109 | Simcoe County DSB | Barrie North | Barrie North Public Secondary School | SEC | 8237 | 9296 | 9296-B01 | 110 GROVE ST E | BARRIE | L4M2P3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4005 | -79.6889 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 231 | - | - | N | - | Approved | 42411 | 9841154 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 1500000 | 0 | 0 | 590731 | 0 | 0 | 0 | 0 | 131802 | 0 | 0 | 0 | 0 | 0 | 0 | 2222533 | 0 | 0 | 0 | 0 | 7618621 | 0 | 0 | 0 | 0 | 0 | 7618621 | 9841154 | 9841154 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7618621
17-016 | 17-016 | 17 | N/A | 66109 | Simcoe County DSB | Barrie South | Barrie South Public Secondary School | SEC | 24283 | 19275 | 19275-B01 | 225 PRINCE WILLIAM WAY | BARRIE | L4N0Y9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3475 | -79.6097 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 1005 | - | - | N | - | Approved | 44365 | 41573314 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44446 | 0 | 0 | 684891 | 3683400 | 7177930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11546221 | 0 | 0 | 0 | 0 | 30027093 | 0 | 0 | 0 | 0 | 0 | 30027093 | 41573314 | 41573314 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 30027093
17-017 | 17-017 | 17 | N/A | 66109 | Simcoe County DSB | Baxter Central | Baxter Central Public Elementary School | ELE | 8194 | 3013 | 3013-B01 | 62 DENNEY DR | EGBERT | L0L1N0 | 35-11-70-602 | Essa | Essa Tp | Simcoe Co | SIMCOE | Central | South | 44.2458 | -79.8328 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3775974 | Construction Complete | Addition | Other | 2009-10 | 40057 | 107904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107904 | 3668070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3668070 | 3775974 | 3775974 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-018 | 17-018 | 17 | N/A | 66109 | Simcoe County DSB | Bayview | Bayview Public Elementary School | ELE | 8195 | 9256 | 9256-B01 | 845 OTTAWA ST | MIDLAND | L4R1C9 | 35-11-70-404 | Midland | Midland T | Simcoe Co | SIMCOE | Central | South | 44.748 | -79.9035 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6707417 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 2653541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2653541 | 4053876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4053876 | 6707417 | 6707417 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-020 | 17-020 | 17 | N/A | 66109 | Simcoe County DSB | Bear Creek | Bear Creek Public Secondary School | SEC | 10167 | 10441 | 10441-B01 | 100 RED OAK DR | BARRIE | L4N9M5 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3317 | -79.7337 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 30810088 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2782704 | 2782704 | 28027384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28027384 | 30810088 | 30810088 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-021 | 17-021 | 17 | N/A | 66109 | Simcoe County DSB | Birchview Dunes | Birchview Dunes Public Elementary School | ELE | 8196 | 9257 | 9257-B01 | 1315 RIVER RD W | WASAGA BEACH | L9Z2W6 | 35-11-70-408 | Wasaga Beach | Wasaga Beach T | Simcoe Co | SIMCOE | Central | South | 44.5118 | -80.0248 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1122164 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 16971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16971 | 1105193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105193 | 1122164 | 1122164 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-023 | 17-023 | 17 | N/A | 66109 | Simcoe County DSB | Bradford | Bradford Facility Holding | HFA | 8197 | 9258 | 9258-B01 | 177 CHURCH ST | BRADFORD | L3Z1R4 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1182 | -79.5692 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1902493 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1902493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1902493 | 1902493 | 1902493 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-024 | 17-024 | 17 | N/A | 66109 | Simcoe County DSB | Bradford District | Bradford District Public Secondary School | SEC | 8238 | 9297 | 9297-B01 | 70 PROFESSOR DAY DR | BRADFORD | L3Z3B9 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1125 | -79.5802 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4952101 | Construction Complete | Addition | Other | 2007-08 | 39326 | 2183385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2183385 | 2768716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2768716 | 4952101 | 4952101 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-025 | 17-025 | 17 | N/A | 66109 | Simcoe County DSB | Brechin | Brechin Public Elementary School | ELE | 8198 | 9259 | 9259-B01 | 3226 RAMARA RD 47 | BRECHIN | L0K1B0 | 35-11-70-622 | Ramara | Ramara Tp | Simcoe Co | SIMCOE | Central | South | 44.5469 | -79.1805 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1398633 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398633 | 1398633 | 1398633 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-026 | 17-026 | 17 | N/A | 66109 | Simcoe County DSB | Chris Hadfield | Chris Hadfield Public Elementary School | ELE | 11025 | 12272 | 12272-B01 | 211 WEST PARK AVE | BRADFORD | L3Z0B9 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1052 | -79.5856 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 507 | - | - | N | - | Not Required | - | 10100880 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211462 | 0 | 8889418 | 0 | 0 | 0 | 0 | 0 | 10100880 | 10100880 | 10100880 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8889418
17-027 | 17-027 | 17 | N/A | 66109 | Simcoe County DSB | Clearview Meadows | Clearview Meadows Public Elementary School | ELE | 10123 | 9305 | 9305-B02 | 12 LOCKE AVE | STAYNER | L0M1S0 | 35-11-70-620 | Clearview | Clearview Tp | Simcoe Co | SIMCOE | Central | South | 44.4264 | -80.095 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4938483 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4938483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4938483 | 4938483 | 4938483 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-028 | 17-028 | 17 | N/A | 66109 | Simcoe County DSB | Cookstown | Cookstown Public Elementary School | ELE | 8204 | 9265 | 9265-B01 | 5088 COUNTY ROAD 27 | COOKSTOWN | L0L1L0 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.196 | -79.7035 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2568405 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572641 | 572641 | 1995764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995764 | 2568405 | 2568405 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-029 | 17-029 | 17 | N/A | 66109 | Simcoe County DSB | Couchiching Heights | Couchiching Heights Public Elementary School | ELE | 8205 | 9266 | 9266-B01 | 455 LACLIE ST | ORILLIA | L3V4P7 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6282 | -79.4233 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1759976 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1759976 | 1759976 | 1759976 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-031 | 17-031 | 17 | N/A | 66109 | Simcoe County DSB | Cundles Heights | Cundles Heights Public Elementary School | ELE | 8206 | 9267 | 9267-B01 | 60 CUNDLES RD E | BARRIE | L4M2Z7 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.408 | -79.699 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1415663 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 7648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7648 | 1408015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408015 | 1415663 | 1415663 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-032 | 17-032 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Boyne River | Boyne River Public Elementary School | ELE | 24427 | 19428 | 19428-B01 | 117 JOHN W TAYLOR AVE | ALLISTON | L9R0E7 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.1624 | -79.8532 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 461 | 2 | 39 | N | - | Approved | 42548 | 12105319 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42983 | 0 | 0 | 0 | 0 | 1201000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1201000 | 0 | 0 | 1285139 | 0 | 8581183 | 0 | 1037997 | 0 | 0 | 0 | 10904319 | 12105319 | 12105319 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9619180
17-033 | 17-033 | 17 | N/A | 66109 | Simcoe County DSB | East Oro | East Oro Public Elementary School | ELE | 8209 | 9269 | 9269-B01 | 744 11 LINE N | ORO-MEDONTE | L0L1T0 | 35-11-70-621 | Oro-Medonte | Oro-Medonte Tp | Simcoe Co | SIMCOE | Central | South | 44.5283 | -79.4952 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1572636 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1572636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1572636 | 1572636 | 1572636 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-034 | 17-034 | 17 | N/A | 66109 | Simcoe County DSB | Elmvale District | Elmvale District Public Secondary School | SEC | 8241 | 9300 | 9300-B01 | 25 LAWSON ST | ELMVALE | L0L1P0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.5796 | -79.8648 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1616524 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 4342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4342 | 1612182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612182 | 1616524 | 1616524 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-035 | 17-035 | 17 | N/A | 66109 | Simcoe County DSB | Elmvale District | Elmvale District Public Secondary School | SEC | 8241 | 9300 | 9300-B01 | 25 LAWSON ST | ELMVALE | L0L1P0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.5796 | -79.8648 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 180 | - | - | N | - | Approved | 42958 | 11431663 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43497 | 0 | 1800000 | 900000 | 0 | 714492 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 4114492 | 0 | 0 | 0 | 0 | 7317171 | 0 | 0 | 0 | 0 | 0 | 7317171 | 11431663 | 11431663 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7317171
17-037 | 17-037 | 17 | N/A | 66109 | Simcoe County DSB | Ferndale Woods | Ferndale Woods Public Elementary School | ELE | 8211 | 9271 | 9271-B01 | 170 FERNDALE DR S | BARRIE | L4N8A1 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.358 | -79.7161 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1364173.75 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 61968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61968 | 1302206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302206 | 1364174 | 1364173.75 | -0.25 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-039 | 17-039 | 17 | N/A | 66109 | Simcoe County DSB | Fieldcrest | Fieldcrest Public Elementary School | ELE | 8266 | 9318 | 9318-B01 | 100 PROFESSOR DAY DR | BRADFORD | L3Z3B9 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1154 | -79.5813 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1875567 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 179541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179541 | 1696026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696026 | 1875567 | 1875567 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-042 | 17-042 | 17 | N/A | 66109 | Simcoe County DSB | Fred C Cook | Fred C Cook Public Elementary School | ELE | 24096 | 9273 | 9273-B02 | 20 FLETCHER ST | BRADFORD | L3Z1L9 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1201 | -79.5673 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9148035 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 400000 | 0 | 1738000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2138000 | 4746482 | 0 | 2263553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7010035 | 9148035 | 9148035 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-043 | 17-043 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Georgian Bay District | Georgian Bay District Public Secondary School | SEC | 24417 | 9301 | 9301-B02 | 865 HUGEL AVE | MIDLAND | L4R1X8 | 35-11-70-404 | Midland | Midland T | Simcoe Co | SIMCOE | Central | South | 44.7421 | -79.9014 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 984 | 2 | 25 | N | - | Approved | 43993 | 34075107 | Construction Complete | New Construction | Consolidation | 2018-19 | 43344 | 0 | 0 | 1686594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798627 | 0 | 0 | 0 | 2485221 | 0 | 0 | 0 | 0 | 30551889 | 0 | 1037997 | 0 | 0 | 0 | 31589886 | 34075107 | 34075107 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 31589886
17-044 | 17-044 | 17 | N/A | 66109 | Simcoe County DSB | Goodfellow | Goodfellow Public Elementary School | ELE | 8138 | 9202 | 9202-B01 | 827 9TH LINE | INNISFIL | L9S1A6 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.3278 | -79.5448 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2304614 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 106238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106238 | 2198376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2198376 | 2304614 | 2304614 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-046 | 17-046 | 17 | N/A | 66109 | Simcoe County DSB | Harriett Todd | Harriett Todd Public Elementary School | ELE | 8140 | 9204 | 9204-B01 | 11 GEORGE ST | ORILLIA | L3V2V1 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.5986 | -79.4323 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6469778 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5069778 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6469778 | 6469778 | 6469778 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-047 | 17-047 | 17 | N/A | 66109 | Simcoe County DSB | Harriett Todd | Harriett Todd Public Elementary School | ELE | 8140 | 9204 | 9204-B01 | 11 GEORGE ST | ORILLIA | L3V2V1 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.5986 | -79.4323 | 41661 | 2013-14 | 2013-14 | - | - | - | 41661 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44365 | 401971 | Construction Complete | Addition | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401971 | 0 | 0 | 0 | 0 | 0 | 401971 | 401971 | 401971 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 401971
17-048 | 17-048 | 17 | N/A | 66109 | Simcoe County DSB | Hewitt's Creek | Hewitt's Creek Public Elementary School | ELE | 10983 | 12127 | 12127-B01 | 41 SANDRINGHAM DR | BARRIE | L4N0J9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3596 | -79.6213 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10670681 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483540 | 983540 | 9687141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9687141 | 10670681 | 10670681 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-049 | 17-049 | 17 | N/A | 66109 | Simcoe County DSB | Hillcrest | Hillcrest Public Elementary School | ELE | 8141 | 9205 | 9205-B01 | 184 TORONTO ST | BARRIE | L4N1V5 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.394 | -79.6989 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6127647 | Construction Complete | Addition | Other | 2010-11 | 40422 | 189907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189907 | 5937740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5937740 | 6127647 | 6127647 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-051 | 17-051 | 17 | N/A | 66109 | Simcoe County DSB | Holly Meadows | Holly Meadows Public Elementary School | ELE | 9899 | 10317 | 10317-B01 | 151 MAPLETON AVE | BARRIE | L4N9N7 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3402 | -79.715 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8957937 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985366 | 985366 | 7972571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7972571 | 8957937 | 8957937 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-053 | 17-053 | 17 | N/A | 66109 | Simcoe County DSB | Honorable Earl Rowe | Honorable Earl Rowe Public Elementary School | ELE | 8144 | 9208 | 9208-B01 | 2516 LINE 12 | BRADFORD | L3Z2A5 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1752 | -79.5826 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1332785 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332785 | 1332785 | 1332785 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-054 | 17-054 | 17 | N/A | 66109 | Simcoe County DSB | Huron Park | Huron Park Public Elementary School | ELE | 8145 | 9209 | 9209-B01 | 425 ROBERT ST | MIDLAND | L4R2M2 | 35-11-70-404 | Midland | Midland T | Simcoe Co | SIMCOE | Central | South | 44.7436 | -79.8764 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5067193 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5067193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5067193 | 5067193 | 5067193 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-056 | 17-056 | 17 | N/A | 66109 | Simcoe County DSB | Hyde Park | Hyde Park Public Elementary School | ELE | 18543 | 19082 | 19082-B01 | 72 THE QUEENSWAY | BARRIE | L4M7J3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3597 | -79.6069 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 528 | - | - | N | - | Approved | 44365 | 12086829 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41520 | 0 | 0 | 0 | 540727 | 1363331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904058 | 0 | 0 | 969170 | 0 | 9213601 | 0 | 0 | 0 | 0 | 0 | 10182771 | 12086829 | 12086829 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9213601
17-058 | 17-058 | 17 | N/A | 66109 | Simcoe County DSB | James Keating | James Keating Public Elementary School | ELE | 8148 | 9212 | 9212-B01 | 20 LORNE AVE | PENETANGUISHENE | L9M1B2 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7739 | -79.9261 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6075258 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6075258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6075258 | 6075258 | 6075258 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-059 | 17-059 | 17 | N/A | 66109 | Simcoe County DSB | Johnson Street | Johnson Street Public Elementary School | ELE | 8149 | 9213 | 9213-B01 | 105 JOHNSON ST | BARRIE | L4M4R4 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3996 | -79.656 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1212167 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 1211617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211617 | 1212167 | 1212167 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-060 | 17-060 | 17 | N/A | 66109 | Simcoe County DSB | Killarney Beach | Killarney Beach Public Elementary School | ELE | 8150 | 9214 | 9214-B01 | 850 20TH SIDE RD | LEFROY | L0L1W0 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.2574 | -79.5647 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1409539 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409539 | 1409539 | 1409539 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-061 | 17-061 | 17 | N/A | 66109 | Simcoe County DSB | Lake Simcoe | Lake Simcoe Public Elementary School | ELE | 24474 | 19477 | 19477-B01 | 1701 WEBSTER BLVD | ALCONA | L9S2A6 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.2979 | -79.5576 | 41765 | 2013-14 | 2014-15 | - | - | - | 41765 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 412 | - | - | N | - | Approved | 42065 | 10008261 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 1280413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280413 | 0 | 0 | 1707786 | 0 | 7020062 | 0 | 0 | 0 | 0 | 0 | 8727848 | 10008261 | 10008261 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7020062
17-062 | 17-062 | 17 | N/A | 66109 | Simcoe County DSB | Lions Oval | Lions Oval Public Elementary School | ELE | 11021 | 12191 | 12191-B01 | 25 BRANT ST W | ORILLIA | L3V3N6 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6124 | -79.4243 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13373574 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388922 | 388922 | 12984652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12984652 | 13373574 | 13373574 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-063 | 17-063 | 17 | N/A | 66109 | Simcoe County DSB | Maple Grove | Maple Grove Public Elementary School | ELE | 8152 | 9216 | 9216-B01 | 242 GROVE ST E | BARRIE | L4M2P9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4059 | -79.6784 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2836528 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268351 | 268351 | 2143177 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2568177 | 2836528 | 2836528 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-065 | 17-065 | 17 | N/A | 66109 | Simcoe County DSB | Mapleview Heights | Mapleview Heights Public Elementary School | ELE | 10139 | 10420 | 10420-B01 | 180 ESTHER DR | BARRIE | L4N9S9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3496 | -79.6473 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7088458 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387335 | 387335 | 6701123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6701123 | 7088458 | 7088458 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-066 | 17-066 | 17 | N/A | 66109 | Simcoe County DSB | Mapleview Heights | Mapleview Heights Public Elementary School | ELE | 10139 | 10420 | 10420-B01 | 180 ESTHER DR | BARRIE | L4N9S9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3496 | -79.6473 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 706447 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706447 | 706447 | 706447 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-068 | 17-068 | 17 | N/A | 66109 | Simcoe County DSB | Marchmont | Marchmont Public Elementary School | ELE | 8153 | 9217 | 9217-B01 | 1902 DIVISION RD W RR 2 | ORILLIA | L3V6H2 | 35-11-70-623 | Severn | Severn Tp | Simcoe Co | SIMCOE | Central | South | 44.626 | -79.5006 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1311438 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311438 | 1311438 | 1311438 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-069 | 17-069 | 17 | N/A | 66109 | Simcoe County DSB | Minesing Central | Minesing Central Public Elementary School | ELE | 8155 | 9219 | 9219-B01 | 7 HURON ST | MINESING | L0L1Y0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.4429 | -79.8402 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2023106 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 144506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144506 | 1878600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1878600 | 2023106 | 2023106 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-071 | 17-071 | 17 | N/A | 66109 | Simcoe County DSB | Mundy's Bay | Mundy's Bay Public Elementary School | ELE | 10942 | 9229 | 9229-B01 | 340 SIXTH ST | MIDLAND | L4R3Y4 | 35-11-70-404 | Midland | Midland T | Simcoe Co | SIMCOE | Central | South | 44.7443 | -79.8921 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 13539574 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805657 | 805657 | 12733917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12733917 | 13539574 | 13539574 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-072 | 17-072 | 17 | N/A | 66109 | Simcoe County DSB | Nantyr Shores | Nantyr Shores Public Secondary School | SEC | 10124 | 10407 | 10407-B01 | 1146 ANNA MARIA AVE | INNISFIL | L9S4X5 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.3051 | -79.5552 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 26355096 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6278833 | 6278833 | 20076263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20076263 | 26355096 | 26355096 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-073 | 17-073 | 17 | N/A | 66109 | Simcoe County DSB | New Lowell Central | New Lowell Central Public Elementary School | ELE | 8159 | 9223 | 9223-B01 | 5197 COUNTY ROAD 9 | NEW LOWELL | L0M1N0 | 35-11-70-620 | Clearview | Clearview Tp | Simcoe Co | SIMCOE | Central | South | 44.3587 | -79.9671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 944986 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 944350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944350 | 944986 | 944986 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-075 | 17-075 | 17 | N/A | 66109 | Simcoe County DSB | Nottawasage Pines | Nottawasage Pines Public Secondary School | SEC | 16844 | 19023 | 19023-B01 | 8505 COUNTY ROAD 10 | ANGUS | L0M1B1 | 35-11-70-602 | Essa | Essa Tp | Simcoe Co | SIMCOE | Central | South | 44.3127 | -79.8842 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 25329687 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 1380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565577 | 3945577 | 21384110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21384110 | 25329687 | 25329687 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-076 | 17-076 | 17 | N/A | 66109 | Simcoe County DSB | Oakley Park | Oakley Park Public Elementary School | ELE | 8163 | 9227 | 9227-B01 | 22 DAVIDSON ST | BARRIE | L4M3R8 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3995 | -79.6882 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2553163 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 127344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127344 | 2425819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2425819 | 2553163 | 2553163 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-077 | 17-077 | 17 | N/A | 66109 | Simcoe County DSB | Orchard Park | Orchard Park Public Elementary School | ELE | 8164 | 9228 | 9228-B01 | 24 CALVERLEY ST | ORILLIA | L3V3T4 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6199 | -79.4311 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1190444 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190444 | 1190444 | 1190444 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-078 | 17-078 | 17 | N/A | 66109 | Simcoe County DSB | Orillia | Orillia Public Secondary School | SEC | 24369 | 9303 | 9303-B02 | 250 COLLEGIATE DR | ORILLIA | L3V7S5 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6123 | -79.4342 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 1110 | - | - | N | - | Not Required | - | 30374496 | Construction Complete | New Construction | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30374496 | 0 | 0 | 0 | 0 | 0 | 30374496 | 30374496 | 30374496 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 30374496
17-079 | 17-079 | 17 | N/A | 66109 | Simcoe County DSB | Pine River | Pine River Public Elementary School | ELE | 8189 | 9252 | 9252-B01 | 45 BRIAN AVE | ANGUS | L0M1B3 | 35-11-70-602 | Essa | Essa Tp | Simcoe Co | SIMCOE | Central | South | 44.322 | -79.8925 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3143138 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3143138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3143138 | 3143138 | 3143138 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-080 | 17-080 | 17 | N/A | 66109 | Simcoe County DSB | Portage View | Portage View Public Elementary School | ELE | 8167 | 9231 | 9231-B01 | 124 LETITIA ST | BARRIE | L4N1P5 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3919 | -79.7151 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5559775 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3559775 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5559775 | 5559775 | 5559775 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-081 | 17-081 | 17 | N/A | 66109 | Simcoe County DSB | Rama Central | Rama Central Public Elementary School | ELE | 8169 | 9233 | 9233-B01 | 7269 COUNTY RD 169 | WASHAGO | L0K2B0 | 35-11-70-622 | Ramara | Ramara Tp | Simcoe Co | SIMCOE | Central | South | 44.7267 | -79.2865 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1207785 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 18882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18882 | 1188903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188903 | 1207785 | 1207785 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-083 | 17-083 | 17 | N/A | 66109 | Simcoe County DSB | Regent Park | Regent Park Public Elementary School | ELE | 8170 | 9234 | 9234-B01 | 485 REGENT ST | ORILLIA | L3V4E2 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.5986 | -79.3979 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8140871 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8140871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8140871 | 8140871 | 8140871 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-084-01 | 17-084 | 17 | N/A | 66109 | Simcoe County DSB | Severn Shores | Severn Shores Public Elementary School | ELE | 24397 | 9254 | 9254-B02 | 2746 CUMBERLAND BEACH RD | CUMBERLAND BEACH | L0K1G0 | 35-11-70-623 | Severn | Severn Tp | Simcoe Co | SIMCOE | Central | South | 44.7022 | -79.3903 | 41877 | 2013-14 | 2014-15 | - | - | - | 41877 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 317 | - | - | N | - | Approved | 42087 | 7335730 | Construction Complete | New Construction | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503976 | 0 | 6831754 | 0 | 0 | 0 | 0 | 0 | 7335730 | 7335730 | 7335730 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6831754
17-084-02 | 17-084 | 17 | N/A | 66109 | Simcoe County DSB | Severn Shores | Severn Shores Public Elementary School | ELE | 24397 | 9254 | 9254-L02 | 2746 CUMBERLAND BEACH RD | CUMBERLAND BEACH | L0K1G0 | 35-11-70-623 | Severn | Severn Tp | Simcoe Co | SIMCOE | Central | South | 44.7022 | -79.3903 | 42087 | 2014-15 | 2014-15 | 42087 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42087 | 1544494 | Construction Complete | Land Acquisition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544494 | 0 | 0 | 0 | 0 | 0 | 0 | 1544494 | 1544494 | 1544494 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1544494
17-085 | 17-085 | 17 | N/A | 66109 | Simcoe County DSB | Tecumseth Beeton | Tecumseth Beeton Public Elementary School | ELE | 8215 | 9275 | 9275-B01 | 43 PATTERSON ST | BEETON | L0G1A0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0811 | -79.782 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1342450 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342450 | 1342450 | 1342450 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-087 | 17-087 | 17 | N/A | 66109 | Simcoe County DSB | Terry Fox | Terry Fox Public Elementary School | ELE | 10120 | 10404 | 10404-B01 | 100 LIVINGSTONE ST E | BARRIE | L4M6X9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4156 | -79.7022 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7143730 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980453 | 980453 | 6163277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6163277 | 7143730 | 7143730 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-089 | 17-089 | 17 | N/A | 66109 | Simcoe County DSB | Tottenham | Tottenham Public Elementary School | ELE | 8218 | 9278 | 9278-B01 | 21 ROGERS RD | TOTTENHAM | L0G1W0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0203 | -79.8018 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 871708 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 15232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15232 | 856476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856476 | 871708 | 871708 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-090 | 17-090 | 17 | N/A | 66109 | Simcoe County DSB | Trillium Woods | Trillium Woods Public Elementary School | ELE | 10663 | 11199 | 11199-B01 | 20 ELMBROOK DR | BARRIE | L4N0Z1 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3429 | -79.6994 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9167001 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581565 | 581565 | 8585436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8585436 | 9167001 | 9167001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-092 | 17-092 | 17 | N/A | 66109 | Simcoe County DSB | Uptergrove | Uptergrove Public Elementary School | ELE | 8219 | 9279 | 9279-B01 | 4833 MULEY POINT RD | RAMARA | L3V8C3 | 35-11-70-622 | Ramara | Ramara Tp | Simcoe Co | SIMCOE | Central | South | 44.5992 | -79.3035 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1196619 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196619 | 1196619 | 1196619 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-094 | 17-094 | 17 | N/A | 66109 | Simcoe County DSB | Tay Shores | Tay Shores Public Elementary School | ELE | 8220 | 9280 | 9280-B01 | 125 JEPHSON ST | VICTORIA HARBOUR | L0K2A0 | 35-11-70-625 | Tay | Tay Tp | Simcoe Co | SIMCOE | Central | South | 44.751 | -79.7706 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2031427 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 140867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140867 | 1890560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1890560 | 2031427 | 2031427 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-095-01 | 17-095 | 17 | N/A | 66109 | Simcoe County DSB | Tay Shores | Tay Shores Public Elementary School | ELE | 8220 | 9280 | 9280-B01 | 125 JEPHSON ST | VICTORIA HARBOUR | L0K2A0 | 35-11-70-625 | Tay | Tay Tp | Simcoe Co | SIMCOE | Central | South | 44.751 | -79.7706 | 41765 | 2013-14 | 2014-15 | - | - | - | 41765 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 239 | - | - | N | - | Not Required | - | 6883881 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 500000 | 1417320 | 3166537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5083857 | 0 | 0 | 503976 | 0 | 1296048 | 0 | 0 | 0 | 0 | 0 | 1800024 | 6883881 | 6883881 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1296048
17-095-02 | 17-095 | 17 | N/A | 66109 | Simcoe County DSB | Tay Shores | Tay Shores Public Elementary School | ELE | 8220 | 9280 | 9280-L01 | 125 JEPHSON ST | VICTORIA HARBOUR | L0K2A0 | 35-11-70-625 | Tay | Tay Tp | Simcoe Co | SIMCOE | Central | South | 44.751 | -79.7706 | 41815 | 2013-14 | 2014-15 | 41815 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41815 | 1072680 | Construction Complete | Land Acquisition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072680 | 0 | 0 | 0 | 0 | 0 | 0 | 1072680 | 1072680 | 1072680 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1072680
17-096 | 17-096 | 17 | N/A | 66109 | Simcoe County DSB | Warminster | Warminster Public Elementary School | ELE | 8154 | 9218 | 9218-B01 | 4031 LINE 13 N | WARMINSTER | L0K2G0 | 35-11-70-621 | Oro-Medonte | Oro-Medonte Tp | Simcoe Co | SIMCOE | Central | South | 44.6389 | -79.5452 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1266810 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1266810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1266810 | 1266810 | 1266810 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-098 | 17-098 | 17 | N/A | 66109 | Simcoe County DSB | WC Little | WC Little Public Elementary School | ELE | 10118 | 10403 | 10403-B01 | 11 BEAR CREEK DR | BARRIE | L4N9M9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3286 | -79.7302 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8970197 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 44109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1403492 | 1447601 | 7522596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7522596 | 8970197 | 8970197 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-099 | 17-099 | 17 | N/A | 66109 | Simcoe County DSB | WC Little | WC Little Public Elementary School | ELE | 10118 | 10403 | 10403-B01 | 11 BEAR CREEK DR | BARRIE | L4N9M9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3286 | -79.7302 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 604407 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604407 | 604407 | 604407 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-101 | 17-101 | 17 | N/A | 66109 | Simcoe County DSB | West Bayfield | West Bayfield Public Elementary School | ELE | 8226 | 9285 | 9285-B01 | 49 FORD ST | BARRIE | L4N7J4 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4074 | -79.7205 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1181766 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1181766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1181766 | 1181766 | 1181766 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-103 | 17-103 | 17 | N/A | 66109 | Simcoe County DSB | WH Day | WH Day Public Elementary School | ELE | 8221 | 9281 | 9281-B01 | 410 MAPLEGROVE AVE | BRADFORD | L3Z2V4 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1045 | -79.5695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1464408 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 55032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55032 | 1409376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409376 | 1464408 | 1464408 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-104 | 17-104 | 17 | N/A | 66109 | Simcoe County DSB | Willow Landing | Willow Landing Public Elementary School | ELE | 8268 | 9319 | 9319-B01 | 330 BIG BAY POINT RD | BARRIE | L4N8A8 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3543 | -79.6617 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1777986 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777986 | 1777986 | 1777986 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-105 | 17-105 | 17 | N/A | 66109 | Simcoe County DSB | Worsley | Worsley Public Elementary School | ELE | 8227 | 9286 | 9286-B01 | 31 40TH ST S | WASAGA BEACH | L9Z1Z9 | 35-11-70-408 | Wasaga Beach | Wasaga Beach T | Simcoe Co | SIMCOE | Central | South | 44.4793 | -80.0643 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1059355 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 7710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7710 | 1051645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051645 | 1059355 | 1059355 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-107 | 17-107 | 17 | N/A | 66109 | Simcoe County DSB | WR Best Memorial | WR Best Memorial Public Elementary School | ELE | 8223 | 9282 | 9282-B01 | 2221 OLD BARRIE RD W | ORO-MEDONTE | L0L2L0 | 35-11-70-621 | Oro-Medonte | Oro-Medonte Tp | Simcoe Co | SIMCOE | Central | South | 44.4902 | -79.6642 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1074341 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074341 | 1074341 | 1074341 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-109 | 17-109 | 17 | N/A | 66109 | Simcoe County DSB | Wyevale Central | Wyevale Central Public Elementary School | ELE | 8229 | 9288 | 9288-B01 | 20 CONCESSION ROAD 5 E | TINY | L0L2T0 | 35-11-70-614 | Tiny | Tiny Tp | Simcoe Co | SIMCOE | Central | South | 44.6549 | -79.9245 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1391406 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1391406 | 1391406 | 1391406 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
17-111 | 17-111 | 17 | N/A | 66109 | Simcoe County DSB | Cameron Street | Cameron Street Public Elementary School | ELE | 8200 | 9261 | 9261-B01 | 575 CAMERON ST | COLLINGWOOD | L9Y2J4 | 35-11-70-403 | Collingwood | Collingwood T | Simcoe Co | SIMCOE | Central | South | 44.488 | -80.2196 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 141 | - | - | N | - | Approved | 43342 | 6487869 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43780 | 968000 | 0 | 1230824 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253824 | 0 | 0 | 259647 | 0 | 3974398 | 0 | 0 | 0 | 0 | 0 | 4234045 | 6487869 | 6487869 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3974398
17-112 | 17-112 | 17 | N/A | 66109 | Simcoe County DSB | Mountain View | Mountain View Public Elementary School | ELE | 8158 | 9222 | 9222-B01 | 300 SPRUCE ST | COLLINGWOOD | L9Y3H1 | 35-11-70-403 | Collingwood | Collingwood T | Simcoe Co | SIMCOE | Central | South | 44.4967 | -80.2307 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Approved | 44365 | 1933696 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933696 | 0 | 0 | 0 | 0 | 0 | 1933696 | 1933696 | 1933696 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1933696
17-113 | 17-113 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Orchard Park | Orchard Park Public Elementary School | ELE | 8164 | 9228 | 9228-B01 | 24 CALVERLEY ST | ORILLIA | L3V3T4 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6199 | -79.4311 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 42650 | 2062509 | Construction Complete | Addition | Child Care | 2016-17 | 42614 | 350000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 1512509 | 0 | 0 | 0 | 1512509 | 2062509 | 2062509 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1512509
17-114 | 17-114 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Chris Hadfield | Chris Hadfield Public Elementary School | ELE | 11025 | 12272 | 12272-B01 | 211 WEST PARK AVE | BRADFORD | L3Z0B9 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1052 | -79.5856 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512510 | 0 | 0 | 0 | 1512510 | 1512510 | 1512510 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1512510
17-115 | 17-115 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Tecumseth Beeton | Tecumseth Beeton Public Elementary School | ELE | 8215 | 9275 | 9275-B01 | 43 PATTERSON ST | BEETON | L0G1A0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0811 | -79.782 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529379 | 0 | 0 | 0 | 529379 | 529379 | 0 | -529379 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 529379
17-116 | 17-116 | 17 | N/A | 66109 | Simcoe County DSB | Collingwood Bus Garage | Collingwood Bus Garage Facility Holding | HFA | 15907 | 18095 | 18095-L02 | 37 CAMPBELL ST | COLLINGWOOD | L9Y2K9 | 35-11-70-403 | Collingwood | Collingwood T | Simcoe Co | SIMCOE | Central | South | 44.4856 | -80.2168 | 42880 | 2016-17 | 2017-18 | 42880 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42880 | 150000 | Construction Complete | Land Acquisition | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 150000
17-117 | 17-117 | 17 | N/A | 66109 | Simcoe County DSB | Clearview Meadows | Clearview Meadows Public Elementary School | ELE | 10123 | 9305 | 9305-B02 | 12 LOCKE AVE | STAYNER | L0M1S0 | 35-11-70-620 | Clearview | Clearview Tp | Simcoe Co | SIMCOE | Central | South | 44.4264 | -80.095 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 153 | - | - | N | - | Approved | 44365 | 2898753 | Construction Complete | Addition | Consolidation | 2020-21 | 44075 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 529379 | 0 | 2069374 | 0 | 0 | 0 | 0 | 0 | 2598753 | 2898753 | 2898753 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2069374
17-118 | 17-118 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Pine River | Pine River Public Elementary School | ELE | 8189 | 9252 | 9252-B01 | 45 BRIAN AVE | ANGUS | L0M1B3 | 35-11-70-602 | Essa | Essa Tp | Simcoe Co | SIMCOE | Central | South | 44.322 | -79.8925 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588138 | 0 | 0 | 0 | 1588138 | 1588138 | 0 | -1588138 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1588138
17-119 | 17-119 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Lake Simcoe | Lake Simcoe Public Elementary School | ELE | 24474 | 19477 | 19477-B01 | 1701 WEBSTER BLVD | ALCONA | L9S2A6 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.2979 | -79.5576 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1588138 | 0 | 0 | 0 | 1588138 | 1588138 | 0 | -1588138 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1588138
17-120 | 17-120 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Harvest Hill | Harvest Hill Elementary Public School | ELE | 24813 | 19820 | 19820-B01 | 400 CROSSLAND BLVD | BRADFORD | L3Z0G8 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.124 | -79.5909 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 501 | 2 | 39 | Y | - | Approved | 44137 | 13761814 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 1622553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622553 | 0 | 0 | 1619898 | 0 | 9460605 | 0 | 1058758 | 0 | 0 | 0 | 12139261 | 13761814 | 13761814 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10519363
17-121 | 17-121 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Oro Medonte | Oro Medonte Public Elementary School | ELE | 24814 | 19821 | 19821-B01 | 3331 LINE 4 N | ORO-MEDONTE | L0L2L0 | 35-11-70-621 | Oro-Medonte | Oro-Medonte Tp | Simcoe Co | SIMCOE | Central | South | 44.5536 | -79.6579 | 43172 | 2017-18 | 2017-18 | - | - | - | 43172 | 2017-18 | 2017-18 | - | - | - | 43172 | 2017-18 | 2017-18 | - | - | - | 570 | - | - | N | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 1942572 | 0 | 0 | 0 | 0 | 6775101 | 0 | 0 | 0 | 0 | 0 | 8717673 | 0 | 0 | 1079933 | 0 | 14049005 | 0 | 0 | 0 | 0 | 0 | 15128938 | 23846611 | 23846610 | -1 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 14049005
17-122 | 17-122 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Wasaga Beach | Wasaga Beach Public Elementary School | ELE | 24815 | 19822 | 19822-B01 | TBD | WASAGA BEACH | TBD | 35-11-70-408 | Wasaga Beach | Wasaga Beach T | Simcoe Co | SIMCOE | Central | South | TBD | TBD | 43172 | 2017-18 | 2017-18 | - | - | - | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 406 | - | - | N | - | Approved | 45070 | 22512681 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45540 | 0 | 0 | 4065147 | 0 | 272071 | 0 | 0 | 0 | 0 | 2524523 | 0 | 0 | 0 | 0 | 0 | 6861741 | 0 | 0 | 0 | 0 | 15650940 | 0 | 0 | 0 | 0 | 0 | 15650940 | 22512681 | 22512681 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 15650940
17-123 | 17-123 | 17 | N/A | 66109 | Simcoe County DSB | Shanty Bay | Shanty Bay Public Elementary School | ELE | 25372 | 20378 | 20378-B01 | 1871 RIDGE RD W | ORO-MEDONTE | L0L2L0 | 35-11-70-621 | Oro-Medonte | Oro-Medonte Tp | Simcoe Co | SIMCOE | Central | South | 44.4145 | -79.5765 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 190 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Condition | 2025-26 | 45905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5867921 | 0 | 0 | 0 | 0 | 0 | 5867921 | 5867921 | 5867921 | 0 | - | No, Ministry is following up with the school board | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5867921
17-124 | 17-124 | 17 | N/A | 66109 | Simcoe County DSB | Marshview | Marshview Elementary Public School | ELE | 25373 | 20379 | 20379-B01 | 742 SIMCOE RD | BRADFORD-WEST GWILLIMBURY | L3Z2A6 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.0911 | -79.567 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 593 | - | - | - | - | Approved | 44820 | 17443654 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 643522 | 0 | 3318743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3962265 | 0 | 0 | 0 | 0 | 13481389 | 0 | 0 | 0 | 0 | 0 | 13481389 | 17443654 | 17443654 | 0 | - | No, Ministry is following up with the school board | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13481389
17-125 | 17-125 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Lake Simcoe | Lake Simcoe Public Elementary School | ELE | 24474 | 19477 | 19477-B01 | 1701 WEBSTER BLVD | ALCONA | L9S2A6 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.2979 | -79.5576 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 190 | 2 | 39 | N | - | Approved | 45022 | 8283038 | Planned | Addition | Accommodation Pressure | 2022-23 | 44935 | 0 | 0 | 0 | 0 | 377160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377160 | 0 | 0 | 0 | 0 | 5785411 | 0 | 2120467 | 0 | 0 | 0 | 7905878 | 8283038 | 8283038 | 0 | - | No, Ministry is following up with the school board | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7905878
17-126 | 17-126 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Tecumseth Beeton | Tecumseth Beeton Public Elementary School | ELE | 8215 | 9275 | 9275-B01 | 43 PATTERSON ST | BEETON | L0G1A0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0811 | -79.782 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | 39 | N | - | Approved | 44985 | 1289203 | Planned | Retrofit | Child Care | 2022-23 | 44866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1289203 | 0 | 0 | 0 | 1289203 | 1289203 | 1289203 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | #REF!
17-127 | 17-127 | 17 | 224 - CMSM Simcoe | 66109 | Simcoe County DSB | Banting Memorial | Banting Memorial Public Secondary School | SEC | TBD | TBD | TBD | SIR FREDERICK BANTING RD / JOHN W TAYLOR AVE | ALLISTON | TBD | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.1645 | -79.8454 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 1288 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Condition | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39631195 | 0 | 1785774 | 0 | 0 | 0 | 41416969 | 41416969 | 41416969 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 41416969
17-128 | 17-128 | 17 | N/A | 66109 | Simcoe County DSB | Killarney Beach | Killarney Beach Public Elementary School | ELE | 8150 | 9214 | 9214-B01 | 820 20TH SIDE RD | INNISFIL | L0L1W0 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.2578 | -79.5645 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 184 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7183691 | 0 | 0 | 0 | 0 | 0 | 7183691 | 7183691 | 7183691 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7183691
17-129 | 17-129 | 17 | N/A | 66109 | Simcoe County DSB | Orillia | Orillia Public Elementary School | ELE | TBD | TBD | TBD | BASS LAKE SIDE RD / ATLANTIS DR | ORILLIA | TBD | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.61 | -79.4609 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 334 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9026347 | 0 | 0 | 0 | 0 | 0 | 9026347 | 9026347 | 9026347 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9026347
17-130 | 17-130 | 17 | N/A | 66109 | Simcoe County DSB | Bradford Transition Centre | Bradford Transition Centre |  | TBD | TBD | TBD | 151 SIMCOE ROAD | BRADFORD | L3Z 1Y3 |  | BRADFORD | Bradford | Simcoe Co | SIMCOE | Central | South | 44.1106 | -79.5635 | [23 empty] | Planned | - | - | Planned |  | Accommodation Pressure | 2024-25 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 0
18-001 | 18-001 | 18 | N/A | 66117 | Upper Grand DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 2722 | 6963 | 6963-B01 | 500 VICTORIA RD N | GUELPH | N1E6K2 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5786 | -80.2635 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-002 | 18-002 | 18 | N/A | 66117 | Upper Grand DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 2722 | 6963 | 6963-B01 | 500 VICTORIA RD N | GUELPH | N1E6K2 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5786 | -80.2635 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 27091928 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27091929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27091929 | 27091929 | 27091929 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-003 | 18-003 | 18 | N/A | 66117 | Upper Grand DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 2722 | 6963 | 6963-B01 | 500 VICTORIA RD N | GUELPH | N1E6K2 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5786 | -80.2635 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 75000 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 75000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-006 | 18-006 | 18 | N/A | 66117 | Upper Grand DSB | Arthur | Arthur Public Elementary School | ELE | 101 | 5359 | 5359-B01 | 130 JOHN ST E | ARTHUR | N0G1A0 | 35-15-75-617 | Wellington North | Wellington North Tp | Wellington Co | WELLINGTON | Southwest | South | 43.8843 | -81.3082 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16900 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16900 | 16900 | 16900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-007 | 18-007 | 18 | N/A | 66117 | Upper Grand DSB | Arthur | Arthur Public Elementary School | ELE | 5213 | 8124 | 8124-B01 | 155 CONESTOGA ST N | ARTHUR | N0G1A0 | 35-15-75-617 | Wellington North | Wellington North Tp | Wellington Co | WELLINGTON | Southwest | South | 43.8348 | -80.5423 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3949042 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3949042 | 3949042 | 3949042 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-010 | 18-010 | 18 | N/A | 66117 | Upper Grand DSB | Brisbane | Brisbane Public Elementary School | ELE | 749 | 5795 | 5795-B01 | 9426 WELLINGTON RD 124 RR 2 | ERIN | N0B1T0 | 35-15-75-405 | Erin | Erin T | Wellington Co | WELLINGTON | Southwest | South | 43.7472 | -80.0736 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3873538 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3873538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3873538 | 3873538 | 3873538 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-011 | 18-011 | 18 | N/A | 66117 | Upper Grand DSB | Brisbane | Brisbane Public Elementary School | ELE | 749 | 5795 | 5795-B01 | 9426 WELLINGTON RD 124 RR 2 | ERIN | N0B1T0 | 35-15-75-405 | Erin | Erin T | Wellington Co | WELLINGTON | Southwest | South | 43.7472 | -80.0736 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 473052 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473052 | 473052 | 473052 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-013 | 18-013 | 18 | N/A | 66117 | Upper Grand DSB | Centennial Hylands | Centennial Hylands Public Elementary School | ELE | 361 | 5527 | 5527-B01 | 35 SCHOOL RD | SHELBURNE | L9V3S5 | 35-11-43-402 | Shelburne | Shelburne T | Dufferin Co | DUFFERIN | Central | South | 44.0795 | -80.1911 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1212537 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212537 | 1212537 | 1212537 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-016 | 18-016 | 18 | N/A | 66117 | Upper Grand DSB | Centre Peel | Centre Peel Public Elementary School | ELE | 411 | 5570 | 5570-B01 | 7623 6TH LINE RR 2 | DRAYTON | N0G1P0 | 35-15-75-616 | Mapleton | Mapleton Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6871 | -80.6421 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 961961 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961961 | 961961 | 961961 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-018 | 18-018 | 18 | N/A | 66117 | Upper Grand DSB | Centre Wellington District | Centre Wellington District Public Secondary School | SEC | 10487 | 11128 | 11128-B01 | 905 SCOTLAND ST | FERGUS | N1M1Y7 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.7018 | -80.3562 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 23198295 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307831 | 307831 | 22890464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22890464 | 23198295 | 23198295 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-019 | 18-019 | 18 | N/A | 66117 | Upper Grand DSB | Credit Meadows | Credit Meadows Public Elementary School | ELE | 1713 | 6398 | 6398-B01 | 220 BLIND LINE | ORANGEVILLE | L9W4V2 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9221 | -80.1163 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 930824 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930824 | 930824 | 930824 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-021 | 18-021 | 18 | N/A | 66117 | Upper Grand DSB | Drayton Heights | Drayton Heights Public Elementary School | ELE | 627 | 5710 | 5710-B01 | 75 WELLINGTON ST S | DRAYTON | N0G1P0 | 35-15-75-616 | Mapleton | Mapleton Tp | Wellington Co | WELLINGTON | Southwest | South | 43.7514 | -80.674 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1931762 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1931762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1931762 | 1931762 | 1931762 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-023 | 18-023 | 18 | N/A | 66117 | Upper Grand DSB | École Arbour Vista | École Arbour Vista Public Elementary School | ELE | 24182 | 19174 | 19174-B01 | 200 MCCANN ST | GUELPH | N1G0C5 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.531 | -80.2029 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 449 | - | - | N | - | Not Required | - | 6989262 | Construction Complete | New Construction | Other | 2014-15 | 41884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250000 | 0 | 2739262 | 0 | 0 | 0 | 0 | 0 | 6989262 | 6989262 | 6989262 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 2739262
18-024 | 18-024 | 18 | N/A | 66117 | Upper Grand DSB | École Guelph Lake | École Guelph Lake Public Elementary School | ELE | 24469 | 19472 | 19472-B01 | 595 WATSON PKY N | GUELPH | N1E6X2 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5805 | -80.2263 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 541 | - | - | N | - | Approved | 42367 | 8844436 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425798 | 0 | 7418638 | 0 | 0 | 0 | 0 | 0 | 8844436 | 8844436 | 8844436 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 7418638
18-025 | 18-025 | 18 | N/A | 66117 | Upper Grand DSB | École Harris Mill | École Harris Mill Public Elementary School | ELE | 24218 | 19210 | 19210-B01 | 207 MACLENNAN ST RR 4 | ROCKWOOD | N0B2K0 | 35-15-75-615 | Guelph-Eramosa | Guelph/Eramosa Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6039 | -80.1368 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 320 | - | - | N | - | Not Required | - | 5887827 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742801 | 0 | 4145026 | 0 | 0 | 0 | 0 | 0 | 5887827 | 5887827 | 5887827 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 4145026
18-026 | 18-026 | 18 | N/A | 66117 | Upper Grand DSB | Edward Johnson | Edward Johnson Public Elementary School | ELE | 704 | 5764 | 5764-B01 | 397 STEVENSON ST N | GUELPH | N1E5C1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5657 | -80.2563 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1448352 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448352 | 1448352 | 1448352 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-028 | 18-028 | 18 | N/A | 66117 | Upper Grand DSB | Elora | Elora Public Elementary School | ELE | 739 | 5789 | 5789-B01 | 288 MILL ST E | ELORA | N0B1S0 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6879 | -80.4195 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3983333 | Construction Complete | Addition | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3983333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3983333 | 3983333 | 3983333 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-029 | 18-029 | 18 | N/A | 66117 | Upper Grand DSB | Elora | Elora Public Elementary School | ELE | 739 | 5789 | 5789-B01 | 288 MILL ST E | ELORA | N0B1S0 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6879 | -80.4195 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 474828 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474828 | 474828 | 474828 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-030 | 18-030 | 18 | N/A | 66117 | Upper Grand DSB | Eramosa | Eramosa Public Elementary School | ELE | 748 | 5794 | 5794-B01 | 5757 5TH LINE RR 1 | ROCKWOOD | N0B2K0 | 35-15-75-615 | Guelph-Eramosa | Guelph/Eramosa Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6834 | -80.235 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 459096 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459096 | 459096 | 459096 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-032 | 18-032 | 18 | N/A | 66117 | Upper Grand DSB | Erin District | Erin District Public Secondary School | SEC | 9987 | 5227 | 5227-B01 | 14 BOLAND DR SS 1 | ERIN | N0B1T0 | 35-15-75-405 | Erin | Erin T | Wellington Co | WELLINGTON | Southwest | South | 43.7787 | -80.0681 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17694539 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17694539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17694539 | 17694539 | 17694539 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-034 | 18-034 | 18 | N/A | 66117 | Upper Grand DSB | Gateway Drive | Gateway Drive Public Elementary School | ELE | 867 | 5864 | 5864-B01 | 33 GATEWAY DR | GUELPH | N1H6X1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5178 | -80.2753 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4259770 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4259770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4259770 | 4259770 | 4259770 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-035 | 18-035 | 18 | N/A | 66117 | Upper Grand DSB | Glenbrook | Glenbrook Public Elementary School | ELE | 24035 | 19157 | 19157-B01 | 300 FIDDLE PARK LANE | SHELBURNE | L9V3C9 | 35-11-43-402 | Shelburne | Shelburne T | Dufferin Co | DUFFERIN | Central | South | 44.0871 | -80.2023 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 449 | - | - | N | - | Not Required | - | 6720456 | Construction Complete | New Construction | Other | 2013-14 | 41519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3362591 | 0 | 3357865 | 0 | 0 | 0 | 0 | 0 | 6720456 | 6720456 | 6720456 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 3357865
18-036 | 18-036 | 18 | N/A | 66117 | Upper Grand DSB | Hyland Heights | Hyland Heights Public Elementary School | ELE | 939 | 5905 | 5905-B02 | 200 FOURTH AVE | SHELBURNE | L9V3R9 | 35-11-43-402 | Shelburne | Shelburne T | Dufferin Co | DUFFERIN | Central | South | 44.082 | -80.2098 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 733441 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733441 | 733441 | 733441 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-038 | 18-038 | 18 | N/A | 66117 | Upper Grand DSB | Island Lake | Island Lake Public Elementary School | ELE | 10489 | 11130 | 11130-B01 | 50 OAK RIDGE DR | ORANGEVILLE | L9W5J6 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9216 | -80.076 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5493296 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5493296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5493296 | 5493296 | 5493296 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-039 | 18-039 | 18 | N/A | 66117 | Upper Grand DSB | Island Lake | Island Lake Public Elementary School | ELE | 10489 | 11130 | 11130-B01 | 50 OAK RIDGE DR | ORANGEVILLE | L9W5J6 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9216 | -80.076 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 792614 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 392614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392614 | 792614 | 792614 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-041 | 18-041 | 18 | N/A | 66117 | Upper Grand DSB | J Douglas Hogarth | J Douglas Hogarth Public Elementary School | ELE | 1192 | 6062 | 6062-B01 | 360 BELSYDE AVE E | FERGUS | N1M1Z5 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.703 | -80.3666 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 907101 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907101 | 907101 | 907101 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-044 | 18-044 | 18 | N/A | 66117 | Upper Grand DSB | Jean Little | Jean Little Public Elementary School | ELE | 1191 | 6061 | 6061-B01 | 56 YOUNGMAN DR | GUELPH | N1G4L2 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5193 | -80.2259 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 948395 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948395 | 948395 | 948395 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-046 | 18-046 | 18 | N/A | 66117 | Upper Grand DSB | John Black | John Black Public Elementary School | ELE | 868 | 5865 | 5865-B01 | 150 LAMOND ST | FERGUS | N1M2A1 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.7145 | -80.3614 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16900 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16900 | 16900 | 16900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-047 | 18-047 | 18 | N/A | 66117 | Upper Grand DSB | John Galt | John Galt Public Elementary School | ELE | 24057 | 6157 | 6157-B02 | 50 LAURINE AVE | GUELPH | N1E4M9 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5564 | -80.2434 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 380 | - | - | N | - | Not Required | - | 6469776 | Construction Complete | New Construction | Other | 2013-14 | 41519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6469776 | 0 | 0 | 0 | 0 | 0 | 6469776 | 6469776 | 6469776 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 6469776
18-048 | 18-048 | 18 | N/A | 66117 | Upper Grand DSB | John McCrae | John McCrae Public Elementary School | ELE | 11202 | 6071 | 6071-B01 | 189 WATER ST | GUELPH | N1G1B3 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5347 | -80.2475 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 50700 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50700 | 50700 | 50700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-049 | 18-049 | 18 | N/A | 66117 | Upper Grand DSB | John McCrae | John McCrae Public Elementary School | ELE | 11202 | 6071 | 6071-B01 | 189 WATER ST | GUELPH | N1G1B3 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5347 | -80.2475 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6672607 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6672607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6672607 | 6672607 | 6672607 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-051 | 18-051 | 18 | N/A | 66117 | Upper Grand DSB | June Avenue | June Avenue Public Elementary School | ELE | 1232 | 6085 | 6085-B01 | 30 JUNE AVE | GUELPH | N1H1H6 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5551 | -80.2752 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2487125 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487125 | 2487125 | 2487125 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-052 | 18-052 | 18 | N/A | 66117 | Upper Grand DSB | Ken Danby | Ken Danby Public Elementary School | ELE | 10641 | 11200 | 11200-B01 | 525 GRANGE RD | GUELPH | N1E7C4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5706 | -80.2216 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6726233 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5093543 | 5093543 | 1632690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1632690 | 6726233 | 6726233 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-054 | 18-054 | 18 | N/A | 66117 | Upper Grand DSB | Kenilworth | Kenilworth Public Elementary School | ELE | 1248 | 6093 | 6093-B01 | 7478 SIDEROAD 7 RR 4 | KENILWORTH | N0G2E0 | 35-15-75-617 | Wellington North | Wellington North Tp | Wellington Co | WELLINGTON | Southwest | South | 43.8971 | -80.6329 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 485260 | Construction Complete | Retrofit | Accommodation Pressure | 2016-17 | 42619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25859 | 0 | 459401 | 0 | 0 | 0 | 0 | 0 | 485260 | 485260 | 485260 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 459401
18-055 | 18-055 | 18 | N/A | 66117 | Upper Grand DSB | École King George | École King George Public Elementary School | ELE | 15532 | 6111 | 6111-B02 | 72 LEMON ST | GUELPH | N1E2H5 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5546 | -80.2469 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 481 | - | - | N | - | Not Required | - | 8339775 | Construction Complete | New Construction | Other | 2012-13 | 41155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3480000 | 0 | 4859775 | 0 | 0 | 0 | 0 | 0 | 8339775 | 8339775 | 8339775 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 4859775
18-056 | 18-056 | 18 | N/A | 66117 | Upper Grand DSB | Kortright Hills | Kortright Hills Public Elementary School | ELE | 10185 | 10452 | 10452-B01 | 23 PTARMIGAN DR | GUELPH | N1C1B5 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.4999 | -80.2405 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6472025 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6472025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6472025 | 6472025 | 6472025 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-059 | 18-059 | 18 | N/A | 66117 | Upper Grand DSB | Minto-Clifford | Minto-Clifford Public Elementary School | ELE | 1553 | 6297 | 6297-B01 | 5804 HIGHWAY 89 RR 1 | HARRISTON | N0G1Z0 | 35-15-75-406 | Minto | Minto T | Wellington Co | WELLINGTON | Southwest | South | 43.9179 | -80.8676 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4104714 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4104714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4104714 | 4104714 | 4104714 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-060 | 18-060 | 18 | N/A | 66117 | Upper Grand DSB | Minto-Clifford | Minto-Clifford Public Elementary School | ELE | 1553 | 6297 | 6297-B01 | 5804 HIGHWAY 89 RR 1 | HARRISTON | N0G1Z0 | 35-15-75-406 | Minto | Minto T | Wellington Co | WELLINGTON | Southwest | South | 43.9179 | -80.8676 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 16900 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16900 | 16900 | 16900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-062 | 18-062 | 18 | N/A | 66117 | Upper Grand DSB | Mitchell Woods | Mitchell Woods Public Elementary School | ELE | 9359 | 10131 | 10131-B01 | 670 WILLOW RD | GUELPH | N1H8K2 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5276 | -80.2942 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8446605 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8446605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8446605 | 8446605 | 8446605 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-064 | 18-064 | 18 | N/A | 66117 | Upper Grand DSB | Mono-Amaranth | Mono-Amaranth Public Elementary School | ELE | 11135 | 6302 | 6302-B01 | 246303 HOCKLEY RD | MONO | L9W6K4 | 35-11-43-403 | Mono | Mono T | Dufferin Co | DUFFERIN | Central | South | 43.9475 | -80.1004 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3022576 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3022576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3022576 | 3022576 | 3022576 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-066 | 18-066 | 18 | N/A | 66117 | Upper Grand DSB | Montgomery Village | Montgomery Village Public Elementary School | ELE | 10388 | 6227 | 6227-B01 | 70 MONTGOMERY BLVD | ORANGEVILLE | L9W5H6 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9074 | -80.1263 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5199429 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5199429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5199429 | 5199429 | 5199429 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-067 | 18-067 | 18 | N/A | 66117 | Upper Grand DSB | Montgomery Village | Montgomery Village Public Elementary School | ELE | 10388 | 6227 | 6227-B01 | 70 MONTGOMERY BLVD | ORANGEVILLE | L9W5H6 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9074 | -80.1263 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 562965 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562965 | 562965 | 562965 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-070 | 18-070 | 18 | N/A | 66117 | Upper Grand DSB | Paisley Road | Paisley Road Public Elementary School | ELE | 1745 | 6418 | 6418-B01 | 406 PAISLEY RD | GUELPH | N1H2R3 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5378 | -80.2667 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 423759 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423759 | 423759 | 423759 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-072 | 18-072 | 18 | N/A | 66117 | Upper Grand DSB | Palmerston | Palmerston Public Elementary School | ELE | 1752 | 6423 | 6423-B01 | 530 PROSPECT ST | PALMERSTON | N0G2P0 | 35-15-75-406 | Minto | Minto T | Wellington Co | WELLINGTON | Southwest | South | 43.8308 | -80.8433 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 536966 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536966 | 536966 | 536966 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-074 | 18-074 | 18 | N/A | 66117 | Upper Grand DSB | Parkinson Centennial | Parkinson Centennial Public Elementary School | ELE | 1766 | 6429 | 6429-B01 | 120 LAWRENCE AVE | ORANGEVILLE | L9W1S8 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9095 | -80.104 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2186780 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2186780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2186780 | 2186780 | 2186780 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-077 | 18-077 | 18 | N/A | 66117 | Upper Grand DSB | Primrose | Primrose Public Elementary School | ELE | 1856 | 6491 | 6491-B01 | 636064 PRINCE OF WALES RD | MULMUR | L9V0B8 | 35-11-43-606 | Mulmur | Mulmur Tp | Dufferin Co | DUFFERIN | Central | South | 44.0973 | -80.1411 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 521682 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521682 | 521682 | 521682 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-079 | 18-079 | 18 | N/A | 66117 | Upper Grand DSB | Princess Elizabeth | Princess Elizabeth Public Elementary School | ELE | 1883 | 6513 | 6513-B01 | 51 ELIZABETH ST | ORANGEVILLE | L9W1C5 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.92 | -80.106 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2228000 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228000 | 2228000 | 2228000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-081 | 18-081 | 18 | N/A | 66117 | Upper Grand DSB | Princess Margaret | Princess Margaret Public Elementary School | ELE | 10451 | 11109 | 11109-B01 | 51 WELLINGTON ST | ORANGEVILLE | L9W2L6 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9151 | -80.0904 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5096353 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22478 | 22478 | 5073875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5073875 | 5096353 | 5096353 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-082 | 18-082 | 18 | N/A | 66117 | Upper Grand DSB | Rickson Ridge | Rickson Ridge Public Elementary School | ELE | 10642 | 11201 | 11201-B01 | 177 RICKSON AVE | GUELPH | N1G4Y6 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5132 | -80.2128 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6899071 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899071 | 6899071 | 6899071 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-084 | 18-084 | 18 | N/A | 66117 | Upper Grand DSB | Rockwood Centennial | Rockwood Centennial Public Elementary School | ELE | 2020 | 6603 | 6603-B01 | 157 PASMORE ST RR 1 | ROCKWOOD | N0B2K0 | 35-15-75-615 | Guelph-Eramosa | Guelph/Eramosa Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6144 | -80.1461 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1898179 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898179 | 1898179 | 1898179 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-088 | 18-088 | 18 | N/A | 66117 | Upper Grand DSB | Sir Isaac Brock | Sir Isaac Brock Public Elementary School | ELE | 10413 | 11106 | 11106-B01 | 111 COLONIAL DR | GUELPH | N1L1R3 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.52 | -80.1852 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4668599 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4668599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4668599 | 4668599 | 4668599 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-089 | 18-089 | 18 | N/A | 66117 | Upper Grand DSB | Sir Isaac Brock | Sir Isaac Brock Public Elementary School | ELE | 10413 | 11106 | 11106-B01 | 111 COLONIAL DR | GUELPH | N1L1R3 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.52 | -80.1852 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1543320 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1543320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1543320 | 1543320 | 1543320 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-091 | 18-091 | 18 | N/A | 66117 | Upper Grand DSB | Spencer Avenue | Spencer Avenue Public Elementary School | ELE | 24183 | 19175 | 19175-B01 | 15 SPENCER AVE | ORANGEVILLE | L9W5E6 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.8979 | -80.1282 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 308 | - | - | N | - | Not Required | - | 6518205 | Construction Complete | New Construction | Other | 2014-15 | 41884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4056589 | 0 | 2461616 | 0 | 0 | 0 | 0 | 0 | 6518205 | 6518205 | 6518205 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 2461616
18-092 | 18-092 | 18 | N/A | 66117 | Upper Grand DSB | Spencer Avenue | Spencer Avenue Public Elementary School | ELE | 24183 | 19175 | 19175-B01 | 15 SPENCER AVE | ORANGEVILLE | L9W5E6 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.8979 | -80.1282 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 230 | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43345 | 0 | 0 | 2219469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2219469 | 0 | 0 | 475266 | 0 | 2092721 | 0 | 0 | 0 | 0 | 0 | 2567987 | 4787456 | 4787456 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 2092721
18-093 | 18-093 | 18 | N/A | 66117 | Upper Grand DSB | Taylor Evans | Taylor Evans Public Elementary School | ELE | 2281 | 6761 | 6761-B01 | 271 STEPHANIE DR | GUELPH | N1K1T1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5225 | -80.2775 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 420634 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420634 | 420634 | 420634 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-095 | 18-095 | 18 | N/A | 66117 | Upper Grand DSB | Victoria Cross | Victoria Cross Public Elementary School | ELE | 5531 | 5073 | 5073-B01 | 355 DURHAM ST W | MOUNT FOREST | N0G2L1 | 35-15-75-617 | Wellington North | Wellington North Tp | Wellington Co | WELLINGTON | Southwest | South | 43.9817 | -80.7428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3558717 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3558717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3558717 | 3558717 | 3558717 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-100 | 18-100 | 18 | N/A | 66117 | Upper Grand DSB | Wellington Heights | Wellington Heights Public Secondary School | SEC | 10488 | 11129 | 11129-B01 | 405 SLIGO RD E | MOUNT FOREST | N0G2L2 | 35-15-75-617 | Wellington North | Wellington North Tp | Wellington Co | WELLINGTON | Southwest | South | 43.9909 | -80.7361 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10778367 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10778367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10778367 | 10778367 | 10778367 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-101 | 18-101 | 18 | N/A | 66117 | Upper Grand DSB | Westminster Woods | Westminster Woods Public Elementary School | ELE | 11192 | 12221 | 12221-B01 | 140 GOODWIN DR | GUELPH | N1L0G7 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5099 | -80.1798 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6823825 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6823825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6823825 | 6823825 | 6823825 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-103 | 18-103 | 18 | N/A | 66117 | Upper Grand DSB | Westside | Westside Public Secondary School | SEC | 9431 | 10166 | 10166-B01 | 300 ALDER ST | ORANGEVILLE | L9W5A2 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9062 | -80.1238 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 840000 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840000 | 840000 | 840000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-104 | 18-104 | 18 | N/A | 66117 | Upper Grand DSB | Westwood | Westwood Public Elementary School | ELE | 2483 | 6895 | 6895-B01 | 495 WILLOW RD | GUELPH | N1H7C7 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5341 | -80.2879 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 786142 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172467 | 172467 | 613675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613675 | 786142 | 786142 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-106 | 18-106 | 18 | N/A | 66117 | Upper Grand DSB | William C Winegard | William C Winegard Public Elementary School | ELE | 24034 | 19156 | 19156-B01 | 25 LEE ST | GUELPH | N1E7E7 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5642 | -80.2199 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 510 | - | - | N | - | Not Required | - | 7365710 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865746 | 0 | 5499964 | 0 | 0 | 0 | 0 | 0 | 7365710 | 7365710 | 7365710 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 5499964
18-107 | 18-107 | 18 | N/A | 66117 | Upper Grand DSB | Willow Road | Willow Road Public Elementary School | ELE | 2515 | 6910 | 6910-B01 | 125 WILLOW RD | GUELPH | N1H1W4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5438 | -80.2773 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4735105 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4735105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4735105 | 4735105 | 4735105 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-108 | 18-108 | 18 | N/A | 66117 | Upper Grand DSB | Willow Road | Willow Road Public Elementary School | ELE | 2515 | 6910 | 6910-B01 | 125 WILLOW RD | GUELPH | N1H1W4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5438 | -80.2773 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 500628 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500628 | 500628 | 500628 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
18-109 | 18-109 | 18 | 225 - CMSM Wellington | 66117 | Upper Grand DSB | Palmerston | Palmerston Public Elementary School | ELE | 1752 | 6423 | 6423-B01 | 530 PROSPECT ST | PALMERSTON | N0G2P0 | 35-15-75-406 | Minto | Minto T | Wellington Co | WELLINGTON | Southwest | South | 43.8308 | -80.8433 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 43717 | 1772476 | Construction Complete | Addition | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 1732476 | 0 | 0 | 0 | 1732476 | 1772476 | 1579018 | -193458 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1732476
18-110 | 18-110 | 18 | 214 - CMSM Dufferin | 66117 | Upper Grand DSB | Centennial Hylands | Centennial Hylands Public Elementary School | ELE | 361 | 5527 | 5527-B01 | 35 SCHOOL RD | SHELBURNE | L9V3S5 | 35-11-43-402 | Shelburne | Shelburne T | Dufferin Co | DUFFERIN | Central | South | 44.0795 | -80.1911 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 4 | 73 | N | - | Approved | 42844 | 2056222 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056222 | 0 | 0 | 0 | 2056222 | 2056222 | 2056222 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2056222
18-111 | 18-111 | 18 | 225 - CMSM Wellington | 66117 | Upper Grand DSB | Erin | Erin Public Elementary School | ELE | 5353 | 5181 | 5181-B01 | 185 DANIEL ST SS 1 | ERIN | N0B1T0 | 35-15-75-405 | Erin | Erin T | Wellington Co | WELLINGTON | Southwest | South | 43.7749 | -80.0676 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | Y | 1 | Approved | 43717 | 1083591 | Construction Complete | Addition | Child Care | 2018-19 | 43437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823943 | 259648 | 0 | 0 | 1083591 | 1083591 | 1277049 | 193458 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1083591
18-112 | 18-112 | 18 | 225 - CMSM Wellington | 66117 | Upper Grand DSB | Rockwood Centennial | Rockwood Centennial Public Elementary School | ELE | 2020 | 6603 | 6603-B01 | 157 PASMORE ST RR 1 | ROCKWOOD | N0B2K0 | 35-15-75-615 | Guelph-Eramosa | Guelph/Eramosa Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6144 | -80.1461 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557886 | 519296 | 0 | 0 | 2077182 | 2077182 | 0 | -2077182 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2077182
18-113 | 18-113 | 18 | N/A | 66117 | Upper Grand DSB | Guelph | Guelph Public Secondary School | SEC | 24835 | 19841 | 19841-B01 | 388 ARKELL RD | GUELPH | N1L1E6 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5248 | -80.1884 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 900 | - | - | N | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25505658 | 0 | 0 | 0 | 0 | 0 | 25505658 | 25505658 | 25505658 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 25505658
18-114 | 18-114 | 18 | N/A | 66117 | Upper Grand DSB | Hyland Heights | Hyland Heights Public Elementary School | ELE | 939 | 5905 | 5905-B02 | 200 FOURTH AVE | SHELBURNE | L9V3R9 | 35-11-43-402 | Shelburne | Shelburne T | Dufferin Co | DUFFERIN | Central | South | 44.0824 | -80.2112 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 92 | - | - | - | - | Approved | 44679 | 3262001 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44927 | 620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620000 | 0 | 0 | 0 | 0 | 2642001 | 0 | 0 | 0 | 0 | 0 | 2642001 | 3262001 | 3262001 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2642001
18-115 | 18-115 | 18 | N/A | 66117 | Upper Grand DSB | Centre Wellington | Centre Wellington Public Elementary School | ELE | TBD | TBD | TBD | COLBORNE ST / BEATTY LINE N | FERGUS | TBD | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.7041 | -80.395 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 308 | - | - | N | - | Approved | 45184 | 16724312 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16724312 | 0 | 0 | 0 | 0 | 0 | 16724312 | 16724312 | 8460434 | -8263878 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 16724312
19-001 | 19-001 | 19 | N/A | 66125 | Peel DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18304 | 19060 | 19060-B01 | 5650 HURONTARIO ST | MISSISSAUGA | L5R1C6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.618 | -79.6707 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9407 | 0 | 0 | 0 | 9407 | 9407 | 0 | -9407 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | NO | YES | 9407
19-002 | 19-002 | 19 | N/A | 66125 | Peel DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18304 | 19060 | 19060-B01 | 5650 HURONTARIO ST | MISSISSAUGA | L5R1C6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.618 | -79.6707 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 94790971 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91906588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91906588 | 91906588 | 95825357 | 3918769 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-003 | 19-003 | 19 | N/A | 66125 | Peel DSB | Agnes Taylor | Agnes Taylor Public Elementary School | ELE | 31 | 5319 | 5319-B01 | 80 BEECH ST | BRAMPTON | L6V1V6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6977 | -79.7573 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4173443 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173443 | 4173443 | 4173443 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-004 | 19-004 | 19 | N/A | 66125 | Peel DSB | Allan A Martin Senior | Allan A Martin Senior Public Elementary School | ELE | 58 | 5334 | 5334-B03 | 1390 OGDEN AVE | MISSISSAUGA | L5E2H8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5844 | -79.5695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 194103 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194103 | 194103 | 194103 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-005 | 19-005 | 19 | N/A | 66125 | Peel DSB | Allan Drive | Allan Drive Public Elementary School | ELE | 9921 | 10329 | 10329-B01 | 254 ALLAN DR | BOLTON | L7E1R9 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8781 | -79.7202 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7418816 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133519 | 133519 | 7285297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7285297 | 7418816 | 7418816 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-006 | 19-006 | 19 | N/A | 66125 | Peel DSB | Alloa | Alloa Public Elementary School | ELE | 24145 | 19166 | 19166-L01 | 12287 MISSISSAUGA RD | CALEDON | L7C1X1 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.7018 | -79.874 | 41156 | 2011-12 | 2012-13 | 41156 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1094082 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094082 | 0 | 0 | 0 | 0 | 0 | 0 | 1094082 | 1094082 | 1094082 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1094082
19-007 | 19-007 | 19 | N/A | 66125 | Peel DSB | Alloa | Alloa Public Elementary School | ELE | 24145 | 19166 | 19166-B01 | 12287 MISSISSAUGA RD | CALEDON | L7C1X1 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.7018 | -79.874 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 625 | - | - | N | - | Not Required | - | 14437303 | Construction Complete | New Construction | Condition | 2015-16 | 42251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13187303 | 0 | 0 | 0 | 0 | 0 | 13187303 | 13187303 | 13437303 | 250000 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 13187303
19-008 | 19-008 | 19 | N/A | 66125 | Peel DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18304 | 19060 | 19060-B01 | 5650 HURONTARIO ST | MISSISSAUGA | L5R1C6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.618 | -79.6707 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4555851 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4555851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4555851 | 4555851 | 4555851 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-009 | 19-009 | 19 | N/A | 66125 | Peel DSB | Alton | Alton Public Elementary School | ELE | 24322 | 5486 | 5486-B02 | 19681 MAIN ST | ALTON | L7K0E1 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8579 | -80.0652 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 245 | - | - | N | - | Not Required | - | 9500000 | Construction Complete | New Construction | Other | 2013-14 | 41641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8978491 | 0 | 0 | 0 | 0 | 0 | 8978491 | 8978491 | 9208491 | 230000 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 8978491
19-010 | 19-010 | 19 | N/A | 66125 | Peel DSB | Arnott Charlton | Arnott Charlton Public Elementary School | ELE | 97 | 5356 | 5356-B01 | 140 WINTERFOLD DR | BRAMPTON | L6V3V8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7148 | -79.7677 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7868438 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7868438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7868438 | 7868438 | 7868438 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-011 | 19-011 | 19 | N/A | 66125 | Peel DSB | Artesian Drive | Artesian Drive Public Elementary School | ELE | 10598 | 11202 | 11202-B01 | 3325 ARTESIAN DR | MISSISSAUGA | L5M7J8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.543 | -79.7188 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7173662 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7173662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7173662 | 7173662 | 7173662 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-013 | 19-013 | 19 | N/A | 66125 | Peel DSB | Aylesbury | Aylesbury Public Elementary School | ELE | 24377 | 19378 | 19378-B01 | 25 AYLESBURY DR | BRAMPTON | L7A0V3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6781 | -79.832 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 850 | - | - | N | - | Not Required | - | 14847049 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42251 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 500000 | 0 | 12571870 | 0 | 0 | 0 | 0 | 0 | 13071870 | 13171870 | 14847049 | 1675179 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12571870
19-014 | 19-014 | 19 | N/A | 66125 | Peel DSB | Balmoral Drive Senior | Balmoral Drive Senior Public Elementary School | ELE | 121 | 5375 | 5375-B01 | 233 BALMORAL DR | BRAMPTON | L6T1V5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7089 | -79.7119 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2044598 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044598 | 2044598 | 2044598 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-015 | 19-015 | 19 | N/A | 66125 | Peel DSB | Barondale | Barondale Public Elementary School | ELE | 6080 | 8559 | 8559-B01 | 200 BARONDALE DR | MISSISSAUGA | L4Z3N7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6189 | -79.6607 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 165 | - | - | N | - | Approved | 43509 | 2376175 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2376175 | 0 | 0 | 0 | 0 | 0 | 2376175 | 2376175 | 2376175 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 2376175
19-016 | 19-016 | 19 | N/A | 66125 | Peel DSB | Beatty-Fleming Senior | Beatty-Fleming Senior Public Elementary School | ELE | 156 | 5397 | 5397-B01 | 21 CAMPBELL DR | BRAMPTON | L6X2H6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.679 | -79.7784 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3236236 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3236236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3236236 | 3236236 | 3236236 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-017 | 19-017 | 19 | N/A | 66125 | Peel DSB | Belfountain | Belfountain Public Elementary School | ELE | 164 | 5402 | 5402-B01 | 17247 SHAWS CREEK RD | BELFOUNTAIN | L7K0E8 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.7884 | -80.0183 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2713892 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713892 | 2713892 | 2713892 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-019 | 19-019 | 19 | N/A | 66125 | Peel DSB | Beryl Ford | Beryl Ford Public Elementary School | ELE | 14542 | 18028 | 18028-B01 | 45 IRONSHIELD DR | BRAMPTON | L6P3N5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7903 | -79.6694 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 772 | - | - | N | - | Approved | 43509 | 11674957 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896051 | 0 | 10778906 | 0 | 0 | 0 | 0 | 0 | 11674957 | 11674957 | 11674957 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 10778906
19-021 | 19-021 | 19 | N/A | 66125 | Peel DSB | Bramalea | Bramalea Public Secondary School | SEC | 5241 | 8138 | 8138-B01 | 510 BALMORAL DR | BRAMPTON | L6T1W4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7155 | -79.7075 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4733250 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4733250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4733250 | 4733250 | 4733250 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-022 | 19-022 | 19 | N/A | 66125 | Peel DSB | Bramalea | Bramalea Public Secondary School | SEC | 5241 | 8138 | 8138-B01 | 510 BALMORAL DR | BRAMPTON | L6T1W4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7155 | -79.7075 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2200000 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 2200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-023 | 19-023 | 19 | N/A | 66125 | Peel DSB | Brampton Centennial | Brampton Centennial Public Secondary School | SEC | 5242 | 8139 | 8139-B01 | 251 MCMURCHY AVE S | BRAMPTON | L6Y1Z4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6669 | -79.7483 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 825289 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825289 | 825289 | 825289 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-024 | 19-024 | 19 | N/A | 66125 | Peel DSB | Brandon Gate | Brandon Gate Public Elementary School | ELE | 227 | 5439 | 5439-B01 | 3800 BRANDON GATE DR | MISSISSAUGA | L4T3V9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.7326 | -79.6414 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1683119 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683119 | 1683119 | 1683119 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-025 | 19-025 | 19 | N/A | 66125 | Peel DSB | Brian W Fleming | Brian W Fleming Public Elementary School | ELE | 1034 | 5977 | 5977-B01 | 3255 HAVENWOOD DR | MISSISSAUGA | L4X2M2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6182 | -79.587 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6375846 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375846 | 6375846 | 6375846 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-026 | 19-026 | 19 | N/A | 66125 | Peel DSB | Briarwood | Briarwood Public Elementary School | ELE | 240 | 5447 | 5447-B01 | 1065 MISSISSAUGA VALLEY BLVD | MISSISSAUGA | L5A2A1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6022 | -79.6197 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2464664 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464664 | 2464664 | 2464664 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-028 | 19-028 | 19 | N/A | 66125 | Peel DSB | Brisdale | Brisdale Public Elementary School | ELE | 10597 | 11203 | 11203-B01 | 370 BRISDALE DR | BRAMPTON | L7A3K7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6977 | -79.8364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8115925 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516050 | 516050 | 7599875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7599875 | 8115925 | 8115925 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-029 | 19-029 | 19 | N/A | 66125 | Peel DSB | Brisdale | Brisdale Public Elementary School | ELE | 10597 | 11203 | 11203-B01 | 370 BRISDALE DR | BRAMPTON | L7A3K7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6977 | -79.8364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3446752 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446752 | 3446752 | 3446752 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-031 | 19-031 | 19 | N/A | 66125 | Peel DSB | Bristol Road | Bristol Road Public Elementary School | ELE | 9918 | 10326 | 10326-B01 | 210 BRISTOL RD E | MISSISSAUGA | L4Z3V5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6158 | -79.6549 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7492338 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232834 | 232834 | 7259504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7259504 | 7492338 | 7492338 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-032 | 19-032 | 19 | N/A | 66125 | Peel DSB | Britannia | Britannia Public Elementary School | ELE | 9770 | 10254 | 10254-B01 | 1145 SWINBOURNE DR | MISSISSAUGA | L5V1C2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6066 | -79.7074 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6099381 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278234 | 278234 | 5821147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5821147 | 6099381 | 6099381 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-033 | 19-033 | 19 | N/A | 66125 | Peel DSB | Britannia | Britannia Public Elementary School | ELE | 9770 | 10254 | 10254-B01 | 1145 SWINBOURNE DR | MISSISSAUGA | L5V1C2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6066 | -79.7074 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5455955 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5455955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5455955 | 5455955 | 5455955 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-034 | 19-034 | 19 | N/A | 66125 | Peel DSB | Brookmede | Brookmede Public Elementary School | ELE | 263 | 5462 | 5462-B01 | 2250 COUNCIL RING RD | MISSISSAUGA | L5L1B7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5376 | -79.6757 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2470831 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2470831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2470831 | 2470831 | 2470831 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-035 | 19-035 | 19 | N/A | 66125 | Peel DSB | Brookmede | Brookmede Public Elementary School | ELE | 263 | 5462 | 5462-B01 | 2250 COUNCIL RING RD | MISSISSAUGA | L5L1B7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5376 | -79.6757 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6777679 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 6777679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6777679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6777679 | 6777679 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-036 | 19-036 | 19 | N/A | 66125 | Peel DSB | Burnt Elm | Burnt Elm Public Elementary School | ELE | 10138 | 10419 | 10419-B01 | 85 BURNT ELM DR | BRAMPTON | L7A1T8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7185 | -79.8184 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7218655 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166840 | 166840 | 7051815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7051815 | 7218655 | 7218655 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-037 | 19-037 | 19 | N/A | 66125 | Peel DSB | Burnt Elm | Burnt Elm Public Elementary School | ELE | 10138 | 10419 | 10419-B01 | 85 BURNT ELM DR | BRAMPTON | L7A1T8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7185 | -79.8184 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4126796 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4126796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4126796 | 4126796 | 4126796 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-039 | 19-039 | 19 | N/A | 66125 | Peel DSB | Calderstone | Calderstone Public Elementary School | ELE | 10719 | 11209 | 11209-B01 | 160 CALDERSTONE RD | BRAMPTON | L6P2L7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7722 | -79.6926 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8347687 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53553 | 53553 | 8294134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8294134 | 8347687 | 8347687 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-040 | 19-040 | 19 | N/A | 66125 | Peel DSB | Caledon Central | Caledon Central Public Elementary School | ELE | 302 | 5484 | 5484-B01 | 18357 KENNEDY RD | CALEDON VILLAGE | L7K1Y7 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8711 | -79.9833 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1519090 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519090 | 1519090 | 1519090 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-041 | 19-041 | 19 | N/A | 66125 | Peel DSB | Caledon Central | Caledon Central Public Elementary School | ELE | 302 | 5484 | 5484-B01 | 18357 KENNEDY RD | CALEDON VILLAGE | L7K1Y7 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8711 | -79.9833 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Demolition | Consolidation | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 0
19-042 | 19-042 | 19 | N/A | 66125 | Peel DSB | Caledon East | Caledon East Public Elementary School | ELE | 303 | 5485 | 5485-B01 | 15738 AIRPORT RD | CALEDON EAST | L7C2W8 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8634 | -79.8618 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2081192 | Construction Complete | Addition | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081192 | 2081192 | 2081192 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-044 | 19-044 | 19 | N/A | 66125 | Peel DSB | Camilla Road | Camilla Road Public Elementary School | ELE | 317 | 5494 | 5494-B02 | 201 CHERRY POST DR | MISSISSAUGA | L5A1J1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5775 | -79.6005 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2711541 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2711541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2711541 | 2711541 | 2711541 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-045 | 19-045 | 19 | N/A | 66125 | Peel DSB | Carberry | Carberry Public Elementary School | ELE | 10980 | 12124 | 12124-B01 | 526 FERNFOREST DR | BRAMPTON | L6R0W1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7568 | -79.7741 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9865530 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114152 | 114152 | 9751378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9751378 | 9865530 | 9865530 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-047 | 19-047 | 19 | N/A | 66125 | Peel DSB | Cashmere Avenue | Cashmere Avenue Public Elementary School | ELE | 399 | 5562 | 5562-B01 | 2455 CASHMERE AVE | MISSISSAUGA | L5B2M7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.565 | -79.626 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1518583 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1518583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1518583 | 1518583 | 1518583 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-049 | 19-049 | 19 | N/A | 66125 | Peel DSB | Castle Oaks | Castle Oaks Public Elementary School | ELE | 24343 | 19341 | 19341-B01 | 155 CASTLE OAKS CROSS | BRAMPTON | L6P3V4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7946 | -79.6712 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 850 | - | - | N | - | Approved | 44678 | 12831641 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 500000 | 0 | 12104671 | 0 | 0 | 0 | 0 | 0 | 12604671 | 12704671 | 12831641 | 126970 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12104671
19-050 | 19-050 | 19 | N/A | 66125 | Peel DSB | Castlebridge | Castlebridge Public Elementary School | ELE | 9779 | 10263 | 10263-B01 | 2801 CASTLEBRIDGE DR | MISSISSAUGA | L5M5J9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.568 | -79.7329 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5960000 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5960000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5960000 | 5960000 | 5960000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-051 | 19-051 | 19 | N/A | 66125 | Peel DSB | Castlebrooke | Castlebrooke Public Secondary School | SEC | 11015 | 12277 | 12277-B01 | 10 GARDENBROOKE TRAIL | BRAMPTON | L6P3L1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7843 | -79.6772 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 1533 | - | - | N | - | Approved | 43509 | 32422562 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32422562 | 0 | 0 | 0 | 0 | 0 | 32422562 | 32422562 | 32422562 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 32422562
19-052 | 19-052 | 19 | N/A | 66125 | Peel DSB | Castlemore | Castlemore Public Elementary School | ELE | 338 | 5510 | 5510-B01 | 9916 THE GORE RD | BRAMPTON | L6P0A7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7899 | -79.6881 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10861784 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52365 | 52365 | 10809419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10809419 | 10861784 | 10861784 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-053 | 19-053 | 19 | N/A | 66125 | Peel DSB | Centennial Senior | Centennial Senior Public Elementary School | ELE | 2087 | 6645 | 6645-B01 | 50 LADORE DR | BRAMPTON | L6Y1V5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6726 | -79.749 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1178613 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178613 | 1178613 | 1178613 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-054 | 19-054 | 19 | N/A | 66125 | Peel DSB | Centennial Senior | Centennial Senior Public Elementary School | ELE | 2087 | 6645 | 6645-B01 | 50 LADORE DR | BRAMPTON | L6Y1V5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6726 | -79.749 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5573368 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5573368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5573368 | 5573368 | 5573368 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-055 | 19-055 | 19 | N/A | 66125 | Peel DSB | Champlain Trail | Champlain Trail Public Elementary School | ELE | 342 | 5514 | 5514-B01 | 895 CEREMONIAL DR | MISSISSAUGA | L5R3B5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6036 | -79.6785 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1066200 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066200 | 1066200 | 1066200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-056 | 19-056 | 19 | N/A | 66125 | Peel DSB | Champlain Trail | Champlain Trail Public Elementary School | ELE | 342 | 5514 | 5514-B01 | 895 CEREMONIAL DR | MISSISSAUGA | L5R3B5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6036 | -79.6785 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5966461 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5966461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5966461 | 5966461 | 5966461 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-057 | 19-057 | 19 | N/A | 66125 | Peel DSB | Cherrytree | Cherrytree Public Elementary School | ELE | 436 | 5586 | 5586-B01 | 155 CHERRYTREE DR | BRAMPTON | L6Y3M9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6542 | -79.7249 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2323048 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2323048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2323048 | 2323048 | 2323048 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-059 | 19-059 | 19 | N/A | 66125 | Peel DSB | Cherrytree | Cherrytree Public Elementary School | ELE | 436 | 5586 | 5586-B01 | 155 CHERRYTREE DR | BRAMPTON | L6Y3M9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6542 | -79.7249 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2379954 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154476 | 0 | 2225478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2379954 | 2379954 | 2379954 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-060 | 19-060 | 19 | N/A | 66125 | Peel DSB | Cheyne | Cheyne Public Elementary School | ELE | 10646 | 11218 | 11218-B01 | 236 QUEEN MARY DR | BRAMPTON | L7A3L3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7057 | -79.8178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11000704 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95826 | 95826 | 10904878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10904878 | 11000704 | 11000704 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-061 | 19-061 | 19 | N/A | 66125 | Peel DSB | Chinguacousy | Chinguacousy Public Secondary School | SEC | 5281 | 8166 | 8166-B01 | 1370 WILLIAMS PKY | BRAMPTON | L6S1V3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7374 | -79.7283 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7252744 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7252744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7252744 | 7252744 | 7252744 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-062 | 19-062 | 19 | N/A | 66125 | Peel DSB | Chris Hadfield | Chris Hadfield Public Elementary School | ELE | 24226 | 19218 | 19218-B01 | 465 FAIRVIEW RD W | MISSISSAUGA | L5B3W7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5775 | -79.6351 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 615 | - | - | N | - | Not Required | - | 12323436 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397841 | 0 | 10883570 | 0 | 0 | 0 | 0 | 0 | 12281411 | 12281411 | 12281411 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10883570
19-063 | 19-063 | 19 | N/A | 66125 | Peel DSB | Churchill Meadows | Churchill Meadows Public Elementary School | ELE | 9898 | 10316 | 10316-B01 | 3310 MCDOWELL DR | MISSISSAUGA | L5M6R8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5595 | -79.7476 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7049136 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76786 | 76786 | 6972350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6972350 | 7049136 | 7049136 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-065 | 19-065 | 19 | N/A | 66125 | Peel DSB | Churchville | Churchville Public Elementary School | ELE | 24295 | 19287 | 19287-B01 | 90 BONNIE BRAES DR | BRAMPTON | L6Y0Y3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6564 | -79.7804 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 850 | - | - | N | - | Not Required | - | 14664828 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 42109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 11741068 | 0 | 0 | 0 | 0 | 0 | 12241068 | 12241068 | 12364828 | 123760 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11741068
19-066 | 19-066 | 19 | N/A | 66125 | Peel DSB | Claireville | Claireville Public Elementary School | ELE | 10490 | 11131 | 11131-B01 | 97 GALLUCCI CRES | BRAMPTON | L6P1R6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7711 | -79.6706 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7198918 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7198918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7198918 | 7198918 | 7198918 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-068 | 19-068 | 19 | N/A | 66125 | Peel DSB | Clark Boulevard | Clark Boulevard Public Elementary School | ELE | 455 | 5592 | 5592-B01 | 201 CLARK BLVD | BRAMPTON | L6T2C9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7148 | -79.7183 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7029575 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4341421 | 0 | 2688154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7029575 | 7029575 | 7029575 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-069 | 19-069 | 19 | N/A | 66125 | Peel DSB | Clifton | Clifton Public Elementary School | ELE | 466 | 5599 | 5599-B01 | 2389 CLIFF RD | MISSISSAUGA | L5A2P1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5838 | -79.602 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2428088 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2428088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2428088 | 2428088 | 2428088 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-071 | 19-071 | 19 | N/A | 66125 | Peel DSB | Conestoga | Conestoga Public Elementary School | ELE | 998 | 5949 | 5949-B01 | 300 CONESTOGA DR | BRAMPTON | L6Z3M1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7153 | -79.7863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3647650 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3647650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3647650 | 3647650 | 3647650 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-073 | 19-073 | 19 | N/A | 66125 | Peel DSB | Cooksville Creek | Cooksville Creek Public Elementary School | ELE | 9919 | 10327 | 10327-B01 | 5100 SALISHAN CIR | MISSISSAUGA | L5R3E3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6072 | -79.6589 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7034313 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505316 | 505316 | 6528997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6528997 | 7034313 | 7034313 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-074 | 19-074 | 19 | N/A | 66125 | Peel DSB | Copeland JPS | Copeland JPS Public Elementary School | ELE | 10722 | 11211 | 11211-B01 | 5 YOUNG DR | BRAMPTON | L6Y0P4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6488 | -79.7638 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9185160 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53636 | 53636 | 9131524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9131524 | 9185160 | 9185160 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-076 | 19-076 | 19 | N/A | 66125 | Peel DSB | Corsair | Corsair Public Elementary School | ELE | 514 | 5494 | 5494-B01 | 2230 CORSAIR RD | MISSISSAUGA | L5A2L9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5783 | -79.5995 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7195220 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7195220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7195220 | 7195220 | 7195220 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-077 | 19-077 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Countryside Village | Countryside Village Public Elementary School | ELE | 24300 | 19292 | 19292-B01 | 40 DOLBYHILL DR | BRAMPTON | L6R3V8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7585 | -79.7815 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 885 | 3 | 49 | N | - | Approved | 44621 | 16087373 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977135 | 0 | 12479073 | 0 | 1482853 | 0 | 0 | 0 | 15939061 | 15939061 | 16087373 | 148312 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13961926
19-078 | 19-078 | 19 | N/A | 66125 | Peel DSB | Credit Valley | Credit Valley Public Elementary School | ELE | 528 | 5648 | 5648-B01 | 2365 CREDIT VALLEY RD | MISSISSAUGA | L5M4E8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5543 | -79.7065 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6381317 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6381317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6381317 | 6381317 | 6381317 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-079 | 19-079 | 19 | N/A | 66125 | Peel DSB | McClure | McClure Public Elementary School | ELE | 24485 | 19490 | 19490-B01 | 50 PARITY RD | BRAMPTON | L6X5M8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6721 | -79.7929 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 861 | - | - | N | - | Approved | 44678 | 13904521 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977136 | 0 | 11391743 | 0 | 0 | 0 | 0 | 0 | 13368879 | 13368879 | 13904521 | 535642 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11391743
19-080 | 19-080 | 19 | N/A | 66125 | Peel DSB | David Leeder | David Leeder Public Elementary School | ELE | 9916 | 6275 | 6275-B01 | 6900 GOODERHAM ESTATE BLVD | MISSISSAUGA | L5W1B4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6278 | -79.7224 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7164611 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7164611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7164611 | 7164611 | 7164611 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-081 | 19-081 | 19 | N/A | 66125 | Peel DSB | David Leeder | David Leeder Public Elementary School | ELE | 9916 | 6275 | 6275-B01 | 6900 GOODERHAM ESTATE BLVD | MISSISSAUGA | L5W1B4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6278 | -79.7224 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3518046 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518046 | 3518046 | 3518046 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-082 | 19-082 | 19 | N/A | 66125 | Peel DSB | David Suzuki | David Suzuki Public Secondary School | SEC | 10974 | 12118 | 12118-B01 | 45 DAVISELM DR | BRAMPTON | L6X0Z3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6696 | -79.7867 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 33856232 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33856232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33856232 | 33856232 | 33856232 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-083 | 19-083 | 19 | N/A | 66125 | Peel DSB | Derry West Village | Derry West Village Public Elementary School | ELE | 10135 | 10416 | 10416-B01 | 620 TWAIN AVE | MISSISSAUGA | L5W1M1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6405 | -79.7229 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8026742 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154828 | 154828 | 7871914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7871914 | 8026742 | 8026742 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-085 | 19-085 | 19 | N/A | 66125 | Peel DSB | Dolphin | Dolphin Public Elementary School | ELE | 593 | 5687 | 5687-B01 | 18 BROOKSIDE DR | MISSISSAUGA | L5M1H3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5855 | -79.7221 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2079550 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079550 | 2079550 | 2079550 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-086 | 19-086 | 19 | N/A | 66125 | Peel DSB | Dolphin | Dolphin Public Elementary School | ELE | 593 | 5687 | 5687-B01 | 18 BROOKSIDE DR | MISSISSAUGA | L5M1H3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5855 | -79.7221 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5637281 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5637281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5637281 | 5637281 | 5637281 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-089 | 19-089 | 19 | N/A | 66125 | Peel DSB | Eagle Plains | Eagle Plains Public Elementary School | ELE | 10721 | 11214 | 11214-B01 | 40 EAGLE PLAINS DR | BRAMPTON | L6R2X8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.774 | -79.7417 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9609250 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400635 | 400635 | 9208615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9208615 | 9609250 | 9609250 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-092 | 19-092 | 19 | N/A | 66125 | Peel DSB | Edenbrook Hill | Edenbrook Hill Public Elementary School | ELE | 10402 | 11101 | 11101-B01 | 61 EDENBROOK HILL DR | BRAMPTON | L7A1X6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6957 | -79.8082 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6719677 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27602 | 27602 | 6692075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6692075 | 6719677 | 6719677 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-093 | 19-093 | 19 | N/A | 66125 | Peel DSB | Edenbrook Hill | Edenbrook Hill Public Elementary School | ELE | 10402 | 11101 | 11101-B01 | 61 EDENBROOK HILL DR | BRAMPTON | L7A1X6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6957 | -79.8082 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4171018 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4171018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4171018 | 4171018 | 4171018 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-094 | 19-094 | 19 | N/A | 66125 | Peel DSB | Edenrose | Edenrose Public Elementary School | ELE | 705 | 5765 | 5765-B01 | 1342 EDENROSE ST | MISSISSAUGA | L5V1K9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.579 | -79.6759 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7007221 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7007221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7007221 | 7007221 | 7007221 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-095 | 19-095 | 19 | N/A | 66125 | Peel DSB | Edenwood | Edenwood Public Elementary School | ELE | 706 | 5766 | 5766-B01 | 6770 EDENWOOD DR | MISSISSAUGA | L5N3B2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.579 | -79.764 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1203162 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203162 | 1203162 | 1203162 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-096 | 19-096 | 19 | N/A | 66125 | Peel DSB | Eldorado | Eldorado Public Elementary School | ELE | 12605 | 12282 | 12282-B01 | 25 WARDSVILLE DR | BRAMPTON | L6Y0T7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6351 | -79.7795 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 792 | - | - | N | - | Approved | 43509 | 10784202 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896051 | 0 | 9888151 | 0 | 0 | 0 | 0 | 0 | 10784202 | 10784202 | 10784202 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 9888151
19-097 | 19-097 | 19 | N/A | 66125 | Peel DSB | Ellwood Memorial | Ellwood Memorial Public Elementary School | ELE | 730 | 5782 | 5782-B01 | 35 ELLWOOD DR E | BOLTON | L7E2A7 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8753 | -79.7292 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3465582 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465582 | 3465582 | 3465582 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-098 | 19-098 | 19 | N/A | 66125 | Peel DSB | Erin Centre | Erin Centre Public Elementary School | ELE | 10644 | 11204 | 11204-B01 | 3240 ERIN CENTRE BLVD | MISSISSAUGA | L5M7T9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5469 | -79.728 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9964216 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51747 | 51747 | 9912469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9912469 | 9964216 | 9964216 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-099 | 19-099 | 19 | N/A | 66125 | Peel DSB | Erin Mills | Erin Mills Public Elementary School | ELE | 754 | 5798 | 5798-B01 | 3546 SOUTH COMMON CRT | MISSISSAUGA | L5L2B1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5425 | -79.6866 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1994409 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1994409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1994409 | 1994409 | 1994409 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-100 | 19-100 | 19 | N/A | 66125 | Peel DSB | Erin Mills | Erin Mills Public Elementary School | ELE | 754 | 5798 | 5798-B01 | 3546 SOUTH COMMON CRT | MISSISSAUGA | L5L2B1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5425 | -79.6866 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2816334 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 2816334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2816334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2816334 | 2816334 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-102 | 19-102 | 19 | N/A | 66125 | Peel DSB | Fairlawn | Fairlawn Public Elementary School | ELE | 20022 | 19120 | 19120-B01 | 40 FAIRLAWN BLVD | BRAMPTON | L6P2X4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7678 | -79.7245 | 40749 | 2010-11 | 2011-12 | - | - | - | 40749 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 800 | - | - | N | - | Not Required | - | 12545023 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 11936971 | 0 | 0 | 0 | 0 | 0 | 12436971 | 12436971 | 12587048 | 150077 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11936971
19-103 | 19-103 | 19 | N/A | 66125 | Peel DSB | Fairview | Fairview Public Elementary School | ELE | 784 | 5812 | 5812-B01 | 3590 JOAN DR | MISSISSAUGA | L5B1T8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5888 | -79.6365 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1613193 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613193 | 1613193 | 1613193 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-104 | 19-104 | 19 | N/A | 66125 | Peel DSB | Fairview | Fairview Public Elementary School | ELE | 784 | 5812 | 5812-B01 | 3590 JOAN DR | MISSISSAUGA | L5B1T8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5888 | -79.6365 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3130202 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3130202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3130202 | 3130202 | 3130202 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-105 | 19-105 | 19 | N/A | 66125 | Peel DSB | Fairview | Fairview Public Elementary School | ELE | 784 | 5812 | 5812-B01 | 3590 JOAN DR | MISSISSAUGA | L5B1T8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5888 | -79.6365 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4198437 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4198437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4198437 | 4198437 | 4198437 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-107 | 19-107 | 19 | N/A | 66125 | Peel DSB | Fairwind | Fairwind Public Elementary School | ELE | 786 | 5814 | 5814-B01 | 5235 FAIRWIND DR | MISSISSAUGA | L5R3L2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6056 | -79.6661 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2291300 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2291300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2291300 | 2291300 | 2291300 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-109 | 19-109 | 19 | N/A | 66125 | Peel DSB | Fernforest | Fernforest Public Elementary School | ELE | 9771 | 10255 | 10255-B01 | 275 FERNFOREST DR | BRAMPTON | L6R1L9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7464 | -79.7579 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7275936 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128363 | 128363 | 7147573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7147573 | 7275936 | 7275936 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-111 | 19-111 | 19 | N/A | 66125 | Peel DSB | Fletcher's Creek Senior | Fletcher's Creek Senior Public Elementary School | ELE | 826 | 5837 | 5837-B01 | 92 MALTA AVE | BRAMPTON | L6Y4C8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6585 | -79.7304 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1786775 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1786775 | 1786775 | 1786775 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-112 | 19-112 | 19 | N/A | 66125 | Peel DSB | Fletcher's Meadow | Fletcher's Meadow Public Secondary School | SEC | 10493 | 11132 | 11132-B01 | 10750 CHINGUACOUSY RD | BRAMPTON | L7A2Z7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6984 | -79.8265 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 32132306 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32132306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32132306 | 32132306 | 32132306 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-113 | 19-113 | 19 | N/A | 66125 | Peel DSB | Floradale | Floradale Public Elementary School | ELE | 828 | 5839 | 5839-B01 | 210 PAISLEY BLVD W | MISSISSAUGA | L5B2A4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5716 | -79.6155 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1385491 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385491 | 1385491 | 1385491 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-114 | 19-114 | 19 | N/A | 66125 | Peel DSB | Floradale | Floradale Public Elementary School | ELE | 828 | 5839 | 5839-B01 | 210 PAISLEY BLVD W | MISSISSAUGA | L5B2A4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5716 | -79.6155 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4012890 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4012890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4012890 | 4012890 | 4012890 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-117 | 19-117 | 19 | N/A | 66125 | Peel DSB | Garthwood Park | Garthwood Park Public Elementary School | ELE | 871 | 5868 | 5868-B01 | 3245 COLONIAL DR | MISSISSAUGA | L5L5G2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5238 | -79.6931 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2272558 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2272558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2272558 | 2272558 | 2272558 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-118 | 19-118 | 19 | N/A | 66125 | Peel DSB | Garthwood Park | Garthwood Park Public Elementary School | ELE | 871 | 5868 | 5868-B01 | 3245 COLONIAL DR | MISSISSAUGA | L5L5G2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5238 | -79.6931 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4370836 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 4216215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4216215 | 0 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 5148109 | 4370836 | -777273 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-119 | 19-119 | 19 | N/A | 66125 | Peel DSB | Glendale | Glendale Public Elementary School | ELE | 920 | 5893 | 5893-B01 | 35 SUNSET BLVD | BRAMPTON | L6X1X1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6873 | -79.7764 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1887367 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887367 | 1887367 | 1887367 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-121 | 19-121 | 19 | N/A | 66125 | Peel DSB | Goldcrest | Goldcrest Public Elementary School | ELE | 928 | 5899 | 5899-B01 | 24 GOLDCREST RD | BRAMPTON | L6S1G3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.73 | -79.7209 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2116105 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2116105 | 2116105 | 2116105 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-123 | 19-123 | 19 | N/A | 66125 | Peel DSB | Gordon Graydon Senior | Gordon Graydon Senior Public Elementary School | ELE | 2064 | 6631 | 6631-B01 | 170 RUTHERFORD RD N | BRAMPTON | L6V2X9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7077 | -79.7548 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2833505 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2833505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2833505 | 2833505 | 2833505 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-124 | 19-124 | 19 | N/A | 66125 | Peel DSB | Great Lakes | Great Lakes Public Elementary School | ELE | 9816 | 10283 | 10283-B01 | 285 GREAT LAKES DR | BRAMPTON | L6R2R8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7368 | -79.7682 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7268863 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7268863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7268863 | 7268863 | 7268863 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-125 | 19-125 | 19 | N/A | 66125 | Peel DSB | Great Lakes | Great Lakes Public Elementary School | ELE | 9816 | 10283 | 10283-B01 | 285 GREAT LAKES DR | BRAMPTON | L6R2R8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7368 | -79.7682 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2936550 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2936550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2936550 | 2936550 | 2936550 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-127 | 19-127 | 19 | N/A | 66125 | Peel DSB | Greenbriar | Greenbriar Public Elementary School | ELE | 963 | 5926 | 5926-B02 | 1140 CENTRAL PARK DR | BRAMPTON | L6S2C9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7362 | -79.7155 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1220221 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220221 | 1220221 | 1220221 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-130 | 19-130 | 19 | N/A | 66125 | Peel DSB | Harold M Brathwaite | Harold M Brathwaite Public Secondary School | SEC | 10134 | 10415 | 10415-B01 | 415 GREAT LAKES DR | BRAMPTON | L6R2Z4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7397 | -79.7707 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 25830495 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418061 | 418061 | 25412434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25412434 | 25830495 | 25830495 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-132 | 19-132 | 19 | N/A | 66125 | Peel DSB | Hazel McCallion | Hazel McCallion Public Elementary School | ELE | 990 | 5943 | 5943-B02 | 5750 RIVER GROVE AVE | MISSISSAUGA | L5M4R5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5892 | -79.7091 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1648569 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1648569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1648569 | 1648569 | 1648569 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-133 | 19-133 | 19 | N/A | 66125 | Peel DSB | Heart Lake | Heart Lake Public Secondary School | SEC | 5415 | 5949 | 5949-B02 | 296 CONESTOGA DR | BRAMPTON | L6Z3M1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7167 | -79.7887 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3612280 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3612280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3612280 | 3612280 | 3612280 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-135 | 19-135 | 19 | N/A | 66125 | Peel DSB | Herb Campbell | Herb Campbell Public Elementary School | ELE | 1052 | 5985 | 5985-B01 | 3749 KING ST | INGLEWOOD | L7C0T6 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.787 | -79.8621 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1748966 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748966 | 1748966 | 1748966 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-136 | 19-136 | 19 | N/A | 66125 | Peel DSB | Herb Campbell | Herb Campbell Public Elementary School | ELE | 1052 | 5985 | 5985-B01 | 3749 KING ST | INGLEWOOD | L7C0T6 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.787 | -79.8621 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1771143 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771143 | 1771143 | 1771143 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-137 | 19-137 | 19 | N/A | 66125 | Peel DSB | Herb Campbell | Herb Campbell Public Elementary School | ELE | 1052 | 5985 | 5985-B01 | 3749 KING ST | INGLEWOOD | L7C0T6 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.787 | -79.8621 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 23 | - | - | N | - | Approved | 42727 | 1706678 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397841 | 0 | 308837 | 0 | 0 | 0 | 0 | 0 | 1706678 | 1706678 | 1706678 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 308837
19-138 | 19-138 | 19 | N/A | 66125 | Peel DSB | Hewson | Hewson Public Elementary School | ELE | 10937 | 12092 | 12092-B01 | 235 FATHER TOBIN RD | BRAMPTON | L6R0G2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7667 | -79.7594 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8616442 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40992 | 40992 | 8575450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8575450 | 8616442 | 8616442 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-140 | 19-140 | 19 | N/A | 66125 | Peel DSB | Hickory Wood | Hickory Wood Public Elementary School | ELE | 1058 | 5989 | 5989-B01 | 630 RAY LAWSON BLVD | BRAMPTON | L6Y4W8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6463 | -79.7428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1113181 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113181 | 1113181 | 1113181 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-141 | 19-141 | 19 | N/A | 66125 | Peel DSB | Hickory Wood | Hickory Wood Public Elementary School | ELE | 1058 | 5989 | 5989-B01 | 630 RAY LAWSON BLVD | BRAMPTON | L6Y4W8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6463 | -79.7428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2980795 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2980795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2980795 | 2980795 | 2980795 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-142 | 19-142 | 19 | N/A | 66125 | Peel DSB | Hickory Wood | Hickory Wood Public Elementary School | ELE | 1058 | 5989 | 5989-B01 | 630 RAY LAWSON BLVD | BRAMPTON | L6Y4W8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6463 | -79.7428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4970599 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4970599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4970599 | 4970599 | 4970599 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-143 | 19-143 | 19 | N/A | 66125 | Peel DSB | Hickory Wood | Hickory Wood Public Elementary School | ELE | 1058 | 5989 | 5989-B01 | 630 RAY LAWSON BLVD | BRAMPTON | L6Y4W8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6463 | -79.7428 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 750000 | Construction Complete | Demolition | Consolidation | 2016-17 | 42840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167586 | 0 | 0 | 0 | 0 | 0 | 167586 | 167586 | 167586 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 167586
19-145-01 | 19-145 | 19 | N/A | 66125 | Peel DSB | Hillside | Hillside Public Elementary School | ELE | 1093 | 6008 | 6008-B01 | 1290 KELLY RD | MISSISSAUGA | L5J3V1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5089 | -79.6465 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42129 | 14671024 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 6121575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6121575 | 7617555 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8549449 | 14671024 | 14671024 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-145-02 | 19-145 | 19 | N/A | 66125 | Peel DSB | Hillside | Hillside Public Elementary School | ELE | 1093 | 6008 | 6008-L01 | 1290 KELLY RD | MISSISSAUGA | L5J3V1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5089 | -79.6465 | 41372 | 2012-13 | 2013-14 | 41372 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 4307914 | Construction Complete | Land Acquisition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4307914 | 0 | 0 | 0 | 0 | 0 | 0 | 4307914 | 4307914 | 4307914 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4307914
19-146 | 19-146 | 19 | N/A | 66125 | Peel DSB | Homestead | Homestead Public Elementary School | ELE | 9917 | 10325 | 10325-B01 | 99 FLETCHERS CREEK BLVD | BRAMPTON | L6X4T7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6883 | -79.7988 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7836513 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380136 | 380136 | 7456377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7456377 | 7836513 | 7836513 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-147 | 19-147 | 19 | N/A | 66125 | Peel DSB | Homestead | Homestead Public Elementary School | ELE | 9917 | 10325 | 10325-B01 | 99 FLETCHERS CREEK BLVD | BRAMPTON | L6X4T7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6883 | -79.7988 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4120933 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120933 | 4120933 | 4120933 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-148 | 19-148 | 19 | N/A | 66125 | Peel DSB | Huntington Ridge | Huntington Ridge Public Elementary School | ELE | 1131 | 6027 | 6027-B01 | 345 HUNTINGTON RIDGE DR | MISSISSAUGA | L5R1R6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5967 | -79.6572 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4112737 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4112737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4112737 | 4112737 | 4112737 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-150 | 19-150 | 19 | N/A | 66125 | Peel DSB | Huttonville | Huttonville Public Elementary School | ELE | 1141 | 6033 | 6033-B01 | 2322 EMBLETON RD | BRAMPTON | L6X0C9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6413 | -79.8094 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1017751 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017751 | 1017751 | 1017751 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-151 | 19-151 | 19 | N/A | 66125 | Peel DSB | Huttonville | Huttonville Public Elementary School | ELE | 1141 | 6033 | 6033-B01 | 2322 EMBLETON RD | BRAMPTON | L6X0C9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6413 | -79.8094 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 438 | - | - | N | - | Approved | 41858 | 8200000 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7735424 | 0 | 0 | 0 | 0 | 0 | 7735424 | 7735424 | 8200000 | 464576 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 7735424
19-152 | 19-152 | 19 | N/A | 66125 | Peel DSB | Ingleborough | Ingleborough Public Elementary School | ELE | 14543 | 18029 | 18029-B01 | 60 INGLEBOROUGH DR | BRAMPTON | L6X0X5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6593 | -79.8035 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10656921 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9760870 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10656921 | 10656921 | 10656921 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-153 | 19-153 | 19 | N/A | 66125 | Peel DSB | James Bolton | James Bolton Public Elementary School | ELE | 35 | 5074 | 5074-B01 | 225 KINGSVIEW DR | BOLTON | L7E3X8 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8867 | -79.7411 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6625343 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6625343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6625343 | 6625343 | 6625343 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-154 | 19-154 | 19 | N/A | 66125 | Peel DSB | James Bolton | James Bolton Public Elementary School | ELE | 35 | 5074 | 5074-B01 | 225 KINGSVIEW DR | BOLTON | L7E3X8 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8867 | -79.7411 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11873434 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11873434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11873434 | 11873434 | 11873434 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-156 | 19-156 | 19 | N/A | 66125 | Peel DSB | James Potter | James Potter Public Elementary School | ELE | 10720 | 11212 | 11212-B01 | 9775 CREDITVIEW RD | BRAMPTON | L6X0H7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6719 | -79.8081 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9073582 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174331 | 174331 | 8899251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8899251 | 9073582 | 9073582 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-159 | 19-159 | 19 | N/A | 66125 | Peel DSB | Janet I McDougald | Janet I McDougald Public Elementary School | ELE | 11344 | 6198 | 6198-B02 | 498 HARTSDALE AVE | MISSISSAUGA | L5G2G6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5726 | -79.5785 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8944131 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8944131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8944131 | 8944131 | 8944131 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-160 | 19-160 | 19 | N/A | 66125 | Peel DSB | Jean Augustine | Jean Augustine Public Secondary School | SEC | 24224 | 19216 | 19216-B01 | 500 ELBERN MARKELL DR | BRAMPTON | L6X5L3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6676 | -79.8263 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 1479 | - | - | N | - | Approved | 42055 | 36039377 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 2455614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2455614 | 0 | 0 | 0 | 0 | 38370118 | 0 | 0 | 0 | 0 | 0 | 38370118 | 40825732 | 40825732 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 38370118
19-161 | 19-161 | 19 | N/A | 66125 | Peel DSB | Jefferson | Jefferson Public Elementary School | ELE | 1193 | 6063 | 6063-B01 | 48 JEFFERSON RD | BRAMPTON | L6S2N9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7381 | -79.7305 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1830655 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1830655 | 1830655 | 1830655 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-163 | 19-163 | 19 | N/A | 66125 | Peel DSB | John Fraser | John Fraser Public Secondary School | SEC | 5450 | 8260 | 8260-B01 | 2665 ERIN CENTRE BLVD | MISSISSAUGA | L5M5H6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.56 | -79.7167 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4342024 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4342024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4342024 | 4342024 | 4342024 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-165 | 19-165 | 19 | N/A | 66125 | Peel DSB | Kindree | Kindree Public Elementary School | ELE | 9778 | 10262 | 10262-B01 | 7370 TERRAGAR BLVD | MISSISSAUGA | L5N7L8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5832 | -79.7892 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5810407 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5810407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5810407 | 5810407 | 5810407 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-166 | 19-166 | 19 | N/A | 66125 | Peel DSB | Kindree | Kindree Public Elementary School | ELE | 9778 | 10262 | 10262-B01 | 7370 TERRAGAR BLVD | MISSISSAUGA | L5N7L8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5832 | -79.7892 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4000583 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000583 | 4000583 | 4000583 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-168 | 19-168 | 19 | N/A | 66125 | Peel DSB | Kingswood Drive | Kingswood Drive Public Elementary School | ELE | 1287 | 6119 | 6119-B01 | 235 KINGSWOOD DR | BRAMPTON | L6V3B3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7024 | -79.7659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1230226 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230226 | 1230226 | 1230226 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-169 | 19-169 | 19 | N/A | 66125 | Peel DSB | Kingswood Drive | Kingswood Drive Public Elementary School | ELE | 1287 | 6119 | 6119-B01 | 235 KINGSWOOD DR | BRAMPTON | L6V3B3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7024 | -79.7659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4542985 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4542985 | 4542985 | 4542985 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-171 | 19-171 | 19 | N/A | 66125 | Peel DSB | Lancaster | Lancaster Public Elementary School | ELE | 1327 | 6146 | 6146-B01 | 7425 NETHERWOOD RD | MISSISSAUGA | L4T2N7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.7178 | -79.6476 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6286221 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6286221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6286221 | 6286221 | 6286221 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-172 | 19-172 | 19 | N/A | 66125 | Peel DSB | Larkspur | Larkspur Public Elementary School | ELE | 9914 | 10323 | 10323-B01 | 111 LARKSPUR RD | BRAMPTON | L6R1X2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7543 | -79.7492 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8124142 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424852 | 424852 | 7699290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7699290 | 8124142 | 8124142 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-173 | 19-173 | 19 | N/A | 66125 | Peel DSB | Larkspur | Larkspur Public Elementary School | ELE | 9914 | 10323 | 10323-B01 | 111 LARKSPUR RD | BRAMPTON | L6R1X2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7543 | -79.7492 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3930042 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3930042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3930042 | 3930042 | 3930042 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-175 | 19-175 | 19 | N/A | 66125 | Peel DSB | Levi Creek | Levi Creek Public Elementary School | ELE | 9897 | 10315 | 10315-B01 | 1525 SAMUELSON CIR | MISSISSAUGA | L5N7Z1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6228 | -79.7474 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6875760 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270292 | 270292 | 6605468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6605468 | 6875760 | 6875760 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-177 | 19-177 | 19 | N/A | 66125 | Peel DSB | Lincoln M Alexander | Lincoln M Alexander Public Secondary School | SEC | 5755 | 8429 | 8429-B01 | 3545 MORNING STAR DR | MISSISSAUGA | L4T1Y3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.7247 | -79.6398 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3821733 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3821733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3821733 | 3821733 | 3821733 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-178 | 19-178 | 19 | N/A | 66125 | Peel DSB | Lisgar | Lisgar Public Elementary School | ELE | 1371 | 6174 | 6174-B01 | 6755 LISGAR DR | MISSISSAUGA | L5N6S9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5723 | -79.7781 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3917408 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917408 | 3917408 | 3917408 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-179 | 19-179 | 19 | N/A | 66125 | Peel DSB | Lorenville | Lorenville Public Elementary School | ELE | 14544 | 18030 | 18030-B01 | 10 LORENVILLE DR | BRAMPTON | L6X2Z9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6635 | -79.8108 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 792 | - | - | N | - | Approved | 43509 | 11797052 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162212 | 162212 | 0 | 0 | 1863788 | 0 | 9771052 | 0 | 0 | 0 | 0 | 0 | 11634840 | 11797052 | 11797052 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 9771052
19-180 | 19-180 | 19 | N/A | 66125 | Peel DSB | Lorne Park | Lorne Park Public Elementary School | ELE | 1394 | 6188 | 6188-B01 | 1325 INDIAN RD | MISSISSAUGA | L5H1S3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5373 | -79.6274 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4622248 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282045 | 1282045 | 3340203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3340203 | 4622248 | 4622248 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-181 | 19-181 | 19 | N/A | 66125 | Peel DSB | Lougheed | Lougheed Public Elementary School | ELE | 10643 | 11207 | 11207-B01 | 475 FATHER TOBIN RD | BRAMPTON | L6R0J9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7567 | -79.7724 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10084496 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274911 | 274911 | 9809585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9809585 | 10084496 | 10084496 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-182 | 19-182 | 19 | N/A | 66125 | Peel DSB | Louise Arbour | Louise Arbour Public Secondary School | SEC | 11016 | 12228 | 12228-B01 | 365 FATHER TOBIN RD | BRAMPTON | L6R0R4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7597 | -79.7672 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 34872390 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107847 | 107847 | 34764543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34764543 | 34872390 | 34872390 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-183 | 19-183 | 19 | N/A | 66125 | Peel DSB | Macville | Macville Public Elementary School | ELE | 1417 | 6204 | 6204-B01 | 7280 KING ST | BOLTON | L7C0S3 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8557 | -79.7871 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2863375 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2863375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2863375 | 2863375 | 2863375 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-184 | 19-184 | 19 | N/A | 66125 | Peel DSB | Massey | Massey Public Elementary School | ELE | 1427 | 6211 | 6211-B01 | 95 MASSEY ST | BRAMPTON | L6S3A3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7379 | -79.7467 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1110218 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110218 | 1110218 | 1110218 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-185 | 19-185 | 19 | N/A | 66125 | Peel DSB | Mayfield | Mayfield Public Secondary School | SEC | 5512 | 8296 | 8296-B01 | 5000 MAYFIELD RD | CALEDON EAST | L7C0Z5 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.774 | -79.782 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7588428 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7588428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7588428 | 7588428 | 7588428 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-186 | 19-186 | 19 | N/A | 66125 | Peel DSB | McBride Avenue | McBride Avenue Public Elementary School | ELE | 1496 | 5140 | 5140-B02 | 974 MCBRIDE AVE | MISSISSAUGA | L5C1L6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5637 | -79.6466 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1210597 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210597 | 1210597 | 1210597 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-188 | 19-188 | 19 | N/A | 66125 | Peel DSB | McCrimmon | McCrimmon Public Elementary School | ELE | 10404 | 11103 | 11103-B01 | 83 MCCRIMMON DR | BRAMPTON | L7A2Z3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6908 | -79.8272 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7678461 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24161 | 24161 | 7654300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7654300 | 7678461 | 7678461 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-189 | 19-189 | 19 | N/A | 66125 | Peel DSB | McCrimmon | McCrimmon Public Elementary School | ELE | 10404 | 11103 | 11103-B01 | 83 MCCRIMMON DR | BRAMPTON | L7A2Z3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6908 | -79.8272 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3706685 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3706685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3706685 | 3706685 | 3706685 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-191 | 19-191 | 19 | N/A | 66125 | Peel DSB | McKinnon | McKinnon Public Elementary School | ELE | 10976 | 12120 | 12120-B01 | 3270 TACC DR | MISSISSAUGA | L5M0H3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5509 | -79.7338 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9512126 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522454 | 522454 | 8989672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8989672 | 9512126 | 9512126 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-193 | 19-193 | 19 | N/A | 66125 | Peel DSB | Meadowvale | Meadowvale Public Secondary School | SEC | 5516 | 5766 | 5766-B02 | 6700 EDENWOOD DR | MISSISSAUGA | L5N3B2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5779 | -79.7613 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4509226 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4509226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4509226 | 4509226 | 4509226 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-194 | 19-194 | 19 | N/A | 66125 | Peel DSB | Meadowvale Village | Meadowvale Village Public Elementary School | ELE | 10723 | 6275 | 6275-B02 | 890 OLD DERRY RD | MISSISSAUGA | L5W1A1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6272 | -79.7255 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9390929 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301239 | 301239 | 9089690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9089690 | 9390929 | 9390929 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-196 | 19-196 | 19 | N/A | 66125 | Peel DSB | Middlebury | Middlebury Public Elementary School | ELE | 1536 | 6289 | 6289-B01 | 5482 MIDDLEBURY DR | MISSISSAUGA | L5M5G7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5654 | -79.7222 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5631089 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5631089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5631089 | 5631089 | 5631089 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-197 | 19-197 | 19 | N/A | 66125 | Peel DSB | Miller's Grove | Miller's Grove Public Elementary School | ELE | 1545 | 6294 | 6294-B01 | 6325 MILLER'S GROVE | MISSISSAUGA | L5N3K2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5723 | -79.7558 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1931172 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1931172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1931172 | 1931172 | 1931172 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-198 | 19-198 | 19 | N/A | 66125 | Peel DSB | Mineola | Mineola Public Elementary School | ELE | 1551 | 6296 | 6296-B01 | 145 WINDY OAKS | MISSISSAUGA | L5G1Z4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5635 | -79.585 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 883000 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 0 | 434975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434975 | 0 | 0 | 448025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448025 | 883000 | 883000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-199 | 19-199 | 19 | N/A | 66125 | Peel DSB | Mississauga | Mississauga Public Secondary School | SEC | 10638 | 11222 | 11222-B01 | 550 COURTNEYPARK DR W | MISSISSAUGA | L5W1L9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6251 | -79.7029 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 30066123 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198446 | 198446 | 29867677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29867677 | 30066123 | 30066123 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-200 | 19-200 | 19 | N/A | 66125 | Peel DSB | Morton Way | Morton Way Public Elementary School | ELE | 1441 | 6221 | 6221-B01 | 200 MORTON WAY | BRAMPTON | L6Y2P8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6565 | -79.751 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1097803 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097803 | 1097803 | 1097803 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-201 | 19-201 | 19 | N/A | 66125 | Peel DSB | Morton Way | Morton Way Public Elementary School | ELE | 1441 | 6221 | 6221-B01 | 200 MORTON WAY | BRAMPTON | L6Y2P8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6565 | -79.751 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2829643 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2829643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2829643 | 2829643 | 2829643 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-202 | 19-202 | 19 | N/A | 66125 | Peel DSB | Morton Way | Morton Way Public Elementary School | ELE | 1441 | 6221 | 6221-B01 | 200 MORTON WAY | BRAMPTON | L6Y2P8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6565 | -79.751 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3768194 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528066 | 0 | 2240128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3768194 | 3768194 | 3768194 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-203 | 19-203 | 19 | N/A | 66125 | Peel DSB | Mount Pleasant Village | Mount Pleasant Village Public Elementary School | ELE | 12604 | 12281 | 12281-B01 | 100 COMMUTER DR | BRAMPTON | L7A0P7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6774 | -79.8211 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9419045 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7626942 | 0 | 1792103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9419045 | 9419045 | 9419045 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-204 | 19-204 | 19 | N/A | 66125 | Peel DSB | Mount Royal | Mount Royal Public Elementary School | ELE | 10715 | 11221 | 11221-B01 | 65 MOUNT ROYAL CIR | BRAMPTON | L6P2K4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7911 | -79.7464 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9230579 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75106 | 75106 | 9155473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9155473 | 9230579 | 9230579 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-206 | 19-206 | 19 | N/A | 66125 | Peel DSB | Mountain Ash | Mountain Ash Public Elementary School | ELE | 10406 | 11105 | 11105-B01 | 280 MOUNTAINASH RD | BRAMPTON | L6R3G2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7718 | -79.7437 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7240460 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89731 | 89731 | 7150729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7150729 | 7240460 | 7240460 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-208 | 19-208 | 19 | N/A | 66125 | Peel DSB | Munden Park | Munden Park Public Elementary School | ELE | 1589 | 6320 | 6320-B01 | 515 TEDWYN DR | MISSISSAUGA | L5A1J8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5832 | -79.5925 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 546870 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546870 | 546870 | 546870 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-210 | 19-210 | 19 | N/A | 66125 | Peel DSB | Nahani Way | Nahani Way Public Elementary School | ELE | 1601 | 6331 | 6331-B01 | 235 NAHANI WAY | MISSISSAUGA | L4Z3J6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6147 | -79.6507 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1190582 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190582 | 1190582 | 1190582 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-211 | 19-211 | 19 | N/A | 66125 | Peel DSB | Nahani Way | Nahani Way Public Elementary School | ELE | 1601 | 6331 | 6331-B01 | 235 NAHANI WAY | MISSISSAUGA | L4Z3J6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6147 | -79.6507 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4872891 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4872891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4872891 | 4872891 | 4872891 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-213 | 19-213 | 19 | N/A | 66125 | Peel DSB | Nelson Mandela | Nelson Mandela Public Elementary School | ELE | 24294 | 19286 | 19286-L01 | 10125 CHINGUACOUSY RD | BRAMPTON | L7A3Z6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6916 | -79.8139 | 40994 | 2011-12 | 2011-12 | 40994 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5880393 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5880393 | 0 | 0 | 0 | 0 | 0 | 0 | 5880393 | 5880393 | 5880393 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 5880393
19-214 | 19-214 | 19 | N/A | 66125 | Peel DSB | Nelson Mandela | Nelson Mandela Public Elementary School | ELE | 24294 | 19286 | 19286-B01 | 10125 CHINGUACOUSY RD | BRAMPTON | L7A3Z6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6916 | -79.8139 | 40749 | 2010-11 | 2011-12 | - | - | - | 40749 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 800 | - | - | N | - | Not Required | - | 14676778 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3727576 | 0 | 10949202 | 0 | 0 | 0 | 0 | 0 | 14676778 | 14676778 | 14676778 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10949202
19-215 | 19-215 | 19 | N/A | 66125 | Peel DSB | North Park | North Park Public Secondary School | SEC | 5552 | 8320 | 8320-B01 | 10 NORTH PARK DR | BRAMPTON | L6S3M1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7202 | -79.7483 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4656198 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4656198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4656198 | 4656198 | 4656198 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-216 | 19-216 | 19 | N/A | 66125 | Peel DSB | Northwood | Northwood Public Elementary School | ELE | 1673 | 6379 | 6379-B01 | 70 GRETNA DR | BRAMPTON | L6X2E9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6747 | -79.7756 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2071698 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2071698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2071698 | 2071698 | 2071698 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-218 | 19-218 | 19 | N/A | 66125 | Peel DSB | Oscar Peterson | Oscar Peterson Public Elementary School | ELE | 10977 | 11204 | 11204-B02 | 5120 PERENNIAL DR | MISSISSAUGA | L5M7T6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5453 | -79.7271 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9521085 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87003 | 87003 | 9434082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9434082 | 9521085 | 9521085 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-220 | 19-220 | 19 | N/A | 66125 | Peel DSB | Osprey Woods | Osprey Woods Public Elementary School | ELE | 10137 | 10418 | 10418-B01 | 6135 LISGAR DR | MISSISSAUGA | L5N7V2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5625 | -79.7633 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7664036 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364372 | 364372 | 7299664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7299664 | 7664036 | 7664036 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-221 | 19-221 | 19 | N/A | 66125 | Peel DSB | Palgrave | Palgrave Public Elementary School | ELE | 11132 | 6421 | 6421-B01 | 8962 PATTERSON SIDEROAD | PALGRAVE | L7E0L2 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.9473 | -79.833 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12818267 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1755278 | 1755278 | 11062989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11062989 | 12818267 | 12818267 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-222 | 19-222 | 19 | N/A | 66125 | Peel DSB | Parkway | Parkway Public Elementary School | ELE | 1777 | 6438 | 6438-B01 | 24 DUNCAN BULL DR | BRAMPTON | L6W1H4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6766 | -79.7386 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2930502 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2930502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2930502 | 2930502 | 2930502 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-224 | 19-224 | 19 | N/A | 66125 | Peel DSB | Plowman's Park | Plowman's Park Public Elementary School | ELE | 1834 | 6474 | 6474-B01 | 5940 MONTEVIDEO RD | MISSISSAUGA | L5N3J5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.582 | -79.7479 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2826380 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2826380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2826380 | 2826380 | 2826380 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-225 | 19-225 | 19 | N/A | 66125 | Peel DSB | Plum Tree Park | Plum Tree Park Public Elementary School | ELE | 1833 | 6473 | 6473-B01 | 6855 TENTH LINE W | MISSISSAUGA | L5N5R2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5812 | -79.7714 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3983771 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3983771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3983771 | 3983771 | 3983771 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-226 | 19-226 | 19 | N/A | 66125 | Peel DSB | Plum Tree Park | Plum Tree Park Public Elementary School | ELE | 1833 | 6473 | 6473-B01 | 6855 TENTH LINE W | MISSISSAUGA | L5N5R2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5812 | -79.7714 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3371603 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3371603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3371603 | 3371603 | 3371603 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-227 | 19-227 | 19 | N/A | 66125 | Peel DSB | Plum Tree Park | Plum Tree Park Public Elementary School | ELE | 1833 | 6473 | 6473-B01 | 6855 TENTH LINE W | MISSISSAUGA | L5N5R2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5812 | -79.7714 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2273440 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2273440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2273440 | 2273440 | 2273440 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-228 | 19-228 | 19 | N/A | 66125 | Peel DSB | Queen Street | Queen Street Public Elementary School | ELE | 10405 | 11104 | 11104-B01 | 20 ACADEMIC DR | BRAMPTON | L6Y0R7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6707 | -79.7755 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9127125 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1520028 | 1520028 | 7607097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7607097 | 9127125 | 9127125 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-230 | 19-230 | 19 | N/A | 66125 | Peel DSB | Ray Lawson | Ray Lawson Public Elementary School | ELE | 14545 | 18031 | 18031-B01 | 725 RAY LAWSON BLVD | BRAMPTON | L6Y0T8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6423 | -79.7458 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 713 | - | - | N | - | Not Required | - | 11910835 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896051 | 0 | 10697354 | 0 | 0 | 0 | 0 | 0 | 11593405 | 11593405 | 11910835 | 317430 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 10697354
19-231 | 19-231 | 19 | N/A | 66125 | Peel DSB | Ray Underhill | Ray Underhill Public Elementary School | ELE | 1956 | 6563 | 6563-B01 | 32 SUBURBAN DR | MISSISSAUGA | L5N1G6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5937 | -79.7223 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2716457 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716457 | 2716457 | 2716457 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-233 | 19-233 | 19 | N/A | 66125 | Peel DSB | Red Willow | Red Willow Public Elementary School | ELE | 10713 | 11217 | 11217-B01 | 80 REDWILLOW RD | BRAMPTON | L6P2B1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7739 | -79.7015 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7627325 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47959 | 47959 | 7579366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7579366 | 7627325 | 7627325 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-234 | 19-234 | 19 | N/A | 66125 | Peel DSB | Red Willow | Red Willow Public Elementary School | ELE | 10713 | 11217 | 11217-B01 | 80 REDWILLOW RD | BRAMPTON | L6P2B1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7739 | -79.7015 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3384095 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3384095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3384095 | 3384095 | 3384095 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-235 | 19-235 | 19 | N/A | 66125 | Peel DSB | Rick Hansen | Rick Hansen Public Secondary School | SEC | 6081 | 5818 | 5818-B02 | 1150 DREAM CREST RD | MISSISSAUGA | L5V1N6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5889 | -79.6832 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4925062 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4925062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4925062 | 4925062 | 4925062 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-236 | 19-236 | 19 | N/A | 66125 | Peel DSB | Ridgeview | Ridgeview Public Elementary School | ELE | 1984 | 6577 | 6577-B01 | 25 BRENDA AVE | BRAMPTON | L6Y2A1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6724 | -79.7562 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1913289 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913289 | 1913289 | 1913289 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-237 | 19-237 | 19 | N/A | 66125 | Peel DSB | Ridgeview | Ridgeview Public Elementary School | ELE | 1984 | 6577 | 6577-B01 | 25 BRENDA AVE | BRAMPTON | L6Y2A1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6724 | -79.7562 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6397983 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397983 | 6397983 | 6397983 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-238 | 19-238 | 19 | N/A | 66125 | Peel DSB | Ridgewood | Ridgewood Public Elementary School | ELE | 1987 | 6579 | 6579-B01 | 7207 CAMBRETT DR | MISSISSAUGA | L4T2R3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.7153 | -79.6406 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4221506 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4221506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4221506 | 4221506 | 4221506 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-240 | 19-240 | 19 | N/A | 66125 | Peel DSB | Robert H Lagerquist | Robert H Lagerquist Public Elementary School | ELE | 2012 | 6597 | 6597-B02 | 105 RICHVALE DR N | BRAMPTON | L6Z1Y6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7325 | -79.7953 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2778871 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2778871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2778871 | 2778871 | 2778871 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-241 | 19-241 | 19 | N/A | 66125 | Peel DSB | Robert J Lee | Robert J Lee Public Elementary School | ELE | 2007 | 6595 | 6595-B01 | 160 MOUNTAINASH RD | BRAMPTON | L6R1J1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7639 | -79.7352 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1249996 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249996 | 1249996 | 1249996 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-243 | 19-243 | 19 | N/A | 66125 | Peel DSB | Roberta Bondar | Roberta Bondar Public Elementary School | ELE | 10596 | 11205 | 11205-B01 | 30 PANTOMINE BLVD | BRAMPTON | L6Y5N2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6405 | -79.7557 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9110154 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60004 | 60004 | 9050150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050150 | 9110154 | 9110154 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-244 | 19-244 | 19 | N/A | 66125 | Peel DSB | Ross Drive | Ross Drive Public Elementary School | ELE | 24225 | 19217 | 19217-B01 | 40 ROSS DR | BRAMPTON | L6R3S7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7505 | -79.7842 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 850 | - | - | N | - | Approved | 44621 | 14562669 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 42009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1863788 | 0 | 12555827 | 0 | 0 | 0 | 0 | 0 | 14419615 | 14419615 | 14562669 | 143054 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12555827
19-245 | 19-245 | 19 | N/A | 66125 | Peel DSB | Rowntree | Rowntree Public Elementary School | ELE | 10645 | 11218 | 11218-B02 | 254 QUEEN MARY DR | BRAMPTON | L7A3L6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7069 | -79.8191 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8079487 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211358 | 211358 | 7868129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7868129 | 8079487 | 8079487 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-246 | 19-246 | 19 | N/A | 66125 | Peel DSB | Rowntree | Rowntree Public Elementary School | ELE | 10645 | 11218 | 11218-B02 | 254 QUEEN MARY DR | BRAMPTON | L7A3L6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7069 | -79.8191 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 230 | - | - | N | - | Approved | 43509 | 3677609 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677609 | 0 | 0 | 0 | 0 | 0 | 3677609 | 3677609 | 3677609 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 3677609
19-247 | 19-247 | 19 | N/A | 66125 | Peel DSB | Royal Orchard | Royal Orchard Public Elementary School | ELE | 10622 | 11206 | 11206-B01 | 77 ROYAL ORCHARD DR | BRAMPTON | L6X4M4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6946 | -79.7869 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8046776 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57138 | 57138 | 7989638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7989638 | 8046776 | 8046776 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-248 | 19-248 | 19 | N/A | 66125 | Peel DSB | Russell D Barber | Russell D Barber Public Elementary School | ELE | 2061 | 6629 | 6629-B01 | 255 NORTH PARK DR | BRAMPTON | L6S6A5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7234 | -79.7511 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5345577 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5345577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5345577 | 5345577 | 5345577 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-250 | 19-250 | 19 | N/A | 66125 | Peel DSB | Russell D Barber | Russell D Barber Public Elementary School | ELE | 2061 | 6629 | 6629-B01 | 255 NORTH PARK DR | BRAMPTON | L6S6A5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7234 | -79.7511 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Approved | 41088 | 1278808 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678808 | 678808 | 678808 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 0
19-251 | 19-251 | 19 | N/A | 66125 | Peel DSB | Ruth Thompson | Ruth Thompson Public Elementary School | ELE | 10401 | 11100 | 11100-B01 | 5605 FRESHWATER DR | MISSISSAUGA | L5M7M8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5519 | -79.7403 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7602294 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184171 | 184171 | 7418123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7418123 | 7602294 | 7602294 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-252 | 19-252 | 19 | N/A | 66125 | Peel DSB | Sandalwood Heights | Sandalwood Heights Public Secondary School | SEC | 10717 | 11216 | 11216-B01 | 2671 SANDALWOOD PKY E | BRAMPTON | L6R0K7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7655 | -79.7426 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 30785795 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1645192 | 1645192 | 29140603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29140603 | 30785795 | 30785795 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-253 | 19-253 | 19 | N/A | 66125 | Peel DSB | Sawmill Valley | Sawmill Valley Public Elementary School | ELE | 2084 | 6642 | 6642-B01 | 3625 SAWMILL VALLEY DR | MISSISSAUGA | L5L2Z5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5521 | -79.6808 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3175762 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175762 | 3175762 | 3175762 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-254 | 19-254 | 19 | N/A | 66125 | Peel DSB | Sawmill Valley | Sawmill Valley Public Elementary School | ELE | 2084 | 6642 | 6642-B01 | 3625 SAWMILL VALLEY DR | MISSISSAUGA | L5L2Z5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5521 | -79.6808 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3791957 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 2929145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2929145 | 0 | 0 | 931894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 3861039 | 3791957 | -69082 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-255 | 19-255 | 19 | N/A | 66125 | Peel DSB | Settler's Green | Settler's Green Public Elementary School | ELE | 2176 | 6694 | 6694-B01 | 5800 MONTEVIDEO RD | MISSISSAUGA | L5N2S1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5783 | -79.7507 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1037421 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1037421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1037421 | 1037421 | 1037421 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-257 | 19-257 | 19 | N/A | 66125 | Peel DSB | Shaw | Shaw Public Elementary School | ELE | 10975 | 12119 | 12119-B01 | 10 FATHER TOBIN RD | BRAMPTON | L6R3K2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7753 | -79.7513 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9436291 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80988 | 80988 | 9355303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9355303 | 9436291 | 9436291 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-259 | 19-259 | 19 | N/A | 66125 | Peel DSB | Shelter Bay | Shelter Bay Public Elementary School | ELE | 2121 | 6666 | 6666-B01 | 6735 SHELTER BAY RD | MISSISSAUGA | L5N2C5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5871 | -79.763 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 966068 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966068 | 966068 | 966068 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-261 | 19-261 | 19 | N/A | 66125 | Peel DSB | Sherwood Mills | Sherwood Mills Public Elementary School | ELE | 9896 | 10314 | 10314-B01 | 1385 SHERWOOD MILLS BLVD | MISSISSAUGA | L5V2B8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5828 | -79.6849 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6917880 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294896 | 294896 | 6622984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6622984 | 6917880 | 6917880 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-262 | 19-262 | 19 | N/A | 66125 | Peel DSB | Sherwood Mills | Sherwood Mills Public Elementary School | ELE | 9896 | 10314 | 10314-B01 | 1385 SHERWOOD MILLS BLVD | MISSISSAUGA | L5V2B8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5828 | -79.6849 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3536321 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2640270 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3536321 | 3536321 | 3536321 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-266 | 19-266 | 19 | N/A | 66125 | Peel DSB | Sir Isaac Brock | Sir Isaac Brock Public Elementary School | ELE | 10981 | 12125 | 12125-B01 | 45 MELTWATER CRES | BRAMPTON | L6P3V8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7954 | -79.6759 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 861 | - | - | N | - | Approved | 43509 | 12310545 | Construction Complete | New Construction | Other | 2013-14 | 41520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1863788 | 0 | 10352523 | 0 | 0 | 0 | 0 | 0 | 12216311 | 12216311 | 12310545 | 94234 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 10352523
19-267 | 19-267 | 19 | N/A | 66125 | Peel DSB | Sir John A Macdonald | Sir John A Macdonald Public Elementary School | ELE | 2145 | 6679 | 6679-B01 | 250 CENTRE ST N | BRAMPTON | L6V2R4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6995 | -79.7658 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3536878 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3536878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3536878 | 3536878 | 3536878 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-268 | 19-268 | 19 | N/A | 66125 | Peel DSB | Sir William Gage | Sir William Gage Public Elementary School | ELE | 10978 | 12122 | 12122-B01 | 625 QUEEN ST W | BRAMPTON | L6Y5L6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.672 | -79.7743 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10434875 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99294 | 99294 | 10335581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10335581 | 10434875 | 10434875 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-269 | 19-269 | 19 | N/A | 66125 | Peel DSB | Sir Winston Churchill | Sir Winston Churchill Public Elementary School | ELE | 2160 | 6685 | 6685-B01 | 89 ARDGLEN DR | BRAMPTON | L6W1V1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6891 | -79.7485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6061532 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6061532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6061532 | 6061532 | 6061532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-270 | 19-270 | 19 | N/A | 66125 | Peel DSB | Somerset Drive | Somerset Drive Public Elementary School | ELE | 2170 | 6691 | 6691-B01 | 50 SOMERSET DR | BRAMPTON | L6Z1C7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7291 | -79.8033 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4881870 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4881870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4881870 | 4881870 | 4881870 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-271 | 19-271 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Tony Pontes | Tony Pontes Public Elementary School | ELE | 24520 | 19525 | 19525-B01 | 12872 KENNEDY RD | CALEDON | L7C4E1 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.7603 | -79.8377 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 650 | 3 | 49 | N | - | Approved | 42970 | 14632569 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43469 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 1512510 | 0 | 11369905 | 0 | 1512510 | 0 | 0 | 0 | 14394925 | 14494925 | 14632569 | 137644 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12882415
19-272 | 19-272 | 19 | N/A | 66125 | Peel DSB | Southfields Village | Southfields Village Public Elementary School | ELE | 14546 | 18032 | 18032-B01 | 110 LEARMONT AVE | CALEDON | L7C3R1 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.7581 | -79.8246 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 763 | - | - | N | - | Not Required | - | 12786039 | Construction Complete | New Construction | Other | 2012-13 | 41156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896051 | 0 | 11463923 | 0 | 0 | 0 | 0 | 0 | 12359974 | 12359974 | 12786039 | 426065 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 11463923
19-273 | 19-273 | 19 | N/A | 66125 | Peel DSB | Springbrook | Springbrook Public Elementary School | ELE | 24378 | 19379 | 19379-B01 | 145 JORDENSEN DR | BRAMPTON | L6X0S1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6661 | -79.7947 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 804 | - | - | N | - | Approved | 44678 | 14754677 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453777 | 0 | 13136674 | 0 | 0 | 0 | 0 | 0 | 14590451 | 14590451 | 14754677 | 164226 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13136674
19-274 | 19-274 | 19 | N/A | 66125 | Peel DSB | Springdale | Springdale Public Elementary School | ELE | 10403 | 11102 | 11102-B01 | 100 DEWSIDE DR | BRAMPTON | L6R3B6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7529 | -79.7668 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8028304 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82678 | 82678 | 7945626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7945626 | 8028304 | 8028304 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-275 | 19-275 | 19 | N/A | 66125 | Peel DSB | Springdale | Springdale Public Elementary School | ELE | 10403 | 11102 | 11102-B01 | 100 DEWSIDE DR | BRAMPTON | L6R3B6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7529 | -79.7668 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1928498 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928498 | 1928498 | 1928498 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-277 | 19-277 | 19 | N/A | 66125 | Peel DSB | Stanley Mills | Stanley Mills Public Elementary School | ELE | 10714 | 11220 | 11220-B01 | 286 SUNNY MEADOW BLVD | BRAMPTON | L6R3C3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7616 | -79.7578 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7814700 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100339 | 100339 | 7714361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714361 | 7814700 | 7814700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-279 | 19-279 | 19 | N/A | 66125 | Peel DSB | Stephen Lewis | Stephen Lewis Public Secondary School | SEC | 10716 | 11215 | 11215-B01 | 3675 THOMAS ST | MISSISSAUGA | L5M7E6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5571 | -79.7442 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 33970668 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359158 | 359158 | 33611510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33611510 | 33970668 | 33970668 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-280 | 19-280 | 19 | N/A | 66125 | Peel DSB | Streetsville | Streetsville Public Secondary School | SEC | 5685 | 8391 | 8391-B01 | 72 JOYMAR DR | MISSISSAUGA | L5M1G3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5792 | -79.7192 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41858 | 7019450 | Construction Complete | Retrofit | Accommodation Pressure | 2016-17 | 42617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7019450 | 0 | 0 | 0 | 0 | 0 | 7019450 | 7019450 | 7019450 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 7019450
19-281 | 19-281 | 19 | N/A | 66125 | Peel DSB | Sunny View | Sunny View Public Elementary School | ELE | 10593 | 11208 | 11208-B01 | 30 CHAPPARAL DR | BRAMPTON | L6R3C4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7616 | -79.7565 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9206488 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9206488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9206488 | 9206488 | 9206488 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-282 | 19-282 | 19 | N/A | 66125 | Peel DSB | Terry Fox | Terry Fox Public Elementary School | ELE | 2290 | 6597 | 6597-B01 | 95 RICHVALE DR N | BRAMPTON | L6Z1Y6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7314 | -79.7925 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2627964 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2627964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2627964 | 2627964 | 2627964 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-283 | 19-283 | 19 | N/A | 66125 | Peel DSB | Terry Fox | Terry Fox Public Elementary School | ELE | 2290 | 6597 | 6597-B01 | 95 RICHVALE DR N | BRAMPTON | L6Z1Y6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7314 | -79.7925 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1394767 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394767 | 1394767 | 1394767 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-284 | 19-284 | 19 | N/A | 66125 | Peel DSB | The Humberview | The Humberview Public Secondary School | SEC | 5427 | 5074 | 5074-B02 | 135 KINGSVIEW DR | BOLTON | L7E3V8 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8884 | -79.7372 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4929969 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4929969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4929969 | 4929969 | 4929969 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-285 | 19-285 | 19 | N/A | 66125 | Peel DSB | The Valleys | The Valleys Public Elementary School | ELE | 2299 | 6774 | 6774-B01 | 1235 MISSISSAUGA VALLEY BLVD | MISSISSAUGA | L5A3R8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5981 | -79.6235 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2357870 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2357870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2357870 | 2357870 | 2357870 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-286 | 19-286 | 19 | N/A | 66125 | Peel DSB | The Woodlands | The Woodlands Public Secondary School | SEC | 5769 | 5140 | 5140-B01 | 3225 ERINDALE STATION RD | MISSISSAUGA | L5C1Y5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5629 | -79.6478 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41858 | 8283015 | Construction Complete | Retrofit | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 763000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763000 | 0 | 0 | 0 | 0 | 6773634 | 0 | 0 | 0 | 0 | 0 | 6773634 | 7536634 | 8283015 | 746381 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 6773634
19-287 | 19-287 | 19 | N/A | 66125 | Peel DSB | Thomas Street | Thomas Street Public Elementary School | ELE | 9767 | 10252 | 10252-B01 | 2640 THOMAS ST | MISSISSAUGA | L5M5G8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5669 | -79.7257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6766037 | Construction Complete | New Construction | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6766037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6766037 | 6766037 | 6766037 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-288 | 19-288 | 19 | N/A | 66125 | Peel DSB | Thomas Street | Thomas Street Public Elementary School | ELE | 9767 | 10252 | 10252-B01 | 2640 THOMAS ST | MISSISSAUGA | L5M5G8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5669 | -79.7257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1887254 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887254 | 1887254 | 1887254 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-289 | 19-289 | 19 | N/A | 66125 | Peel DSB | Thorndale | Thorndale Public Elementary School | ELE | 10718 | 11210 | 11210-B01 | 133 THORNDALE RD | BRAMPTON | L6P1K5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7816 | -79.6694 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8745508 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247501 | 247501 | 8498007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8498007 | 8745508 | 8745508 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-290 | 19-290 | 19 | N/A | 66125 | Peel DSB | Thornwood | Thornwood Public Elementary School | ELE | 2306 | 6779 | 6779-B01 | 277 MISSISSAUGA VALLEY BLVD | MISSISSAUGA | L5A1Y6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.589 | -79.6205 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1286879 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1286879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1286879 | 1286879 | 1286879 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-292 | 19-292 | 19 | N/A | 66125 | Peel DSB | Treeline | Treeline Public Elementary School | ELE | 10133 | 10414 | 10414-B01 | 145 TREELINE BLVD | BRAMPTON | L6P1E7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7785 | -79.7331 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8782850 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283404 | 283404 | 8499446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8499446 | 8782850 | 8782850 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-293 | 19-293 | 19 | N/A | 66125 | Peel DSB | Treeline | Treeline Public Elementary School | ELE | 10133 | 10414 | 10414-B01 | 145 TREELINE BLVD | BRAMPTON | L6P1E7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7785 | -79.7331 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2233829 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2233829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2233829 | 2233829 | 2233829 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-295 | 19-295 | 19 | N/A | 66125 | Peel DSB | Trelawny | Trelawny Public Elementary School | ELE | 2329 | 6791 | 6791-B01 | 3420 TRELAWNY CIR | MISSISSAUGA | L5N6N6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5716 | -79.7689 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3102717 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3102717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3102717 | 3102717 | 3102717 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-296 | 19-296 | 19 | N/A | 66125 | Peel DSB | Tribune Drive | Tribune Drive Public Elementary School | ELE | 24431 | 19433 | 19433-B01 | 30 TRIBUNE DR | BRAMPTON | L7A0X5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6909 | -79.8401 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 873 | - | - | N | - | Approved | 44621 | 15828307 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977136 | 0 | 11447152 | 0 | 0 | 0 | 0 | 0 | 13424288 | 13424288 | 15828307 | 2404019 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11447152
19-297 | 19-297 | 19 | N/A | 66125 | Peel DSB | Turner Fenton North | Turner Fenton North Public Secondary School | SEC | 5442 | 3014 | 3014-B01 | 7935 KENNEDY RD | BRAMPTON | L6W0A2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.675 | -79.719 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4683246 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4683246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4683246 | 4683246 | 4683246 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-298 | 19-298 | 19 | N/A | 66125 | Peel DSB | Vista Heights | Vista Heights Public Elementary School | ELE | 2395 | 6839 | 6839-B01 | 89 VISTA BLVD | MISSISSAUGA | L5M1V8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5752 | -79.7257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1269475 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1269475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1269475 | 1269475 | 1269475 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-299 | 19-299 | 19 | N/A | 66125 | Peel DSB | Vista Heights | Vista Heights Public Elementary School | ELE | 2395 | 6839 | 6839-B01 | 89 VISTA BLVD | MISSISSAUGA | L5M1V8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5752 | -79.7257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8499964 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8499964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8499964 | 8499964 | 8499964 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-301 | 19-301 | 19 | N/A | 66125 | Peel DSB | Walnut Grove | Walnut Grove Public Elementary School | ELE | 24223 | 19215 | 19215-B01 | 10 PINESTAFF RD | BRAMPTON | L6P3X8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7791 | -79.6949 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 798 | - | - | N | - | Approved | 44678 | 12796946 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 11978453 | 0 | 0 | 0 | 0 | 0 | 12478453 | 12478453 | 12796946 | 318493 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11978453
19-303 | 19-303 | 19 | N/A | 66125 | Peel DSB | Westervelts Corners | Westervelts Corners Public Elementary School | ELE | 9786 | 10178 | 10178-B01 | 20 BRICKYARD WAY | BRAMPTON | L6V4L5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7042 | -79.7804 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5377701 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5377701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5377701 | 5377701 | 5377701 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-305 | 19-305 | 19 | N/A | 66125 | Peel DSB | WG Davis | WG Davis Public Elementary School | ELE | 2107 | 6658 | 6658-B01 | 491 BARTLEY BULL PKY | BRAMPTON | L6W2M7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.671 | -79.7324 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1894225 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894225 | 1894225 | 1894225 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-306 | 19-306 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Whaley's Corner | Whaley's Corner Public Elementary School | ELE | 24518 | 19523 | 19523-B01 | 140 HOWARD STEWART RD | BRAMPTON | L6Y6B1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6318 | -79.7865 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 650 | 2 | 39 | N | - | Approved | 44678 | 13128399 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 43178 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 1512510 | 0 | 10405438 | 0 | 1008340 | 0 | 0 | 0 | 12926288 | 13026288 | 13128399 | 102111 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11413778
19-307 | 19-307 | 19 | N/A | 66125 | Peel DSB | Whitehorn | Whitehorn Public Elementary School | ELE | 9920 | 10328 | 10328-B01 | 5785 WHITEHORN AVE | MISSISSAUGA | L5V2A9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5961 | -79.7024 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7003601 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7003601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7003601 | 7003601 | 7003601 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-308 | 19-308 | 19 | N/A | 66125 | Peel DSB | Whitehorn | Whitehorn Public Elementary School | ELE | 9920 | 10328 | 10328-B01 | 5785 WHITEHORN AVE | MISSISSAUGA | L5V2A9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5961 | -79.7024 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1155394 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155394 | 1155394 | 1155394 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-310 | 19-310 | 19 | N/A | 66125 | Peel DSB | Whiteoaks | Whiteoaks Public Elementary School | ELE | 2493 | 6899 | 6899-B01 | 1690 MAZO CRES | MISSISSAUGA | L5J1Y8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5267 | -79.632 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2762759 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2762759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2762759 | 2762759 | 2762759 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-312 | 19-312 | 19 | N/A | 66125 | Peel DSB | Williams Parkway | Williams Parkway Public Elementary School | ELE | 2531 | 6920 | 6920-B01 | 1285 WILLIAMS PKY | BRAMPTON | L6S3J8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7307 | -79.7331 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1778239 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778239 | 1778239 | 1778239 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-313 | 19-313 | 19 | N/A | 66125 | Peel DSB | Willow Way | Willow Way Public Elementary School | ELE | 2554 | 5943 | 5943-B01 | 1715 WILLOW WAY | MISSISSAUGA | L5M3W5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5878 | -79.7097 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3397287 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3397287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3397287 | 3397287 | 3397287 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-314 | 19-314 | 19 | N/A | 66125 | Peel DSB | Worthington | Worthington Public Elementary School | ELE | 10132 | 10413 | 10413-B01 | 71 WORTHINGTON AVE | BRAMPTON | L7A1N9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6844 | -79.8188 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7467434 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7467434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7467434 | 7467434 | 7467434 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-315 | 19-315 | 19 | N/A | 66125 | Peel DSB | Worthington | Worthington Public Elementary School | ELE | 10132 | 10413 | 10413-B01 | 71 WORTHINGTON AVE | BRAMPTON | L7A1N9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6844 | -79.8188 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3938588 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3938588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3938588 | 3938588 | 3938588 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-317 | 19-317 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Dolson | Dolson Public Elementary School | ELE | 24887 | 19893 | 19893-B01 | 95 REMEMBRANCE RD | BRAMPTON | L7A4W3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6947 | -79.8514 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 852 | 2 | 39 | Y | - | Approved | 42892 | 17970246 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43346 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 2016680 | 0 | 12188713 | 0 | 1008340 | 0 | 0 | 0 | 15213733 | 15313733 | 17970246 | 2656513 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13197053
19-318 | 19-318 | 19 | N/A | 66125 | Peel DSB | Ruth Thompson | Ruth Thompson Public Elementary School | ELE | 10401 | 11100 | 11100-B01 | 5605 FRESHWATER DR | MISSISSAUGA | L5M7M8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5519 | -79.7403 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 184 | - | - | N | - | Approved | 42880 | 3608434 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3407667 | 0 | 0 | 0 | 0 | 0 | 3407667 | 3407667 | 3608434 | 200767 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3407667
19-319 | 19-319 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Caledon Central | Caledon Central Public Elementary School | ELE | 302 | 5484 | 5484-B01 | 18357 KENNEDY RD | CALEDON VILLAGE | L7K1Y7 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8711 | -79.9833 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44678 | 1118861 | Construction Complete | Addition | Child Care | 2018-19 | 43357 | 0 | 0 | 0 | 0 | 0 | 0 | 1118861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118861 | 1118861 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-320 | 19-320 | 19 | N/A | 66125 | Peel DSB | Esker Lake | Esker Lake Public Elementary School | ELE | 758 | 5801 | 5801-B01 | 10420 HEART LAKE RD | BRAMPTON | L6Z4S2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7326 | -79.7773 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 391 | - | - | N | - | Approved | 43166 | 7983063 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6518943 | 0 | 0 | 0 | 0 | 0 | 6518943 | 6518943 | 6518943 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6518943
19-321 | 19-321 | 19 | N/A | 66125 | Peel DSB | Glenforest | Glenforest Public Secondary School | SEC | 5394 | 5848 | 5848-B02 | 3575 FIELDGATE DR | MISSISSAUGA | L4X2J6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6271 | -79.5926 | 43509 | 2018-19 | 2018-19 | - | - | - | 43509 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43509 | 8200000 | Construction Complete | Retrofit | Condition | 2021-22 | 44443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8200000 | 0 | 0 | 0 | 0 | 0 | 8200000 | 8200000 | 8200000 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8200000
19-322 | 19-322 | 19 | N/A | 66125 | Peel DSB | TL Kennedy | TL Kennedy Public Secondary School | SEC | 5706 | 8403 | 8403-B01 | 3100 HURONTARIO ST | MISSISSAUGA | L5B1N7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5815 | -79.6205 | 43182 | 2017-18 | 2017-18 | - | - | - | 43182 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43182 | 2500000 | Construction Complete | Retrofit | Condition | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000 | 2500000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2500000
19-323 | 19-323 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Hickory Wood | Hickory Wood Public Elementary School | ELE | 1058 | 5989 | 5989-B01 | 630 RAY LAWSON BLVD | BRAMPTON | L6Y4W8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6463 | -79.7428 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 34 | Y | - | Approved | 45142 | 1427893 | Construction Complete | Retrofit | Child Care | 2021-22 | 44443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1427893 | 0 | 0 | 0 | 1427893 | 1427893 | 1427893 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1427893
19-324 | 19-324 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Lancaster | Lancaster Public Elementary School | ELE | 1327 | 6146 | 6146-B01 | 7425 NETHERWOOD RD | MISSISSAUGA | L4T2N7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.7178 | -79.6476 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Approved | 45142 | 823208 | Construction Complete | Retrofit | Child Care | 2020-21 | 44228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823208 | 0 | 0 | 0 | 823208 | 823208 | 773454 | 823208 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 823208
19-325 | 19-325 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Massey | Massey Public Elementary School | ELE | 1427 | 6211 | 6211-B01 | 95 MASSEY ST | BRAMPTON | L6S3A3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7379 | -79.7467 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44287 | 1994793 | Under Construction | Retrofit | Child Care | 2022-23 | 44956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1994793 | 0 | 0 | 0 | 1994793 | 1994793 | 1994793 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1994793
19-326 | 19-326 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Munden Park | Munden Park Public Elementary School | ELE | 1589 | 6320 | 6320-B01 | 515 TEDWYN DR | MISSISSAUGA | L5A1J8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5832 | -79.5925 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 43887 | 632371 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771116 | 0 | 0 | 0 | 771116 | 771116 | 771116 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 771116
19-327 | 19-327 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Gordon Graydon Memorial | Gordon Graydon Memorial Public Secondary School | SEC | 5399 | 5334 | 5334-B02 | 1490 OGDEN AVE | MISSISSAUGA | L5E2H8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5859 | -79.5721 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43887 | 2308816 | Construction Complete | Retrofit | Child Care | 2021-22 | 44443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2358675 | 0 | 0 | 0 | 2358675 | 2358675 | 2358675 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2358675
19-328 | 19-328 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Meadowvale | Meadowvale Public Secondary School | SEC | 5516 | 5766 | 5766-B02 | 6700 EDENWOOD DR | MISSISSAUGA | L5N3B2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5779 | -79.7613 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43887 | 1504883 | Construction Complete | Retrofit | Child Care | 2020-21 | 44235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1553921 | 0 | 0 | 0 | 1553921 | 1553921 | 1553921 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1553921
19-329 | 19-329 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Worthington | Worthington Public Elementary School | ELE | 10132 | 10413 | 10413-B01 | 71 WORTHINGTON AVE | BRAMPTON | L7A1N9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6844 | -79.8188 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 45142 | 1163870 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163870 | 0 | 0 | 0 | 1163870 | 1163870 | 1163870 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1163870
19-330 | 19-330 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Shaw | Shaw Public Elementary School | ELE | 10975 | 12119 | 12119-B01 | 10 FATHER TOBIN RD | BRAMPTON | L6R3K2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7753 | -79.7513 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44071 | 1536658 | Under Construction | Retrofit | Child Care | 2023-24 | 45173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536658 | 0 | 0 | 0 | 1536658 | 1536658 | 1536658 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1536658
19-331 | 19-331 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Palgrave | Palgrave Public Elementary School | ELE | 11132 | 6421 | 6421-B01 | 8962 PATTERSON SIDEROAD | PALGRAVE | L7E0L2 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.9473 | -79.833 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43887 | 929963 | Construction Complete | Retrofit | Child Care | 2020-21 | 44137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033916 | 0 | 0 | 0 | 1033916 | 1033916 | 1033916 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1033916
19-332 | 19-332 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Elm Drive | Elm Drive Public Elementary School | ELE | 24521 | 5125 | 5125-B02 | 3492 KARIYA DR | MISSISSAUGA | L5B0L2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5879 | -79.6328 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 650 | 4 | 73 | Y | 1 | Approved | 43929 | 19773297 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44650 | 0 | 0 | 0 | 0 | 2371303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2371303 | 0 | 0 | 1542760 | 0 | 13338382 | 0 | 2016682 | 504170 | 0 | 0 | 17401994 | 19773297 | 19773297 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15859234
19-333 | 19-333 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Private Buckam Singh | Private Buckam Singh Public Elementary School | ELE | 25094 | 20100 | 20100-B01 | 100 MARTIN BYRNE DRIVE | BRAMPTON | L6P4C7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.8158 | -79.7303 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 662 | 4 | 73 | Y | 1 | Approved | 43560 | 16113986 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542759 | 0 | 12050374 | 0 | 2016682 | 504171 | 0 | 0 | 16113986 | 16113986 | 16113986 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14571227
19-334 | 19-334 | 19 | N/A | 66125 | Peel DSB | Thomas Street | Thomas Street Public Elementary School | ELE | 9767 | 10252 | 10252-B01 | 2640 THOMAS ST | MISSISSAUGA | L5M5G8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5671 | -79.7257 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 138 | - | - | - | - | Approved | 44785 | 4733084 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4733084 | 0 | 0 | 0 | 0 | 0 | 4733084 | 4733084 | 4733084 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4733084
19-335 | 19-335 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Malala Yousafzai | Malala Yousafzai Public Elementary School | ELE | 25108 | 20114 | 20114-B01 | 565 REMEMBRANCE RD | BRAMPTON | L7A4L2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7152 | -79.8321 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 850 | 4 | 73 | - | - | Approved | 44750 | 29596459 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45171 | 0 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 25993999 | 0 | 3127460 | 0 | 0 | 0 | 29121459 | 29596459 | 29596459 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 29121459
19-336 | 19-336 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Mount Pleasant 9 | Mount Pleasant 9 Public Elementary School | ELE | 25110 | 20116 | 20116-B01 | CHINGUACOUSY RD / MAYFIELD RD | BRAMPTON | TBD | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7141 | -79.8461 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 850 | 4 | 73 | N | - | Approved | 45184 | 34231972 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45356 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 2979408 | 0 | 28713268 | 0 | 2139296 | 0 | 0 | 0 | 33831972 | 34231972 | 31252564 | -2979408 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 30852564
19-337 | 19-337 | 19 | N/A | 66125 | Peel DSB | Brandon Gate | Brandon Gate Public Elementary School | ELE | 227 | 5439 | 5439-B01 | 3800 BRANDON GATE DR | MISSISSAUGA | L4T3V9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.7326 | -79.6414 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44124 | 860003 | Construction Complete | Addition | FDK | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860003 | 860003 | 860003 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-338 | 19-338 | 19 | N/A | 66125 | Peel DSB | Elmcrest | Elmcrest Public Elementary School | HFA | 734 | 5785 | 5785-B01 | 2620 CHALKWELL CLOSE | MISSISSAUGA | L5J2B9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.509 | -79.6547 | 44168 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44168 | 900000 | Construction Complete | Demolition | Other | 2021-22 | 44440 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
19-339 | 19-339 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Cashmere Avenue | Cashmere Avenue Public Elementary School | ELE | 399 | 5562 | 5562-B01 | 2455 CASHMERE AVE | MISSISSAUGA | L5B2M7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.565 | -79.626 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 73 | N | - | Planned | - | - | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139296 | 0 | 0 | 0 | 2139296 | 2139296 | 2139296 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 2139296
19-340 | 19-340 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Agnes Taylor | Agnes Taylor Public Elementary School | ELE | 31 | 5319 | 5319-B01 | 80 BEECH ST | BRAMPTON | L6V1V6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6977 | -79.7573 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 73 | N | - | Planned | - | - | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139296 | 0 | 0 | 0 | 2139296 | 2139296 | 2139296 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 2139296
19-341 | 19-341 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Ellengale | Ellengale Public Elementary School | ELE | 728 | 5781 | 5781-B01 | 3480 ELLENGDALE DR | MISSISSAUGA | L5C1Z7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5636 | -79.6591 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 875 | 4 | 73 | N | - | Approved | 44678 | 26305689 | Under Construction | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22258951 | 0 | 4046738 | 0 | 0 | 0 | 26305689 | 26305689 | 26305689 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 26305689
19-342 | 19-342 | 19 | 232 - CMSM Peel | 66125 | Peel DSB | Caledon East | Caledon East Public Elementary School | ELE | TBD | TBD | TBD | TBD | CALEDON | L7C1P6 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 650 | 4 | 73 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2025-26 | 45908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16836434 | 0 | 2607797 | 0 | 0 | 0 | 19444231 | 19444231 | 19444231 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19444231
20-001 | 20-001 | 20 | N/A | 66133 | Halton DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | -72 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 72
20-002 | 20-002 | 20 | N/A | 66133 | Halton DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 41297126 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41049948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41049948 | 41049948 | 41297126 | 247178 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-003 | 20-003 | 20 | N/A | 66133 | Halton DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Other | Other | 2016-17 | 42614 | 0 | 0 | 4223000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4223000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4223000 | 4223000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-004 | 20-004 | 20 | N/A | 66133 | Halton DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 394124 | Construction Complete | Other | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394124 | 394124 | 394124 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-005 | 20-005 | 20 | N/A | 66133 | Halton DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1144138 | Construction Complete | Other | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144138 | 1144138 | 1144138 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-006 | 20-006 | 20 | N/A | 66133 | Halton DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4115415 | Construction Complete | Other | Other | 2007-08 | 39326 | 1780820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 569124 | 2349944 | 1765471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765471 | 4115415 | 4115415 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-007 | 20-007 | 20 | N/A | 66133 | Halton DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1982339 | Construction Complete | Other | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452220 | 452220 | 1530119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530119 | 1982339 | 1982339 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-008 | 20-008 | 20 | N/A | 66133 | Halton DSB | Abbey Park | Abbey Park Public Secondary School | SEC | 10577 | 11223 | 11223-B01 | 1455 GLEN ABBEY GATE | OAKVILLE | L6M2G5 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4364 | -79.7362 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17617840 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 1297571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1297571 | 16320269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16320269 | 17617840 | 17617840 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-009 | 20-009 | 20 | N/A | 66133 | Halton DSB | Aldershot | Aldershot Public Secondary School | SEC | 5200 | 8113 | 8113-B01 | 50 FAIRWOOD PL W | BURLINGTON | L7T1E5 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3036 | -79.8526 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2147066 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 54214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 154214 | 1992852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992852 | 2147066 | 2147066 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-010 | 20-010 | 20 | N/A | 66133 | Halton DSB | Alexander's | Alexander's Public Elementary School | ELE | 10824 | 12058 | 12058-B01 | 2223 SUTTON DR | BURLINGTON | L7L0B9 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4058 | -79.7853 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8849764 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8849764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8849764 | 8849764 | 8849764 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-012 | 20-012 | 20 | N/A | 66133 | Halton DSB | Alton Village | Alton Village Public Elementary School | ELE | 22140 | 19140 | 19140-B01 | 3290 STEEPLECHASE DR | BURLINGTON | L7M0W1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4003 | -79.8272 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 704 | - | - | N | - | Approved | 40774 | 12890733 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1901064 | 0 | 10989669 | 0 | 0 | 0 | 0 | 0 | 12890733 | 12890733 | 12890733 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10989669
20-013 | 20-013 | 20 | N/A | 66133 | Halton DSB | Alton Village | Alton Village Public Elementary School | ELE | 22140 | 19140 | 19140-B01 | 3290 STEEPLECHASE DR | BURLINGTON | L7M0W1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4003 | -79.8272 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 115 | - | - | N | - | Approved | 42447 | 2271364 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2104524 | 0 | 0 | 0 | 0 | 0 | 2104524 | 2104524 | 2104524 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2104524
20-014 | 20-014 | 20 | N/A | 66133 | Halton DSB | Anne J MacArthur | Anne J MacArthur Public Elementary School | ELE | 24244 | 19236 | 19236-B01 | 820 FARMSTEAD DR | MILTON | L9T8J6 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4963 | -79.8613 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 740 | - | - | N | - | Not Required | - | 11219226 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 623065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623065 | 0 | 0 | 950532 | 0 | 10268694 | 0 | 0 | 0 | 0 | 0 | 11219226 | 11842291 | 11219226 | -623065 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10268694
20-015 | 20-015 | 20 | N/A | 66133 | Halton DSB | Boyne | Boyne Public Elementary School | ELE | 24385 | 19386 | 19386-B01 | 1110 FARMSTEAD DR | MILTON | L9E0B5 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4909 | -79.8537 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 740 | - | - | N | - | Not Required | - | 13502903 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1901064 | 0 | 11004224 | 0 | 0 | 0 | 0 | 0 | 12905288 | 12905288 | 12905288 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11004224
20-016 | 20-016 | 20 | N/A | 66133 | Halton DSB | Brant Hills | Brant Hills Public Elementary School | ELE | 232 | 5443 | 5443-B01 | 2330 DUNCASTER DR | BURLINGTON | L7P4S6 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.365 | -79.8457 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 247182 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247182 | 247182 | 247182 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-019 | 20-019 | 20 | N/A | 66133 | Halton DSB | Bruce Trail | Bruce Trail Public Elementary School | ELE | 10823 | 12057 | 12057-B01 | 1199 COSTIGAN RD | MILTON | L9T6N8 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5231 | -79.8494 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8929161 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8929161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8929161 | 8929161 | 8929161 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-020 | 20-020 | 20 | N/A | 66133 | Halton DSB | Bruce Trail | Bruce Trail Public Elementary School | ELE | 10823 | 12057 | 12057-B01 | 1199 COSTIGAN RD | MILTON | L9T6N8 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5231 | -79.8494 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1745615 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317088 | 317088 | 1428527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428527 | 1745615 | 1745615 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-022 | 20-022 | 20 | N/A | 66133 | Halton DSB | Captain R Wilson | Captain R Wilson Public Elementary School | ELE | 10612 | 11180 | 11180-B01 | 2145 GRAND OAK TRAIL | OAKVILLE | L6M4S7 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4289 | -79.7592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8015636 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8015636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8015636 | 8015636 | 8015636 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-026 | 20-026 | 20 | N/A | 66133 | Halton DSB | Charles R Beaudoin | Charles R Beaudoin Public Elementary School | ELE | 10640 | 11176 | 11176-B01 | 4313 CLUBVIEW DR | BURLINGTON | L7M5A1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3967 | -79.8078 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7835388 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 289300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289300 | 7546088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7546088 | 7835388 | 7835388 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-027 | 20-027 | 20 | N/A | 66133 | Halton DSB | Charles R Beaudoin | Charles R Beaudoin Public Elementary School | ELE | 10640 | 11176 | 11176-B01 | 4313 CLUBVIEW DR | BURLINGTON | L7M5A1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3967 | -79.8078 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1968376 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968376 | 1968376 | 1968376 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-028 | 20-028 | 20 | N/A | 66133 | Halton DSB | Chris Hadfield | Chris Hadfield Public Elementary School | ELE | 10469 | 11116 | 11116-B01 | 1114 WOODWARD AVE | MILTON | L9T5P5 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5349 | -79.8676 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7547849 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 311854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311854 | 7235995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7235995 | 7547849 | 7547849 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-030 | 20-030 | 20 | N/A | 66133 | Halton DSB | Chris Hadfield | Chris Hadfield Public Elementary School | ELE | 10469 | 11116 | 11116-B01 | 1114 WOODWARD AVE | MILTON | L9T5P5 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5349 | -79.8676 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1557001 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 1557001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557001 | 1557001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-032 | 20-032 | 20 | N/A | 66133 | Halton DSB | Craig Kielburger | Craig Kielburger Public Secondary School | SEC | 11148 | 12286 | 12286-B01 | 1151 FERGUSON DR | MILTON | L9T7V8 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5147 | -79.8268 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 28586912 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28586912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28586912 | 28586912 | 28586912 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-033 | 20-033 | 20 | N/A | 66133 | Halton DSB | Craig Kielburger | Craig Kielburger Public Secondary School | SEC | 11148 | 12286 | 12286-B01 | 1151 FERGUSON DR | MILTON | L9T7V8 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5147 | -79.8268 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 210 | - | - | N | - | Approved | 42760 | 7216998 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7216998 | 0 | 0 | 0 | 0 | 0 | 7216998 | 7216998 | 7216998 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7216998
20-035 | 20-035 | 20 | N/A | 66133 | Halton DSB | Dr. Frank J Hayden | Dr. Frank J Hayden Public Secondary School | SEC | 24203 | 19195 | 19195-B01 | 3040 TIM DOBBIE DR | BURLINGTON | L7M0M3 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.398 | -79.8184 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 1194 | - | - | N | - | Not Required | - | 31439209 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 2000004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000004 | 0 | 0 | 0 | 0 | 29439205 | 0 | 0 | 0 | 0 | 0 | 29439205 | 31439209 | 31439209 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 29439205
20-037 | 20-037 | 20 | N/A | 66133 | Halton DSB | Emily Carr | Emily Carr Public Elementary School | ELE | 11051 | 12162 | 12162-B01 | 2255 PINE GLEN RD | OAKVILLE | L6M0G5 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4428 | -79.7637 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10036637 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10036637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10036637 | 10036637 | 10036637 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-039 | 20-039 | 20 | N/A | 66133 | Halton DSB | Escarpment View | Escarpment View Public Elementary School | ELE | 11146 | 12188 | 12188-B01 | 351 SCOTT BLVD | MILTON | L9T0T1 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4975 | -79.8812 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11710125 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10379489 | 0 | 1330636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710125 | 11710125 | 11710125 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-042 | 20-042 | 20 | N/A | 66133 | Halton DSB | Florence Meares | Florence Meares Public Elementary School | ELE | 10391 | 10492 | 10492-B01 | 2102 BERWICK DR | BURLINGTON | L7M4W6 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3863 | -79.8088 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7966851 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 334378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334378 | 7632473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7632473 | 7966851 | 7966851 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-044 | 20-044 | 20 | N/A | 66133 | Halton DSB | Forest Trail | Forest Trail Public Elementary School | ELE | 10909 | 12072 | 12072-B01 | 1406 PINE GLEN RD | OAKVILLE | L6M4B9 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4508 | -79.7531 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9146752 | Construction Complete | New Construction | Accommodation Pressure | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9146752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9146752 | 9146752 | 9146752 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-045 | 20-045 | 20 | N/A | 66133 | Halton DSB | Forest Trail | Forest Trail Public Elementary School | ELE | 10909 | 12072 | 12072-B01 | 1406 PINE GLEN RD | OAKVILLE | L6M4B9 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4508 | -79.7531 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 184 | - | - | N | - | Not Required | - | 2034419 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034419 | 0 | 0 | 0 | 0 | 0 | 2034419 | 2034419 | 2034419 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2034419
20-046 | 20-046 | 20 | N/A | 66133 | Halton DSB | Ethel Gardiner | Ethel Gardiner Public Elementary School | ELE | 10910 | 12073 | 12073-B01 | 14365 DANBY RD | GEORGETOWN | L7G6L8 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6268 | -79.8813 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10951410 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10951410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10951410 | 10951410 | 10951410 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-047 | 20-047 | 20 | N/A | 66133 | Halton DSB | Garth Webb | Garth Webb Public Secondary School | SEC | 18628 | 19084 | 19084-B01 | 2820 WESTOAK TRAILS BLVD | OAKVILLE | L6M4W2 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4348 | -79.7547 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 27505001 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 8242668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8242668 | 19262333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19262333 | 27505001 | 27505001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-049 | 20-049 | 20 | N/A | 66133 | Halton DSB | Georgetown District | Georgetown District Public Secondary School | SEC | 5387 | 5218 | 5218-B02 | 70 GUELPH ST | GEORGETOWN | L7G3Z5 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6508 | -79.9211 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13284365 | Construction Complete | Addition | Other | 2014-15 | 41883 | 6000000 | 0 | 4623257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10623257 | 1708616 | 952492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2661108 | 13284365 | 13284365 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-054 | 20-054 | 20 | N/A | 66133 | Halton DSB | Hawthorne Village | Hawthorne Village Public Elementary School | ELE | 10647 | 11182 | 11182-B01 | 850 BENNETT BLVD | MILTON | L9T6X9 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5142 | -79.838 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8540395 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8540395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8540395 | 8540395 | 8540395 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-055 | 20-055 | 20 | N/A | 66133 | Halton DSB | Hawthorne Village | Hawthorne Village Public Elementary School | ELE | 10647 | 11182 | 11182-B01 | 850 BENNETT BLVD | MILTON | L9T6X9 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5142 | -79.838 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1733453 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733453 | 1733453 | 1733453 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-057 | 20-057 | 20 | N/A | 66133 | Halton DSB | Heritage Glen | Heritage Glen Public Elementary School | ELE | 1050 | 5984 | 5984-B01 | 1641 HERITAGE WAY | OAKVILLE | L6M2Z4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.432 | -79.7418 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1156153 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1156153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1156153 | 1156153 | 1156153 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-058 | 20-058 | 20 | N/A | 66133 | Halton DSB | Irma Coulson | Irma Coulson Public Elementary School | ELE | 24206 | 19198 | 19198-B01 | 625 SAUVE ST | MILTON | L9T8M4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5232 | -79.842 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 704 | - | - | N | - | Not Required | - | 12373890 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1901064 | 0 | 10472826 | 0 | 0 | 0 | 0 | 0 | 12373890 | 12373890 | 12373890 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10472826
20-059 | 20-059 | 20 | N/A | 66133 | Halton DSB | James W Hill | James W Hill Public Elementary School | ELE | 11525 | 12250 | 12250-B01 | 2860 KINGSWAY DR | OAKVILLE | L6J6R3 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.5013 | -79.6608 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9461857 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8819716 | 8819716 | 642141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642141 | 9461857 | 9461857 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-062 | 20-062 | 20 | N/A | 66133 | Halton DSB | John William Boich | John William Boich Public Elementary School | ELE | 11257 | 12285 | 12285-B01 | 2474 SUTTON DR | BURLINGTON | L7L0G2 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4116 | -79.802 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 267701 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 267701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267701 | 267701 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-063 | 20-063 | 20 | N/A | 66133 | Halton DSB | John William Boich | John William Boich Public Elementary School | ELE | 11257 | 12285 | 12285-B01 | 2474 SUTTON DR | BURLINGTON | L7L0G2 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4116 | -79.802 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11046001 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9715365 | 0 | 1330636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11046001 | 11046001 | 11046001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-065 | 20-065 | 20 | N/A | 66133 | Halton DSB | Joshua Creek | Joshua Creek Public Elementary School | ELE | 10648 | 11185 | 11185-B01 | 1450 ARROWHEAD RD | OAKVILLE | L6H7P9 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4996 | -79.6977 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8348759 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8348759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8348759 | 8348759 | 8348759 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-066 | 20-066 | 20 | N/A | 66133 | Halton DSB | Joshua Creek | Joshua Creek Public Elementary School | ELE | 10648 | 11185 | 11185-B01 | 1450 ARROWHEAD RD | OAKVILLE | L6H7P9 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4996 | -79.6977 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2775449 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775449 | 2775449 | 2775449 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-068 | 20-068 | 20 | N/A | 66133 | Halton DSB | Kilbride | Kilbride Public Elementary School | ELE | 1261 | 6100 | 6100-B01 | 1-6611 PANTON ST | BURLINGTON | L7P0L8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4275 | -79.9364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 732773 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732773 | 732773 | 732773 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-069 | 20-069 | 20 | N/A | 66133 | Halton DSB | Lakeshore | Lakeshore Public Elementary School | ELE | 1314 | 6138 | 6138-B01 | 2243 LAKESHORE RD | BURLINGTON | L7R1B1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3299 | -79.7871 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3613660 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3613660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3613660 | 3613660 | 3613660 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-070 | 20-070 | 20 | N/A | 66133 | Halton DSB | Lorne Skuce | Lorne Skuce Public Elementary School | ELE | 1395 | 6189 | 6189-L01 | 150 RIDGE DR | OAKVILLE | L6H1B8 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4608 | -79.6929 | 41568 | 2013-14 | 2013-14 | 41568 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 278688 | Construction Complete | Land Acquisition | Other | 2013-14 | 41730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278688 | 0 | 0 | 0 | 0 | 0 | 0 | 278688 | 278688 | 278688 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 278688
20-071 | 20-071 | 20 | N/A | 66133 | Halton DSB | Maple Grove | Maple Grove Public Elementary School | ELE | 1444 | 6224 | 6224-B01 | 288 MAPLE GROVE DR | OAKVILLE | L6J4V5 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4737 | -79.6505 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6148124 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5131033 | 0 | 1017091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6148124 | 6148124 | 6148124 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-073-01 | 20-073 | 20 | N/A | 66133 | Halton DSB | Martin Street | Martin Street Public Elementary School | ELE | 24528 | 6245 | 6245-B02 | 184 MARTIN ST | MILTON | L9T2R4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5159 | -79.8885 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 746 | - | - | N | - | Approved | 42499 | 13534012 | Construction Complete | New Construction | Condition | 2017-18 | 42979 | 0 | 0 | 1141705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | oo | 1141705 | 0 | 0 | 988568 | 0 | 11212258 | 0 | 0 | 0 | 0 | 0 | 12200826 | 13342531 | 13342531 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11212258
20-073-03 | 20-073 | 20 | N/A | 66133 | Halton DSB | Martin Street | Martin Street Public Elementary School | ELE | 1474 | 6245 | 6245-B01 | 184 MARTIN ST | MILTON | L9T2R4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5162 | -79.889 | 42347 | 2015-16 | 2015-16 | - | - | - | 42347 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42347 | 637420 | Construction Complete | Demolition | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637420 | 0 | 0 | 0 | 0 | 0 | 637420 | 637420 | 637420 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 637420
20-075 | 20-075 | 20 | N/A | 66133 | Halton DSB | Mohawk Gardens | Mohawk Gardens Public Elementary School | ELE | 1557 | 6300 | 6300-B01 | 5280 SPRUCE AVE | BURLINGTON | L7L1N3 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3711 | -79.7401 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1939114 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939114 | 1939114 | 1939114 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-076 | 20-076 | 20 | N/A | 66133 | Halton DSB | Montclair | Montclair Public Elementary School | ELE | 1575 | 6313 | 6313-B01 | 1285 MONTCLAIR DR | OAKVILLE | L6H1Z3 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4631 | -79.6991 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3574861 | Construction Complete | Addition | Other | 2009-10 | 40057 | 100000 | 0 | 1552455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432948 | 2085403 | 751913 | 294000 | 443545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489458 | 3574861 | 3574861 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-078 | 20-078 | 20 | N/A | 66133 | Halton DSB | Munns | Munns Public Elementary School | ELE | 1590 | 6321 | 6321-B01 | 1511 SIXTH LINE | OAKVILLE | L6H1X8 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4655 | -79.7095 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3843146 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1227146 | 1607146 | 1736000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2236000 | 3843146 | 3843146 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-079 | 20-079 | 20 | N/A | 66133 | Halton DSB | New Central | New Central Public Elementary School | ELE | 1613 | 6341 | 6341-B01 | 133 BALSAM DR | OAKVILLE | L6J3X4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4534 | -79.6619 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2100000 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 1656455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656455 | 0 | 0 | 443545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443545 | 2100000 | 2100000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-080 | 20-080 | 20 | N/A | 66133 | Halton DSB | Oodenawi | Oodenawi Public Elementary School | ELE | 24384 | 19385 | 19385-B01 | 385 SIXTEEN MILE DR | OAKVILLE | L6M0Z4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4735 | -79.7435 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 746 | - | - | N | - | Not Required | - | 14503807 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 1218673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218673 | 0 | 0 | 988568 | 0 | 11403739 | 0 | 0 | 0 | 0 | 0 | 12392307 | 13610980 | 13610980 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11403739
20-081 | 20-081 | 20 | N/A | 66133 | Halton DSB | Orchard Park | Orchard Park Public Elementary School | ELE | 10468 | 11115 | 11115-B01 | 5151 DRYDEN AVE | BURLINGTON | L7L7J3 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4019 | -79.7971 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7327818 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 290122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290122 | 7037696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7037696 | 7327818 | 7327818 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-083 | 20-083 | 20 | N/A | 66133 | Halton DSB | Palermo | Palermo Public Elementary School | ELE | 11256 | 12249 | 12249-B01 | 2561 VALLEYRIDGE DR | OAKVILLE | L6M5H4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4321 | -79.7762 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10842111 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9511475 | 0 | 1330636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10842111 | 10842111 | 10842111 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-088 | 20-088 | 20 | N/A | 66133 | Halton DSB | Pilgrim Wood | Pilgrim Wood Public Elementary School | ELE | 1803 | 6454 | 6454-B01 | 1551 PILGRIMS WAY | OAKVILLE | L6M2W7 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4342 | -79.7289 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Not Required | - | 2168888 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168888 | 0 | 0 | 0 | 0 | 0 | 2168888 | 2168888 | 2168888 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2168888
20-090 | 20-090 | 20 | N/A | 66133 | Halton DSB | PL Robertson | PL Robertson Public Elementary School | ELE | 11147 | 12187 | 12187-B01 | 840 SCOTT BLVD | MILTON | L9T2C9 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4877 | -79.871 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11874239 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10543603 | 0 | 1330636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11874239 | 11874239 | 11874239 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-091 | 20-091 | 20 | N/A | 66133 | Halton DSB | Post's Corners | Post's Corners Public Elementary School | ELE | 10341 | 11076 | 11076-B01 | 2220 CALDWELL DR | OAKVILLE | L6H6B5 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4757 | -79.7146 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8022869 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 108671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319343 | 428014 | 7594855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7594855 | 8022869 | 8022869 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-095 | 20-095 | 20 | N/A | 66133 | Halton DSB | Robert Bateman | Robert Bateman Public Secondary School | SEC | 5497 | 8288 | 8288-B01 | 5151 NEW ST | BURLINGTON | L7L1V3 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3717 | -79.7498 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8826156 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 18358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18358 | 8807798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8807798 | 8826156 | 8826156 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-101 | 20-101 | 20 | N/A | 66133 | Halton DSB | Silver Creek | Silver Creek Public Elementary School | ELE | 10450 | 11108 | 11108-B01 | 170 EATON ST | GEORGETOWN | L7G5V6 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.631 | -79.8939 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7869699 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7869699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7869699 | 7869699 | 7869699 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-103 | 20-103 | 20 | N/A | 66133 | Halton DSB | Sunningdale | Sunningdale Public Elementary School | ELE | 2260 | 6750 | 6750-B01 | 1434 OXFORD AVE | OAKVILLE | L6H1T4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4589 | -79.7121 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2941906 | Construction Complete | Addition | Other | 2010-11 | 40422 | 928000 | 0 | 432000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1010095 | 2370095 | 371811 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571811 | 2941906 | 2941906 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-104 | 20-104 | 20 | N/A | 66133 | Halton DSB | Tiger Jeet Singh | Tiger Jeet Singh Public Elementary School | ELE | 11145 | 12248 | 12248-B01 | 650 YATES DR | MILTON | L9T7P6 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5085 | -79.8536 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11319250 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9988614 | 0 | 1330636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11319250 | 11319250 | 11319250 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-106 | 20-106 | 20 | N/A | 66133 | Halton DSB | West Oak | West Oak Public Elementary School | ELE | 10393 | 10493 | 10493-B01 | 2071 FOURTH LINE | OAKVILLE | L6M3K1 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4485 | -79.7362 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8073741 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 360044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360044 | 7713697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7713697 | 8073741 | 8073741 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-108 | 20-108 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Viola Desmond | Viola Desmond Public Elementary School | ELE | 24593 | 19599 | 19599-B01 | 1450 LEGER WAY | MILTON | L9E1H9 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4795 | -79.8511 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 776 | 5 | 88 | Y | 2 | Approved | 43227 | 19295572 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2016679 | 0 | 13449703 | 0 | 2820850 | 1008340 | 0 | 0 | 19295572 | 19295572 | 19295572 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 17278893
20-109 | 20-109 | 20 | N/A | 66133 | Halton DSB | Elsie MacGill | Elsie MacGill Public Secondary School | SEC | 24594 | 19600 | 19600-B01 | 1410 BRONTE ST S | MILTON | L9T7K4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4829 | -79.8477 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 1221 | - | - | N | - | Approved | 43664 | 42489753 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44593 | 0 | 0 | 2827637 | 0 | 6915032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9742669 | 0 | 0 | 0 | 0 | 32747084 | 0 | 0 | 0 | 0 | 0 | 32747084 | 42489753 | 42489753 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 32747084
20-110 | 20-110 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Oakwood | Oakwood Public Elementary School | ELE | 1695 | 6388 | 6388-B01 | 357 BARTOS DR | OAKVILLE | L6K3E5 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4472 | -79.6833 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | N | 3 | Approved | 43091 | 1016630 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016630 | 0 | 0 | 1016630 | 1016630 | 1016630 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1016630
20-111 | 20-111 | 20 | N/A | 66133 | Halton DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 6448 | 11678 | 11678-B01 | 2050 GUELPH LINE | BURLINGTON | L7P5A8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3662 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42129 | 5000000 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
20-113 | 20-113 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Brant Hills | Brant Hills Public Elementary School | ELE | 232 | 5443 | 5443-B01 | 2330 DUNCASTER DR | BURLINGTON | L7P4S6 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.365 | -79.8457 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 48 | Y | - | Approved | 43258 | 771381 | Construction Complete | Retrofit | Child Care | 2018-19 | 43374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323172 | 0 | 0 | 0 | 323172 | 323172 | 771381 | 448209 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 323172
20-114 | 20-114 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Frontenac | Frontenac Public Elementary School | ELE | 861 | 5860 | 5860-B01 | 5140 PINEDALE AVE | BURLINGTON | L7L3V4 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3741 | -79.7529 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43993 | 2367026 | Construction Complete | Retrofit | Child Care | 2021-22 | 44561 | 500614 | 396504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897118 | 0 | 0 | 0 | 0 | 0 | 0 | 1469908 | 0 | 0 | 0 | 1469908 | 2367026 | 2367026 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1469908
20-115 | 20-115 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Oakville NE 2 | Oakville NE 2 Public Elementary School | ELE | 24836 | 19842 | 19842-B01 | 3199 POST RD | OAKVILLE | L6H7C5 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.487 | -79.7327 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 776 | 5 | 88 | Y | - | Approved | 43494 | 20746699 | Construction Complete | New Construction | Accommodation Pressure | 2020-21 | 44075 | 0 | 0 | 1626030 | 0 | 458171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084201 | 0 | 0 | 2098154 | 0 | 13993074 | 0 | 2571270 | 0 | 0 | 0 | 18662498 | 20746699 | 20746699 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16564344
20-116 | 20-116 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Milton SW 11 | Milton SW 11 Public Elementary School | ELE | 24837 | 19843 | 19843-B01 | 1385 KOVACHIK BLVD | MILTON | L9T2X5 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4801 | -79.8508 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 908 | 5 | 88 | Y | - | Approved | 44579 | 22874945 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 2388547 | 1500000 | 193900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082447 | 0 | 0 | 2098154 | 0 | 13993074 | 0 | 2701270 | 0 | 0 | 0 | 18792498 | 22874945 | 22874945 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16694344
20-117 | 20-117 | 20 | N/A | 66133 | Halton DSB | Nelson | Nelson Public Secondary School | SEC | 5535 | 8311 | 8311-B01 | 4181 NEW ST | BURLINGTON | L7L1T3 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.358 | -79.7653 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 219 | - | - | N | - | Approved | 43714 | 15184482 | Construction Complete | Addition | Consolidation | 2021-22 | 44562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15184482 | 0 | 0 | 0 | 0 | 0 | 15184482 | 15184482 | 15184482 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 15184482
20-118 | 20-118 | 20 | N/A | 66133 | Halton DSB | MM Robinson | MM Robinson Public Secondary School | SEC | 5501 | 8291 | 8291-B01 | 2425 UPPER MIDDLE RD | BURLINGTON | L7P3N9 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3638 | -79.8248 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 147 | - | - | N | - | Approved | 43509 | 7317037 | Construction Complete | Addition | Consolidation | 2020-21 | 44075 | 753889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 753889 | 0 | 0 | 0 | 0 | 6563148 | 0 | 0 | 0 | 0 | 0 | 6563148 | 7317037 | 7317037 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6563148
20-119 | 20-119 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Oakville NE 1 | Oakville NE 1 Public Secondary School | SEC | 24479 | 19484 | 19484-B01 | 1013 DUNDAS ST W | OAKVILLE | L6M4L8 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4649 | -79.7461 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | TBD | 2021-22 | 2021-22 | - | - | - | - | - | - | 1200 | 5 | 88 | N | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33640009 | 0 | 2891253 | 0 | 0 | 0 | 36531262 | 36531262 | 36531262 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 36531262
20-120 | 20-120 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Milton SW 12 | Milton SW 12 Public Elementary School | ELE | 25375 | 20381 | 20381-B01 | 815 KENNEDY CIRCLE WEST | MILTON | TBD | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5022 | -79.8354 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 770 | 5 | 88 | - | - | Approved | 44543 | 23161603 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44927 | 0 | 0 | 2053775 | 0 | 408640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2462415 | 0 | 0 | 0 | 0 | 17662015 | 0 | 3037173 | 0 | 0 | 0 | 20699188 | 23161603 | 23161603 | 0 | - | No, Site to be acquired. Sign installation planned for October 1, 2021 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 20699188
20-121 | 20-121 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Oakville NE 3 | Oakville NE 3 Public Elementary School | ELE | TBD | TBD | TBD | DUNDAS ST E / PRINCE MICHAEL DR | OAKVILLE | TBD | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4982 | -79.7088 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 788 | 5 | 88 | N | - | Approved | 44985 | 29973242 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 5640380 | 0 | 510800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6151180 | 0 | 0 | 0 | 0 | 20012609 | 0 | 4257662 | 0 | 0 | 0 | 24270271 | 30421451 | 29973242 | -448209 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 24270271
20-123 | 20-123 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Milton SE 13 | Milton SE 13 Public Elementary School | ELE | TBD | TBD | TBD | LOUIS ST. LAURENT AVE / TRUDEAU DR | MILTON | TBD | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5184 | -79.8244 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 926 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21431025 | 0 | 2891253 | 0 | 0 | 0 | 24322278 | 24322278 | 24322278 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 24322278
20-125 | 20-125 | 20 | 230 - CMSM Halton | 66133 | Halton DSB | Oakville NE 5 | Oakville NE 5 Public Elementary School | ELE | TBD | TBD | TBD | TBD | OAKVILLE | L6H7C8 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 788 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20549028 | 0 | 3324941 | 0 | 0 | 0 | 23873969 | 23873969 | 23873969 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23873969
20-126 | 20-126
21-001 | 21-001 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 24606 | 19612 | 19612-B01 | 20 EDUCATION CRT | HAMILTON | L9A0B9 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2208 | -79.8657 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-002 | 21-002 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 24606 | 19612 | 19612-B01 | 20 EDUCATION CRT | HAMILTON | L9A0B9 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2208 | -79.8657 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 28630061 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28862803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28862803 | 28862803 | 28862803 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-003 | 21-003 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24606 | 19612 | 19612-B01 | 20 EDUCATION CRT | HAMILTON | L9A0B9 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2208 | -79.8657 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3321172 | Construction Complete | Other | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3321172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3321172 | 3321172 | 3321172 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-005 | 21-005 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Allan A Greenleaf | Allan A Greenleaf Public Elementary School | ELE | 10012 | 8417 | 8417-B02 | 211 PARKSIDE DR | WATERDOWN | L0R2H1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.3341 | -79.9098 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7486634 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 1020965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6465669 | 7486634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7486634 | 7486634 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-007 | 21-007 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Ancaster Meadow | Ancaster Meadow Public Elementary School | ELE | 10674 | 11226 | 11226-B01 | 93 KITTY MURRAY LANE | ANCASTER | L9K1S3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2218 | -79.9534 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8542274 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 30619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7320736 | 7351355 | 1190919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190919 | 8542274 | 8542274 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-010 | 21-010 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Tiffany Hills | Tiffany Hills Public Elementary School | ELE | 24269 | 19261 | 19261-B01 | 255 RAYMOND RD | ANCASTER | L9K0H8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2127 | -79.9376 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 546 | 2 | 39 | N | - | Approved | 42312 | 12125141 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 879300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879300 | 0 | 0 | 1097836 | 0 | 10148005 | 0 | 1008339 | 0 | 0 | 0 | 12254180 | 13133480 | 13133480 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11156344
21-011 | 21-011 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Bellmoore | Bellmoore Public Elementary School | ELE | 11519 | 12289 | 12289-B01 | 35 PUMPKIN PASS | BINBROOK | L0R1C0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1258 | -79.8116 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 17413698 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 6661080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6661080 | 9892409 | 0 | 860209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10752618 | 17413698 | 17413698 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-016-01 | 21-016 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Cathy Wever | Cathy Wever Public Elementary School | ELE | 10613 | 9140 | 9140-B02 | 160 WENTWORTH ST N | HAMILTON | L8L5V7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2571 | -79.8464 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10603471 | Construction Complete | New Construction | Condition | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14313 | 14313 | 10589158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10589158 | 10603471 | 10603471 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-016-03 | 21-016 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Sanford Avenue | Sanford Avenue Public Elementary School | ELE | 8075 | 9140 | 9140-B01 | 149 SANFORD AVE N | HAMILTON | L8L5Z4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2568 | -79.8447 | 41284 | 2012-13 | 2012-13 | - | - | - | 41284 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1434617 | Construction Complete | Demolition | Other | 2012-13 | 41153 | 634617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634617 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000 | 1434617 | 1434617 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 800000
21-019 | 21-019 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Central | Central Public Elementary School | ELE | 8038 | 9104 | 9104-B01 | 75 HUNTER ST W | HAMILTON | L8P1P9 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2541 | -79.8745 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 917114 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917114 | 917114 | 917114 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-024 | 21-024 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Cootes Paradise | Cootes Paradise Public Elementary School | ELE | 8006 | 9075 | 9075-B01 | 900 KING ST W | HAMILTON | L8S1K6 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2639 | -79.9027 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 150 | - | - | N | - | Not Required | - | 6650363 | Construction Complete | Addition | Consolidation | 2014-15 | 41883 | 3127957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3127957 | 0 | 0 | 1425602 | 0 | 2096804 | 0 | 0 | 0 | 0 | 0 | 3522406 | 6650363 | 6650363 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2096804
21-025 | 21-025 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Dr. J Edgar Davey | Dr. J Edgar Davey Public Elementary School | ELE | 11046 | 9110 | 9110-B01 | 99 FERGUSON AVE N | HAMILTON | L8R1L6 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2577 | -79.8604 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13890386 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99169 | 99169 | 13791217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13791217 | 13890386 | 13890386 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-029 | 21-029 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Dundas Valley | Dundas Valley Public Secondary School | SEC | 5421 | 8247 | 8247-B01 | 310 GOVERNORS RD | DUNDAS | L9H5P8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.258 | -79.9767 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 126 | - | - | N | - | Approved | 42312 | 16800000 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 10000000 | 0 | 6800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16800000 | 16800000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-033-01 | 21-033 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Greensville | Greensville Public Elementary School | ELE | 24578 | 8596 | 8596-B02 | 625 HARVEST RD | DUNDAS | L9H5K8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2818 | -79.9841 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 381 | 2 | 39 | N | - | Approved | 44405 | 11578726 | Construction Complete | New Construction | Consolidation | 2020-21 | 44076 | 0 | 0 | 7273000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7273000 | 0 | 0 | 494284 | 0 | 2803102 | 0 | 1008340 | 0 | 0 | 0 | 4305726 | 11578726 | 11578726 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3811442
21-033-02 | 21-033 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Greensville | Greensville Public Elementary School | ELE | 24578 | 8596 | 8596-L02 | 625 HARVEST RD | DUNDAS | L9H5K8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2818 | -79.9841 | 43227 | 2017-18 | 2018-19 | 43227 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43227 | 671233 | Construction Complete | Land Acquisition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671233 | 0 | 0 | 0 | 0 | 0 | 0 | 671233 | 671233 | 671233 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 671233
21-033-03 | 21-033 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Greensville | Greensville Public Elementary School | ELE | 6178 | 8596 | 8596-B01 | 625 HARVEST RD | DUNDAS | L9H5K8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2814 | -79.9844 | 42915 | 2016-17 | 2017-18 | - | - | - | 42915 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42915 | 266002 | Construction Complete | Demolition | Consolidation | 2017-18 | 43007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266002 | 0 | 0 | 0 | 0 | 0 | 266002 | 266002 | 266002 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 266002
21-036 | 21-036 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Franklin Road | Franklin Road Public Elementary School | ELE | 8004 | 9073 | 9073-B01 | 500 FRANKLIN RD | HAMILTON | L8V2A4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2255 | -79.8512 | 42279 | 2015-16 | 2015-16 | - | - | - | 42279 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 52 | 3 | 63 | N | - | Approved | 42852 | 4009630 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 1582493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1582493 | 0 | 0 | 522835 | 0 | 450000 | 0 | 1482852 | 0 | 0 | 0 | 2455687 | 4038180 | 4038180 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 1932852
21-037 | 21-037 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Gatestone | Gatestone Public Elementary School | ELE | 10672 | 11227 | 11227-B01 | 127 GATESTONE DR | STONEY CREEK | L8J3Z5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1814 | -79.7887 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8370173 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 4282787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2005536 | 6288323 | 2081850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081850 | 8370173 | 8370173 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-039 | 21-039 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | George L Armstrong | George L Armstrong Public Elementary School | ELE | 8005 | 9074 | 9074-B01 | 460 CONCESSION ST | HAMILTON | L9A1C3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2413 | -79.8561 | 42167 | 2014-15 | 2015-16 | - | - | - | 42167 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44607 | 1304408 | Construction Complete | Addition | Child Care | 2015-16 | 42326 | 810123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810123 | 0 | 0 | 710756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710756 | 1520879 | 1520879 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-043 | 21-043 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Guy Brown | Guy Brown Public Elementary School | ELE | 11520 | 5936 | 5936-B02 | 55 BRAEHEID AVE | WATERDOWN | L0R2H5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.3286 | -79.9085 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11479714 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 1967783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1967783 | 9511931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9511931 | 11479714 | 11479714 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-047 | 21-047 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Hillcrest | Hillcrest Public Elementary School | ELE | 10891 | 9088 | 9088-B01 | 40 EASTWOOD ST | HAMILTON | L8H6R7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2395 | -79.7784 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10637513 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9357383 | 9357383 | 1280130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280130 | 10637513 | 10637513 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-049 | 21-049 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | HWDSB Head Office | Administrative Office | OFF-ADM | 24606 | 19612 | 19612-B01 | 20 EDUCATION CRT | HAMILTON | L9A0B9 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2208 | -79.8657 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 31600000 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 13500000 | 17200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 31600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31600000 | 31600000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-053 | 21-053 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Lawfield | Lawfield Public Elementary School | ELE | 10989 | 9094 | 9094-B01 | 45 BERKO AVE | HAMILTON | L8V2R3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2163 | -79.8484 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9907909 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 766066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766066 | 9141843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9141843 | 9907909 | 9907909 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-061 | 21-061 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Nora Frances Henderson | Nora Frances Henderson Public Secondary School | SEC | 24093 | 19160 | 19160-B01 | 620 RYMAL RD E | HAMILTON | L8W1B3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1939 | -79.8662 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 1245 | - | - | N | - | Approved | 44607 | 34910547 | Construction Complete | New Construction | Consolidation | 2020-21 | 44117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34910547 | 0 | 0 | 0 | 0 | 0 | 34910547 | 34910547 | 34910547 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 34910547
21-061-01 | 21-061 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Nora Frances Henderson | Nora Frances Henderson Public Secondary School | SEC | 24093 | 19160 | 19160-B01 | 620 RYMAL RD E | HAMILTON | L8W1B3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1939 | -79.8662 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - |  | - | - | N | - | Approved | 44607 | 26998049 |  | Land Acquisition | Consolidation | 2020-21 |  | 0 | 0 | 7961953 | 0 | 7843118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3231025 | 19036096 | 0 | 0 | 0 | 7961953 | 0 | 0 | 0 | 0 | 0 | 0 | 7961953 | 26998049 | 26998049 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7961953
21-062-01 | 21-062 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Bernie Curtis | Bernie Curtis Public Secondary School | SEC | 24092 | 9141 | 9141-B02 | 1055 KING ST E | HAMILTON | L8M1E2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2513 | -79.8277 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 1251 | - | - | N | - | Approved | 42803 | 34473723 | Construction Complete | New Construction | Consolidation | 2019-20 | 43711 | 0 | 0 | 1600001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600001 | 0 | 0 | 0 | 0 | 31839111 | 0 | 0 | 0 | 0 | 0 | 31839111 | 33439112 | 33439112 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 31839111
21-062-03 | 21-062 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Scott Park | Scott Park Public Secondary School | SEC | 24092 | 9141 | 9141-B02 | 1055 KING ST E | HAMILTON | L8M1E2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2513 | -79.8277 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42803 | 9729100 | Construction Complete | Demolition | Consolidation | 2015-16 | 42248 | 0 | 0 | 5908482 | 0 | 3820618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9729100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9729100 | 9729100 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-064 | 21-064 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Pauline Johnson | Pauline Johnson Public Elementary School | ELE | 8059 | 9072 | 9072-B02 | 25 HUMMINGBIRD LANE | HAMILTON | L9A4B1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2199 | -79.8705 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 112 | - | - | N | - | Not Required | - | 4296716 | Construction Complete | Addition | Consolidation | 2015-16 | 42248 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 1576208 | 0 | 2422040 | 0 | 0 | 0 | 0 | 0 | 3998248 | 4298248 | 4298248 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2422040
21-066 | 21-066 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Prince of Wales | Prince of Wales Public Elementary School | ELE | 11044 | 9126 | 9126-B01 | 77 MELROSE AVE N | HAMILTON | L8L6X4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2521 | -79.8325 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11762780 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11762780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11762780 | 11762780 | 11762780 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-068 | 21-068 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Queen Victoria | Queen Victoria Public Elementary School | ELE | 11045 | 9129 | 9129-B01 | 166 FOREST AVE | HAMILTON | L8N0A5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2484 | -79.8659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11307902 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636 | 1636 | 11306266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11306266 | 11307902 | 11307902 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-071 | 21-071 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Queensdale | Queensdale Public Elementary School | ELE | 8065 | 9130 | 9130-B01 | 67 QUEENSDALE AVE E | HAMILTON | L9A1K4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2414 | -79.873 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1250438 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 363689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363689 | 0 | 0 | 886749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 886749 | 1250438 | 1250438 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-073 | 21-073 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Ray Lewis | Ray Lewis Public Elementary School | ELE | 10669 | 11225 | 11225-B01 | 27 JESSICA ST | HAMILTON | L8W4A1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1937 | -79.8731 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8667584 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 5334221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1029928 | 6364149 | 2303435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2303435 | 8667584 | 8667584 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-076 | 21-076 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Ridgemount | Ridgemount Public Elementary School | ELE | 8069 | 9134 | 9134-B01 | 65 HESTER ST | HAMILTON | L9A2N3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2245 | -79.8792 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 118 | - | - | N | - | Approved | 42251 | 4020059 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 1141756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141756 | 0 | 0 | 494285 | 0 | 2384018 | 0 | 0 | 0 | 0 | 0 | 2878303 | 4020059 | 4020059 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2384018
21-079 | 21-079 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Saltfleet | Saltfleet Public Secondary School | SEC | 5623 | 8360 | 8360-B01 | 108 HIGHLAND RD W | STONEY CREEK | L8J2T2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1833 | -79.7784 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 210 | - | - | N | - | Approved | 44607 | 4575770 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4575770 | 0 | 0 | 0 | 0 | 0 | 4575770 | 4575770 | 4575770 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4575770
21-081 | 21-081 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Sir William Osler | Sir William Osler Public Elementary School | ELE | 10988 | 12129 | 12129-B01 | 330 GOVERNORS RD | DUNDAS | L9H0A3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.258 | -79.9793 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11839614 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7676633 | 7676633 | 4162981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4162981 | 11839614 | 11839614 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-084 | 21-084 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Templemead | Templemead Public Elementary School | ELE | 10375 | 11086 | 11086-B01 | 62 TEMPLEMEAD DR | HAMILTON | L8W3Z7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1978 | -79.8483 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8880586 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 6432173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1621701 | 8053874 | 826712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826712 | 8880586 | 8880586 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-086 | 21-086 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Waterdown District | Waterdown District Public Secondary School | SEC | 5729 | 8417 | 8417-B01 | 215 PARKSIDE DR | WATERDOWN | L0R2H1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.3341 | -79.9109 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 23921616 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 998956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998956 | 21963051 | 959609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22922660 | 23921616 | 23921616 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-087 | 21-087 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Winona | Winona Public Elementary School | ELE | 11518 | 12288 | 12288-B01 | 301 LEWIS RD | STONEY CREEK | L8E5H1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2139 | -79.6594 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 17674171 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 8751198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8751198 | 8271244 | 0 | 651729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8922973 | 17674171 | 17674171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-088 | 21-088 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Shannen Koostachin | Shannen Koostachin Public Elementary School | ELE | 24579 | 19585 | 19585-B01 | 110 BELLAGIO AVE | HAMILTON | L0R1P0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1771 | -79.8026 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 625 | 3 | 49 | Y | - | Approved | 43059 | 14810900 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43832 | 0 | 0 | 0 | 0 | 422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422000 | 0 | 0 | 1285634 | 0 | 11560505 | 0 | 1542761 | 0 | 0 | 0 | 14388900 | 14810900 | 14810900 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13103266
21-089-01 | 21-089 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Eastdale | Eastdale Public Elementary School | ELE | 24580 | 5751 | 5751-B02 | 99 LINCOLN RD | STONEY CREEK | L8E1Z4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2286 | -79.7346 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 564 | - | - | N | - | Approved | 43353 | 11557854 | Construction Complete | New Construction | Condition | 2019-20 | 43711 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 1028507 | 0 | 10726347 | 0 | 0 | 0 | 0 | 0 | 11754854 | 13154854 | 13154854 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10726347
21-089-03 | 21-089 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Eastdale | Eastdale Public Elementary School | ELE | 685 | 5751 | 5751-B01 | 275 LINCOLN RD | STONEY CREEK | L8E1Z4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2286 | -79.7346 | 43350 | 2018-19 | 2018-19 | - | - | - | 43350 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43353 | 408859 | Construction Complete | Demolition | Condition | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408859 | 0 | 0 | 0 | 0 | 0 | 408859 | 408859 | 408859 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 408859
21-090 | 21-090 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Sir Wilfrid Laurier | Sir Wilfrid Laurier Public Elementary School | ELE | 8083 | 9148 | 9148-B01 | 70 ALBRIGHT RD | HAMILTON | L8K5J3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2179 | -79.7878 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 26 | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257127 | 0 | 830676 | 0 | 0 | 0 | 0 | 0 | 1087803 | 1087803 | 1087803 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 830676
21-091 | 21-091 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Collegiate Avenue | Collegiate Avenue Public Elementary School | ELE | 486 | 5616 | 5616-B01 | 49 COLLEGIATE AVE | STONEY CREEK | L8G3L5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.221 | -79.7491 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | - | - | - | 213 | 3 | 49 | Y | - | Approved | 43880 | 10260280 | Construction Complete | Addition | Consolidation | 2021-22 | 44446 | 2244000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244000 | 0 | 0 | 514254 | 0 | 3959266 | 0 | 1542760 | 0 | 0 | 0 | 6016280 | 10260280 | 10260280 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5502026
21-092-01 | 21-092 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Glen | Glen Public Elementary School | ELE | 24691 | 9078 | 9078-B04 | 50 SECORD DR | HAMILTON | L8K3W7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2277 | -79.7794 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | - | - | - | 682 | 3 | 49 | Y | - | Approved | 43621 | 16122088 | Construction Complete | New Construction | Consolidation | 2021-22 | 44446 | 0 | 0 | 603326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603326 | 0 | 0 | 1285635 | 0 | 12690367 | 0 | 1542760 | 0 | 0 | 0 | 15518762 | 16122088 | 16122088 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14233127
21-092-03 | 21-092 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Glen Brae | Glen Brae Public Elementary School | ELE | 8009 | 9078 | 9078-B03 | 50 SECORD DR | HAMILTON | L8K3W7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2277 | -79.7794 | 43621 | 2018-19 | 2019-20 | - | - | - | 43621 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43621 | 1001090 | Construction Complete | Demolition | Consolidation | 2021-22 | 44652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1001090 | 0 | 0 | 0 | 0 | 0 | 1001090 | 1001090 | 1001090 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1001090
21-093-01 | 21-093 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Memorial | Memorial Public Elementary School | ELE | 24692 | 6282 | 6282-B02 | 211 MEMORIAL AVE | STONEY CREEK | L8G3B2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2167 | -79.7279 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | - | - | - | 495 | 3 | 49 | Y | - | Approved | 43621 | 13303541 | Construction Complete | New Construction | Consolidation | 2020-21 | 44200 | 0 | 0 | 1263639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263639 | 0 | 0 | 1028508 | 0 | 9468634 | 0 | 1542760 | 0 | 0 | 0 | 12039902 | 13303541 | 13303541 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11011394
21-093-03 | 21-093 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Memorial | Memorial Public Elementary School | ELE | 1529 | 6282 | 6282-B01 | 211 MEMORIAL AVE | STONEY CREEK | L8G3B2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2167 | -79.7279 | 43621 | 2018-19 | 2019-20 | - | - | - | 43621 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43621 | 653778 | Construction Complete | Demolition | Consolidation | 2021-22 | 44445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653778 | 0 | 0 | 0 | 0 | 0 | 653778 | 653778 | 653778 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 653778
21-095 | 21-095 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Helen Detwiler | Helen Detwiler Public Elementary School | ELE | 8014 | 9083 | 9083-B01 | 320 BRIGADE DR | HAMILTON | L9B2E3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2028 | -79.8786 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028508 | 0 | 0 | 0 | 1028508 | 1028508 | 0 | -1028508 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1028508
21-096 | 21-096 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Huntington Park | Huntington Park Public Elementary School | ELE | 8021 | 9090 | 9090-B01 | 80 KINGSLEA DR | HAMILTON | L8T4A5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2203 | -79.8272 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 0 | -1542762 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1542762
21-097 | 21-097 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Bennetto | Bennetto Public Elementary School | ELE | 8037 | 9103 | 9103-B01 | 47 SIMCOE ST E | HAMILTON | L8L3N2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2678 | -79.862 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43929 | 1851431 | Construction Complete | Retrofit | Child Care | 2021-22 | 44446 | 205250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205250 | 0 | 0 | 0 | 0 | 0 | 0 | 1646181 | 0 | 0 | 0 | 1646181 | 1851431 | 1851431 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1646181
21-098 | 21-098 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Dr. J Edgar Davey | Dr. J Edgar Davey Public Elementary School | ELE | 11046 | 9110 | 9110-B01 | 99 FERGUSON AVE N | HAMILTON | L8R1L6 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2577 | -79.8604 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44082 | 1021381 | Construction Complete | Retrofit | Child Care | 2020-21 | 44214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021381 | 0 | 0 | 0 | 1021381 | 1021381 | 1021381 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1021381
21-099 | 21-099 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Bellmoore | Bellmoore Public Elementary School | ELE | 11519 | 12289 | 12289-B01 | 35 PUMPKIN PASS | BINBROOK | L0R1C0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1258 | -79.8116 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44088 | 1542762 | Construction Complete | Addition | Child Care | 2021-22 | 44446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832545 | 0 | 0 | 0 | 1832545 | 1832545 | 1832545 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1832545
21-100-01 | 21-100 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Spring Valley | Spring Valley Public Elementary School | ELE | 24812 | 5479 | 5479-B02 | 99 DUNHAM DR | ANCASTER | L9G1X7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2166 | -79.9918 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 495 | 3 | 49 | Y | - | Approved | 43664 | 12249837 | Construction Complete | New Construction | Consolidation | 2020-21 | 44200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049077 | 0 | 9432998 | 0 | 1542762 | 0 | 0 | 0 | 12024837 | 12024837 | 12024837 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10975760
21-100-03 | 21-100 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | CH Bray | CH Bray Public Elementary School | ELE | 297 | 5479 | 5479-B01 | 99 DUNHAM DR | ANCASTER | L9G1X7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2166 | -79.9918 | 43664 | 2018-19 | 2019-20 | - | - | - | 43664 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43664 | 1294157 | Construction Complete | Demolition | Consolidation | 2019-20 | 43784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1294157 | 0 | 0 | 0 | 0 | 0 | 1294157 | 1294157 | 1294157 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1294157
21-101 | 21-101 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Mount Albion | Mount Albion Public Elementary School | ELE | 1573 | 6311 | 6311-B01 | 24 KENNARD ST | STONEY CREEK | L8J2E5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1893 | -79.7911 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 230 | 3 | 49 | Y | - | Approved | 43880 | 8544930 | Construction Complete | Addition | Accommodation Pressure | 2021-22 | 44446 | 0 | 0 | 2075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2075000 | 0 | 0 | 0 | 0 | 4927168 | 0 | 1542762 | 0 | 0 | 0 | 6469930 | 8544930 | 8544930 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 6469930
21-102 | 21-102 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Ancaster Senior | Ancaster Senior Public Elementary School | ELE | 76 | 5343 | 5343-B02 | 295 NAKOMA RD | ANCASTER | L8N3L1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2081 | -79.9932 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 173 | - | - | N | - | Approved | 43621 | 3702489 | Construction Complete | Addition | Consolidation | 2019-20 | 43711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3702489 | 0 | 0 | 0 | 0 | 0 | 3702489 | 3702489 | 3702489 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3702489
21-103 | 21-103 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Rockton | Rockton Public Elementary School | ELE | 24456 | 5418 | 5418-B02 | 670 HIGHWAY 8 | ROCKTON | L0R1X0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2982 | -80.0743 | 43172 | 2017-18 | 2017-18 | - | - | - | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 511 | - | - | N | - | Approved | 43493 | 16397747 | Construction Complete | New Construction | Consolidation | 2020-21 | 44082 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 494285 | 0 | 13903462 | 0 | 0 | 0 | 0 | 0 | 14397747 | 16397747 | 16397747 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13903462
21-104 | 21-104 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Viscount Montgomery | Viscount Montgomery Public Elementary School | ELE | 8091 | 9156 | 9156-B01 | 1525 LUCERNE AVE | HAMILTON | L8K1R3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2322 | -79.7972 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
21-106 | 21-106 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Dalewood | Dalewood Public Elementary School | ELE | 8042 | 9108 | 9108-B01 | 1150 MAIN ST W | HAMILTON | L8S1C2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2583 | -79.9132 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 10300000 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 10300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10300000 | 10300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
21-107 | 21-107 | 21 | N/A | 66141 | Hamilton-Wentworth DSB | Binbrook II | Binbrook II Public Elementary School | ELE | 25377 | 20383 | 20383-B01 | TBD | HAMILTON | TBD | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 615 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13528858 | 0 | 0 | 0 | 0 | 0 | 13528858 | 13528858 | 13528858 | 0 | - | No, Site to be acquired. Sign installation planned for March 3, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13528858
21-115 | 21-115 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Nash Upper Stoney Creek | Nash Upper Stoney Creek Public Elementary School | ELE | 25691 | 20697 | 20697-B01 | FIRST RD W / GREEN MOUNTAIN RD W | STONEY CREEK | TBD | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2016 | -79.7759 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 650 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14933170 | 0 | 1734751 | 0 | 0 | 0 | 16667921 | 16667921 | 16667921 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16667921
21-116 | 21-116 | 21 | 203 - CMSM Hamilton | 66141 | Hamilton-Wentworth DSB | Rosedale | Rosedale Elementary School | ELE | 8071 | 9136 |  | 25 Erindale Avenue | Hamilton | L8K4R2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.22 | -79.81 | [12 empty] | - | - | - | - | - | - |  |  |  |  | - | Planned | - | - | Planned | Addition | Accommodation Pressure |  |  | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 0
22-001 | 22-001 | 22 | N/A | 66150 | DSB Niagara | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16167 | 18114 | 18114-B01 | 191 CARLTON ST | ST CATHARINES | L2R7P4 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1732 | -79.2473 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69035 | 0 | 0 | 0 | 0 | 0 | 69035 | 69035 | 0 | -69035 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 69035
22-002 | 22-002 | 22 | N/A | 66150 | DSB Niagara | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16167 | 18114 | 18114-B01 | 191 CARLTON ST | ST CATHARINES | L2R7P4 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1732 | -79.2473 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10231648 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11168624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11168624 | 11168624 | 10231648 | -936976 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-003 | 22-003 | 22 | N/A | 66150 | DSB Niagara | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 16167 | 18114 | 18114-B01 | 191 CARLTON ST | ST CATHARINES | L2R7P4 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1732 | -79.2473 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1265511 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265511 | 1265511 | 1265511 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-009 | 22-009 | 22 | N/A | 66150 | DSB Niagara | Crossroads | Crossroads Public Elementary School | ELE | 15715 | 18074 | 18074-B01 | 1350 NIAGARA STONE RD | NIAGARA ON THE LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.2164 | -79.1303 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10087235 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 536530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3219524 | 3756054 | 6331181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6331181 | 10087235 | 10087235 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-010 | 22-010 | 22 | N/A | 66150 | DSB Niagara | Crossroads | Crossroads Public Elementary School | ELE | 15715 | 18074 | 18074-B01 | 1350 NIAGARA STONE RD | NIAGARA ON THE LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.2164 | -79.1303 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 37 | - | - | N | - | Not Required | - | 1013989 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 32591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32591 | 0 | 0 | 499130 | 0 | 482268 | 0 | 0 | 0 | 0 | 0 | 981398 | 1013989 | 1013989 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 482268
22-011 | 22-011 | 22 | N/A | 66150 | DSB Niagara | Diamond Trail | Diamond Trail Public Elementary School | ELE | 23573 | 6253 | 6253-B02 | 315 SOUTHWORTH ST S | WELLAND | L3B1Z8 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.9731 | -79.2355 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 354 | - | - | N | - | Not Required | - | 7867398 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 479925 | 0 | 4202797 | 0 | 0 | 0 | 0 | 0 | 4682722 | 7682722 | 7682722 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4202797
22-013 | 22-013 | 22 | N/A | 66150 | DSB Niagara | Forestview | Forestview Public Elementary School | ELE | 11106 | 12291 | 12291-B01 | 8406 FORESTVIEW BLVD | NIAGARA FALLS | L2H0B9 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0832 | -79.1375 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7913811 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 3022473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063469 | 4085942 | 3827869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3827869 | 7913811 | 7913811 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-014 | 22-014 | 22 | N/A | 66150 | DSB Niagara | Forestview | Forestview Public Elementary School | ELE | 11106 | 12291 | 12291-B01 | 8406 FORESTVIEW BLVD | NIAGARA FALLS | L2H0B9 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0832 | -79.1375 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Not Required | - | 1812668 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430551 | 0 | 1382117 | 0 | 0 | 0 | 0 | 0 | 1812668 | 1812668 | 1812668 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1382117
22-017 | 22-017 | 22 | N/A | 66150 | DSB Niagara | Gordon | Gordon Public Elementary School | ELE | 933 | 5902 | 5902-B01 | 468 THOROLD RD | WELLAND | L3C3W6 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0045 | -79.2788 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 118 | - | - | N | - | Not Required | - | 2906617 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 35150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35150 | 0 | 704850 | 726041 | 0 | 1440576 | 0 | 0 | 0 | 0 | 0 | 2871467 | 2906617 | 2906617 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1440576
22-018 | 22-018 | 22 | N/A | 66150 | DSB Niagara | Grand Avenue | Grand Avenue Public Elementary School | ELE | 947 | 5910 | 5910-B01 | 14 GRAND AVE | GRIMSBY | L3M2R7 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.192 | -79.5271 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2901836 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2901836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2901836 | 2901836 | 2901836 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-019-01 | 22-019 | 22 | N/A | 66150 | DSB Niagara | Greater Fort Erie | Greater Fort Erie Public Secondary School | SEC | 24366 | 19367 | 19367-B01 | 1640 GARRISON RD | FORT ERIE | L2A5M4 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.9028 | -78.9779 | 41877 | 2013-14 | 2014-15 | - | - | - | 41877 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 750 | - | - | N | - | Approved | 41996 | 25438280 | Construction Complete | New Construction | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 22438280 | 0 | 0 | 0 | 0 | 0 | 22438280 | 25438280 | 25438280 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 22438280
22-019-02 | 22-019 | 22 | N/A | 66150 | DSB Niagara | Greater Fort Erie | Greater Fort Erie Public Secondary School | SEC | 24366 | 19367 | 19367-L01 | 1640 GARRISON RD | FORT ERIE | L2A5M4 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.9028 | -78.9779 | 41996 | 2014-15 | 2014-15 | 41996 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41996 | 2103000 | Construction Complete | Land Acquisition | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103000 | 0 | 0 | 0 | 0 | 0 | 0 | 2103000 | 2103000 | 2103000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2103000
22-021 | 22-021 | 22 | N/A | 66150 | DSB Niagara | Harriet Tubman | Harriet Tubman Public Elementary School | ELE | 24341 | 19339 | 19339-B01 | 84 HENRY ST | ST CATHARINES | L2R5V4 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1687 | -79.2484 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 599 | - | - | N | - | Approved | 42104 | 12414965 | Construction Complete | New Construction | Consolidation | 2015-16 | 42248 | 0 | 0 | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300000 | 0 | 0 | 1938906 | 0 | 7176056 | 0 | 0 | 0 | 0 | 0 | 9114962 | 12414962 | 11064794 | -1350168 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7176056
22-023 | 22-023 | 22 | N/A | 66150 | DSB Niagara | James Morden | James Morden Public Elementary School | ELE | 1181 | 6055 | 6055-B01 | 7112 DORCHESTER RD | NIAGARA FALLS | L2G5V6 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0724 | -79.1093 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3133703 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 358703 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 2858703 | 3133703 | 3133703 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-024 | 22-024 | 22 | N/A | 66150 | DSB Niagara | John Brant | John Brant Public Elementary School | ELE | 24422 | 19423 | 19423-B01 | 143 RIDGE RD | RIDGEWAY | L0S1N0 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.8786 | -79.0522 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 504 | - | - | N | - | Approved | 42271 | 11272184 | Construction Complete | New Construction | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998260 | 0 | 10273924 | 0 | 0 | 0 | 0 | 0 | 11272184 | 11272184 | 11272184 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10273924
22-029 | 22-029 | 22 | N/A | 66150 | DSB Niagara | Nelles | Nelles Public Elementary School | ELE | 1605 | 6334 | 6334-B01 | 118 MAIN ST E | GRIMSBY | L3M1N8 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.1883 | -79.5512 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1693977 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693977 | 1693977 | 1693977 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-033 | 22-033 | 22 | N/A | 66150 | DSB Niagara | Orchard Park | Orchard Park Public Elementary School | ELE | 1715 | 6400 | 6400-B01 | 3691 DORCHESTER RD | NIAGARA FALLS | L2J3A6 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.1192 | -79.1127 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2816972 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 116972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116972 | 0 | 0 | 0 | 0 | 0 | 2700000 | 0 | 0 | 0 | 0 | 2700000 | 2816972 | 2816972 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-034 | 22-034 | 22 | N/A | 66150 | DSB Niagara | Park | Park Public Elementary School | ELE | 11190 | 6424 | 6424-B01 | 217 MAIN ST E | GRIMSBY | L3M1P5 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.1862 | -79.5346 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1566757 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566757 | 1566757 | 1566757 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-035 | 22-035 | 22 | N/A | 66150 | DSB Niagara | Peace Bridge | Peace Bridge Public Elementary School | ELE | 2323 | 6789 | 6789-B01 | 105 TORRANCE CRES | FORT ERIE | L2A2C1 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.9147 | -78.925 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 121 | - | - | N | - | Not Required | - | 4343273 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 1396914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396914 | 0 | 0 | 457361 | 0 | 2488998 | 0 | 0 | 0 | 0 | 0 | 2946359 | 4343273 | 4343273 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2488998
22-036 | 22-036 | 22 | N/A | 66150 | DSB Niagara | Pine Grove | Pine Grove Public Elementary School | ELE | 2144 | 5059 | 5059-B01 | 690 LAKE ST | ST CATHARINES | L2N4J5 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.2035 | -79.2518 | 41849 | 2013-14 | 2014-15 | - | - | - | 41849 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1509117 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606371 | 0 | 902746 | 0 | 0 | 0 | 0 | 0 | 1509117 | 1509117 | 1509117 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 902746
22-039 | 22-039 | 22 | N/A | 66150 | DSB Niagara | Power Glen | Power Glen Public Elementary School | ELE | 10667 | 6488 | 6488-B01 | 34 WESTLAND ST | ST CATHARINES | L2S4C1 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1301 | -79.2658 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4756022 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 1471084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3284938 | 4756022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4756022 | 4756022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-043 | 22-043 | 22 | N/A | 66150 | DSB Niagara | Queen Mary | Queen Mary Public Elementary School | ELE | 1923 | 6543 | 6543-B01 | 185 CARLTON ST | ST CATHARINES | L2R1S1 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1749 | -79.2484 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2649865 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2649865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2649865 | 2649865 | 2649865 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-045 | 22-045 | 22 | N/A | 66150 | DSB Niagara | River View | River View Public Elementary School | ELE | 1993 | 6584 | 6584-B01 | 3300 CATTELL DR | NIAGARA FALLS | L2G6M9 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0552 | -79.0424 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3608662 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 2719084 | 0 | 310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3029084 | 0 | 341000 | 238578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579578 | 3608662 | 3608662 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-047 | 22-047 | 22 | N/A | 66150 | DSB Niagara | Sir Winston Churchill | Sir Winston Churchill Public Secondary School | SEC | 5659 | 8371 | 8371-B01 | 101 GLEN MORRIS DR | ST CATHARINES | L2T2N1 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1412 | -79.2309 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2785118 | Construction Complete | Addition | Other | 2010-11 | 40422 | 285118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2785118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2785118 | 2785118 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-049 | 22-049 | 22 | N/A | 66150 | DSB Niagara | St. Davids | St. Davids Public Elementary School | ELE | 2213 | 6722 | 6722-B01 | 1344 YORK RD | ST. DAVIDS | L0S1P0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.1587 | -79.1068 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3499429 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1310144 | 1310144 | 0 | 618093 | 0 | 0 | 0 | 1571192 | 0 | 0 | 0 | 0 | 2189285 | 3499429 | 3499429 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-052 | 22-052 | 22 | N/A | 66150 | DSB Niagara | Twenty Valley | Twenty Valley Public Elementary School | ELE | 24342 | 19340 | 19340-B01 | 4057 VICTORIA AVE | VINELAND | L0R2C0 | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1585 | -79.3919 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 481 | - | - | N | - | Not Required | - | 9852671 | Construction Complete | New Construction | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959851 | 0 | 8892820 | 0 | 0 | 0 | 0 | 0 | 9852671 | 9852671 | 9852671 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8892820
22-054 | 22-054 | 22 | N/A | 66150 | DSB Niagara | Wellington Heights | Wellington Heights Public Elementary School | ELE | 5320 | 8190 | 8190-B01 | 9 ALSOP AVE | FENWICK | L0S1E0 | 35-11-18-405 | Pelham | Pelham T | Niagara R | NIAGARA | Central | South | 43.0281 | -79.3564 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Approved | 42569 | 5705936 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 807541 | 0 | 1283000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2090541 | 0 | 0 | 0 | 0 | 3172936 | 0 | 0 | 0 | 0 | 0 | 3172936 | 5263477 | 5263477 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3172936
22-057 | 22-057 | 22 | N/A | 66150 | DSB Niagara | Walker Living | Walker Living Recreational | REC | 24365 | 19366 | 19366-B01 | 1 TAYLOR RD | NIAGARA-ON-THE-LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.1435 | -79.1675 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2662007 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2662007 | 2662007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2662007 | 2662007 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-058-01 | 22-058 | 22 | N/A | 66150 | DSB Niagara | West Niagara | West Niagara Public Secondary School | SEC | 24673 | 19680 | 19680-B01 | 5699 KING ST | BEAMSVILLE | L0R1B3 | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1837 | -79.5127 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 1533 | - | - | N | - | Approved | 44357 | 50356222 | Under Construction | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 2167069 | 7039035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9206104 | 0 | 0 | 0 | 0 | 41150118 | 0 | 0 | 0 | 0 | 0 | 41150118 | 50356222 | 50356222 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 41150118
22-058-02 | 22-058 | 22 | N/A | 66150 | DSB Niagara | West Niagara | West Niagara Public Secondary School | SEC | 24673 | 19680 | 19680-L01 | 5699 KING ST | BEAMSVILLE | L0R1B3 | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1837 | -79.5127 | 43511 | 2018-19 | 2018-19 | 43511 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44186 | 20725000 | Construction Complete | Land Acquisition | Consolidation | 2019-20 | 43709 | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 8725000 | 0 | 0 | 0 | 0 | 0 | 0 | 8725000 | 20725000 | 20725000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 8725000
22-059 | 22-059 | 22 | N/A | 66150 | DSB Niagara | DSBN Education Centre | Administrative Office | OFF-ADM | 16167 | 18114 | 18114-B01 | 191 CARLTON ST | ST CATHARINES | L2R7P4 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1732 | -79.2473 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-060 | 22-060 | 22 | 231 - CMSM Niagara | 66150 | DSB Niagara | Oakridge | Oakridge Public Elementary School | ELE | 1694 | 6387 | 6387-B01 | 1 MARSDALE DR | ST CATHARINES | L2T3R7 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1369 | -79.2429 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
22-061 | 22-061 | 22 | 231 - CMSM Niagara | 66150 | DSB Niagara | Forestview | Forestview Public Elementary School | ELE | 11106 | 12291 | 12291-B01 | 8406 FORESTVIEW BLVD | NIAGARA FALLS | L2H0B9 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0832 | -79.1375 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 184 | 3 | 49 | Y | - | Approved | 43836 | 5642773 | Construction Complete | Addition | Accommodation Pressure | 2020-21 | 44316 | 0 | 0 | 995520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995520 | 0 | 0 | 0 | 0 | 3868310 | 0 | 778943 | 0 | 0 | 0 | 4647253 | 5642773 | 5642773 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4647253
22-062 | 22-062 | 22 | N/A | 66150 | DSB Niagara | Richmond Street | Richmond Street Public Elementary School | ELE | 1976 | 6570 | 6570-B01 | 153 RICHMOND ST | THOROLD | L2V3H3 | 35-11-18-105 | Thorold | Thorold C | Niagara R | NIAGARA | Central | South | 43.1169 | -79.2144 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 101 | - | - | N | - | Approved | 43621 | 2142457 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142457 | 0 | 0 | 0 | 0 | 0 | 2142457 | 2142457 | 2142457 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2142457
22-063 | 22-063+50-067 | 22 | 231 - CMSM Niagara | 66150 | DSB Niagara | Wainfleet | Wainfleet Public Elementary School | ELE | 25378 | 7620 | 7620-B02 | 31950 SUGARLOAF ST | WAINFLEET | L0S1V0 | 35-11-18-601 | Wainfleet | Wainfleet Tp | Niagara R | NIAGARA | Central | South | 42.9213 | -79.3743 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 469 | 3 | 49 | - | - | Approved | 44684 | 18470399 | Under Construction | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 3202271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3202271 | 0 | 0 | 0 | 0 | 13102853 | 0 | 2165275 | 0 | 0 | 0 | 15268128 | 18470399 | 18470399 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15268128
22-064 | 22-064 | 22 | 231 - CMSM Niagara | 66150 | DSB Niagara | Smith | Smith Public Elementary School | ELE | 2168 | 6689 | 6689-B01 | 18 OAKES RD N | GRIMSBY | L3M4B1 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.2064 | -79.6141 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 276 | 3 | 49 | N | - | Approved | 44684 | 11080273 | Under Construction | Addition | Accommodation Pressure | 2023-24 | 45170 | 2999301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999301 | 0 | 0 | 0 | 0 | 4898938 | 0 | 3182034 | 0 | 0 | 0 | 8080972 | 11080273 | 11080273 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 8080972
22-065 | 22-065 | 22 | N/A | 66150 | DSB Niagara | Peace Bridge | Peace Bridge Public Elementary School | ELE | 2323 | 6789 | 6789-B01 | 105 TORRANCE CRES | FORT ERIE | L2A2C1 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.9147 | -78.925 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 230 | - | - | N | - | Approved | 44685 | 6934815 | Under Construction | Addition | Accommodation Pressure | 2023-24 | 45170 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 6034815 | 0 | 0 | 0 | 0 | 0 | 6034815 | 6934815 | 6934815 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6034815
22-066 | 22-066 | 22 | N/A | 66150 | DSB Niagara | South Niagara Falls | South Niagara Falls Public Elementary School | HFA | 25525 | 20531 | 20531-L0- | KALAR RD / MCLEOD RD | NIAGARA FALLS | TBD | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0699 | -79.1355 | 44188 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44188 | 7280462 | Construction Complete | Land Acquisition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 7280462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280462 | 7280462 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
22-067 | 22-067 | 22 | 231 - CMSM Niagara | 66150 | DSB Niagara | Lakeview | Lakeview Public Elementary School | ELE | 1317 | 6141 | 6141-B01 | 33 OLIVE ST | GRIMSBY | L3M2B9 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.201 | -79.5616 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 5 | 88 | N | - | Approved | 45169 | 3063799 | Planned | Addition | Child Care | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3063799 | 0 | 0 | 0 | 3063799 | 3063799 | 3063799 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 3063799
22-068 | 22-066 | 22 | 231 - CMSM Niagara | 66150 | DSB Niagara | South Niagara Falls | South Niagara Falls Public Elementary School | ELE | 25525 | 20531 | 20531-B01 | KALAR RD / MCLEOD RD | NIAGARA FALLS | TBD | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0699 | -79.1355 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 608 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14175587 | 0 | 1751759 | 0 | 0 | 0 | 15927346 | 15927346 | 15927346 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15927346
22-069 | 22-069 | 22 | 231 - CMSM Niagara | 66150 | DSB of Niagara | Quaker Road | Quaker Road Public Elementary School | ELE | 1900 | 6525 | 6525-B01 | 333 QUAKER RD | WELLAND | L3C3G7 |  | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0216 | -79.2616 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 331 | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9385992 | 0 | 1007261 | 0 | 0 | 0 | 10393253 | 10393253 | 10393253 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10393253
22-070 | 22-070 | 22 | 231 - CMSM Niagara | 66150 | DSB of Niagara |  |  | ELE | 1900 | 6525 | 6525-B01 |  | Thorold |  |  | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0216 | -79.2616 | TBD | TBD | TBD |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD | - | - | - | - | - | - | [5 empty] | Planned | - | - | Planned | Land Acquisition | Accommodation Pressure |  |  | 0 | 0 | 0 | 2019000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019000 | 2019000 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 0
22-071 | 22-071 | 22 | 231 - CMSM Niagara | 66151 | DSB of Niagara | Gainsborough | [11 empty] | Niagara R | NIAGARA | Central | South | [28 empty] | Planned | Addition | Other
22-072 | 22-072 | 22 | 231 - CMSM Niagara | 66150 | DSB of Niagara |  | Quaker Road Public Elementary School | ELE |  |  |  | 101 Afton Ave | WELLAND | L3B1W1 |  | Welland | Welland C | Niagara R | NIAGARA | Central | South | [5 empty] | - | - | - | [6 empty] | - | - | - | - | - | - | [10 empty] | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9385992 | 0 | 1007261 | 0 | 0 | 0 | 10393253 | 10393253 | 10393253 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10393253
23-001 | 23-001 | 23 | N/A | 66168 | Grand Erie DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 24237 | 6079 | 6079-B02 | 349 ERIE AVE | BRANTFORD | N3S2H7 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1197 | -80.2513 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-002 | 23-002 | 23 | N/A | 66168 | Grand Erie DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 24237 | 6079 | 6079-B02 | 349 ERIE AVE | BRANTFORD | N3S2H7 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1197 | -80.2513 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15210223 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15013713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15013713 | 15013713 | 15210223 | 196510 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-003 | 23-003 | 23 | N/A | 66168 | Grand Erie DSB | Agnes G Hodge | Agnes G Hodge Public Elementary School | ELE | 6420 | 8720 | 8720-B01 | 52 CLENCH AVE | BRANTFORD | N3T1B6 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1246 | -80.2711 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5440457 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5440457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5440457 | 5440457 | 5440457 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-006 | 23-006 | 23 | N/A | 66168 | Grand Erie DSB | Bellview | Bellview Public Elementary School | ELE | 6433 | 8723 | 8723-B01 | 97 TENTH AVE | BRANTFORD | N3S1G5 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1229 | -80.2503 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 82295 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82295 | 82295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82295 | 82295 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-010 | 23-010 | 23 | N/A | 66168 | Grand Erie DSB | Brantford | Brantford Public Secondary School | SEC | 5243 | 8140 | 8140-B01 | 120 BRANT AVE | BRANTFORD | N3T3H3 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1431 | -80.2732 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 31325619 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 98576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98576 | 31227043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31227043 | 31325619 | 31325619 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-012 | 23-012 | 23 | N/A | 66168 | Grand Erie DSB | Burford | Burford Public Elementary School | ELE | 5249 | 8144 | 8144-B01 | 35 ALEXANDER ST | BURFORD | N0E1A0 | 35-15-14-000 | Brant County | Brant County | Brant County | BRANT | Southwest | South | 43.0995 | -80.4297 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 741342 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741342 | 741342 | 741342 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-016 | 23-016 | 23 | N/A | 66168 | Grand Erie DSB | Cobblestone | Cobblestone Public Elementary School | ELE | 11249 | 12190 | 12190-B01 | 179 GRANDVILLE CIR | PARIS | N3L0A9 | 35-15-14-000 | Brant County | Brant County | Brant County | BRANT | Southwest | South | 43.1794 | -80.3945 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8593739 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 2930282 | 0 | 3033742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5964024 | 2629715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2629715 | 8593739 | 8593739 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-019 | 23-019 | 23 | N/A | 66168 | Grand Erie DSB | Delhi | Delhi Public Elementary School | ELE | 570 | 5671 | 5671-B01 | 227 QUEEN ST | DELHI | N4B2K6 | 35-15-12-103 | Norfolk County | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8528 | -80.4967 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1796187 | Construction Complete | Addition | Other | 2012-13 | 41153 | 1315422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315422 | 0 | 0 | 480765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480765 | 1796187 | 1796187 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-020 | 23-020 | 23 | N/A | 66168 | Grand Erie DSB | Delhi District | Delhi District Public Secondary School | SEC | 5304 | 8179 | 8179-B01 | 393 JAMES ST | DELHI | N4B2B6 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8512 | -80.4922 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1736817 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1736817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1736817 | 1736817 | 1736817 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-021 | 23-021 | 23 | N/A | 66168 | Grand Erie DSB | Doverwood | Doverwood Public Elementary School | ELE | 607 | 5693 | 5693-B01 | 109 HAMILTON PLANK RD | PORT DOVER | N0A1N7 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.7884 | -80.1884 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 801578 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 801578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801578 | 801578 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-023 | 23-023 | 23 | N/A | 66168 | Grand Erie DSB | Dufferin | Dufferin Public Elementary School | ELE | 634 | 5716 | 5716-B01 | 106 CHESTNUT AVE | BRANTFORD | N3T4C6 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1435 | -80.2816 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 150555 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150555 | 150555 | 150555 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-026 | 23-026 | 23 | N/A | 66168 | Grand Erie DSB | Elgin Avenue | Elgin Avenue Public Elementary School | ELE | 715 | 5773 | 5773-B01 | 80 ELGIN AVE | SIMCOE | N3Y4A8 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.837 | -80.3141 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 175034 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175034 | 175034 | 175034 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-028 | 23-028 | 23 | N/A | 66168 | Grand Erie DSB | Confederation | Confederation Public Elementary School | ELE | 9870 | 5113 | 5113-B01 | 54 EWING DR | BRANTFORD | N3R5H8 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1677 | -80.2907 | 41877 | 2013-14 | 2014-15 | - | - | - | 41877 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 115 | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1486498 | 0 | 4322310 | 0 | 0 | 0 | 0 | 0 | 5808808 | 5808808 | 5808808 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4322310
23-032 | 23-032 | 23 | N/A | 66168 | Grand Erie DSB | Hagersville | Hagersville Public Elementary School | ELE | 1771 | 6433 | 6433-B01 | 40 PARKVIEW RD | HAGERSVILLE | N0A1H0 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.9567 | -80.0507 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 805580 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 687428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687428 | 118152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118152 | 805580 | 805580 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-033 | 23-033 | 23 | N/A | 66168 | Grand Erie DSB | Houghton | Houghton Public Elementary School | ELE | 1110 | 6018 | 6018-B01 | 505 FAIRGROUND RD RR 5 | LANGTON | N0E1G0 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.6504 | -80.6619 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 138865 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138865 | 138865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138865 | 138865 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-034 | 23-034 | 23 | N/A | 66168 | Grand Erie DSB | Jarvis | Jarvis Public Elementary School | ELE | 1190 | 6060 | 6060-B01 | 14 MONSON ST | JARVIS | N0A1J0 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.8882 | -80.1104 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1941978 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6561 | 6561 | 1935417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935417 | 1941978 | 1941978 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-036 | 23-036 | 23 | N/A | 66168 | Grand Erie DSB | Joseph Brant Learning Centre | Operational Office | OFF-OPS | 1223 | 6079 | 6079-B01 | 347 ERIE AVE | BRANTFORD | N3S2H7 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1204 | -80.2519 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 245871 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245871 | 245871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245871 | 245871 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-038 | 23-038 | 23 | N/A | 66168 | Grand Erie DSB | Lynndale Heights | Lynndale Heights Public Elementary School | ELE | 9550 | 10196 | 10196-B01 | 55 DONLY DR S | SIMCOE | N3Y5G7 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8391 | -80.287 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 772744 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772744 | 772744 | 772744 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-039 | 23-039 | 23 | N/A | 66168 | Grand Erie DSB | Lynndale Heights | Lynndale Heights Public Elementary School | ELE | 9550 | 10196 | 10196-B01 | 55 DONLY DR S | SIMCOE | N3Y5G7 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8391 | -80.287 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 749131 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749131 | 749131 | 749131 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-042 | 23-042 | 23 | N/A | 66168 | Grand Erie DSB | North Ward | North Ward Public Elementary School | ELE | 1662 | 6373 | 6373-B01 | 107 SILVER ST | PARIS | N3L1V2 | 35-15-14-000 | Brant County | Brant County | Brant County | BRANT | Southwest | South | 43.2048 | -80.3976 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1938413 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1938413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1938413 | 1938413 | 1938413 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-048 | 23-048 | 23 | N/A | 66168 | Grand Erie DSB | Port Dover Composite | Port Dover Composite Public Secondary School | SEC | 5594 | 5224 | 5224-B01 | 713 ST GEORGE ST | PORT DOVER | N0A1N0 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.7905 | -80.2124 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 25000 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-049 | 23-049 | 23 | N/A | 66168 | Grand Erie DSB | Port Rowan | Port Rowan Public Elementary School | ELE | 1845 | 6483 | 6483-B01 | 48 COLLEGE AVE | PORT ROWAN | N0E1M0 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.6244 | -80.4548 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 885925 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 885925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 885925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 885925 | 885925 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-051 | 23-051 | 23 | N/A | 66168 | Grand Erie DSB | Rainham Central | Rainham Central Public Elementary School | ELE | 1949 | 6559 | 6559-B01 | 572 CONCESSION 5 RD RR 1 | FISHERVILLE | N0A1G0 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.8826 | -79.8952 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 328705 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328705 | 328705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328705 | 328705 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-053 | 23-053 | 23 | N/A | 66168 | Grand Erie DSB | River Heights | River Heights Public Elementary School | ELE | 1991 | 6582 | 6582-B01 | 37 FORFAR ST E | CALEDONIA | N3W1L6 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0708 | -79.9514 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 926736 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 93728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833008 | 926736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926736 | 926736 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-054 | 23-054 | 23 | N/A | 66168 | Grand Erie DSB | River Heights | River Heights Public Elementary School | ELE | 1991 | 6582 | 6582-B01 | 37 FORFAR ST E | CALEDONIA | N3W1L6 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0708 | -79.9514 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 472083 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472083 | 472083 | 472083 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-056 | 23-056 | 23 | N/A | 66168 | Grand Erie DSB | Russel Reid | Russel Reid Public Elementary School | ELE | 2063 | 10412 | 10412-B01 | 43 CAMBRIDGE DR | BRANTFORD | N3R5E3 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1717 | -80.2886 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 100 | - | - | N | - | Not Required | - | 2057853 | Construction Complete | Addition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479925 | 0 | 1577928 | 0 | 0 | 0 | 0 | 0 | 2057853 | 2057853 | 2057853 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1577928
23-057 | 23-057 | 23 | N/A | 66168 | Grand Erie DSB | Ryerson Heights | Ryerson Heights Public Elementary School | ELE | 10907 | 12070 | 12070-B01 | 33 DOWDEN AVE | BRANTFORD | N3T0A3 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1238 | -80.2977 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8843894 | Construction Complete | Addition | Other | 2006-07 | 38961 | 3743894 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6243894 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 8843894 | 8843894 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-058 | 23-058 | 23 | N/A | 66168 | Grand Erie DSB | Simcoe Composite | Simcoe Composite Public Secondary School | SEC | 5640 | 8366 | 8366-B01 | 40 WILSON DR | SIMCOE | N3Y2E5 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8414 | -80.3044 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2977226 | Construction Complete | Addition | Other | 2005-06 | 38596 | 1709865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267361 | 2977226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2977226 | 2977226 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-059 | 23-059 | 23 | N/A | 66168 | Grand Erie DSB | St. George-German | St. George-German Public Elementary School | ELE | 2181 | 6697 | 6697-B01 | 3 COLLEGE ST | ST. GEORGE | N0E1N0 | 35-15-14-000 | Brant County | Brant County | Brant County | BRANT | Southwest | South | 43.2444 | -80.2573 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1224120 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224120 | 1224120 | 1224120 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-061 | 23-061 | 23 | N/A | 66168 | Grand Erie DSB | Thompson Creek | Thompson Creek Public Elementary School | ELE | 650 | 5726 | 5726-B01 | 800 CROSS ST W | DUNNVILLE | N1A1N7 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.9141 | -79.6307 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 311077 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311077 | 311077 | 311077 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-063 | 23-063 | 23 | N/A | 66168 | Grand Erie DSB | Walsh | Walsh Public Elementary School | ELE | 2416 | 6855 | 6855-B01 | 933 ST JOHN'S RD W RR 2 | SIMCOE | N3Y4K1 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.7635 | -80.39 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 629532 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 629532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629532 | 629532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-064 | 23-064 | 23 | N/A | 66168 | Grand Erie DSB | Walsh | Walsh Public Elementary School | ELE | 2416 | 6855 | 6855-B01 | 933 ST JOHN'S RD W RR 2 | SIMCOE | N3Y4K1 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.7635 | -80.39 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 452625 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452625 | 452625 | 452625 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-066 | 23-006+51-016 | 23 | N/A | 66168 | Grand Erie DSB | Walter Gretzky | Walter Gretzky Public Elementary School | ELE | 14687 | 18009 | 18009-B01 | 365 BLACKBURN DR | BRANTFORD | N3T0G5 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1104 | -80.2984 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9649750 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 254360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254360 | 9395390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9395390 | 9649750 | 9649750 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-067 | 23-067 | 23 | N/A | 66168 | Grand Erie DSB | Waterford | Waterford Public Elementary School | ELE | 9873 | 5163 | 5163-B01 | 100 EAST CHURCH ST | WATERFORD | N0E1Y0 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.9323 | -80.2854 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2285982 | Construction Complete | Addition | Other | 2010-11 | 40422 | 2285982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2285982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2285982 | 2285982 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-068 | 23-068 | 23 | N/A | 66168 | Grand Erie DSB | Waterford District | Waterford District Public Secondary School | SEC | 5730 | 8418 | 8418-B01 | 227 MAIN ST S | WATERFORD | N0E1Y0 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.9283 | -80.2884 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 504735 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 504735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504735 | 504735 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-069 | 23-069 | 23 | N/A | 66168 | Grand Erie DSB | West Lynn | West Lynn Public Elementary School | ELE | 2458 | 6882 | 6882-B01 | 18 PARKER DR | SIMCOE | N3Y1A1 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8211 | -80.2997 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1461334 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1461334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1461334 | 1461334 | 1461334 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
23-071-1-01 | 23-071 | 23 | 228 - CMSM Norfolk | 66168 | Grand Erie DSB | Mapleview | Mapleview Public Elementary School | ELE | 24581 | 5811 | 5811-B02 | 223 FAIRVIEW AVE W | DUNNVILLE | N1A1M4 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.9126 | -79.6174 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 423 | 1 | 16 | Y | 1 | Approved | 44235 | 10811536 | Construction Complete | New Construction | Consolidation | 2018-19 | 43344 | 0 | 0 | 474245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474245 | 0 | 0 | 880094 | 0 | 8937901 | 0 | 259648 | 259648 | 0 | 0 | 10337291 | 10811536 | 10811536 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9457197
23-071-1-03 | 23-071 | 23 | N/A | 66168 | Grand Erie DSB | Fairview Avenue | Fairview Avenue Public Elementary School | ELE | 783 | 5811 | 5811-B01 | 223 FAIRVIEW AVE W | DUNNVILLE | N1A1M4 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.9126 | -79.6174 | 43350 | 2018-19 | 2018-19 | - | - | - | 43350 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43350 | 980000 | Construction Complete | Demolition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980000 | 0 | 0 | 0 | 0 | 0 | 980000 | 980000 | 980000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 980000
23-071-2 | 23-071 | 23 | N/A | 66168 | Grand Erie DSB | Thompson Creek | Thompson Creek Public Elementary School | ELE | 650 | 5726 | 5726-B01 | 800 CROSS ST W | DUNNVILLE | N1A1N7 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.9141 | -79.6307 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Approved | 42970 | 1110000 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259647 | 0 | 1022343 | 0 | 0 | 0 | 0 | 0 | 1281990 | 1281990 | 1281990 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1022343
23-072 | 23-072 | 23 | 228 - CMSM Norfolk | 66168 | Grand Erie DSB | Hagersville | Hagersville Public Secondary School | SEC | 5408 | 8239 | 8239-B01 | 70 PARKVIEW RD | HAGERSVILLE | N0A1H0 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.9576 | -80.0451 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43727 | 786506 | Construction Complete | Addition | Child Care | 2020-21 | 44136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786506 | 0 | 0 | 0 | 786506 | 786506 | 786506 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 786506
23-073 | 23-073 | 23 | 228 - CMSM Norfolk | 66168 | Grand Erie DSB | Elgin Avenue | Elgin Avenue Public Elementary School | ELE | 715 | 5773 | 5773-B01 | 80 ELGIN AVE | SIMCOE | N3Y4A8 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.837 | -80.3141 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | 98 | 3 | 49 | Y | 1 | Planned | - | 0 | Planned | Addition | Consolidation | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524337 | 0 | 3558461 | 0 | 1573010 | 524337 | 0 | 0 | 6180145 | 6180145 | 6180145 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5655808
23-074 | 23-074 | 23 | 200 - CMSM Brantford | 66168 | Grand Erie DSB | Central | Central Public Elementary School | ELE | 364 | 5529 | 5529-B01 | 135 GEORGE ST | BRANTFORD | N3T6B4 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1445 | -80.2628 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 64 | Y | - | Approved | 43727 | 2057016 | Construction Complete | Addition | Child Care | 2020-21 | 44305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057016 | 0 | 0 | 0 | 2057016 | 2057016 | 2057016 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2057016
23-075 | 23-075 | 23 | 200 - CMSM Brantford | 66168 | Grand Erie DSB | SW Brantford | SW Brantford Public Elementary School | ELE | 25473 | 20479 | 20479-B01 | 230 SHELLARD LANE | BRANTFORD | N3T0B9 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Central | South | 43.1221 | -80.2996 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 650 | 4 | 64 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26100000 | 0 | 0 | 0 | 0 | 0 | 26100000 | 0 | 0 | 0 | 0 | 14087896 | 0 | 2182082 | 0 | 0 | 0 | 16269978 | 42369978 | 42369978 | 0 | - | No, Site to be acquired. Sign installation planned for July 1, 2022 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16269978
23-076 | 23-071 | 23 | N/A | 66168 | Grand Erie DSB | Mapleview | Mapleview Public Elementary School | ELE | 24581 | 5811 | 5811-L02 | 223 FAIRVIEW AVE W | DUNNVILLE | N1A1M4 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 42.9126 | -79.6174 | 44235 | 2020-21 | 2020-21 | 44235 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44235 | 677835 | Construction Complete | Land Acquisition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677835 | 0 | 0 | 0 | 0 | 0 | 0 | 677835 | 677835 | 677835 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 677835
23-077 | 23-077 | 23 | 200 - CMSM Brantford | 66168 | Grand Erie DSB | Cobblestone | Cobblestone Public Elementary School | ELE | 11249 | 12190 | 12190-B01 | 179 GRANDVILLE CIR | PARIS | N3L0A9 | 35-15-14-000 | Brant | Brant County | Brant County | BRANT | Southwest | South | 43.1794 | -80.3945 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 64 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224868 | 0 | 0 | 0 | 2224868 | 2224868 | 2224868 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 2224868
23-078 | 23-078 | 23 | 200 - CMSM Brantford | 66168 | Grand Erie DSB | Banbury Heights | Banbury Heights Public Elementary School | ELE | 170 | 5407 | 5407-B01 | 141 BANBURY RD | BRANTFORD | N3P1E3 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1893 | -80.2368 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 64 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2182082 | 0 | 0 | 0 | 2182082 | 2182082 | 2182082 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 2182082
23-079 | 23-079+51-030 | 23 | 228 - CMSM Norfolk | 66168 | Grand Erie DSB | Caledonia | Caledonia Public Elementary School | ELE | TBD | TBD | TBD | MACLACHLAN AVE / WHITHORN CRES | CALEDONIA | TBD | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0735 | -79.9313 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 441 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10537226 | 0 | 1751759 | 0 | 0 | 0 | 12288985 | 12288985 | 12288985 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12288985
23-080 | 23-080+51-032 | 23 | 228 - CMSM Norfolk | 66168 | Grand Erie DSB | Caledonia | Caledonia Public Elementary School | ELE | TBD | TBD | TBD | MACLACHLAN AVE / WHITHORN CRES | CALEDONIA | TBD | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0735 | -79.9313 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 441 | 3 | 49 | N | - | Planned | - | - | Planned | Land Acquisition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6381801 | 0 | 0 | 0 | 0 | 0 | 0 | 6381801 | 6381801 | 6381801 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 6381801
24-001 | 24-001 | 24 | N/A | 66176 | Waterloo Region DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3662 | 0 | 0 | 0 | 0 | 0 | 3662 | 3662 | 0 | -3662 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 3662
24-002 | 24-002 | 24 | N/A | 66176 | Waterloo Region DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 48511536 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48698830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48698830 | 48698830 | 48511536 | -187294 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-003 | 24-003 | 24 | N/A | 66176 | Waterloo Region DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 522740 | Construction Complete | Other | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522740 | 522740 | 522740 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-004 | 24-004 | 24 | N/A | 66176 | Waterloo Region DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1033590 | Construction Complete | Other | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033590 | 1033590 | 1033590 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-005 | 24-005 | 24 | N/A | 66176 | Waterloo Region DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2261584 | Construction Complete | Other | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2261584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2261584 | 2261584 | 2261584 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-007 | 24-007 | 24 | N/A | 66176 | Waterloo Region DSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13999573 | Construction Complete | Other | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 1548375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12451198 | 13999573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13999573 | 13999573 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-008 | 24-008 | 24 | N/A | 66176 | Waterloo Region DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3558292 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3558292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3558292 | 3558292 | 3558292 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-009 | 24-009 | 24 | N/A | 66176 | Waterloo Region DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 268250 | Construction Complete | Other | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268250 | 268250 | 268250 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-010 | 24-010 | 24 | N/A | 66176 | Waterloo Region DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 70000 | Construction Complete | Other | Other | 2012-13 | 41153 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-011 | 24-011 | 24 | N/A | 66176 | Waterloo Region DSB | Abraham Erb | Abraham Erb Public Elementary School | ELE | 10660 | 11229 | 11229-B01 | 710 LAURELWOOD DR | WATERLOO | N2V2V3 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4699 | -80.597 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5801235 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5801235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5801235 | 5801235 | 5801235 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-015 | 24-015 | 24 | N/A | 66176 | Waterloo Region DSB | Avenue Road | Avenue Road Public Elementary School | ELE | 111 | 5366 | 5366-B01 | 40 GAIL ST | CAMBRIDGE | N1R4M2 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3795 | -80.3129 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6271535 | Construction Complete | Addition | Other | 2012-13 | 41153 | 467807 | 0 | 4250000 | 0 | 492279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5210086 | 631344 | 0 | 430105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061449 | 6271535 | 6271535 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-016 | 24-016 | 24 | N/A | 66176 | Waterloo Region DSB | Baden | Baden Public Elementary School | ELE | 10750 | 11965 | 11965-B01 | 155 LIVINGSTON BLVD | BADEN | N3A4M6 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.4076 | -80.6718 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8189126 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8189126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8189126 | 8189126 | 8189126 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-019 | 24-019 | 24 | N/A | 66176 | Waterloo Region DSB | Bluevale | Bluevale Public Secondary School | SEC | 5237 | 8135 | 8135-B01 | 80 BLUEVALE ST N | WATERLOO | N2J3R5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4751 | -80.5001 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15656487 | Construction Complete | Addition | Other | 2011-12 | 40787 | 5900000 | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 9200000 | 6456487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6456487 | 15656487 | 15656487 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-020 | 24-020 | 24 | N/A | 66176 | Waterloo Region DSB | Breslau | Breslau Public Elementary School | ELE | 2428 | 6863 | 6863-B01 | 58 JOSEPH ST | BRESLAU | N0B1M0 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.4781 | -80.4163 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 196 | - | - | N | - | Approved | 41688 | 4697790 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 100000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 200000 | 0 | 1753183 | 0 | 1944331 | 0 | 0 | 0 | 0 | 0 | 3897514 | 4597514 | 4597514 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1944331
24-021 | 24-021 | 24 | N/A | 66176 | Waterloo Region DSB | Bridgeport | Bridgeport Public Elementary School | ELE | 242 | 5448 | 5448-B01 | 59 BRIDGE ST W | KITCHENER | N2K1K6 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4832 | -80.4862 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3007217 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3007217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3007217 | 3007217 | 3007217 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-023 | 24-023 | 24 | N/A | 66176 | Waterloo Region DSB | Cameron Heights | Cameron Heights Public Secondary School | SEC | 5257 | 8149 | 8149-B01 | 301 CHARLES ST E | KITCHENER | N2G2P8 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4448 | -80.4818 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 400000 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-024 | 24-024 | 24 | N/A | 66176 | Waterloo Region DSB | Cedar Creek | Cedar Creek Public Elementary School | ELE | 9963 | 10342 | 10342-B01 | 55 HILLTOP DR | AYR | N0B1E0 | 35-15-25-601 | North Dumfries | North Dumfries Tp | Waterloo R | WATERLOO | Southwest | South | 43.2838 | -80.4402 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4762741 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63147 | 63147 | 4699594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4699594 | 4762741 | 4762741 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-026 | 24-026 | 24 | N/A | 66176 | Waterloo Region DSB | Centennial | Centennial Public Elementary School | ELE | 357 | 5523 | 5523-B01 | 100 WEAVER ST | CAMBRIDGE | N3C1W4 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4233 | -80.318 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 382476 | Construction Complete | Retrofit | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382476 | 382476 | 382476 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-029 | 24-029 | 24 | N/A | 66176 | Waterloo Region DSB | Chalmers Street | Chalmers Street Public Elementary School | ELE | 417 | 5575 | 5575-B01 | 35 CHALMERS ST S | CAMBRIDGE | N1R5B4 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3519 | -80.2967 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 383971 | Construction Complete | Retrofit | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383971 | 383971 | 383971 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-030 | 24-030 | 24 | N/A | 66176 | Waterloo Region DSB | Chicopee Hills | Chicopee Hills Public Elementary School | ELE | 18633 | 19087 | 19087-B01 | 300 CHICOPEE HILLS DR | KITCHENER | N2A0J6 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4449 | -80.4145 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 646 | - | - | N | - | Approved | 42412 | 11334850 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 636862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636862 | 0 | 0 | 426577 | 0 | 11185269 | 0 | 0 | 0 | 0 | 0 | 11611846 | 12248708 | 12248708 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11185269
24-032 | 24-032 | 24 | N/A | 66176 | Waterloo Region DSB | Conestogo | Conestogo Public Elementary School | ELE | 2570 | 6945 | 6945-B01 | 1948 SAWMILL RD SS 6 | CONESTOGO | N0B1N0 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.5422 | -80.5082 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1203272 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203272 | 1203272 | 1203272 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-038 | 24-038 | 24 | N/A | 66176 | Waterloo Region DSB | Eastwood | Eastwood Public Secondary School | SEC | 5341 | 8200 | 8200-B01 | 760 WEBER ST E | KITCHENER | N2H1H6 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4396 | -80.461 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1245305 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245305 | 1245305 | 1245305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-039 | 24-039 | 24 | N/A | 66176 | Waterloo Region DSB | Edna Staebler | Edna Staebler Public Elementary School | ELE | 10957 | 12107 | 12107-B01 | 450 BERNAY DR | WATERLOO | N2T3A3 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4507 | -80.577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10026300 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476643 | 476643 | 9549657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9549657 | 10026300 | 10026300 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-043 | 24-043 | 24 | N/A | 66176 | Waterloo Region DSB | Elmira District | Elmira District Public Secondary School | SEC | 5349 | 8203 | 8203-L01 | 4 UNIVERSITY AVE W | ELMIRA | N3B1K2 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.5938 | -80.5626 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 750000 | Construction Complete | Land Acquisition | Other | 2011-12 | 40787 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-046 | 24-046 | 24 | N/A | 66176 | Waterloo Region DSB | Floradale | Floradale Public Elementary School | ELE | 24260 | 5840 | 5840-B02 | 35 FLORAPINE RD | ELMIRA | N3B2Z1 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.6356 | -80.5759 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5950588 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 1311256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311256 | 4639332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4639332 | 5950588 | 5950588 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-048 | 24-048 | 24 | N/A | 66176 | Waterloo Region DSB | Forest Hill | Forest Hill Public Elementary School | ELE | 842 | 5850 | 5850-B01 | 255 WESTMOUNT RD E | KITCHENER | N2M4Z2 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4262 | -80.5058 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2789765 | Construction Complete | Addition | Other | 2011-12 | 40787 | 278873 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358873 | 456890 | 0 | 1974002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430892 | 2789765 | 2789765 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-049 | 24-049 | 24 | N/A | 66176 | Waterloo Region DSB | Franklin | Franklin Public Elementary School | ELE | 852 | 5856 | 5856-B01 | 371 FRANKLIN ST N | KITCHENER | N2A1Y9 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4443 | -80.4475 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4142805 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4142805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4142805 | 4142805 | 4142805 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-050 | 24-050 | 24 | N/A | 66176 | Waterloo Region DSB | Galt | Galt Public Secondary School | SEC | 5375 | 8214 | 8214-L01 | 200 WATER ST N | CAMBRIDGE | N1R6V2 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3689 | -80.3185 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 671708 | Construction Complete | Land Acquisition | Other | 2011-12 | 40787 | 0 | 0 | 671708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671708 | 671708 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-052 | 24-052 | 24 | N/A | 66176 | Waterloo Region DSB | Glenview Park | Glenview Park Public Secondary School | SEC | 5396 | 8229 | 8229-B01 | 55 MCKAY ST | CAMBRIDGE | N1R4G6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3463 | -80.307 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1460523 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460523 | 1460523 | 1460523 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-053 | 24-053 | 24 | N/A | 66176 | Waterloo Region DSB | Grand River | Grand River Public Secondary School | SEC | 5401 | 8234 | 8234-B01 | 175 INDIAN RD | KITCHENER | N2B2S7 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4573 | -80.4375 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 705906 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705906 | 705906 | 705906 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-054 | 24-054 | 24 | N/A | 66176 | Waterloo Region DSB | Grand View | Grand View Public Elementary School | ELE | 16170 | 18117 | 18117-B01 | 1144 HAMILTON ST | CAMBRIDGE | N3H3G2 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3915 | -80.3551 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8134926 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7704821 | 0 | 430105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8134926 | 8134926 | 8134926 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-056 | 24-056 | 24 | N/A | 66176 | Waterloo Region DSB | Groh | Groh Public Elementary School | ELE | 24443 | 19446 | 19446-L01 | 225 THOMAS SLEE DR | KITCHENER | N2P0B8 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.3724 | -80.439 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7842252 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7467252 | 7842252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7842252 | 7842252 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-057 | 24-057 | 24 | N/A | 66176 | Waterloo Region DSB | Groh | Groh Public Elementary School | ELE | 24443 | 19446 | 19446-B01 | 225 THOMAS SLEE DR | KITCHENER | N2P0B8 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.3724 | -80.439 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 574 | - | - | N | - | Approved | 42139 | 12859506 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 999327 | 619806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1619133 | 0 | 0 | 931894 | 0 | 10265035 | 0 | 0 | 0 | 0 | 0 | 11196929 | 12816062 | 12816057 | -5 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10265035
24-058 | 24-058 | 24 | N/A | 66176 | Waterloo Region DSB | Hespeler | Hespeler Public Elementary School | ELE | 390 | 5553 | 5553-B01 | 300 WINSTON BLVD | CAMBRIDGE | N3C3J6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4207 | -80.3053 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 709957 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709957 | 709957 | 709957 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-059 | 24-059 | 24 | N/A | 66176 | Waterloo Region DSB | Hespeler | Hespeler Public Elementary School | ELE | 390 | 5553 | 5553-B01 | 300 WINSTON BLVD | CAMBRIDGE | N3C3J6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4207 | -80.3053 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2450658 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450658 | 2450658 | 2450658 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-062 | 24-062 | 24 | N/A | 66176 | Waterloo Region DSB | Hillcrest | Hillcrest Public Elementary School | ELE | 1084 | 6002 | 6002-B01 | 31 RENWICK AVE | CAMBRIDGE | N3C2T5 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4353 | -80.3008 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1213780 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213780 | 1213780 | 1213780 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-064 | 24-064 | 24 | N/A | 66176 | Waterloo Region DSB | Huron Heights | Huron Heights Public Secondary School | SEC | 10712 | 11230 | 11230-B01 | 1825 STRASBURG RD | KITCHENER | N2R1S3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.3947 | -80.4665 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 23882969 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23882969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23882969 | 23882969 | 23882969 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-065 | 24-065 | 24 | N/A | 66176 | Waterloo Region DSB | Jacob Hespeler | Jacob Hespeler Public Secondary School | SEC | 5445 | 5523 | 5523-B02 | 355 HOLIDAY INN DR | CAMBRIDGE | N3C1Z2 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4177 | -80.317 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5949781 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5949781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5949781 | 5949781 | 5949781 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-066 | 24-066 | 24 | N/A | 66176 | Waterloo Region DSB | Jean Steckle | Jean Steckle Public Elementary School | ELE | 16803 | 19021 | 19021-L01 | 130 WOODBINE AVE | KITCHENER | N2R1X9 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.3882 | -80.4842 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3251792 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 3251792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3251792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3251792 | 3251792 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-067 | 24-067 | 24 | N/A | 66176 | Waterloo Region DSB | Jean Steckle | Jean Steckle Public Elementary School | ELE | 16803 | 19021 | 19021-B01 | 130 WOODBINE AVE | KITCHENER | N2R1X9 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.3882 | -80.4842 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 650 | - | - | N | - | Approved | 44222 | 11432626 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 926314 | 846357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1772671 | 0 | 0 | 931894 | 0 | 8530874 | 0 | 0 | 0 | 0 | 0 | 9462768 | 11235439 | 11432626 | 197187 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8530874
24-069 | 24-069 | 24 | N/A | 66176 | Waterloo Region DSB | JW Gerth | JW Gerth Public Elementary School | ELE | 10956 | 12106 | 12106-B01 | 171 APPLE RIDGE DR | KITCHENER | N2P0A1 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.384 | -80.439 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8457479 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000 | 7857479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7857479 | 8457479 | 8457479 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-072 | 24-072 | 24 | N/A | 66176 | Waterloo Region DSB | Kitchener-Waterloo | Kitchener-Waterloo Public Secondary School | SEC | 5463 | 8268 | 8268-L01 | 787 KING ST W | KITCHENER | N2G1E3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4556 | -80.5088 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 705958 | Construction Complete | Land Acquisition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 705958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705958 | 705958 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-073 | 24-073 | 24 | N/A | 66176 | Waterloo Region DSB | Lackner Woods | Lackner Woods Public Elementary School | ELE | 9965 | 10344 | 10344-B01 | 151 ZELLER DR | KITCHENER | N2A4H4 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4523 | -80.4189 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5506959 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506959 | 5506959 | 5506959 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-075 | 24-075 | 24 | N/A | 66176 | Waterloo Region DSB | Laurelwood | Laurelwood Public Elementary School | ELE | 9313 | 5145 | 5145-B01 | 460 BRENTCLIFFE DR | WATERLOO | N2T2R5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4685 | -80.5762 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 367974 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367974 | 367974 | 367974 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-077 | 24-077 | 24 | N/A | 66176 | Waterloo Region DSB | Lester B Pearson | Lester B Pearson Public Elementary School | ELE | 10164 | 10438 | 10438-B01 | 520 CHESAPEAKE DR | WATERLOO | N2K4G5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.5074 | -80.5065 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6575994 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102538 | 103348 | 6472646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6472646 | 6575994 | 6575994 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-081 | 24-081 | 24 | N/A | 66176 | Waterloo Region DSB | Linwood | Linwood Public Elementary School | ELE | 1369 | 6173 | 6173-B01 | 50 PINE ST | LINWOOD | N0B2A0 | 35-15-25-602 | Wellesley | Wellesley Tp | Waterloo R | WATERLOO | Southwest | South | 43.5804 | -80.7329 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 998143 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998143 | 998143 | 998143 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-083 | 24-083 | 24 | N/A | 66176 | Waterloo Region DSB | Mackenzie King | Mackenzie King Public Elementary School | ELE | 2430 | 6865 | 6865-B01 | 51 NATCHEZ RD | KITCHENER | N2B3A7 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4659 | -80.4476 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 190 | - | - | N | - | Not Required | - | 3696389 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 0 | 2764013 | 0 | 0 | 0 | 0 | 0 | 3695907 | 3695907 | 3696389 | 482 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2764013
24-084 | 24-084 | 24 | N/A | 66176 | Waterloo Region DSB | Manchester | Manchester Public Elementary School | ELE | 1433 | 6216 | 6216-B01 | 455 DUNDAS ST | CAMBRIDGE | N1R5R5 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.371 | -80.3135 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41656 | 5022304 | Construction Complete | Addition | Other | 2014-15 | 41883 | 1008935 | 1500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3508935 | 0 | 0 | 1513369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513369 | 5022304 | 5022304 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-085 | 24-085 | 24 | N/A | 66176 | Waterloo Region DSB | Mary Johnston | Mary Johnston Public Elementary School | ELE | 1479 | 6250 | 6250-B01 | 475 BRYNHURST BLVD | WATERLOO | N2T2C6 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4582 | -80.5643 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1866994 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866994 | 1866994 | 1866994 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-087 | 24-087 | 24 | N/A | 66176 | Waterloo Region DSB | Millen Woods | Millen Woods Public Elementary School | ELE | 11157 | 12244 | 12244-L01 | 640 NEW HAMPSHIRE ST | WATERLOO | N2K0A5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.5134 | -80.5042 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 700000 | Construction Complete | Land Acquisition | Other | 2010-11 | 40422 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-088 | 24-088 | 24 | N/A | 66176 | Waterloo Region DSB | Millen Woods | Millen Woods Public Elementary School | ELE | 11157 | 12244 | 12244-B01 | 640 NEW HAMPSHIRE ST | WATERLOO | N2K0A5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.5134 | -80.5042 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9583363 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000 | 910000 | 7383049 | 0 | 1290314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673363 | 9583363 | 9583363 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-089 | 24-089 | 24 | N/A | 66176 | Waterloo Region DSB | Moffat Creek | Moffat Creek Public Elementary School | ELE | 16169 | 18116 | 18116-B01 | 710 MYERS RD | CAMBRIDGE | N1P0A8 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3455 | -80.2763 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 14505934 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819274 | 2569274 | 11076451 | 0 | 860209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11936660 | 14505934 | 14505934 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-090 | 24-090 | 24 | N/A | 66176 | Waterloo Region DSB | Moffat Creek | Moffat Creek Public Elementary School | ELE | 16169 | 18116 | 18116-L01 | 710 MYERS RD | CAMBRIDGE | N1P0A8 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3455 | -80.2763 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5037066 | Construction Complete | Land Acquisition | Other | 2014-15 | 41883 | 0 | 0 | 5037066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5037066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5037066 | 5037066 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-095 | 24-095 | 24 | N/A | 66176 | Waterloo Region DSB | Preston | Preston Public Secondary School | SEC | 5598 | 8346 | 8346-B01 | 550 ROSE ST | CAMBRIDGE | N3H2E6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3912 | -80.3655 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1425045 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425045 | 1425045 | 1425045 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-098-01 | 24-098 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Riverside | Riverside Public Elementary School | ELE | 24435 | 19438 | 19438-B01 | 250 WILLIAM ST | ELMIRA | N3B1N3 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.6014 | -80.5706 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 557 | 5 | 88 | N | - | Approved | 41458 | 15656410 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453777 | 0 | 9692499 | 0 | 2514265 | 0 | 0 | 0 | 13660541 | 13660541 | 15813790 | 2153249 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12206764
24-098-02 | 24-098 | 24 | N/A | 66176 | Waterloo Region DSB | Riverside | Riverside Public Elementary School | ELE | 24435 | 19438 | 19438-L01 | 250 WILLIAM ST | ELMIRA | N3B1N3 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.6014 | -80.5706 | 41458 | 2012-13 | 2013-14 | 41458 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41458 | 370000 | Construction Complete | Land Acquisition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 228829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228829 | 0 | 0 | 0 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 370000 | 598829 | 598829 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 370000
24-100 | 24-100 | 24 | N/A | 66176 | Waterloo Region DSB | Ryerson | Ryerson Public Elementary School | ELE | 24261 | 6635 | 6635-B02 | 749 GRAND VALLEY DR | CAMBRIDGE | N3H2S3 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3901 | -80.3349 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7874047 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 750000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 905000 | 5678733 | 0 | 1290314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6969047 | 7874047 | 7874047 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-102 | 24-102 | 24 | N/A | 66176 | Waterloo Region DSB | Saginaw | Saginaw Public Elementary School | ELE | 9314 | 10118 | 10118-B01 | 740 SAGINAW PKY | CAMBRIDGE | N1T1V6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3937 | -80.2789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 759252 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759252 | 759252 | 759252 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-103 | 24-103 | 24 | N/A | 66176 | Waterloo Region DSB | Sandhills | Sandhills Public Elementary School | ELE | 9964 | 10343 | 10343-B01 | 1250 VICTORIA ST S | KITCHENER | N2N3J2 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4324 | -80.5437 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6545287 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20200 | 20200 | 6525087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6525087 | 6545287 | 6545287 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-105 | 24-105 | 24 | N/A | 66176 | Waterloo Region DSB | Sandowne | Sandowne Public Elementary School | ELE | 2080 | 6640 | 6640-B01 | 265 SANDOWNE DR | WATERLOO | N2K2C1 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4918 | -80.5059 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3591603 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 2131394 | 0 | 860209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2991603 | 3591603 | 3591603 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-106 | 24-106 | 24 | N/A | 66176 | Waterloo Region DSB | Silverheights | Silverheights Public Elementary School | ELE | 2223 | 6727 | 6727-B01 | 390 SCOTT RD | CAMBRIDGE | N3C3Z7 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4419 | -80.3153 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 276 | - | - | N | - | Not Required | - | 6873320 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 307780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307780 | 0 | 0 | 1397841 | 0 | 5068700 | 0 | 0 | 0 | 0 | 0 | 6466541 | 6774321 | 6774320 | -1 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5068700
24-107 | 24-107 | 24 | N/A | 66176 | Waterloo Region DSB | Sir Adam Beck | Sir Adam Beck Public Elementary School | ELE | 11153 | 8420 | 8420-L02 | 1140 SNYDER'S RD W | BADEN | N3A0A8 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.4016 | -80.6859 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 420000 | Construction Complete | Land Acquisition | Other | 2010-11 | 40422 | 0 | 0 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 420000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-108 | 24-108 | 24 | N/A | 66176 | Waterloo Region DSB | Sir Adam Beck | Sir Adam Beck Public Elementary School | ELE | 11153 | 8420 | 8420-B02 | 1140 SNYDER'S RD W | BADEN | N3A0A8 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.4016 | -80.6859 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9578092 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 600000 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350000 | 7117778 | 0 | 1110314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8228092 | 9578092 | 9578092 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-109 | 24-109 | 24 | N/A | 66176 | Waterloo Region DSB | Sir Adam Beck | Sir Adam Beck Public Elementary School | ELE | 11153 | 8420 | 8420-B02 | 1140 SNYDER'S RD W | BADEN | N3A0A8 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.4016 | -80.6859 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Approved | 42425 | 1881335 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356435 | 0 | 0 | 0 | 0 | 0 | 1356435 | 1356435 | 1356435 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1356435
24-110 | 24-110 | 24 | N/A | 66176 | Waterloo Region DSB | Sir John A MacDonald | Sir John A MacDonald Public Secondary School | SEC | 10273 | 10476 | 10476-B01 | 650 LAURELWOOD DR | WATERLOO | N2V2V1 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4715 | -80.5942 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 26195726 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26195726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26195726 | 26195726 | 26195726 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-111 | 24-111 | 24 | N/A | 66176 | Waterloo Region DSB | Sir John A MacDonald | Sir John A MacDonald Public Secondary School | SEC | 10273 | 10476 | 10476-B01 | 650 LAURELWOOD DR | WATERLOO | N2V2V1 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4715 | -80.5942 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 365006 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365006 | 365006 | 365006 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-113 | 24-113 | 24 | N/A | 66176 | Waterloo Region DSB | St. Jacobs | St. Jacobs Public Elementary School | ELE | 2573 | 6948 | 6948-B01 | 72 QUEENSWAY DR | ST JACOBS | N0B2N0 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.5369 | -80.5556 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 655319 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655319 | 655319 | 655319 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-115 | 24-115 | 24 | N/A | 66176 | Waterloo Region DSB | Stewart Avenue | Stewart Avenue Public Elementary School | ELE | 2236 | 6734 | 6734-B01 | 145 STEWART AVE | CAMBRIDGE | N1R2V5 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3486 | -80.3025 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 636970 | Construction Complete | Retrofit | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636970 | 636970 | 636970 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-118-01 | 24-118 | 24 | N/A | 66176 | Waterloo Region DSB | Tait Street | Tait Street Public Elementary School | ELE | 2275 | 6757 | 6757-B01 | 184 TAIT ST | CAMBRIDGE | N1S3G3 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.339 | -80.3235 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2911733 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 1534121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534121 | 0 | 0 | 1377612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377612 | 2911733 | 2911733 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-118-02 | 24-118 | 24 | N/A | 66176 | Waterloo Region DSB | Tait Street | Tait Street Public Elementary School | ELE | 2275 | 6757 | 6757-L01 | 184 TAIT ST | CAMBRIDGE | N1S3G3 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.339 | -80.3235 | 41211 | 2012-13 | 2012-13 | 41211 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41211 | 400000 | Construction Complete | Land Acquisition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 379771 | -20229 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 400000
24-120 | 24-120 | 24 | N/A | 66176 | Waterloo Region DSB | Vista Hills | Vista Hills Public Elementary School | ELE | 24442 | 19445 | 19445-L01 | 314 SWEET GALE ST | WATERLOO | N2V0B3 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4524 | -80.5907 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3136388 | Construction Complete | Land Acquisition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136388 | 3136388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136388 | 3136388 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-121 | 24-121 | 24 | N/A | 66176 | Waterloo Region DSB | Vista Hills | Vista Hills Public Elementary School | ELE | 24442 | 19445 | 19445-B01 | 314 SWEET GALE ST | WATERLOO | N2V0B3 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4524 | -80.5907 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 646 | - | - | N | - | Approved | 42115 | 12285160 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 257744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257744 | 0 | 0 | 931894 | 0 | 11349699 | 0 | 0 | 0 | 0 | 0 | 12281593 | 12539337 | 12539336 | -1 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11349699
24-122 | 24-122 | 24 | N/A | 66176 | Waterloo Region DSB | Waterloo-Oxford District | Waterloo-Oxford District Public Secondary School | SEC | 5732 | 8420 | 8420-B01 | 1206 SNYDER'S RD W | NEW HAMBURG | N3A1A4 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.4015 | -80.6893 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 342461 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342461 | 342461 | 342461 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-123 | 24-123 | 24 | N/A | 66176 | Waterloo Region DSB | Waterloo-Oxford District | Waterloo-Oxford District Public Secondary School | SEC | 5732 | 8420 | 8420-B01 | 1206 SNYDER'S RD W | NEW HAMBURG | N3A1A4 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.4015 | -80.6893 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1084281 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084281 | 1084281 | 1084281 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-124 | 24-124 | 24 | N/A | 66176 | Waterloo Region DSB | Wellesley | Wellesley Public Elementary School | ELE | 2440 | 6873 | 6873-B01 | 1059 QUEENS BUSH RD RR 1 | WELLESLEY | N0B2T0 | 35-15-25-602 | Wellesley | Wellesley Tp | Waterloo R | WATERLOO | Southwest | South | 43.4775 | -80.7559 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1257969 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1257969 | 1257969 | 1257969 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-125 | 24-125 | 24 | N/A | 66176 | Waterloo Region DSB | Wellesley | Wellesley Public Elementary School | ELE | 2440 | 6873 | 6873-B01 | 1059 QUEENS BUSH RD RR 1 | WELLESLEY | N0B2T0 | 35-15-25-602 | Wellesley | Wellesley Tp | Waterloo R | WATERLOO | Southwest | South | 43.4775 | -80.7559 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1036260 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036260 | 1036260 | 1036260 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-126 | 24-126 | 24 | N/A | 66176 | Waterloo Region DSB | Wellesley | Wellesley Public Elementary School | ELE | 2440 | 6873 | 6873-B01 | 1059 QUEENS BUSH RD RR 1 | WELLESLEY | N0B2T0 | 35-15-25-602 | Wellesley | Wellesley Tp | Waterloo R | WATERLOO | Southwest | South | 43.4775 | -80.7559 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3159075 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159075 | 3159075 | 3159075 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-128 | 24-128 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Janet Metcalfe | Janet Metcalfe Public Elementary School | ELE | 24585 | 19591 | 19591-B01 | 335 SEABROOK DR | KITCHENER | N2R0G3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.3854 | -80.4984 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 663 | 5 | 88 | N | - | Approved | 43713 | 16410348 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 104051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 204051 | 0 | 0 | 1729994 | 0 | 11342041 | 0 | 2471419 | 0 | 0 | 0 | 15543454 | 15747505 | 16410348 | 662843 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13813460
24-129 | 24-129 | 24 | N/A | 66176 | Waterloo Region DSB | Westmount | Westmount Public Elementary School | ELE | 24396 | 6890 | 6890-B02 | 329 GLASGOW ST | KITCHENER | N2M2M9 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4492 | -80.5209 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 182348 | Construction Complete | Retrofit | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182348 | 182348 | 182348 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-130 | 24-130 | 24 | N/A | 66176 | Waterloo Region DSB | Westmount | Westmount Public Elementary School | ELE | 24396 | 6890 | 6890-B02 | 329 GLASGOW ST | KITCHENER | N2M2M9 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4492 | -80.5209 | 41858 | 2013-14 | 2014-15 | - | - | - | 41858 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 493 | - | - | N | - | Not Required | - | 10328756 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 7949411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7949411 | 0 | 0 | 1791345 | 0 | 588000 | 0 | 0 | 0 | 0 | 0 | 2379345 | 10328756 | 10328756 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 588000
24-132 | 24-132 | 24 | N/A | 66176 | Waterloo Region DSB | Williamsburg | Williamsburg Public Elementary School | ELE | 10787 | 11992 | 11992-B01 | 760 COMMONWEALTH CRES | KITCHENER | N2E4K7 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.403 | -80.5043 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10370926 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8637067 | 0 | 1733859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10370926 | 10370926 | 10370926 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-133 | 24-133 | 24 | N/A | 66176 | Waterloo Region DSB | Wilmot Senior | Wilmot Senior Public Elementary School | ELE | 2521 | 6914 | 6914-B01 | TBD | PETERSBURG | TBD | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | TBD | TBD | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 525532 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525532 | 525532 | 525532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-134 | 24-134 | 24 | N/A | 66176 | Waterloo Region DSB | Wilson Avenue | Wilson Avenue Public Elementary School | ELE | 2524 | 6917 | 6917-B01 | 221 WILSON AVE | KITCHENER | N2C1G9 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4264 | -80.4532 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4791471 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4791471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4791471 | 4791471 | 4791471 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-136 | 24-136 | 24 | N/A | 66176 | Waterloo Region DSB | WRDSB Head Office | Administrative Office | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3053189 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3053189 | 3053189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3053189 | 3053189 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-137 | 24-137 | 24 | N/A | 66176 | Waterloo Region DSB | WRDSB Head Office | Administrative Office | OFF-ADM | 18119 | 19051 | 19051-B01 | 51 ARDELT AVE | KITCHENER | N2C2R5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4282 | -80.4789 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 935022 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 0 | 935022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935022 | 935022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-138 | 24-138 | 24 | N/A | 66176 | Waterloo Region DSB | WT Townshend | WT Townshend Public Elementary School | ELE | 10376 | 11058 | 11058-B01 | 245 ACTIVA AVE | KITCHENER | N2E4A3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4064 | -80.5158 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5635244 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5635244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5635244 | 5635244 | 5635244 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-139 | 24-139 | 24 | N/A | 66176 | Waterloo Region DSB | WT Townshend | WT Townshend Public Elementary School | ELE | 10376 | 11058 | 11058-B01 | 245 ACTIVA AVE | KITCHENER | N2E4A3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4064 | -80.5158 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1380655 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380655 | 1380655 | 1380655 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-141 | 24-141 | 24 | N/A | 66176 | Waterloo Region DSB | Grand River | Grand River Public Secondary School | SEC | 5401 | 8234 | 8234-B01 | 175 INDIAN RD | KITCHENER | N2B2S7 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4573 | -80.4375 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Approved | 44222 | 11878402 | Construction Complete | Addition | Consolidation | 2019-20 | 43798 | 750000 | 200000 | 7217870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8167870 | 0 | 0 | 0 | 0 | 3647588 | 0 | 0 | 0 | 0 | 0 | 3647588 | 11815458 | 11878402 | 62944 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3647588
24-142 | 24-142 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Cedar Creek | Cedar Creek Public Elementary School | ELE | 9963 | 10342 | 10342-B01 | 55 HILLTOP DR | AYR | N0B1E0 | 35-15-25-601 | North Dumfries | North Dumfries Tp | Waterloo R | WATERLOO | Southwest | South | 43.2838 | -80.4402 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 190 | 5 | 72 | Y | 3 | Approved | 43166 | 8845721 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43711 | 366938 | 0 | 0 | 0 | 495225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862163 | 0 | 0 | 504170 | 0 | 3446028 | 0 | 2520850 | 1512510 | 0 | 0 | 7983558 | 8845721 | 8845721 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7479388
24-143 | 24-143 | 24 | N/A | 66176 | Waterloo Region DSB | Ryerson | Ryerson Public Elementary School | ELE | 24261 | 6635 | 6635-B02 | 749 GRAND VALLEY DR | CAMBRIDGE | N3H2S3 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3901 | -80.3349 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 199 | - | - | N | - | Approved | 43056 | 4706749 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43711 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 1260425 | 0 | 3146324 | 0 | 0 | 0 | 0 | 0 | 4406749 | 4706749 | 4706749 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3146324
24-144 | 24-144 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Southeast Cambridge | Southeast Cambridge Public Elementary School | ELE | 24610 | 19617 | 19617-B01 | FRANKLIN BLVD / GREEN GATE | CAMBRIDGE | TBD | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3567 | -80.2761 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 519 | 5 | 72 | Y | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285634 | 0 | 9646368 | 0 | 2571267 | 0 | 0 | 0 | 13503269 | 13503269 | 13503269 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12217635
24-145 | 24-145 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Huron South Tartan | Huron South Tartan Public Elementary School | ELE | 24838 | 19844 | 19844-B01 | 80 TARTAN AVE | KITCHENER | N2R0N6 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.3817 | -80.4794 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 591 | 5 | 88 | Y | 3 | Not Required | - | 0 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 1381998 | 0 | 0 | 0 | 0 | 2160622 | 0 | 0 | 0 | 0 | 0 | 3542620 | 0 | 0 | 1542760 | 0 | 11475107 | 0 | 2552154 | 1512511 | 0 | 0 | 17082532 | 20625152 | 20625152 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15539772
24-146 | 24-146 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Lackner Woods | Lackner Woods Public Elementary School | ELE | 9965 | 10344 | 10344-B01 | 151 ZELLER DR | KITCHENER | N2A4H4 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4523 | -80.4189 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44224 | 3506047 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3506047 | 0 | 0 | 0 | 3506047 | 3506047 | 3506047 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3506047
24-147 | 24-147 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Saginaw | Saginaw Public Elementary School | ELE | 9314 | 10118 | 10118-B01 | 740 SAGINAW PKY | CAMBRIDGE | N1T1V6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3937 | -80.2789 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44224 | 3903649 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3903649 | 0 | 0 | 0 | 3903649 | 3903649 | 3903649 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3903649
24-148 | 24-148 | 24 | N/A | 66176 | Waterloo Region DSB | Manchester | Manchester Public Elementary School | ELE | 1433 | 6216 | 6216-B01 | 455 DUNDAS ST | CAMBRIDGE | N1R5R5 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.371 | -80.3135 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44754 | 2737281 | Construction Complete | Addition | Other | 2021-22 | 44445 | 0 | 0 | 0 | 2737281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2737281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2737281 | 2737281 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
24-149 | 24-149 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | South Kitchener | South Kitchener Public Elementary School | ELE | 25381 | 20387 | 20387-B01 | 670 THOMAS SLEE DR | KITCHENER | TBD | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.377 | -80.4215 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 591 | 3 | 49 | - | - | Approved | 45106 | 25092850 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 1259883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259883 | 0 | 0 | 0 | 0 | 20735119 | 0 | 3097848 | 0 | 0 | 0 | 23832967 | 25092850 | 25092850 | 0 | - | No, Site to be acquired. Sign installation planned for November 1, 2021 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23832967
24-150 | 24-150 | 24 | N/A | 66176 | Waterloo Region DSB | Laurelwood | Laurelwood Public Elementary School | ELE | 9913 | 5145 | 5145-B01 | 460 BRENTCLIFFE DR | WATERLOO | N2T2R5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Central | South | 43.4685 | -80.5762 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 184 | 8 | - | N | - | Approved | 44951 | 6421759 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6421759 | 0 | 0 | 0 | 0 | 0 | 6421759 | 6421759 | 6421759 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6421759
24-151 | 24-151 | 24 | 233 - CMSM Waterloo | 66176 | Waterloo Region DSB | Breslau-Hopewell Crossing | Breslau-Hopewell Crossing Public Elementary School | ELE | TBD | TBD | TBD | LOXLEIGH LANE / IRONHORSE DR | BRESLAU | TBD | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.493 | -80.4009 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 611 | 4 | 73 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14217239 | 0 | 2335678 | 0 | 0 | 0 | 16552917 | 16552917 | 16552917 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16552917
25-001 | 25-001 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16430 | 8369 | 8369-B02 | 133 GREENBANK RD | NEPEAN | K2H6L3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3336 | -75.7816 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-002 | 25-002 | 25 | N/A | 66184 | Ottawa-Carleton DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16430 | 8369 | 8369-B02 | 133 GREENBANK RD | NEPEAN | K2H6L3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3336 | -75.7816 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 43982084 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44984007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44984007 | 44984007 | 42549639.67 | -2434367.33 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-003 | 25-003 | 25 | N/A | 66184 | Ottawa-Carleton DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 16430 | 8369 | 8369-B02 | 133 GREENBANK RD | NEPEAN | K2H6L3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3336 | -75.7816 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6771846 | Construction Complete | Other | Other | 2011-12 | 40787 | 0 | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 4371846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4371846 | 6771846 | 6771846 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-004 | 25-004 | 25 | N/A | 66184 | Ottawa-Carleton DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 16430 | 8369 | 8369-B02 | 133 GREENBANK RD | NEPEAN | K2H6L3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3336 | -75.7816 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 557880 | Construction Complete | Other | Other | 2012-13 | 41153 | 0 | 0 | 557880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557880 | 557880 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-006 | 25-006 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Adrienne Clarkson | Adrienne Clarkson Public Elementary School | ELE | 10042 | 10373 | 10373-B01 | 170 STONEWAY DR | NEPEAN | K2G6R2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2887 | -75.7165 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9122121 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9122121 | 9122121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9122121 | 9122121 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-011 | 25-011 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Avalon | Avalon Public Elementary School | ELE | 10701 | 11232 | 11232-B01 | 2080 PORTOBELLO BLVD | ORLEANS | K4A0K5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4584 | -75.4661 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 513 | - | - | N | - | Approved | 39691 | 14089673 | Construction Complete | New Construction | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14008484 | 0 | 0 | 0 | 0 | 0 | 14008484 | 14008484 | 14008484 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 14008484
25-017 | 25-017 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Berrigan | Berrigan Public Elementary School | ELE | 10610 | 11235 | 11235-B01 | 199 BERRIGAN DR | NEPEAN | K2J5C6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2802 | -75.7379 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11180864 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9244 | 9244 | 11171620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11171620 | 11180864 | 11180864 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-018 | 25-018 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Berrigan | Berrigan Public Elementary School | ELE | 10610 | 11235 | 11235-B01 | 199 BERRIGAN DR | NEPEAN | K2J5C6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2802 | -75.7379 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5195027 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5195027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5195027 | 5195027 | 5195027 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-022-01 | 25-022 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Broadview Avenue | Broadview Avenue Public Elementary School | ELE | 24564 | 5458 | 5458-B03 | 535 DOVERCOURT AVE | OTTAWA | K2A3W3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3813 | -75.758 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 782 | - | - | N | - | Approved | 42874 | 16127421 | Construction Complete | New Construction | Condition | 2016-17 | 42614 | 0 | 0 | 8383062 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 8733062 | 0 | 0 | 1500000 | 0 | 5894359 | 0 | 0 | 0 | 0 | 0 | 7394359 | 16127421 | 16127421 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5894359
25-022-03 | 25-022 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Broadview Avenue | Broadview Avenue Public Elementary School | ELE | 256 | 5458 | 5458-B01 | 590 BROADVIEW AVE | OTTAWA | K2A2L8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3829 | -75.7582 | 42209 | 2014-15 | 2015-16 | - | - | - | 42209 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42874 | 2607505 | Construction Complete | Demolition | Condition | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607505 | 0 | 0 | 0 | 0 | 0 | 2607505 | 2607505 | 2607505 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2607505
25-023 | 25-023 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Carleton Heights | Carleton Heights Public Elementary School | ELE | 330 | 5504 | 5504-B01 | 1660 PRINCE OF WALES DR | OTTAWA | K2C1P4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3605 | -75.7006 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 100000 | Construction Complete | Retrofit | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70912 | 0 | 0 | 0 | 0 | 0 | 70912 | 70912 | 70912 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 70912
25-025 | 25-025 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Carleton Heights | Carleton Heights Public Elementary School | ELE | 330 | 5504 | 5504-B01 | 1660 PRINCE OF WALES DR | OTTAWA | K2C1P4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3605 | -75.7006 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3083000 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 483000 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3083000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3083000 | 3083000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-030 | 25-030 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Chapman Mills | Chapman Mills Public Elementary School | ELE | 18890 | 19094 | 19094-B01 | 260 LEAMINGTON WAY | NEPEAN | K2J3V1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2695 | -75.7318 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 600 | - | - | N | - | Not Required | - | 12308119 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 730561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730561 | 0 | 0 | 1439776 | 0 | 10137795 | 0 | 0 | 0 | 0 | 0 | 11577571 | 12308132 | 12308132 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10137795
25-037 | 25-037 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Earl of March | Earl of March Public Secondary School | SEC | 5322 | 8191 | 8191-B01 | FRNT-4 PARKWAY (THE) | KANATA | K2K1Y4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3229 | -75.8946 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 552 | - | - | N | - | Approved | 42874 | 14797075 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 1012581 | 0 | 0 | 0 | 1865705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2878286 | 0 | 0 | 1300000 | 0 | 10689718 | 0 | 0 | 0 | 0 | 0 | 11989718 | 14868004 | 14797075 | -70929 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10689718
25-041 | 25-041 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Farley Mowat | Farley Mowat Public Elementary School | ELE | 10700 | 11231 | 11231-B01 | 75 WATERBRIDGE DR | NEPEAN | K2G6T3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2817 | -75.7084 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11051279 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11051279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11051279 | 11051279 | 11051279 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-047 | 25-047 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Greely | Greely Public Elementary School | ELE | 1727 | 6407 | 6407-B01 | 7066 PARKWAY RD | GREELY | K4P1A9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.261 | -75.5637 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1766790 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766790 | 1766790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1766790 | 1766790 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-049 | 25-049 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Half Moon Bay | Half Moon Bay Public Elementary School | ELE | 24467 | 19470 | 19470-B01 | 3525 RIVER RUN AVE | NEPEAN | K2J6E2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2532 | -75.7462 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 674 | - | - | N | - | Approved | 42125 | 14049142 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 1922312 | 0 | 11323301 | 0 | 0 | 0 | 0 | 0 | 13245613 | 13995613 | 13995612 | -1 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11323301
25-051 | 25-051 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Heritage | Heritage Public Elementary School | ELE | 10702 | 6276 | 6276-B01 | 1375 COLONIAL RD | NAVAN | K4B1N1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4216 | -75.4167 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10620520 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180921 | 180921 | 10439599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10439599 | 10620520 | 10620520 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-053 | 25-053 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Huntley Centennial | Huntley Centennial Public Elementary School | ELE | 1132 | 6028 | 6028-B01 | 118 LANGSTAFF DR | CARP | K0A1L0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.346 | -76.0309 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5393894 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393894 | 5393894 | 5393894 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-055 | 25-055 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Jack Donohue | Jack Donohue Public Elementary School | ELE | 10569 | 11173 | 11173-B01 | 101 PENRITH ST | KANATA | K2W1H4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3537 | -75.9417 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9949116 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9949116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9949116 | 9949116 | 9949116 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-056 | 25-056 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Jack Donohue | Jack Donohue Public Elementary School | ELE | 10569 | 11173 | 11173-B01 | 101 PENRITH ST | KANATA | K2W1H4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3537 | -75.9417 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2780606 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780606 | 2780606 | 2780606 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-060 | 25-060 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Kanata Highlands | Kanata Highlands Public Elementary School | ELE | 24466 | 19469 | 19469-B01 | 425 TERRY FOX DR | OTTAWA | K2T0N3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3118 | -75.9315 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 628 | - | - | N | - | Approved | 42874 | 16366341 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 1342093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342093 | 0 | 0 | 1439776 | 0 | 13448337 | 0 | 0 | 0 | 0 | 0 | 14888113 | 16230206 | 16230207 | 1 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13448337
25-061 | 25-061 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Kars on the Rideau | Kars on the Rideau Public Elementary School | ELE | 1239 | 6087 | 6087-B02 | 6680 DORACK DR | KARS | K0A2E0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.1528 | -75.6505 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8668290 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8668290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8668290 | 8668290 | 8668290 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-065 | 25-065 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Vimy Ridge | Vimy Ridge Public Elementary School | ELE | 24546 | 19551 | 19551-B01 | 4180 KELLY FARM DR | GLOUCESTER | K1T4J2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3181 | -75.6042 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 674 | 2 | 39 | N | - | Approved | 42451 | 15333355 | Construction Complete | New Construction | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 1751893 | 0 | 11387032 | 0 | 1018226 | 0 | 0 | 0 | 14157151 | 14907151 | 15000000 | 92849 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12405258
25-066 | 25-066 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Longfields-Davidson Heights | Longfields-Davidson Heights Public Secondary School | SEC | 10996 | 11235 | 11235-B02 | 149 BERRIGAN DR | NEPEAN | K2J5C6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2791 | -75.7411 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 1353 | - | - | N | - | Not Required | - | 39764411 | Construction Complete | New Construction | Other | 2017-18 | 42979 | 0 | 0 | 35633016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941998 | 38575014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38575014 | 38114411 | -460603 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-067 | 25-067 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Longfields-Davidson Heights | Longfields-Davidson Heights Public Secondary School | SEC | 10996 | 11235 | 11235-B02 | 149 BERRIGAN DR | NEPEAN | K2J5C6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2791 | -75.7411 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 704 | - | - | N | - | Approved | 42874 | 14313785 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 265000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265000 | 500000 | 0 | 798958 | 0 | 12749827 | 0 | 0 | 0 | 0 | 0 | 14048785 | 14313785 | 14313785 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12749827
25-074 | 25-074 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Mutchmor | Mutchmor Public Elementary School | ELE | 1598 | 6328 | 6328-B01 | 185 FIFTH AVE | OTTAWA | K1S2N1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4008 | -75.6906 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 242 | - | - | N | - | Not Required | - | 7750000 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 250000 | 0 | 1621821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 3121821 | 0 | 0 | 1919701 | 0 | 2708478 | 0 | 0 | 0 | 0 | 0 | 4628179 | 7750000 | 7750000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2708478
25-087 | 25-087 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Roch Carrier | Roch Carrier Public Elementary School | ELE | 10697 | 11237 | 11237-B01 | 401 STONEHAVEN DR | KANATA | K2M3B5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2839 | -75.8466 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9443028 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195750 | 195750 | 9247278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9247278 | 9443028 | 9443028 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-093 | 25-093 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Sir Winston Churchill | Sir Winston Churchill Public Elementary School | ELE | 2162 | 6440 | 6440-B02 | 49 MULVAGH AVE | NEPEAN | K2E6M7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3541 | -75.7281 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 773760 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 773760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773760 | 773760 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-095 | 25-095 | 25 | N/A | 66184 | Ottawa-Carleton DSB | South March | South March Public Elementary School | ELE | 10997 | 12134 | 12134-B01 | 1032 KLONDIKE RD | KANATA | K2K0H9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3573 | -75.928 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 752 | - | - | N | - | Not Required | - | 13179373 | Construction Complete | New Construction | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13122845 | 0 | 0 | 0 | 0 | 0 | 13122845 | 13122845 | 13122845 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 13122845
25-096 | 25-096 | 25 | N/A | 66184 | Ottawa-Carleton DSB | South March | South March Public Elementary School | ELE | 10997 | 12134 | 12134-B01 | 1032 KLONDIKE RD | KANATA | K2K0H9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3573 | -75.928 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 285 | - | - | N | - | Approved | 42874 | 4658437 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1518581 | 0 | 3139856 | 0 | 0 | 0 | 0 | 0 | 4658437 | 4658437 | 4658437 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3139856
25-098 | 25-098 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Steve MacLean | Steve MacLean Public Elementary School | ELE | 10699 | 11233 | 11233-B01 | 4175 SPRATT RD | GLOUCESTER | K1V1T6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2817 | -75.6857 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12400521 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12400521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12400521 | 12400521 | 12400521 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-099 | 25-099 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Steve MacLean | Steve MacLean Public Elementary School | ELE | 10699 | 11233 | 11233-B01 | 4175 SPRATT RD | GLOUCESTER | K1V1T6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2817 | -75.6857 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3759781 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 2250373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250373 | 0 | 0 | 1509408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509408 | 3759781 | 3759781 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-100 | 25-100 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Stittsville | Stittsville Public Elementary School | ELE | 10698 | 11236 | 11236-B01 | 40 GRANITE RIDGE DR | STITTSVILLE | K2S1Y9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2719 | -75.9085 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11883435 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 48000 | 11835435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11835435 | 11883435 | 11883435 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-103 | 25-103 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Stonecrest | Stonecrest Public Elementary School | ELE | 9537 | 10189 | 10189-B01 | 3791 STONECREST RD | WOODLAWN | K0A3M0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4361 | -76.1154 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2681843 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2681843 | 2681843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2681843 | 2681843 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-104 | 25-104 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Stonecrest | Stonecrest Public Elementary School | ELE | 9537 | 10189 | 10189-B01 | 3791 STONECREST RD | WOODLAWN | K0A3M0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4361 | -76.1154 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4238392 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4238392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4238392 | 4238392 | 4238392 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
25-105 | 25-105 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Summerside | Summerside Public Elementary School | ELE | 24465 | 19468 | 19468-B01 | 2350 PORTOBELLO BLVD | ORLEANS | K4A0W3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4505 | -75.4637 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 674 | - | - | N | - | Approved | 42125 | 14049142 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 1922312 | 0 | 11099102 | 0 | 0 | 0 | 0 | 0 | 13021414 | 13771414 | 13771415 | 1 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11099102
25-111 | 25-111 | 25 | N/A | 66184 | Ottawa-Carleton DSB | West Carleton | West Carleton Public Secondary School | SEC | 5734 | 8422 | 8422-B01 | 3088 DUNROBIN RD | DUNROBIN | K0A1T0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4343 | -76.0351 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 252 | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 0 | 0 | 0 | 0 | 6964749 | 0 | 0 | 0 | 0 | 0 | 6964749 | 7814749 | 7792188 | -22561 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6964749
25-112 | 25-112 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Westwind | Westwind Public Elementary School | ELE | 11334 | 12294 | 12294-B01 | 111 HARTSMERE DR | STITTSVILLE | K2S2G1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2466 | -75.9069 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 628 | - | - | N | - | Not Required | - | 10978108 | Construction Complete | New Construction | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660400 | 660400 | 0 | 0 | 1290314 | 0 | 8724969 | 0 | 0 | 0 | 0 | 0 | 10015283 | 10675683 | 10675683 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 8724969
25-116 | 25-116 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Agincourt Road | Agincourt Road Public Elementary School | ELE | 29 | 5317 | 5317-B01 | 1250 AGINCOURT RD | OTTAWA | K2C2J2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3605 | -75.752 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 230 | - | - | N | - | Approved | 43280 | 5072957 | Construction Complete | Addition | Consolidation | 2018-19 | 43533 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 4697957 | 0 | 0 | 0 | 0 | 0 | 4697957 | 5072957 | 5072957 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4697957
25-117 | 25-117 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Bell | Bell Public Secondary School | SEC | 169 | 5406 | 5406-B01 | 40 CASSIDY RD | NEPEAN | K2H6K1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3265 | -75.8089 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43280 | 8984878 | Construction Complete | Addition | Consolidation | 2018-19 | 43477 | 0 | 5575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5575000 | 0 | 0 | 0 | 0 | 3409878 | 0 | 0 | 0 | 0 | 0 | 3409878 | 8984878 | 8984878 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3409878
25-118 | 25-118 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Briargreen | Briargreen Public Elementary School | ELE | 239 | 5446 | 5446-B01 | 19 PARKFIELD CRES | NEPEAN | K2G0R9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3376 | -75.7771 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43280 | 800000 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 800000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 800000
25-119 | 25-119 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Gloucester | Gloucester Public Secondary School | SEC | 5397 | 8230 | 8230-B01 | 2060 OGILVIE RD | GLOUCESTER | K1J7N8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4387 | -75.5993 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43280 | 2700000 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 0 | 0 | 0 | 0 | 0 | 2700000 | 2700000 | 2700000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2700000
25-120 | 25-120 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Merivale | Merivale Public Secondary School | SEC | 5518 | 8302 | 8302-B01 | 1755 MERIVALE RD | NEPEAN | K2G1E2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3431 | -75.7279 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43280 | 6044878 | Construction Complete | Addition | Consolidation | 2018-19 | 43533 | 0 | 2950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 0 | 0 | 0 | 0 | 3094878 | 0 | 0 | 0 | 0 | 0 | 3094878 | 6044878 | 6044878 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3094878
25-121 | 25-121 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Pinecrest | Pinecrest Public Elementary School | ELE | 1814 | 6461 | 6461-B01 | 1281 MCWATTERS RD | OTTAWA | K2C3E7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3439 | -75.785 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43280 | 500000 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 174033 | -325967 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 500000
25-122 | 25-122 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Sir Robert Borden | Sir Robert Borden Public Secondary School | SEC | 5650 | 8369 | 8369-B01 | 131 GREENBANK RD | NEPEAN | K2H8R1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3336 | -75.7816 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43280 | 4299878 | Construction Complete | Addition | Consolidation | 2018-19 | 43533 | 0 | 2050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050000 | 0 | 0 | 0 | 0 | 2249878 | 0 | 0 | 0 | 0 | 0 | 2249878 | 4299878 | 4299878 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2249878
25-123 | 25-123 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Woodroffe | Woodroffe Public Elementary School | ELE | 2566 | 6942 | 6942-B01 | 235 WOODROFFE AVE | OTTAWA | K2A3V3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3743 | -75.7724 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43280 | 850000 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 850000 | 850000 | 850000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 850000
25-124 | 25-124 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Jockvale | Jockvale Public Elementary School | ELE | 1229 | 6083 | 6083-B01 | 101 MALVERN DR | NEPEAN | K2J2S8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2793 | -75.7597 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Planned | - | 0 | Planned | Retrofit | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259648 | 0 | 0 | 0 | 259648 | 259648 | 259648 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 259648
25-125 | 25-125 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Knoxdale | Knoxdale Public Elementary School | ELE | 1304 | 5929 | 5929-B01 | 170 GREENBANK RD | NEPEAN | K2H5V2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3276 | -75.7811 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44405 | 519295 | Construction Complete | Retrofit | Child Care | 2021-22 | 44446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519296 | 0 | 0 | 0 | 519296 | 519296 | 519296 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 519296
25-126 | 25-126 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Mary Honeywell | Mary Honeywell Public Elementary School | ELE | 1478 | 6249 | 6249-B01 | 54 KENNEVALE DR | NEPEAN | K2J3B2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2688 | -75.7672 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Planned | - | 0 | Planned | Retrofit | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259648 | 0 | 0 | 0 | 259648 | 259648 | 259648 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 259648
25-127 | 25-127 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Queen Mary | Queen Mary Public Elementary School | ELE | 1924 | 6544 | 6544-B01 | 557 QUEEN MARY ST | OTTAWA | K1K1V9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4263 | -75.6423 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259648 | 0 | 0 | 0 | 259648 | 259648 | 0 | -259648 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 259648
25-128 | 25-128 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Heritage | Heritage Public Elementary School | ELE | 10702 | 6276 | 6276-B01 | 1375 COLONIAL RD | NAVAN | K4B1N1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4216 | -75.4167 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 44405 | 259648 | Construction Complete | Retrofit | Child Care | 2021-22 | 44446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259648 | 0 | 0 | 0 | 259648 | 259648 | 259648 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 259648
25-129 | 25-129 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Stittsville | Stittsville Public Secondary School | SEC | 24811 | 19818 | 19818-B01 | 700 COPE DR | STITTSVILLE | K2S2P8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2677 | -75.8905 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 1353 | - | - | N | - | Approved | 44054 | 43049507 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 5000000 | 0 | 1458224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6458224 | 0 | 0 | 0 | 0 | 41591283 | 0 | 0 | 0 | 0 | 0 | 41591283 | 48049507 | 48068969 | 19462 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 41591283
25-130-01 | 25-130 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Elmdale | Elmdale Public Elementary School | ELE | 735 | 5786 | 5786-B01 | 49 IONA ST | OTTAWA | K1Y3L9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3942 | -75.736 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 170 | - | - | N | - | Approved | 43720 | 4726116 | Construction Complete | Addition | Accommodation Pressure | 2021-22 | 44446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726116 | 0 | 0 | 0 | 0 | 0 | 4726116 | 4726116 | 4726116 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4726116
25-130-02 | 25-130 | 25 | N/A | 66184 | Ottawa-Carleton DSB | Elmdale | Elmdale Public Elementary School | ELE | 735 | 5786 | 5786-L01 | 49 IONA ST | OTTAWA | K1Y3L9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3942 | -75.736 | 43720 | 2019-20 | 2019-20 | 43720 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43720 | 197864 | Construction Complete | Land Acquisition | Accommodation Pressure | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197864 | 0 | 0 | 0 | 0 | 0 | 0 | 197864 | 197864 | 197864 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 197864
25-131 | 25-131 | 25 | N/A | 66184 | Ottawa-Carleton DSB | First Avenue | First Avenue Public Elementary School | ELE | 812 | 5830 | 5830-B01 | 73 FIRST AVE | OTTAWA | K1S2G1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4063 | -75.6854 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
25-132 | 25-132 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Fernbank | Fernbank Public Elementary School | ELE | 25383 | 20389 | 20389-B01 | 480 COPE DR | OTTAWA | K2S1B6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2725 | -75.8807 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 628 | 2 | 39 | - | - | Approved | 44439 | 22166509 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 1656400 | 0 | 945551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601951 | 0 | 0 | 0 | 0 | 18264431 | 0 | 1300127 | 0 | 0 | 0 | 19564558 | 22166509 | 22166509 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19564558
25-133 | 25-133 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Half Moon Bay 2 | Half Moon Bay 2 Public Elementary School | ELE | 25385 | 20391 | 20391-B01 | 2535 RIVER MIST RD | OTTAWA | K2J6E6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2395 | -75.7345 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 674 | 2 | 39 | - | - | Approved | 44596 | 24238664 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 1250000 | 0 | 959254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209254 | 0 | 0 | 0 | 0 | 20523305 | 0 | 1506105 | 0 | 0 | 0 | 22029410 | 24238664 | 24238664 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 22029410
25-134 | 25-134 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Riverside South | Riverside South Public Secondary School | SEC | 25407-25408 | 20413 | 20413-B01 | 702 EARL ARMSTRONG RD | OTTAWA | K1H1H7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2715 | -75.6868 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 1516 | 2 | 39 | N | - | Approved | 45043 | 63092503 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45538 | 0 | 0 | 0 | 0 | 2427531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2427531 | 0 | 0 | 0 | 0 | 59072850 | 0 | 1592122 | 0 | 0 | 0 | 60664972 | 63092503 | 63092503 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 60664972
25-135 | 25-135 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | WE Gowling | WE Gowling Public Elementary School | ELE | 2401 | 6843 | 6843-B01 | 250 ANNA AVE | OTTAWA | K1Z7V6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3829 | -75.7312 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | 39 | N | - | Planned | - | - | Planned | Retrofit | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550869 | 0 | 0 | 0 | 550869 | 550869 | 550869 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 550869
25-136 | 25-136 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Findlay Creek 2 | Findlay Creek 2 Public Elementary School | ELE | TBD | TBD | TBD | TBD | GLOUCESTER | K1X0E7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 674 | 2 | 39 | N | - | Approved | 45043 | 25570218 | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 959254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959254 | 0 | 0 | 0 | 0 | 22892445 | 0 | 1718519 | 0 | 0 | 0 | 24610964 | 25570218 | 25570218 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 24610964
25-137 | 25-137 | 25 | 207 - CMSM Ottawa | 66184 | Ottawa-Carleton DSB | Wateridge Village ES | Wateridge Village ES Public Elementary School | ELE | TBD | TBD | TBD | 565 WANAKI ROAD | OTTAWA |  | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | TBD | TBD | [12 empty] | - | - | - | - | - | - | [6 empty] | - | - | Planned | Land Acquisition | Accommodation Pressure |  |  | 0 | 0 | 0 | 0 | 9103410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9103410 | 0 | 0 | 0 | 4689636 |  | 0 | 0 | 0 | 0 | 0 | 4689636 | 13793046 | 13793046 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4689636
26-001 | 26-001 | 26 | N/A | 66192 | Upper Canada DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16790 | 19014 | 19014-B01 | 225 CENTRAL AVE W | BROCKVILLE | K6V5X1 | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.5933 | -75.703 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-002 | 26-002 | 26 | N/A | 66192 | Upper Canada DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16790 | 19014 | 19014-B01 | 225 CENTRAL AVE W | BROCKVILLE | K6V5X1 | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.5933 | -75.703 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 17299697 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17292696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17292696 | 17292696 | 17292696 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-003 | 26-003 | 26 | N/A | 66192 | Upper Canada DSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 16790 | 19014 | 19014-B01 | 225 CENTRAL AVE W | BROCKVILLE | K6V5X1 | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.5933 | -75.703 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 305339 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305339 | 305339 | 305339 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-004 | 26-004 | 26 | N/A | 66192 | Upper Canada DSB | Beckwith | Beckwith Public Elementary School | ELE | 160 | 5400 | 5400-B01 | 1523 9TH LINE RR 2 | CARLETON PLACE | K7C3P2 | 35-12-55-602 | Beckwith | Beckwith Tp | Lanark Co | LANARK | East | South | 45.1125 | -76.0955 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1715293 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1715293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1715293 | 1715293 | 1715293 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-005-01 | 26-005 | 26 | N/A | 66192 | Upper Canada DSB | Bridgewood | Bridgewood Public Elementary School | ELE | 24276 | 19268 | 19268-B01 | 850 NICK KANEB DR | CORNWALL | K6H0G4 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0362 | -74.7064 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 415 | - | - | N | - | Approved | 41976 | 12057772 | Construction Complete | New Construction | Consolidation | 2016-17 | 42619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 978489 | 0 | 11079283 | 0 | 0 | 0 | 0 | 0 | 12057772 | 12057772 | 12057772 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11079283
26-005-02 | 26-005 | 26 | N/A | 66192 | Upper Canada DSB | Bridgewood | Bridgewood Public Elementary School | ELE | 24276 | 19268 | 19268-L01 | 850 NICK KANEB DR | CORNWALL | K6H0G4 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0362 | -74.7064 | 41661 | 2013-14 | 2013-14 | 41661 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41661 | 2173681 | Construction Complete | Land Acquisition | Consolidation | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173681 | 0 | 0 | 0 | 0 | 0 | 0 | 2173681 | 2173681 | 2173681 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2173681
26-007 | 26-007 | 26 | N/A | 66192 | Upper Canada DSB | Cambridge | Cambridge Public Elementary School | ELE | 312 | 5492 | 5492-B01 | 2123 RTE 500 | EMBRUN | K0A1W0 | 35-12-67-614 | The Nation | The Nation M | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2931 | -75.219 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2989131 | Construction Complete | Addition | Other | 2003-04 | 37865 | 324075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324075 | 2665056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2665056 | 2989131 | 2989131 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-009 | 26-009 | 26 | N/A | 66192 | Upper Canada DSB | Central | Central Public Elementary School | ELE | 10704 | 11240 | 11240-B01 | 200 AMELIA ST | CORNWALL | K6H0A5 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0197 | -74.7257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10720677 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 5505497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5505497 | 5215180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5215180 | 10720677 | 10720677 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-015-01 | 26-015 | 26 | N/A | 66192 | Upper Canada DSB | Kemptville | Kemptville Public Elementary School | ELE | 24274 | 19266 | 19266-B01 | 224 LEEDS AND GRENVILLE 44 RD | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0213 | -75.6519 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 438 | - | - | N | - | Approved | 42087 | 9145921 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1896306 | 0 | 1881623 | 0 | 5367992 | 0 | 0 | 0 | 0 | 0 | 9145921 | 9145921 | 9145921 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5367992
26-015-02 | 26-015 | 26 | N/A | 66192 | Upper Canada DSB | Kemptville | Kemptville Public Elementary School | ELE | 24274 | 19266 | 19266-L01 | 224 LEEDS AND GRENVILLE 44 RD | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0213 | -75.6519 | 41597 | 2013-14 | 2013-14 | 41597 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41597 | 4233928 | Construction Complete | Land Acquisition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4233928 | 0 | 0 | 0 | 0 | 0 | 0 | 4233928 | 4233928 | 4233928 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4233928
26-019 | 26-019 | 26 | N/A | 66192 | Upper Canada DSB | Meadowview | Meadowview Public Elementary School | ELE | 10551 | 5312 | 5312-B01 | 9234 ADDISON-GREENBUSH RD | ADDISON | K0E1A0 | 35-12-56-622 | Elizabethtown-Kitley | Elizabethtown-Kitley Tp | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.6664 | -75.8761 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5506544 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 5506544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5506544 | 5506544 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-021 | 26-021 | 26 | N/A | 66192 | Upper Canada DSB | Montague | Montague Public Elementary School | ELE | 10552 | 11164 | 11164-B01 | 1200 ROSEDALE RD S RR 5 | SMITHS FALLS | K7A4S6 | 35-12-55-610 | Montague | Montague Tp | Lanark Co | LANARK | East | South | 44.9426 | -75.9635 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4996055 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 3331534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3331534 | 1664521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1664521 | 4996055 | 4996055 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-022 | 26-022 | 26 | N/A | 66192 | Upper Canada DSB | North Dundas District | North Dundas District Public Secondary School | SEC | 5544 | 10472 | 10472-B01 | 12835 HIGHWAY 43 | CHESTERVILLE | K0C1H0 | 35-12-71-613 | North Dundas | North Dundas Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0917 | -75.2866 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 212290 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 212290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212290 | 212290 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-023 | 26-023 | 26 | N/A | 66192 | Upper Canada DSB | North Grenville District | North Grenville District Public Secondary School | SEC | 11333 | 6706 | 6706-B02 | 2605 CONCESSION RD | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0082 | -75.6468 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 17368128 | Construction Complete | New Construction | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17368128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17368128 | 17368128 | 17368128 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-029 | 26-029 | 26 | N/A | 66192 | Upper Canada DSB | Russell | Russell Public Secondary School | SEC | 10685 | 10172 | 10172-B01 | 982 RUSSEL RD N | RUSSEL | K4R1C8 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2666 | -75.364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 17681031 | Construction Complete | Addition | Other | 2009-10 | 40057 | 6461257 | 0 | 310344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10909430 | 17681031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17681031 | 17681031 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-030 | 26-030 | 26 | N/A | 66192 | Upper Canada DSB | Smiths Falls & District | Smiths Falls & District Public Secondary School | SEC | 10549 | 11162 | 11162-B01 | 299 PERCY ST | SMITHS FALLS | K7A5M2 | 35-12-55-301 | Smiths Falls | Smiths Falls ST | Lanark Co | LANARK | East | South | 44.8853 | -76.0174 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 19278136 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 2333893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333893 | 16944243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16944243 | 19278136 | 19278136 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-032 | 26-032 | 26 | N/A | 66192 | Upper Canada DSB | The Stewart School | The Stewart School Public Elementary School | ELE | 10628 | 8110 | 8110-B01 | 7 SUNSET BLVD | PERTH | K7H0A1 | 35-12-55-403 | Perth | Perth T | Lanark Co | LANARK | East | South | 44.9042 | -76.2577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7748500 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 1888947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1888947 | 5859553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5859553 | 7748500 | 7748500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-033 | 26-033 | 26 | N/A | 66192 | Upper Canada DSB | Thousand Islands | Thousand Islands Public Elementary School | ELE | 10553 | 11165 | 11165-B01 | 101 KING ST W | LANSDOWNE | K0E1L0 | 35-12-56-621 | Leeds and the Thousand Islands | Leeds and the Thousand Islands Tp | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.4052 | -76.0241 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8508051 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 1859533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1859533 | 6648518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6648518 | 8508051 | 8508051 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-035 | 26-035 | 26 | N/A | 66192 | Upper Canada DSB | VanKleek Hill | VanKleek Hill Public Secondary School | SEC | 11196 | 5034 | 5034-B01 | 5814 HWY 34 | VANKLEEK HILL | K0B1R0 | 35-12-67-613 | Champlain | Champlain Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5221 | -74.6519 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15287823 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2348774 | 2348774 | 12939049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12939049 | 15287823 | 15287823 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-036 | 26-036 | 26 | N/A | 66192 | Upper Canada DSB | Viscount Alexander | Viscount Alexander Public Elementary School | ELE | 2392 | 6837 | 6837-B01 | 1401 DOVER RD | CORNWALL | K6J1V6 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0152 | -74.7664 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2646506 | Construction Complete | Addition | Other | 2003-04 | 37865 | 2646506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2646506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2646506 | 2646506 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-042 | 26-042 | 26 | 201 - CMSM Cornwall | 66192 | Upper Canada DSB | Winchester | Winchester Public Elementary School | ELE | 2528 | 6918 | 6918-B01 | 547 LOUISE ST S | WINCHESTER | K0C2K0 | 35-12-71-613 | North Dundas | North Dundas Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0901 | -75.3532 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 44222 | 5394587 | Under Construction | Addition | Child Care | 2022-23 | 44809 | 732622 | 2626618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3359240 | 0 | 0 | 0 | 0 | 0 | 0 | 2035347 | 0 | 0 | 0 | 2035347 | 5394587 | 5394587 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2035347
26-043 | 26-043 | 26 | 236 - CMSM Prescott & Russell | 66192 | Upper Canada DSB | Cambridge | Cambridge Public Elementary School | ELE | 312 | 5492 | 5492-B01 | 2123 RTE 500 | EMBRUN | K0A1W0 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2931 | -75.219 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 16 | Y | - | Approved | 44224 | 1553837 | Under Construction | Addition | Child Care | 2022-23 | 44809 | 0 | 811748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 811748 | 0 | 0 | 0 | 0 | 0 | 0 | 742089 | 0 | 0 | 0 | 742089 | 1553837 | 1553837 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 742089
26-044 | 26-044 | 26 | 201 - CMSM Cornwall | 66192 | Upper Canada DSB | Roxmore | Roxmore Public Elementary School | ELE | 113 | 5368 | 5368-B01 | 16279 FAIRVIEW DR | AVONMORE | K0C1C0 | 35-12-71-617 | North Stormont | North Stormont Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.1702 | -74.9728 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 114 | 1 | 15 | Y | - | Approved | 43621 | 3823090 | Construction Complete | Addition | Consolidation | 2021-22 | 44444 | 0 | 406705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406705 | 0 | 0 | 0 | 0 | 2850022 | 0 | 566363 | 0 | 0 | 0 | 3416385 | 3823090 | 3823090 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3416385
26-045-01 | 26-045 | 26 | 235 - CMSM Leeds & Grenville | 66192 | Upper Canada DSB | Brockville South | Brockville Public Elementary School | ELE | 24667 | 19674 | 19674-B01 | 556 KING ST W | BROCKVILLE | TBD | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.5768 | -75.7038 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 43090 | 2017-18 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | 500 | 4 | 64 | Y | 3 | Approved | 44811 | 28172314 | Under Construction | New Construction | Consolidation | 2024-25 | 45536 | 239223 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1739223 | 0 | 0 | 1119840 | 0 | 19443512 | 0 | 4357227 | 1512511 | 0 | 0 | 26433090 | 28172313 | 28172313 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 25313250
26-045-02 | 26-045 | 26 | N/A | 66192 | Upper Canada DSB | Brockville South | Brockville Public Elementary School | ELE | 24667 | 19674 | 19674-L01 | 556 KING ST W | BROCKVILLE | TBD | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.5768 | -75.7038 | 43433 | 2018-19 | 2018-19 | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43433 | 1625667 | Construction Complete | Land Acquisition | Consolidation | 2020-21 | 44286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625667 | 0 | 0 | 0 | 0 | 0 | 0 | 1625667 | 1625667 | 1625667 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1625667
26-046 | 26-046 | 26 | N/A | 66192 | Upper Canada DSB | New Cornwall | New Cornwall Public Secondary School | SEC | 24671-24672 | 19678 | 19678-B01 | TBD | CORNWALL | TBD | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | TBD | TBD | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 1400 | - | - | N | - | Planned | - | 0 | Planned | New Construction | Consolidation | 2024-25 | 45658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39062944 | 0 | 0 | 0 | 0 | 0 | 39062944 | 39062944 | 39062944 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 39062944
26-048 | 26-048 | 26 | 201 - CMSM Cornwall | 66192 | Upper Canada DSB | Nationview | Nationview Public Elementary School | ELE | 1604 | 6333 | 6333-B01 | 3045 COUNTY RD 1 | SOUTH MOUNTAIN | K0E1W0 | 35-12-71-613 | North Dundas | North Dundas Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 44.9852 | -75.4541 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 34 | Y | - | Approved | 43257 | 524338 | Construction Complete | Retrofit | Child Care | 2018-19 | 43405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365666 | 0 | 0 | 0 | 365666 | 365666 | 365666 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 365666
26-049 | 26-049 | 26 | 236 - CMSM Prescott & Russell | 66192 | Upper Canada DSB | Rockland | Rockland Public Elementary School | ELE | 2018 | 6601 | 6601-B01 | 999 GIROUX ST | ROCKLAND | K4K1C2 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5457 | -75.2867 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43250 | 786506 | Construction Complete | Retrofit | Child Care | 2019-20 | 43819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675725 | 0 | 0 | 0 | 675725 | 675725 | 675725 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 675725
26-050 | 26-050 | 26 | 236 - CMSM Prescott & Russell | 66192 | Upper Canada DSB | Russell | Russell Public Elementary School | ELE | 2062 | 6630 | 6630-B01 | 14 MILL ST | RUSSEL | K4R1A6 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2571 | -75.3629 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43250 | 492030 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 229861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229861 | 0 | 0 | 0 | 0 | 0 | 0 | 262169 | 0 | 0 | 0 | 262169 | 492030 | 492030 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 262169
26-051 | 26-051 | 26 | 235 - CMSM Leeds & Grenville | 66192 | Upper Canada DSB | Kemptville | Kemptville Public Elementary School | ELE | 24274 | 19266 | 19266-B01 | 224 LEEDS AND GRENVILLE 44 RD | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0213 | -75.6519 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | - | 3 | 49 | Y | 2 | Approved | 44187 | 3262558 | Under Construction | Addition | Child Care | 2022-23 | 44809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000427 | 1262131 | 0 | 0 | 3262558 | 3262558 | 3262558 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3262558
26-053 | 26-053 | 26 | N/A | 66192 | Upper Canada DSB | North Grenville District | North Grenville District Public Secondary School | SEC | 11333 | 6706 | 6706-B02 | 2605 CONCESSION RD | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0082 | -75.6468 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 221 | - | - | N | - | Approved | 43809 | 7273701 | Construction Complete | Addition | Consolidation | 2021-22 | 44444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7273701 | 0 | 0 | 0 | 0 | 0 | 7273701 | 7273701 | 7273701 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7273701
26-054 | 26-054 | 26 | N/A | 66192 | Upper Canada DSB | TR Léger | TR Léger Public Secondary Alternative School | SEC-ALT | 24903 | 7188 | 7188-B01 | 600 MCCONNELL AVE | CORNWALL | K6H4M1 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0254 | -74.7139 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43213 | 480000 | Construction Complete | Purchase | Consolidation | 2018-19 | 43344 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | 480000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
26-055 | 26-055 | 26 | 235 - CMSM Leeds & Grenville | 66192 | Upper Canada DSB | Westminster | Westminster Public Elementary School | ELE | 2471 | 6889 | 6889-B01 | 29 CENTRAL AVE W | BROCKVILLE | K6V4N6 | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.5989 | -75.6954 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | 2 | 25 | - | - | Approved | 44769 | 10605195 | Under Construction | Addition | Condition | 2023-24 | 45174 | 803402 | 4457065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5260467 | 0 | 0 | 0 | 0 | 4513448 | 0 | 831280 | 0 | 0 | 0 | 5344728 | 10605195 | 10605195 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5344728
26-056 | 26-056 | 26 | N/A | 66192 | Upper Canada DSB | Williamstown | Williamstown Public Elementary School | ELE | 2512 | 6908 | 6908-B01 | 19754 COUNTY RD 17 | WILLIAMSTOWN | K0C2J0 | 35-12-71-616 | South Glengarry | South Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.1346 | -74.5509 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 121 | - | - | - | - | Approved | 44547 | 6632838 | Under Construction | Addition | Accommodation Pressure | 2023-24 | 45170 | 974660 | 1938770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2913430 | 0 | 0 | 402645 | 0 | 3316763 | 0 | 0 | 0 | 0 | 0 | 3719408 | 6632838 | 6632838 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3316763
27-001 | 27-001 | 27 | N/A | 66206 | Limestone DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18278 | 19055 | 19055-B01 | 220 PORTSMOUTH AVE | KINGSTON | K7L4X4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2281 | -76.5271 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-002 | 27-002 | 27 | N/A | 66206 | Limestone DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18278 | 19055 | 19055-B01 | 220 PORTSMOUTH AVE | KINGSTON | K7L4X4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2281 | -76.5271 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15968520 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15968520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15968520 | 15968520 | 15968520 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-004 | 27-004 | 27 | N/A | 66206 | Limestone DSB | Bath | Bath Public Elementary School | ELE | 132 | 5380 | 5380-B01 | 247 CHURCH ST | BATH | K0H1G0 | 35-12-57-612 | Loyalist | Loyalist Tp | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.1867 | -76.7796 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2380524 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 2160992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160992 | 0 | 0 | 219532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219532 | 2380524 | 2380524 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-005 | 27-005 | 27 | N/A | 66206 | Limestone DSB | Bayridge | Bayridge Public Secondary School | SEC | 5224 | 8129 | 8129-B01 | 1059 TAYLOR-KIDD BLVD | KINGSTON | K7M6J9 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2511 | -76.5957 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5182859 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5182859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5182859 | 5182859 | 5182859 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-009 | 27-009 | 27 | N/A | 66206 | Limestone DSB | Centennial | Centennial Public Elementary School | ELE | 356 | 5522 | 5522-B01 | 120 NORMAN ROGERS DR | KINGSTON | K7M2R2 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2318 | -76.5196 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21723 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21723 | 21723 | 21723 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-010 | 27-010 | 27 | N/A | 66206 | Limestone DSB | École Sir John A Macdonald | École Sir John A Macdonald Public Elementary School | ELE | 20024 | 19121 | 19121-B01 | 529 ST MARTHA ST | KINGSTON | K7K7C2 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2665 | -76.4469 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 17335799 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 51364 | 0 | 490937 | 1821994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364295 | 14971504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14971504 | 17335799 | 17335799 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-012 | 27-012 | 27 | N/A | 66206 | Limestone DSB | Frontenac | Frontenac Public Secondary School | SEC | 5373 | 5080 | 5080-B01 | 1789 BATH RD | KINGSTON | K7M4Y3 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2371 | -76.5768 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6187737 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6187737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6187737 | 6187737 | 6187737 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-013 | 27-013 | 27 | N/A | 66206 | Limestone DSB | Granite Ridge | Granite Ridge Public Elementary and Secondary School | ELE/SEC | 24231 | 6663 | 6663-B02 | 14432 HWY 38 | SHARBOT LAKE | K0H2P0 | 35-12-46-616 | Central Frontenac | Central Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 44.7844 | -76.6794 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 21084386 | Construction Complete | New Construction | Consolidation | 2013-14 | 41518 | 0 | 0 | 561268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561268 | 20084053 | 0 | 439065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20523118 | 21084386 | 21084386 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-015 | 27-015 | 27 | N/A | 66206 | Limestone DSB | James R Henderson | James R Henderson Public Elementary School | ELE | 1182 | 6056 | 6056-B01 | 361 ROOSEVELT DR | KINGSTON | K7M4A8 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2291 | -76.5754 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1342218 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342218 | 1342218 | 1342218 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-017 | 27-017 | 27 | N/A | 66206 | Limestone DSB | JE Horton | JE Horton Public Elementary School | ELE | 1822 | 5202 | 5202-B01 | 411 WELLINGTON ST | KINGSTON | K7K5R5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.242 | -76.461 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 78478 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78478 | 78478 | 78478 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-019-01 | 27-019 | 27 | N/A | 66206 | Limestone DSB | Kingston Central / Module Vanier | Kingston Central / Module Vanier Public Secondary School | SEC | 24452-25170 | 8348 | 8348-B03 | 145 KIRKPATRICK ST | KINGSTON | K7K2P4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2545 | -76.5015 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 1341 | - | - | N | - | Approved | 44540 | 45861880 | Construction Complete | New Construction | Consolidation | 2019-20 | 43891 | 0 | 0 | 7524972 | 937245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8462217 | 0 | 0 | 0 | 0 | 37399663 | 0 | 0 | 0 | 0 | 0 | 37399663 | 45861880 | 45861880 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 37399663
27-019-02 | 27-019 | 27 | N/A | 66206 | Limestone DSB | Kingston Central / Module Vanier | Kingston Central / Module Vanier Public Secondary School | SEC | 24452-25170 | 8348 | 8348-L03 | 145 KIRKPATRICK ST | KINGSTON | K7K2P4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2545 | -76.5015 | 42422 | 2015-16 | 2015-16 | 42422 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44540 | 3948373 | Construction Complete | Land Acquisition | Consolidation | 2020-21 | 44179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3948373 | 0 | 0 | 0 | 0 | 0 | 0 | 3948373 | 3948373 | 3948373 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3948373
27-019-03 | 27-019 | 27 | N/A | 66206 | Limestone DSB | Queen Elizabeth | Queen Elizabeth Public Secondary School | SEC | 5601 | 8348 | 8348-B01 | 145 KIRKPATRICK ST | KINGSTON | K7K2P4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2535 | -76.5021 | 42534 | 2015-16 | 2016-17 | - | - | - | 42534 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Demolition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2130000 | 0 | 0 | 0 | 0 | 0 | 2130000 | 2130000 | 2130000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2130000
27-021 | 27-021 | 27 | N/A | 66206 | Limestone DSB | Lord Strathcona | Lord Strathcona Public Elementary School | ELE | 1391 | 6187 | 6187-B01 | 251 MCMAHON AVE | KINGSTON | K7M3H4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2503 | -76.5226 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 364381 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364381 | 364381 | 364381 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-023 | 27-023 | 27 | N/A | 66206 | Limestone DSB | Loughborough | Loughborough Public Elementary School | ELE | 1396 | 6190 | 6190-B01 | 4330 WEATHLEY ST | SYDENHAM | K0H2T0 | 35-12-46-619 | South Frontenac | South Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 44.4079 | -76.5938 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 25744 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25744 | 25744 | 25744 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-025 | 27-025 | 27 | N/A | 66206 | Limestone DSB | Marysville | Marysville Public Elementary School | ELE | 2548 | 6931 | 6931-B01 | 53 VICTORIA ST | WOLFE ISLAND | K0H2Y0 | 35-12-46-617 | Frontenac Islands | Frontenac Islands Tp | Frontenac Co | FRONTENAC | East | South | 44.1926 | -76.4382 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 98053 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98053 | 98053 | 98053 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-026-01 | 27-026 | 27 | N/A | 66206 | Limestone DSB | Molly Brant | Molly Brant Public Elementary School | ELE | 24451 | 8348 | 8348-B02 | 30 LYONS ST | KINGSTON | K7K0J5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2545 | -76.4994 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 459 | - | - | N | - | Approved | 42167 | 11057165 | Construction Complete | New Construction | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776101 | 776101 | 0 | 0 | 1496321 | 0 | 8799160 | 0 | 0 | 0 | 0 | 0 | 10295481 | 11071582 | 11071582 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8799160
27-026-02 | 27-026 | 27 | N/A | 66206 | Limestone DSB | Molly Brant | Molly Brant Public Elementary School | ELE | 24451 | 8348 | 8348-L02 | 30 LYONS ST | KINGSTON | K7K0J5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2545 | -76.4994 | 42135 | 2014-15 | 2015-16 | 42135 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42135 | 561243 | Construction Complete | Land Acquisition | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561243 | 0 | 0 | 0 | 0 | 0 | 0 | 561243 | 561243 | 561243 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 561243
27-030 | 27-030 | 27 | N/A | 66206 | Limestone DSB | Rideau | Rideau Public Elementary School | ELE | 1979 | 6573 | 6573-B01 | 9 DUNDAS ST | KINGSTON | K7L1N2 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2354 | -76.5048 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 138379 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138379 | 138379 | 138379 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-032 | 27-032 | 27 | N/A | 66206 | Limestone DSB | Southview | Southview Public Elementary School | ELE | 20025 | 19122 | 19122-B01 | 18 GOLF COURSE LANE RR 1 | NAPANEE | K7R3K6 | 35-12-57-402 | Greater Napanee | Greater Napanee T | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.238 | -76.937 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 16478590 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 347722 | 991263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338985 | 15139605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15139605 | 16478590 | 16478590 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-034 | 27-034 | 27 | N/A | 66206 | Limestone DSB | Sydenham | Sydenham Public Secondary School | SEC | 5690 | 8392 | 8392-B01 | 2860 RUTLEDGE RD | SYDENHAM | K0H2T0 | 35-12-46-619 | South Frontenac | South Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 44.4075 | -76.5951 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 304548 | Construction Complete | Retrofit | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397 | 397 | 304151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304151 | 304548 | 304548 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-035 | 27-035 | 27 | N/A | 66206 | Limestone DSB | Sydenham | Sydenham Public Secondary School | SEC | 5690 | 8392 | 8392-B01 | 2860 RUTLEDGE RD | SYDENHAM | K0H2T0 | 35-12-46-619 | South Frontenac | South Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 44.4075 | -76.5951 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5580287 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580287 | 5580287 | 5580287 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-036 | 27-036 | 27 | N/A | 66206 | Limestone DSB | Tamworth | Tamworth Public Elementary School | ELE | 2277 | 6758 | 6758-B01 | 6668 WHEELER ST RR 2 | TAMWORTH | K0K3G0 | 35-12-57-613 | Stone Mills | Stone Mills Tp | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.4849 | -76.9909 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 95766 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95766 | 95766 | 95766 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-038 | 27-038 | 27 | N/A | 66206 | Limestone DSB | Truedell | Truedell Public Elementary School | ELE | 2332 | 6794 | 6794-B01 | 641 TRUEDELL RD | KINGSTON | K7M6W6 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.244 | -76.5794 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 22901 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22901 | 22901 | 22901 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-040 | 27-040 | 27 | N/A | 66206 | Limestone DSB | Welborne Avenue | Welborne Avenue Public Elementary School | ELE | 2438 | 6871 | 6871-B01 | 190 WELBORNE AVE | KINGSTON | K7M4G3 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2224 | -76.5794 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9031 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9031 | 9031 | 9031 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-043 | 27-043 | 27 | N/A | 66206 | Limestone DSB | WJ Holsgrove | WJ Holsgrove Public Elementary School | ELE | 1103 | 6013 | 6013-B01 | 1414 SPROULE ST | KINGSTON | K7P2V3 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2685 | -76.6209 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 83073 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83073 | 83073 | 83073 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
27-046 | 27-046 | 27 | 220 - CMSM Lennox & Addington | 66206 | Limestone DSB | North Addington Education Centre | North Addington Education Centre Public Elementary School | ELE | 1642 | 6360 | 6360-B01 | 14196 HWY 41 | CLOYNE | K0H1K0 | 35-12-57-611 | Addington Highlands | Addington Highlands Tp | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.8161 | -77.1856 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 41 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2018-19 | 43435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945319 | 0 | 0 | 0 | 945319 | 945319 | 945319 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 945319
27-047 | 27-047 | 27 | 220 - CMSM Lennox & Addington | 66206 | Limestone DSB | The Prince Charles | The Prince Charles Public Elementary School | ELE | 2298 | 6773 | 6773-B02 | 75 GRAHAM ST W | NAPANEE | K7R2J9 | 35-12-57-402 | Greater Napanee | Greater Napanee T | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.2497 | -76.9572 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 16 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264690 | 0 | 0 | 0 | 264690 | 264690 | 264690 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 264690
28-001 | 28-001 | 28 | N/A | 66214 | Renfrew County DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18277 | 19054 | 19054-B01 | 1270 PEMBROKE ST W | PEMBROKE | K8A4G4 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8327 | -77.149 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-002 | 28-002 | 28 | N/A | 66214 | Renfrew County DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18277 | 19054 | 19054-B01 | 1270 PEMBROKE ST W | PEMBROKE | K8A4G4 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8327 | -77.149 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1384889 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1832915 | 1832915 | 1384889 | -448026 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-003 | 28-003 | 28 | N/A | 66214 | Renfrew County DSB | AJ Charbonneau | AJ Charbonneau Public Elementary School | ELE | 9618 | 10204 | 10204-B01 | 225 BASKIN DR W | ARNPRIOR | K7S0E3 | 35-12-69-401 | Arnprior | Arnprior T | Renfrew Co | RENFREW | East | South | 45.4294 | -76.3738 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 880745 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 580745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580745 | 880745 | 880745 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-006 | 28-006 | 28 | N/A | 66214 | Renfrew County DSB | Eganville | Eganville Public Elementary School | ELE | 9445 | 10170 | 10170-B01 | 259 JANE ST | EGANVILLE | K0J1T0 | 35-12-69-635 | Bonnechere Valley | Bonnechere Valley Tp | Renfrew Co | RENFREW | East | South | 45.5428 | -77.1102 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1403483 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1403483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1403483 | 1403483 | 1403483 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-007 | 28-007 | 28 | N/A | 66214 | Renfrew County DSB | General Lake | General Lake Facility Holding | HFA | 877 | 5871 | 5871-B01 | 1900 BORDEN AVE | PETAWAWA | K8H2T6 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8988 | -77.2594 | 42524 | 2015-16 | 2016-17 | - | - | - | 42524 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 320363 | Construction Complete | Demolition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319863 | 0 | 0 | 0 | 0 | 0 | 319863 | 319863 | 287770 | -32093 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 319863
28-008 | 28-008 | 28 | N/A | 66214 | Renfrew County DSB | General Panet | General Panet Public Secondary School | SEC | 5380 | 8219 | 8219-B01 | 14 YPRES BLVD | PETAWAWA | K8H1C6 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.9125 | -77.2774 | 42102 | 2014-15 | 2015-16 | - | - | - | 42102 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 613442 | Construction Complete | Demolition | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613442 | 0 | 0 | 0 | 0 | 0 | 613442 | 613442 | 613442 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 613442
28-009 | 28-009 | 28 | N/A | 66214 | Renfrew County DSB | Herman Street | Herman Street Public Elementary School | ELE | 1054 | 5987 | 5987-B01 | 15 HERMAN ST | PETAWAWA | K8H1W1 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8919 | -77.2737 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 452657 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452657 | 452657 | 452657 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-010 | 28-010 | 28 | N/A | 66214 | Renfrew County DSB | MacKenzie Community | MacKenzie Community Public Elementary School | ELE | 10766 | 5220 | 5220-B01 | 87 BROCKHOUSE WAY | DEEP RIVER | K0J1P0 | 35-12-69-402 | Deep River | Deep River T | Renfrew Co | RENFREW | East | South | 46.106 | -77.4884 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8106556 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 762392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631141 | 1393533 | 0 | 1836435 | 0 | 0 | 0 | 4876588 | 0 | 0 | 0 | 0 | 6713023 | 8106556 | 8106556 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-011 | 28-011 | 28 | N/A | 66214 | Renfrew County DSB | Madawaska Valley District | Madawaska Valley District Public Secondary School | SEC | 5502 | 8292 | 8292-B01 | 341 JOHN ST | BARRYS BAY | K0J1B0 | 35-12-69-634 | Madawaska Valley | Madawaska Valley Tp | Renfrew Co | RENFREW | East | South | 45.481 | -77.6732 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42162 | 6709865 | Construction Complete | Retrofit | Consolidation | 2016-17 | 42739 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000 | 0 | 0 | 271372 | 0 | 2838493 | 0 | 0 | 0 | 0 | 0 | 3109865 | 6709865 | 6709865 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2838493
28-012 | 28-012 | 28 | N/A | 66214 | Renfrew County DSB | Pinecrest | Pinecrest Facility Holding | HFA | 1812 | 6460 | 6460-B01 | 43 YPRES BLVD | PETAWAWA | K8H1E5 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.9084 | -77.2729 | 42524 | 2015-16 | 2016-17 | - | - | - | 42524 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 319863 | Construction Complete | Demolition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319863 | 0 | 0 | 0 | 0 | 0 | 319863 | 319863 | 319363 | -500 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 319863
28-013 | 28-013 | 28 | N/A | 66214 | Renfrew County DSB | Queen Elizabeth | Queen Elizabeth Public Elementary School | ELE | 1908 | 6530 | 6530-B01 | 100 VETERANS MEMORIAL DR | RENFREW | K7V2R6 | 35-12-69-404 | Renfrew | Renfrew T | Renfrew Co | RENFREW | East | South | 45.4699 | -76.6766 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 850753 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850753 | 850753 | 850753 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-016 | 28-016 | 28 | N/A | 66214 | Renfrew County DSB | Valour | Valour Public Elementary and Secondary School | ELE/SEC | 24318 | 12305 | 12305-B01 | 19 LEEDER LANE | PETAWAWA | K8H0B8 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8951 | -77.257 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 32623133 | Construction Complete | New Construction | Consolidation | 2015-16 | 42248 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 31223133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31223133 | 32623133 | 32623133 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-017 | 28-017 | 28 | N/A | 66214 | Renfrew County DSB | Westmeath | Westmeath Facility Holding | HFA | 2468 | 6887 | 6887-B01 | 502 GRAHAM ST | WESTMEATH | K0J2L0 | 35-12-69-636 | Whitewater Region | Whitewater Region Tp | Renfrew Co | RENFREW | East | South | 45.8151 | -76.8865 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 538424 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538424 | 538424 | 538424 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
28-018 | 28-018 | 28 | 223 - CMSM Renfrew | 66214 | Renfrew County DSB | Herman Street | Herman Street Public Elementary School | ELE | 1054 | 5987 | 5987-B01 | 15 HERMAN ST | PETAWAWA | K8H1W1 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8919 | -77.2737 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44036 | 2772938 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2772938 | 0 | 0 | 0 | 2772938 | 2772938 | 2772938 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2772938
29-001 | 29-001 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15768 | 18085 | 18085-B01 | 156 ANN ST | BELLEVILLE | K8N3L3 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1628 | -77.3754 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
29-002 | 29-002 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15768 | 18085 | 18085-B01 | 156 ANN ST | BELLEVILLE | K8N3L3 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1628 | -77.3754 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7062799 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5394199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5394199 | 5394199 | 7062799 | 1668600 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
29-003 | 29-003 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Athol-South Marysburgh | Athol-South Marysburgh Public Elementary School | ELE | 108 | 5363 | 5363-B01 | 1764 COUNTY RD 10 RR 1 | CHERRY VALLEY | K0K1P0 | 35-12-68-000 | Prince Edward | Prince Edward Co | Prince Edward Co | PRINCE EDWARD | East | South | 43.9343 | -77.1522 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1613211 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303227 | 303227 | 0 | 0 | 303529 | 0 | 0 | 1006455 | 0 | 0 | 0 | 0 | 1309984 | 1613211 | 1613211 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
29-009 | 29-009 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Harmony | Harmony Public Elementary School | ELE | 24319 | 19311 | 19311-B01 | 626 HARMONY RD | CORBYVILLE | K0K1V0 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.2404 | -77.3846 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 591 | - | - | N | - | Approved | 42482 | 13860259 | Construction Complete | New Construction | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592269 | 0 | 1701693 | 0 | 11566297 | 0 | 0 | 0 | 0 | 0 | 13860259 | 13860259 | 13860259 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11566297
29-010 | 29-010 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Harry J Clark | Harry J Clark Public Elementary School | ELE | 1028 | 5972 | 5972-B01 | 77 ROLLINS DR | BELLEVILLE | K8N4J6 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1748 | -77.3568 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 150 | - | - | N | - | Not Required | - | 2312258 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552686 | 0 | 759572 | 0 | 0 | 0 | 0 | 0 | 2312258 | 2312258 | 2312258 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 759572
29-013 | 29-013 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Marmora | Marmora Public Elementary School | ELE | 1471 | 6242 | 6242-B01 | 91 MADOC ST | MARMORA | K0K2M0 | 35-12-51-626 | Marmora and Lake | Marmora and Lake M | Hastings Co | HASTINGS | East | South | 44.4883 | -77.6723 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 133 | - | - | N | - | Approved | 42803 | 5441393 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 0 | 1711393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711393 | 0 | 0 | 526295 | 0 | 3203705 | 0 | 0 | 0 | 0 | 0 | 3730000 | 5441393 | 5441393 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3203705
29-016 | 29-016 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Prince Charles | Prince Charles Public Elementary School | ELE | 1861 | 6496 | 6496-B01 | 138 DUFFERIN AVE | TRENTON | K8V5E1 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.0924 | -77.5807 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1821555 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750888 | 0 | 1070667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821555 | 1821555 | 1821555 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
29-017 | 29-017 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Prince Charles | Prince Charles Public Elementary School | ELE | 1863 | 6498 | 6498-B01 | 75 RITCHIE AVE | BELLEVILLE | K8P3W2 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1646 | -77.3958 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7206574 | Construction Complete | Addition | Other | 2011-12 | 40787 | 1866971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866971 | 4674285 | 0 | 665318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5339603 | 7206574 | 7206574 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
29-019-01 | 29-019 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Trent River | Trent River Public Elementary School | ELE | 24565 | 19571 | 19571-B01 | 84 DIXON DR | TRENTON | K8V0H1 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.1094 | -77.5747 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 562 | - | - | N | - | Approved | 42727 | 12133226 | Construction Complete | New Construction | Consolidation | 2016-17 | 42795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997127 | 0 | 11136099 | 0 | 0 | 0 | 0 | 0 | 12133226 | 12133226 | 12133226 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11136099
29-019-02 | 29-019 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Trent River | Trent River Public Elementary School | ELE | 24565 | 19571 | 19571-L01 | 84 DIXON DR | TRENTON | K8V0H1 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.1094 | -77.5747 | 41330 | 2012-13 | 2012-13 | 41330 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43705 | 1231983 | Construction Complete | Land Acquisition | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231983 | 0 | 0 | 0 | 0 | 0 | 0 | 1231983 | 1231983 | 1231983 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1231983
29-020 | 29-020 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Sir John A Macdonald | Sir John A Macdonald Public Elementary School | ELE | 2154 | 6682 | 6682-B02 | 22 HARDER DR | BELLEVILLE | K8P1H2 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1558 | -77.4092 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3426111 | Construction Complete | Addition | Other | 2011-12 | 40787 | 82860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82860 | 3343251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3343251 | 3426111 | 3426111 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
29-023 | 29-023 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Stirling Senior | Stirling Senior Public Elementary School | ELE | 24245 | 6738 | 6738-B02 | 107 ST JAMES ST | STIRLING | K0K3E0 | 35-12-51-622 | Stirling-Rawdon | Stirling-Rawdon Tp | Hastings Co | HASTINGS | East | South | 44.2937 | -77.5521 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 600 | - | - | N | - | Not Required | - | 13240907 | Construction Complete | New Construction | Condition | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110753 | 110753 | 500000 | 0 | 997127 | 0 | 11633027 | 0 | 0 | 0 | 0 | 0 | 13130154 | 13240907 | 13240907 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11633027
29-024 | 29-024 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Tweed | Tweed Public Elementary School | ELE | 24247 | 6796 | 6796-B02 | 52 MCCLELLAN ST | TWEED | K0K3J0 | 35-12-51-623 | Tweed | Tweed M | Hastings Co | HASTINGS | East | South | 44.4751 | -77.3185 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 350 | - | - | N | - | Not Required | - | 8442819 | Construction Complete | New Construction | Condition | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958122 | 0 | 7484697 | 0 | 0 | 0 | 0 | 0 | 8442819 | 8442819 | 8442819 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7484697
29-027 | 29-027 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | York River | York River Public Elementary School | ELE | 1654 | 6367 | 6367-B01 | 132 NEWKIRK BLVD | BANCROFT | K0L1C0 | 35-12-51-403 | Bancroft | Bancroft T | Hastings Co | HASTINGS | East | South | 45.0541 | -77.8449 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4671556 | Construction Complete | Addition | Other | 2011-12 | 40787 | 403579 | 0 | 0 | 0 | 0 | 326400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729979 | 0 | 0 | 1979741 | 0 | 0 | 1961836 | 0 | 0 | 0 | 0 | 3941577 | 4671556 | 4671556 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
29-028 | 29-028 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Athol | Athol Facility Holding | HFA | 5804 | 5363 | 5363-B02 | 1764 COUNTY RD 10 RR 1 | CHERRY VALLEY | K0K1P0 | 35-12-68-000 | Prince Edward | Prince Edward Co | Prince Edward Co | PRINCE EDWARD | East | South | 43.9342 | -77.1529 | 42844 | 2016-17 | 2017-18 | - | - | - | 42844 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42844 | 93321 | Construction Complete | Demolition | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93321 | 0 | 0 | 0 | 0 | 0 | 93321 | 93321 | 93321 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 93321
29-029 | 29-029 | 29 | 216 - CMSM Hastings | 66222 | Hastings and Prince Edward DSB | Easthill | Easthill Public Elementary School | ELE | 24840 | 6536 | 6536-B02 | 135 MACDONALD AVE | BELLEVILLE | K8N3Y4 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1654 | -77.3644 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 472 | 3 | 49 | Y | - | Approved | 45054 | 17694690 | Under Construction | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 621081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621081 | 0 | 0 | 1215800 | 0 | 14277112 | 0 | 1580697 | 0 | 0 | 0 | 17073609 | 17694690 | 17694690 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15857809
29-030 | 29-030 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Eastside | Eastside Public Secondary School | SEC | 6353 | 8688 | 8688-B01 | 275 FARLEY AVE | BELLEVILLE | K8N4M2 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1754 | -77.352 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 189 | - | - | N | - | Planned | - | 0 | Planned | Addition | Consolidation | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7890201 | 0 | 0 | 0 | 0 | 0 | 7890201 | 7890201 | 7890201 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7890201
29-031 | 29-031 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Centre Hastings | Centre Hastings Public Elementary and Secondary School | ELE/SEC | 5276 | 6206 | 6206-B01 | 129 ELGIN ST | MADOC | K0K2K0 | 35-12-51-610 | Madoc | Madoc Tp | Hastings Co | HASTINGS | East | South | 44.505 | -77.468 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 52 | - | - | N | - | Approved | 43922 | 3126788 | Construction Complete | Addition | Consolidation | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3126788 | 0 | 0 | 0 | 0 | 0 | 3126788 | 3126788 | 3126788 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3126788
29-032 | 29-032 | 29 | N/A | 66222 | Hastings and Prince Edward DSB | Madoc | Madoc Public Elementary School | ELE | 1419 | 6206 | 6206-B02 | 32 BALDWIN ST | MADOC | K0K2K0 | 35-12-51-610 | Madoc | Madoc Tp | Hastings Co | HASTINGS | East | South | 44.504 | -77.4706 | 43922 | 2019-20 | 2020-21 | - | - | - | 43922 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43922 | 2724390 | Construction Complete | Demolition | Consolidation | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2724390 | 0 | 0 | 0 | 0 | 0 | 2724390 | 2724390 | 2724390 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2724390
30.1-001 | 30.1-001 | 30.1 | N/A | 29009 | Northeastern CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 7707 | 8844 | 8844-B01 | 101 SPRUCE ST N | TIMMINS | P4N6M9 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4783 | -81.3272 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-002 | 30.1-002 | 30.1 | N/A | 29009 | Northeastern CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 7707 | 8844 | 8844-B01 | 101 SPRUCE ST N | TIMMINS | P4N6M9 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4783 | -81.3272 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 62687 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126923 | 126923 | 62687 | -64236 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-003 | 30.1-003 | 30.1 | N/A | 29009 | Northeastern CDSB | ACCESS | ACCESS Catholic Secondary School | SEC | 24097 | 6539 | 6539-L01 | 383 BIRCH ST N | TIMMINS | P4N6E8 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4834 | -81.3321 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 340000 | Construction Complete | Land Acquisition | Other | 2011-12 | 40787 | 0 | 0 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340000 | 340000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-004 | 30.1-004 | 30.1 | N/A | 29009 | Northeastern CDSB | Aileen-Wright English | Aileen-Wright English Catholic Elementary School | ELE | 4145 | 7785 | 7785-B01 | 75 SIXTH ST | COCHRANE | P0L1C0 | 35-13-81-407 | Cochrane | Cochrane T | Cochrane District | COCHRANE | Northeast | North | 49.0662 | -81.0289 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 48842.03 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 0 | 0 | 48842.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48842.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48842.03 | 48842.03 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-005 | 30.1-005 | 30.1 | N/A | 29009 | Northeastern CDSB | Aileen-Wright English | Aileen-Wright English Catholic Elementary School | ELE | 4145 | 7785 | 7785-B01 | 75 SIXTH ST | COCHRANE | P0L1C0 | 35-13-81-407 | Cochrane | Cochrane T | Cochrane District | COCHRANE | Northeast | North | 49.0662 | -81.0289 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 44468 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 44468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44468 | 44468 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-006 | 30.1-006 | 30.1 | N/A | 29009 | Northeastern CDSB | English Central | English Central Catholic Elementary School | ELE | 7744 | 8876 | 8876-B01 | 245 SHEPHERDSON RD RR 1 | NEW LISKEARD | P0J1P0 | 35-13-90-101 | Temiskaming Shores | Temiskaming Shores C | Timiskaming District | TIMISKAMING | Northeast | North | 47.5018 | -79.6937 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 765826 | Construction Complete | Addition | Other | 2010-11 | 40422 | 146441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619385 | 765826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765826 | 765826 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-007 | 30.1-007 | 30.1 | N/A | 29009 | Northeastern CDSB | O'Gorman | O'Gorman Catholic Secondary School | SEC | 7702 | 8839 | 8839-B01 | 490 MACLEAN DR | TIMMINS | P4N4W6 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.486 | -81.3344 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4655647 | Construction Complete | Addition | Other | 2006-07 | 38961 | 4500000 | 0 | 155647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4655647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4655647 | 4655647 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-008 | 30.1-008 | 30.1 | N/A | 29009 | Northeastern CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 7747 | 8878 | 8878-B01 | 63 CHURCHILL DR | KIRKLAND LAKE | P2N1T8 | 35-13-90-405 | Kirkland Lake | Kirkland Lake T | Timiskaming District | TIMISKAMING | Northeast | North | 48.1474 | -80.0291 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 80114.18 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 80114.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80114.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80114.18 | 80114.18 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-009 | 30.1-009 | 30.1 | N/A | 29009 | Northeastern CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 7748 | 8879 | 8879-B01 | 119 LANG ST | COBALT | P0J1C0 | 35-13-90-606 | Coleman | Coleman Tp | Timiskaming District | TIMISKAMING | Northeast | North | 47.3993 | -79.6785 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1071819 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 632013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439806 | 1071819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071819 | 1071819 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-010 | 30.1-010 | 30.1 | N/A | 29009 | Northeastern CDSB | Pope Francis | Pope Francis Catholic Elementary School | ELE | 7715 | 8852 | 8852-B01 | 387 BALSAM ST N | TIMMINS | P4N6H5 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4838 | -81.3314 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 218913 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218913 | 218913 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.1-011 | 30.1-011 | 30.1 | 301 - DSSAB Cochrane | 29009 | Northeastern CDSB | Pope Francis | Pope Francis Catholic Elementary School | ELE | 7715 | 8852 | 8852-B01 | 387 BALSAM ST N | TIMMINS | P4N6H5 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4838 | -81.3314 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 150 | 2 | 34 | Y | - | Approved | 42905 | 8248106 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 0 | 619470 | 912000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1531470 | 0 | 0 | 1512510 | 0 | 3691616 | 0 | 1512510 | 0 | 0 | 0 | 6716636 | 8248106 | 8248106 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5204126
30.1-012 | 30.1-012 | 30.1 | 301 - DSSAB Cochrane | 29009 | Northeastern CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 7713 | 8850 | 8850-B01 | 207 HUOT ST | SOUTH PORCUPINE | P0N1H0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4839 | -81.2059 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 45121 | 5459836 | Under Construction | Addition | Child Care | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5459836 | 0 | 0 | 0 | 5459836 | 5459836 | 4276200 | -1183636 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 5459836
30.1-013 | 30.1-013 | 30.1 | N/A | 29009 | Northeastern CDSB | Teacherage | Teacherage | TEA | 15521-15527 | 18059-18065 | 18059-18065-B01 | 60 WABUN RD / 92 FERGUSON RD | MOOSONEE | P0L1Y0 | 35-13-81-408 | Moosonee | Moosonee T | Cochrane District | COCHRANE | Northeast | North | 51.275 | -80.6389 | 44460 | 2021-22 | 2021-22 | - | - | - | 44460 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44460 | 384604 | Construction Complete | Retrofit | Condition | 2021-22 | 44470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384604 | 0 | 0 | 0 | 0 | 0 | 384604 | 384604 | 384604 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 384604
30.2-001 | 30.2-001 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15760 | 7435 | 7435-B01 | 1000 HIGH ST | NORTH BAY | P1B6S6 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3243 | -79.4606 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140864 | 0 | 0 | 0 | 0 | 0 | 140864 | 140864 | 0 | -140864 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 140864
30.2-002 | 30.2-002 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15760 | 7435 | 7435-B01 | 1000 HIGH ST | NORTH BAY | P1B6S6 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3243 | -79.4606 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 654476 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693707 | 693707 | 654476 | -39231 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-003 | 30.2-003 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | Mother St. Bride | Mother St. Bride Catholic Elementary School | ELE | 3439 | 7262 | 7262-L01 | 414 SECOND AVE W | NORTH BAY | P1B3L2 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3165 | -79.463 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 824198 | Construction Complete | Land Acquisition | Other | 2007-08 | 39326 | 824198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824198 | 824198 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-005 | 30.2-005 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | St. Hubert | St. Hubert Catholic Elementary School | ELE | 3999 | 7435 | 7435-B02 | 850 LORNE AVE | NORTH BAY | P1B8M2 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3243 | -79.4606 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 71512 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71512 | 71512 | 71512 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-006 | 30.2-006 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | St. Joseph-Scollard Hall | St. Joseph-Scollard Hall Catholic Secondary School | SEC | 3674 | 7435 | 7435-B01 | 675 O'BRIEN ST | NORTH BAY | P1B9R3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3224 | -79.4577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1548738 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548738 | 1548738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548738 | 1548738 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-007 | 30.2-007 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | St. Joseph-Scollard Hall | St. Joseph-Scollard Hall Catholic Secondary School | SEC | 3674 | 7435 | 7435-B01 | 675 O'BRIEN ST | NORTH BAY | P1B9R3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3224 | -79.4577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2579784 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2579784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2579784 | 2579784 | 2579784 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-008 | 30.2-008 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | St. Joseph-Scollard Hall | St. Joseph-Scollard Hall Catholic Secondary School | SEC | 3674 | 7435 | 7435-B01 | 675 O'BRIEN ST | NORTH BAY | P1B9R3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3224 | -79.4577 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1987472 | Construction Complete | Retrofit | Other | 2009-10 | 40057 | 0 | 0 | 492250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495222 | 1987472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1987472 | 1987472 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-009 | 30.2-009 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | St. Luke | St. Luke Catholic Elementary School | ELE | 15460 | 7420 | 7420-B01 | 225 MILANI RD | NORTH BAY | P1B7P4 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3325 | -79.4604 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7367208 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7367208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7367208 | 7367208 | 7367208 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-010 | 30.2-010 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | St. Theresa | St. Theresa Catholic Elementary School | ELE | 10830 | 12009 | 12009-B01 | 1475 MAIN ST N | CALLANDER | P0H1H0 | 35-13-86-607 | Callander | Callander M | Parry Sound District | PARRY SOUND | Northeast | North | 46.2348 | -79.3728 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8061719 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 605651 | 0 | 290966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4020753 | 4917370 | 3144349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3144349 | 8061719 | 8061719 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-011 | 30.2-011 | 30.2 | N/A | 29017 | Nipissing-Parry Sound CDSB | St. Victor | St. Victor Catholic Elementary School | ELE | 24326 | 8047 | 8047-B02 | 800 JOHN ST W | MATTAWA | P0H1V0 | 35-13-85-403 | Mattawa | Mattawa T | Nipissing District | NIPISSING | Northeast | North | 46.3094 | -78.7125 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8353541 | Construction Complete | New Construction | Condition | 2014-15 | 41883 | 232580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232580 | 8120961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8120961 | 8353541 | 8353541 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
30.2-012 | 30.2-012 | 30.2 | 302 - DSSAB Nipissing | 29017 | Nipissing-Parry Sound CDSB | Our Lady of Sorrows | Our Lady of Sorrows Catholic Elementary School | ELE | 3560 | 7344 | 7344-B01 | 680 COURSOL RD | STURGEON FALLS | P2B3L1 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3698 | -79.9143 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2018-19 | 43556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299982 | 0 | 0 | 0 | 299982 | 299982 | 299982 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 299982
30.2-014 | 30.2-014 | 30.2 | 302 - DSSAB Nipissing | 29017 | Nipissing-Parry Sound CDSB | St. Francis | St. Francis Catholic Elementary School | ELE | 3933 | 7630 | 7630-B01 | 68 GERTRUDE ST E | NORTH BAY | P1A1J8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.2893 | -79.4471 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43342 | 2399852 | Construction Complete | Addition | Child Care | 2019-20 | 43836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399852 | 0 | 0 | 0 | 2399852 | 2399852 | 3278894 | 879042 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2399852
30.2-015 | 30.2-015 | 30.2 | 302 - DSSAB Nipissing | 29017 | Nipissing-Parry Sound CDSB | Mother St. Bride | Mother St. Bride Catholic Elementary School | ELE | 3439 | 7262 | 7262-B01 | 414 SECOND AVE W | NORTH BAY | P1B3L2 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3165 | -79.463 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43342 | 899944 | Construction Complete | Retrofit | Child Care | 2018-19 | 43591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899945 | 0 | 0 | 0 | 899945 | 899945 | 956403 | 56458 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 899945
31-001 | 31-001 | 31 | N/A | 29025 | Huron Superior CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 6326 | 8676 | 8676-B01 | 100 ONTARIO AVE | SAULT STE. MARIE | P6B1E3 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5127 | -84.3135 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
31-002 | 31-002 | 31 | N/A | 29025 | Huron Superior CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 6326 | 8676 | 8676-B01 | 100 ONTARIO AVE | SAULT STE. MARIE | P6B1E3 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5127 | -84.3135 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2297099 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443547 | 2443547 | 2297099 | -146448 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
31-003 | 31-003 | 31 | N/A | 29025 | Huron Superior CDSB | Holy Cross | Holy Cross Catholic Elementary School | ELE | 4350 | 7926 | 7926-B01 | 16 TEXAS AVE | SAULT STE. MARIE | P6A4Y8 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5106 | -84.279 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 500 | - | - | N | - | Not Required | - | 15989672 | Construction Complete | Addition | Consolidation | 2012-13 | 41153 | 0 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1393500 | 1504500 | 2236690 | 0 | 1012538 | 0 | 0 | 11235944 | 0 | 0 | 0 | 0 | 14485172 | 15989672 | 15989672 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
31-007-01 | 31-007+61-026 | 31 | 307 - DSSAB Manitoulin-Sudbury | 29025 | Huron Superior CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 24470 | 7405 | 7405-B02 | 273 MEAD BLVD | ESPANOLA | P5E1B3 | 35-13-88-405 | Espanola | Espanola T | Sudbury District | SUDBURY | Northeast | North | 46.2606 | -81.7738 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 245 | 3 | 49 | N | 1 | Approved | 43161 | 11307581 | Construction Complete | New Construction | Condition | 2021-22 | 44446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211987 | 211987 | 0 | 0 | 605731 | 0 | 8686757 | 0 | 1145644 | 657462 | 0 | 0 | 11095594 | 11307581 | 11307581 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10489863
31-007-02 | 31-007+61-026 | 31 | N/A | 29025 | Huron Superior CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 24470 | 7405 | 7405-L02 | 273 MEAD BLVD | ESPANOLA | P5E1B3 | 35-13-88-405 | Espanola | Espanola T | Sudbury District | SUDBURY | Northeast | North | 46.2606 | -81.7738 | 42178 | 2014-15 | 2015-16 | 42178 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42178 | 274262 | Construction Complete | Land Acquisition | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274262 | 0 | 0 | 0 | 0 | 0 | 0 | 274262 | 274262 | 274262 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 274262
31-008 | 31-008 | 31 | N/A | 29025 | Huron Superior CDSB | St. Mary's | St. Mary's Catholic Elementary School | ELE | 4492 | 8022 | 8022-B01 | 124 GIBBS ST | SAULT STE. MARIE | P6A5H6 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5224 | -84.2669 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2527936 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 344505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927769 | 1272274 | 1255662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255662 | 2527936 | 2527936 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
31-009 | 31-009 | 31 | N/A | 29025 | Huron Superior CDSB | St. Mary's | St. Mary's Catholic Elementary School | ELE | 4492 | 8022 | 8022-B01 | 124 GIBBS ST | SAULT STE. MARIE | P6A5H6 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5224 | -84.2669 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 685268 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 178999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178999 | 0 | 0 | 506269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506269 | 685268 | 685268 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
31-010 | 31-010 | 31 | N/A | 29025 | Huron Superior CDSB | St. Basil | St. Basil Catholic Elementary School | ELE | 3781 | 5040 | 5040-B01 | 250 ST GEORGE'S AVE E | SAULT STE. MARIE | P6B1X5 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5232 | -84.3301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42405 | 1626562 | Construction Complete | Retrofit | Consolidation | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1626562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1626562 | 1626562 | 1626562 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
31-011 | 31-011 | 31 | 304 - DSSAB Sault Ste Marie | 29025 | Huron Superior CDSB | St. Basil | St. Basil Catholic Elementary School | ELE | 24455 | 5040 | 5040-B01 | 250 ST GEORGE'S AVE E | SAULT STE. MARIE | P6B1X5 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5227 | -84.3292 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | 3 | 49 | N | 1 | Approved | 42803 | 10979157 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 294000 | 2900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194000 | 0 | 0 | 629970 | 0 | 4691279 | 0 | 1838737 | 625171 | 0 | 0 | 7785157 | 10979157 | 10979157 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7155187
31-012 | 31-012 | 31 | N/A | 29025 | Huron Superior CDSB | St. Francis | St. Francis Catholic Elementary School | ELE | 3940 | 7635 | 7635-B01 | 147 BROOKFIELD AVE | SAULT STE. MARIE | P6C5P2 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5326 | -84.3976 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1736325 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339200 | 339200 | 0 | 0 | 1397125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397125 | 1736325 | 1736325 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
31-015-01 | 31-015 | 31 | N/A | 29025 | Huron Superior CDSB | St. Mary's College | St. Mary's College Catholic Secondary School | SEC | 24398 | 19399 | 19399-B01 | 868 SECOND LINE E | SAULT STE. MARIE | P6B4K4 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5403 | -84.3068 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 1413 | - | - | N | - | Not Required | - | 46295617 | Construction Complete | New Construction | Consolidation | 2015-16 | 42248 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 45395617 | 0 | 0 | 0 | 0 | 0 | 45395617 | 46295617 | 46295617 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 45395617
31-015-02 | 31-015 | 31 | N/A | 29025 | Huron Superior CDSB | St. Mary's College | St. Mary's College Catholic Secondary School | SEC | 24398 | 19399 | 19399-L01 | 868 SECOND LINE E | SAULT STE. MARIE | P6B4K4 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5403 | -84.3068 | 40793 | 2011-12 | 2011-12 | 40793 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 40793 | 6085371 | Construction Complete | Land Acquisition | Consolidation | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6085371 | 0 | 0 | 0 | 0 | 0 | 0 | 6085371 | 6085371 | 6085371 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 6085371
31-016 | 31-016 | 31 | N/A | 29025 | Huron Superior CDSB | St. Paul | St. Paul Catholic Elementary School | ELE | 4385 | 7946 | 7946-B01 | 78 DABLON ST | SAULT STE. MARIE | P6B5E6 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5306 | -84.3096 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 734151 | Construction Complete | Addition | Other | 2011-12 | 40787 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 587151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587151 | 734151 | 734151 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-001 | 32-001 | 32 | N/A | 29033 | Sudbury CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 10819 | 5115 | 5115-B01 | 165 D'YOUVILLE ST | SUDBURY | P3C5E7 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4965 | -80.9948 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-002 | 32-002 | 32 | N/A | 29033 | Sudbury CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 10819 | 5115 | 5115-B01 | 165 D'YOUVILLE ST | SUDBURY | P3C5E7 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4965 | -80.9948 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1316584 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1704211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1704211 | 1704211 | 1704211 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-003 | 32-003 | 32 | N/A | 29033 | Sudbury CDSB | Holy Trinity | Holy Trinity Catholic Elementary School | ELE | 24408 | 19409 | 19409-B01 | 1945 HAWTHORNE DR | SUDBURY | P3A0C1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.516 | -80.927 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 18983930 | Construction Complete | New Construction | Consolidation | 2012-13 | 41153 | 500000 | 0 | 1820000 | 305668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 3125668 | 14827803 | 0 | 1030459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15858262 | 18983930 | 18983930 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-004-01 | 32-004 | 32 | N/A | 29033 | Sudbury CDSB | Holy Trinity | Holy Trinity Catholic Elementary School | ELE | 24408 | 19409 | 19409-B01 | 1945 HAWTHORNE DR | SUDBURY | P3A0C1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.516 | -80.927 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 578 | - | - | N | - | Approved | 41487 | 11148062 | Construction Complete | New Construction | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090316 | 0 | 10685704 | 0 | 0 | 0 | 0 | 0 | 11776020 | 11776020 | 11151164 | -624856 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10685704
32-004-02 | 32-004 | 32 | N/A | 29033 | Sudbury CDSB | Holy Trinity | Holy Trinity Catholic Elementary School | ELE | 24408 | 19409 | 19409-L01 | 1945 HAWTHORNE DR | SUDBURY | P3A0C1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.516 | -80.927 | 41487 | 2012-13 | 2013-14 | 41487 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41487 | 830000 | Construction Complete | Land Acquisition | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830000 | 0 | 0 | 0 | 0 | 0 | 0 | 830000 | 830000 | 830000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 830000
32-005 | 32-005 | 32 | N/A | 29033 | Sudbury CDSB | SCDSB Head Office | Administrative Office | OFF-ADM | 10819 | 5115 | 5115-B01 | 165 D'YOUVILLE ST | SUDBURY | P3C5E7 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4965 | -80.9948 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 184348 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 184348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184348 | 184348 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-006 | 32-006 | 32 | N/A | 29033 | Sudbury CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 10485 | 7430 | 7430-B01 | 4500 ST. MICHEL ST | HANMER | P3P1M8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6522 | -80.934 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 500000 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 32629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32629 | 467371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467371 | 500000 | 500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-007 | 32-007 | 32 | N/A | 29033 | Sudbury CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 10485 | 7430 | 7430-B01 | 4500 ST. MICHEL ST | HANMER | P3P1M8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6522 | -80.934 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2823648 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2823648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2823648 | 2823648 | 2823648 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-008 | 32-008 | 32 | N/A | 29033 | Sudbury CDSB | Bishop Alexander Carter | Bishop Alexander Carter Catholic Secondary School | SEC | 3727 | 7472 | 7472-B01 | 539 FRANCIS ST | HANMER | P3P1E6 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6569 | -80.9674 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9074047 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9074047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9074047 | 9074047 | 9074047 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-009 | 32-009 | 32 | N/A | 29033 | Sudbury CDSB | St. Charles College | St. Charles College Catholic Secondary School | SEC | 3851 | 7567 | 7567-B01 | 1940 HAWTHORNE DR | SUDBURY | P3A1M8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5177 | -80.9268 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 96 | - | - | N | - | Not Required | - | 6307929 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 1994548 | 0 | 746142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246627 | 2987317 | 0 | 0 | 0 | 0 | 3320612 | 0 | 0 | 0 | 0 | 0 | 3320612 | 6307929 | 6307929 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3320612
32-010-01 | 32-010 | 32 | N/A | 29033 | Sudbury CDSB | St. David | St. David Catholic Elementary School | ELE | 24404 | 19405 | 19405-B01 | 549 FROOD RD | SUDBURY | P3C5A2 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5068 | -81.0067 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 200 | - | - | N | - | Approved | 41487 | 9374264 | Construction Complete | New Construction | Condition | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8746306 | 0 | 0 | 0 | 0 | 0 | 8746306 | 8746306 | 9371162 | 624856 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8746306
32-010-02 | 32-010 | 32 | N/A | 29033 | Sudbury CDSB | St. David | St. David Catholic Elementary School | ELE | 24404 | 19405 | 19405-L01 | 549 FROOD RD | SUDBURY | P3C5A2 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5068 | -81.0067 | 41487 | 2012-13 | 2013-14 | 41487 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41487 | 1270000 | Construction Complete | Land Acquisition | Condition | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 1270000 | 1270000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1270000
32-011 | 32-011 | 32 | N/A | 29033 | Sudbury CDSB | St. Francis | St. Francis Catholic Elementary School | ELE | 3941 | 7636 | 7636-B01 | 691 LILAC ST | SUDBURY | P3E4E2 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4776 | -81.0134 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3031151 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 358333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358333 | 0 | 2209638 | 463180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2672818 | 3031151 | 3031151 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
32-014 | 32-014 | 32 | N/A | 29033 | Sudbury CDSB | St. Paul the Apostle | St. Paul the Apostle Catholic Elementary School | ELE | 3550 | 7337 | 7337-B01 | 1 EDWARD AVE | CONISTON | P0M1M0 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4943 | -80.8506 | 42499 | 2015-16 | 2016-17 | - | - | - | 42499 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42984 | 1520280 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43344 | 193489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193489 | 0 | 0 | 0 | 0 | 1269122 | 0 | 0 | 0 | 0 | 0 | 1269122 | 1462611 | 1462611 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1269122
33.1-001 | 33.1-001 | 33.1 | N/A | 29041 | Northwest CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 24177 | 7631 | 7631-B02 | 555 FLINDERS AVE | FORT FRANCES | P9A3L2 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6111 | -93.4218 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.1-002 | 33.1-002 | 33.1 | N/A | 29041 | Northwest CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 24177 | 7631 | 7631-B02 | 555 FLINDERS AVE | FORT FRANCES | P9A3L2 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6111 | -93.4218 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 626154 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294992 | 294992 | 765769 | 470777 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.1-003 | 33.1-003 | 33.1 | N/A | 29041 | Northwest CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3648 | 7416 | 7416-B01 | 41 EIGHTH AVE | SIOUX LOOKOUT | P8T1B7 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.1024 | -91.9274 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 111964 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111964 | 111964 | 111964 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.1-004 | 33.1-004 | 33.1 | N/A | 29041 | Northwest CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3648 | 7416 | 7416-B01 | 41 EIGHTH AVE | SIOUX LOOKOUT | P8T1B7 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.1024 | -91.9274 | 41046 | 2011-12 | 2012-13 | - | - | - | 41046 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | 155 | - | - | N | - | Not Required | - | 1675217 | Construction Complete | Addition | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205838 | 205838 | 0 | 0 | 622755 | 0 | 846624 | 0 | 0 | 0 | 0 | 0 | 1469379 | 1675217 | 1675217 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 846624
33.1-005 | 33.1-005 | 33.1 | N/A | 29041 | Northwest CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4133 | 7776 | 7776-B01 | 185 PARKDALE RD | DRYDEN | P8N1S5 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7739 | -92.8275 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 770205 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708754 | 61451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770205 | 770205 | 770205 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.1-006-01 | 33.1-006 | 33.1 | 308 - DSSAB Rainy River | 29041 | Northwest CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 24586 | 7631 | 7631-B03 | 755 FLINDERS AVE | FORT FRANCES | P9A3L2 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6108 | -93.4218 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 345 | 2 | 39 | Y | - | Approved | 43266 | 16539912 | Construction Complete | New Construction | Consolidation | 2019-20 | 43836 | 100000 | 0 | 0 | 2763835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2863835 | 0 | 0 | 1201110 | 0 | 10861621 | 0 | 1613346 | 0 | 0 | 0 | 13676077 | 16539912 | 16539912 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12474967
33.1-006-02 | 33.1-006 | 33.1 | N/A | 29041 | Northwest CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 24586 | 7631 | 7631-L03 | 755 FLINDERS AVE | FORT FRANCES | P9A3L2 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6108 | -93.4218 | 43012 | 2017-18 | 2017-18 | 43012 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43012 | 1145413 | Construction Complete | Land Acquisition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1145413 | 0 | 0 | 0 | 0 | 0 | 0 | 1145413 | 1145413 | 1145413 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1145413
33.1-007 | 33.1-007 | 33.1 | N/A | 29041 | Northwest CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4309 | 7899 | 7899-B01 | 820 FIFTH ST E | FORT FRANCES | P9A1V4 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.615 | -93.3819 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1558329 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336116 | 336116 | 0 | 0 | 1222213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222213 | 1558329 | 1558329 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.1-008 | 33.1-008 | 33.1 | N/A | 29041 | Northwest CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 24586 | 7631 | 7631-B03 | 755 FLINDERS AVE | FORT FRANCES | P9A3L2 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6125 | -93.4218 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 69 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5851846 | 0 | 0 | 0 | 0 | 0 | 5851846 | 5851846 | 5851846 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5851846
33.2-001 | 33.2-001 | 33.2 | N/A | 29050 | Kenora CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15767 | 8778 | 8778-B02 | 1292 HEENAN PL | KENORA | P9N2Y8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7815 | -94.46 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-002 | 33.2-002 | 33.2 | N/A | 29050 | Kenora CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15767 | 8778 | 8778-B02 | 1292 HEENAN PL | KENORA | P9N2Y8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7815 | -94.46 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84231 | 84231 | 84231 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-003 | 33.2-003 | 33.2 | N/A | 29050 | Kenora CDSB | Our Lady of the Valley | Our Lady of the Valley Catholic Elementary School | ELE | 3568 | 7351 | 7351-B01 | 1 BRINKMAN RD | KENORA | P9N2R5 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7731 | -94.472 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 30922 | Construction Complete | Retrofit | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30922 | 30922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30922 | 30922 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-004 | 33.2-004 | 33.2 | N/A | 29050 | Kenora CDSB | Our Lady of the Valley | Our Lady of the Valley Catholic Elementary School | ELE | 3568 | 7351 | 7351-B01 | 1 BRINKMAN RD | KENORA | P9N2R5 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7731 | -94.472 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 145515 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145515 | 145515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145515 | 145515 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-005 | 33.2-005 | 33.2 | N/A | 29050 | Kenora CDSB | Pope John Paul II | Pope John Paul II Catholic Elementary School | ELE | 10826 | 5084 | 5084-B03 | 1290 HEENAN PL | KENORA | P9N2Y8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7814 | -94.4603 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9507097 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7107 | 7107 | 9499990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9499990 | 9507097 | 9507097 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-006 | 33.2-006 | 33.2 | N/A | 29050 | Kenora CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 4576 | 5084 | 5084-B02 | 1 POIRIER DR | KENORA | P9N4G8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7839 | -94.4592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1089994 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273328 | 273328 | 816666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816666 | 1089994 | 1089994 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-007 | 33.2-007 | 33.2 | N/A | 29050 | Kenora CDSB | St. Thomas Aquinas Annex | St. Thomas Aquinas Annex Catholic Elementary School | ELE | 10543 | 8778 | 8778-B02 | 1292 HEENAN PL | KENORA | P9N2Y8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7817 | -94.4601 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3305392 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3305392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3305392 | 3305392 | 3305392 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-008 | 33.2-008 | 33.2 | N/A | 29050 | Kenora CDSB | St. Thomas Aquinas Annex | St. Thomas Aquinas Annex Catholic Elementary School | ELE | 10543 | 8778 | 8778-B02 | 1292 HEENAN PL | KENORA | P9N2Y8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7817 | -94.4601 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 827736 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 111406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111406 | 716330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716330 | 827736 | 827736 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-009 | 33.2-009 | 33.2 | N/A | 29050 | Kenora CDSB | Ste. Marguerite Bourgeoys | Ste. Marguerite Bourgeoys Catholic Elementary School | ELE | 4190 | 5084 | 5084-B01 | 20 GUNNE CRES | KENORA | P9N3N5 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7819 | -94.4587 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 150 | - | - | N | - | Not Required | - | 4593236 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3019336 | 0 | 1702951 | 0 | 0 | 0 | 0 | 0 | 4722287 | 4722287 | 4593236 | -129051 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1702951
33.2-010 | 33.2-010 | 33.2 | 306 - DSSAB Kenora | 29050 | Kenora CDSB | Pope John Paul II | Pope John Paul II Catholic Elementary School | ELE | 10826 | 5084 | 5084-B03 | 1290 HEENAN PL | KENORA | P9N2Y8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7814 | -94.4603 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403337 | 0 | 0 | 0 | 403337 | 403337 | 403337 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 403337
33.2-011 | 33.2-011 | 33.2 | N/A | 29050 | Kenora CDSB | Multi Skills Training Center | Administrative Office | OFF-ADM | 15767 | 8778 | 8778-B02 | 1292 HEENAN PL | KENORA | P9N2Y8 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7815 | -94.46 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 300000 | Construction Complete | Retrofit | Other | 2008-09 | 39692 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
33.2-012 | 33.2-012 | 33.2 | 306 - DSSAB Kenora | 29050 | Kenora CDSB | St. Louis | St. Louis Catholic Elementary School | ELE | 4171 | 7804 | 7804-B01 | 420 8TH ST | KEEWATIN | P0X1C0 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7591 | -94.5565 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 1 | 15 | N | - | Not Required | - | - | Construction Complete | Retrofit | Child Care | 2021-22 | 44562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 427859 | 0 | 0 | 0 | 427859 | 427859 | 427859 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 427859
34.1-001 | 34.1-001 | 34.1 | N/A | 29068 | Thunder Bay CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 4500 | 8027 | 8027-B01 | 459 VICTORIA AVE W | THUNDER BAY | P7C0A4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3842 | -89.288 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-002 | 34.1-002 | 34.1 | N/A | 29068 | Thunder Bay CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 4500 | 8027 | 8027-B01 | 459 VICTORIA AVE W | THUNDER BAY | P7C0A4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3842 | -89.288 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5395770 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5395770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5395770 | 5395770 | 5395770 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-003 | 34.1-003 | 34.1 | N/A | 29068 | Thunder Bay CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 4500 | 8027 | 8027-B01 | 459 VICTORIA AVE W | THUNDER BAY | P7C0A4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3842 | -89.288 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 274230 | Construction Complete | Other | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274230 | 274230 | 274230 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-004 | 34.1-004 | 34.1 | N/A | 29068 | Thunder Bay CDSB | Corpus Christi | Corpus Christi Catholic Elementary School | ELE | 3156 | 7076 | 7076-B01 | 110 MARLBOROUGH ST | THUNDER BAY | P7B4G4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4362 | -89.2441 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2535200 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2535200 | 2535200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2535200 | 2535200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-005 | 34.1-005 | 34.1 | N/A | 29068 | Thunder Bay CDSB | Holy Cross | Holy Cross Catholic Elementary School | ELE | 3273 | 7150 | 7150-B01 | 420 BRITTANY DR | THUNDER BAY | P7B5X8 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4507 | -89.2615 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2429874 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389768 | 389768 | 2040106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040106 | 2429874 | 2429874 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-008 | 34.1-008 | 34.1 | N/A | 29068 | Thunder Bay CDSB | Pope John Paul II | Pope John Paul II Catholic Elementary School | ELE | 3653 | 7421 | 7421-B01 | 205 FRANKLIN ST S | THUNDER BAY | P7E1R2 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.382 | -89.2571 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8703026 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393143 | 393143 | 8309883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8309883 | 8703026 | 8703026 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-009 | 34.1-009 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Jude | St. Jude Catholic Elementary School | ELE | 4149 | 7788 | 7788-B01 | 345 OGDEN ST | THUNDER BAY | P7C2N4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3942 | -89.2426 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1211669 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487789 | 487789 | 723880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723880 | 1211669 | 1211669 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-010 | 34.1-010 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Bernard | St. Bernard Catholic Elementary School | ELE | 3807 | 7536 | 7536-B01 | 655 RIVER ST | THUNDER BAY | P7A3S5 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4482 | -89.2369 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4339702 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2479829 | 2479829 | 1859873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1859873 | 4339702 | 4339702 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-014 | 34.1-014 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Ignatius | St. Ignatius Catholic Secondary School | SEC | 4004 | 5023 | 5023-B01 | 285 GIBSON ST | THUNDER BAY | P7A2J6 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4532 | -89.1964 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5000200 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199681 | 1199681 | 3800519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800519 | 5000200 | 5000200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-016 | 34.1-016 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 6311 | 8668 | 8668-B01 | 100-115 MARY ST W | THUNDER BAY | P7E2L8 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3697 | -89.2778 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 367801 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367801 | 367801 | 367801 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-017 | 34.1-017 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 6311 | 8668 | 8668-B01 | 100-115 MARY ST W | THUNDER BAY | P7E2L8 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3697 | -89.2778 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 104 | - | - | N | - | Not Required | - | 3622924 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422924 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 3622924 | 3622924 | 3622924 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1200000
34.1-018 | 34.1-018 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Pius X | St. Pius X Catholic Elementary School | ELE | 4434 | 7977 | 7977-B01 | 140 CLARKSON ST S | THUNDER BAY | P7B4W8 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4415 | -89.2538 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1636800 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408119 | 1408119 | 228681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228681 | 1636800 | 1636800 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-020 | 34.1-020 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Elementary School | ELE | 3906 | 5192 | 5192-B01 | 2645 DONALD ST E | THUNDER BAY | P7E5X5 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3831 | -89.2761 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 156183 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156183 | 156183 | 156183 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-021 | 34.1-021 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Vincent | St. Vincent Catholic Elementary School | ELE | 4528 | 8052 | 8052-B01 | 150 REDWOOD AVE W | THUNDER BAY | P7C1Z6 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3934 | -89.2846 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 152516 | Construction Complete | Retrofit | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152516 | 152516 | 152516 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-022 | 34.1-022 | 34.1 | N/A | 29068 | Thunder Bay CDSB | Education Resource Centre | Administrative Office | OFF-ADM | 6310 | 8668 | 8668-B01 | 100-115 MARY ST W | THUNDER BAY | P7E2L8 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3697 | -89.2778 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1401329 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28872 | 28872 | 1372457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1372457 | 1401329 | 1401329 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.1-023 | 34.1-023 | 34.1 | N/A | 29068 | Thunder Bay CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Elementary School | ELE | 3906 | 5192 | 5192-B01 | 2645 DONALD ST E | THUNDER BAY | P7E5X5 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.3831 | -89.2761 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
34.2-001 | 34.2-001 | 34.2 | N/A | 29076 | Superior North CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18306 | 19062 | 19062-B01 | 21 SIMCOE PLAZA | TERRACE BAY | P0T2W0 | 35-14-89-613 | Terrace Bay | Terrace Bay Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7832 | -87.1017 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.2-002 | 34.2-002 | 34.2 | N/A | 29076 | Superior North CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18306 | 19062 | 19062-B01 | 21 SIMCOE PLAZA | TERRACE BAY | P0T2W0 | 35-14-89-613 | Terrace Bay | Terrace Bay Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7832 | -87.1017 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 52692 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52692 | 52692 | 52692 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.2-003 | 34.2-003 | 34.2 | N/A | 29076 | Superior North CDSB | Saint Edward | Saint Edward Catholic Elementary School | ELE | 10661 | 8703 | 8703-B01 | 121 GREENMANTLE DR | NIPIGON | P0T2J0 | 35-14-89-607 | Nipigon | Nipigon Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 49.0071 | -88.2705 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4061491 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961491 | 961491 | 3100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 4061491 | 4061491 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.2-004 | 34.2-004 | 34.2 | N/A | 29076 | Superior North CDSB | Saint Edward | Saint Edward Catholic Elementary School | ELE | 10661 | 8703 | 8703-B01 | 121 GREENMANTLE DR | NIPIGON | P0T2J0 | 35-14-89-607 | Nipigon | Nipigon Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 49.0071 | -88.2705 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 550681 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550681 | 550681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550681 | 550681 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.2-005 | 34.2-005-62-011 | 34.2 | N/A | 29076 | Superior North CDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 10901 | 12063 | 12063-B01 | 17 CARTIER DR | TERRACE BAY | P0T2W0 | 35-14-89-613 | Terrace Bay | Terrace Bay Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7813 | -87.1044 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4009887 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771848 | 771848 | 3238039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3238039 | 4009887 | 4009887 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.2-006 | 34.2-006 | 34.2 | N/A | 29076 | Superior North CDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 10901 | 12063 | 12063-B01 | 17 CARTIER DR | TERRACE BAY | P0T2W0 | 35-14-89-613 | Terrace Bay | Terrace Bay Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7813 | -87.1044 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1022305 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303067 | 303067 | 719238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719238 | 1022305 | 1022305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.2-007 | 34.2-007 | 34.2 | N/A | 29076 | Superior North CDSB | Catholic Education Centre | Catholic Education Centre | OFF-ADM | 24687 | 12063 | 12063-B01 | 17 CARTIER DR | TERRACE BAY | P0T2W0 | 35-14-89-613 | Terrace Bay | Terrace Bay Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7813 | -87.1044 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43010 | 2020000 | Construction Complete | Addition | Other | 2019-20 | 43791 | 0 | 0 | 0 | 2020000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020000 | 2020000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
34.2-008 | 34.2-008 | 34.2 | N/A | 29076 | Superior North CDSB | St. Hilary | St. Hilary Catholic Elementary School | ELE | 3996 | 7677 | 7677-B01 | 62 SALLS ST | RED ROCK | P0T2P0 | 35-14-89-617 | Red Rock | Red Rock Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.9404 | -88.2618 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 23 | - | - | N | - | Approved | 45133 | 2742996 | Planned | Addition | Other | 2023-24 | 45174 | 274643 | 0 | 88210 | 741350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104203 | 0 | 0 | 0 | 0 | 1638793 | 0 | 0 | 0 | 0 | 0 | 1638793 | 2742996 | 2742996 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1638793
34.2-009 | 34.2-009 | 34.2 | N/A | 29076 | Superior North CDSB | St. Hilary | St. Hilary Catholic Elementary School | ELE | [37 empty] | - |  | - | - | Planned | Addition | Other |  |  | 0 | 0 | 0 | 11827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11827 | 11827 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 0
35-001 | 35-001 | 35 | N/A | 67008 | Bruce-Grey CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16463 | 17110 | 17110-B01 | 799 16TH AVE | HANOVER | N4N3A1 | 35-15-47-402 | Hanover | Hanover T | Grey Co | GREY | Southwest | South | 44.1604 | -81.0191 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-002 | 35-002 | 35 | N/A | 67008 | Bruce-Grey CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16463 | 17110 | 17110-B01 | 799 16TH AVE | HANOVER | N4N3A1 | 35-15-47-402 | Hanover | Hanover T | Grey Co | GREY | Southwest | South | 44.1604 | -81.0191 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 447699 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740913 | 740913 | 447699 | -293214 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-003 | 35-003 | 35 | N/A | 67008 | Bruce-Grey CDSB | École Immaculée-Conception | École Immaculée-Conception Catholic Elementary School | ELE | 3327 | 7185 | 7185-B01 | 201 CONCESSION 12 RR 1 | FORMOSA | N0G1W0 | 35-15-41-626 | South Bruce | South Bruce M | Bruce Co | BRUCE | Southwest | South | 44.0679 | -81.2104 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 118 | - | - | N | - | Not Required | - | 2533113 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 219553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219553 | 0 | 0 | 229867 | 0 | 2083693 | 0 | 0 | 0 | 0 | 0 | 2313560 | 2533113 | 2533113 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2083693
35-004 | 35-004 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Teresa of Calcutta | St. Teresa of Calcutta Catholic Elementary School | ELE | 3434 | 7257 | 7257-B01 | 81 HWY 9 RR 3 | WALKERTON | N0G2V0 | 35-15-41-622 | Brockton | Brockton M | Bruce Co | BRUCE | Southwest | South | 44.1155 | -81.1478 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1259260 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259260 | 1259260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259260 | 1259260 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-005 | 35-005 | 35 | N/A | 67008 | Bruce-Grey CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3421 | 7248 | 7248-B01 | 18 PETER ST S | MILDMAY | N0G2J0 | 35-15-41-626 | South Bruce | South Bruce M | Bruce Co | BRUCE | Southwest | South | 44.0404 | -81.117 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 52 | - | - | N | - | Not Required | - | 1901428 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 244957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244957 | 0 | 0 | 518998 | 0 | 1137473 | 0 | 0 | 0 | 0 | 0 | 1656471 | 1901428 | 1901428 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1137473
35-007 | 35-007 | 35 | N/A | 67008 | Bruce-Grey CDSB | Sacred Heart | Sacred Heart Catholic Secondary School | SEC | 3661 | 7425 | 7425-B01 | 450 ROBINSON ST | WALKERTON | N0G2V0 | 35-15-41-622 | Brockton | Brockton M | Bruce Co | BRUCE | Southwest | South | 44.1272 | -81.1436 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 540006 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79718 | 79718 | 460288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460288 | 540006 | 540006 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-008 | 35-008 | 35 | N/A | 67008 | Bruce-Grey CDSB | Sacred Heart | Sacred Heart Catholic Secondary School | SEC | 3661 | 7425 | 7425-B01 | 450 ROBINSON ST | WALKERTON | N0G2V0 | 35-15-41-622 | Brockton | Brockton M | Bruce Co | BRUCE | Southwest | South | 44.1272 | -81.1436 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 42 | - | - | N | - | Not Required | - | 2159773 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 1441674 | 0 | 0 | 90765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627334 | 2159773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159773 | 2159773 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-010 | 35-010 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Basil's | St. Basil's Catholic Elementary School | ELE | 3787 | 5017 | 5017-B01 | 925 9TH AVE W | OWEN SOUND | N4K4N8 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5637 | -80.9608 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2111700 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 93663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398174 | 491837 | 1619863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1619863 | 2111700 | 2111700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-011 | 35-011 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Basil's | St. Basil's Catholic Elementary School | ELE | 3787 | 5017 | 5017-B01 | 925 9TH AVE W | OWEN SOUND | N4K4N8 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5637 | -80.9608 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1486403 | Construction Complete | Addition | Other | 2011-12 | 40787 | 170357 | 0 | 0 | 411034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581391 | 0 | 0 | 905012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905012 | 1486403 | 1486403 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-012 | 35-012 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Joseph's | St. Joseph's Catholic Elementary School | ELE | 3595 | 7372 | 7372-B01 | 584 STAFFORD ST | PORT ELGIN | N0H2C0 | 35-15-41-408 | Saugeen Shores | Saugeen Shores T | Bruce Co | BRUCE | Southwest | South | 44.4369 | -81.3926 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Not Required | - | 1317862 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 335428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335428 | 0 | 0 | 193184 | 0 | 789250 | 0 | 0 | 0 | 0 | 0 | 982434 | 1317862 | 1317862 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 789250
35-013 | 35-013 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 3786 | 7519 | 7519-B01 | 555 15TH ST E | OWEN SOUND | N4K1X2 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5739 | -80.9341 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3946263 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99071 | 99071 | 3847192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847192 | 3946263 | 3946263 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-014 | 35-014 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 3786 | 7519 | 7519-B01 | 555 15TH ST E | OWEN SOUND | N4K1X2 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5739 | -80.9341 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3953664 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3953664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3953664 | 3953664 | 3953664 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-015 | 35-015 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 3786 | 7519 | 7519-B01 | 555 15TH ST E | OWEN SOUND | N4K1X2 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5739 | -80.9341 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 697770 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697770 | 697770 | 697770 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-016 | 35-016 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Peter's & St. Paul's | St. Peter's & St. Paul's Catholic Elementary School | ELE | 3184 | 7095 | 7095-B01 | 190 JOHN ST W | DURHAM | N0G1R0 | 35-15-47-624 | West Grey | West Grey M | Grey Co | GREY | Southwest | South | 44.1851 | -80.8221 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2308459 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84637 | 84637 | 727071 | 0 | 0 | 0 | 0 | 1496751 | 0 | 0 | 0 | 0 | 2223822 | 2308459 | 2308459 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
35-017 | 35-017 | 35 | 213 - CMSM Bruce | 67008 | Bruce-Grey CDSB | St. Teresa of Calcutta | St. Teresa of Calcutta Catholic Elementary School | ELE | 3434 | 7257 | 7257-B01 | 81 HWY 9 RR 3 | WALKERTON | N0G2V0 | 35-15-41-622 | Brockton | Brockton M | Bruce Co | BRUCE | Southwest | South | 44.1155 | -81.1478 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43879 | 1628489 | Construction Complete | Addition | Child Care | 2020-21 | 44136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628489 | 0 | 0 | 0 | 1628489 | 1628489 | 1628489 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1628489
35-018 | 35-018 | 35 | 213 - CMSM Bruce | 67008 | Bruce-Grey CDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 3768 | 7504 | 7504-B01 | 709 RUSSELL ST | KINCARDINE | N2Z1R1 | 35-15-41-625 | Kincardine | Kincardine M | Bruce Co | BRUCE | Southwest | South | 44.1702 | -81.6228 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 190 | 4 | 78 | Y | - | Approved | 44629 | 13799950 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44927 | 353253 | 289024 | 0 | 3451238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4093515 | 0 | 0 | 0 | 0 | 6376505 | 0 | 3329930 | 0 | 0 | 0 | 9706435 | 13799950 | 13799950 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9706435
35-019 | 35-019 | 35 | 215 - CMSM Grey | 67008 | Bruce-Grey CDSB | St. Basil's | St. Basil's Catholic Elementary School | ELE | 3787 | 5017 | 5017-B01 | 925 9TH AVE W | OWEN SOUND | N4K4N8 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5637 | -80.9608 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 78 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2077180 | 0 | 0 | 0 | 2077180 | 2077180 | 2077180 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2077180
35-020 | 35-020 | 35 | 215 - CMSM Grey | 67008 | Bruce-Grey CDSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 3464 | 7276 | 7276-B01 | 885 25TH ST E | OWEN SOUND | N4K6X6 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5887 | -80.9224 | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43223 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 78 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2077180 | 0 | 0 | 0 | 2077180 | 2077180 | 2077180 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2077180
35-021 | 35-021 | 35 | N/A | 67008 | Bruce-Grey CDSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 7519 | 7519 | 7519-B02 | 555 15TH ST E | OWEN SOUND | N4K1X2 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5739 | -80.9341 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 1012 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2027-28 | 46631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36097630 | 0 | 0 | 0 | 0 | 0 | 36097630 | 36097630 | 36097630 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 36097630
36-001 | 36-001 | 36 | N/A | 67016 | Huron Perth CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15770 | 18086 | 18086-B01 | 3927 PERTH RD RR 180 | DUBLIN | N0K1E0 | 35-15-52-408 | Huron East | Huron East M | Huron Co | HURON | Southwest | South | 43.5004 | -81.289 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-002 | 36-002 | 36 | N/A | 67016 | Huron Perth CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15770 | 18086 | 18086-B01 | 3927 PERTH RD RR 180 | DUBLIN | N0K1E0 | 35-15-52-408 | Huron East | Huron East M | Huron Co | HURON | Southwest | South | 43.5004 | -81.289 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1229554 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243277 | 1243277 | 1229554 | -13723 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-003 | 36-003 | 36 | N/A | 67016 | Huron Perth CDSB | Holy Name of Mary | Holy Name of Mary Catholic Elementary School | ELE | 3299 | 7167 | 7167-B01 | 161 PEEL ST N | ST MARYS | N4X1B2 | 35-15-65-301 | St. Marys | St. Marys ST | Perth Co | PERTH | Southwest | South | 43.2643 | -81.1398 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1356609 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64625 | 64625 | 1291984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1291984 | 1356609 | 1356609 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-004 | 36-004 | 36 | N/A | 67016 | Huron Perth CDSB | Jeanne Sauvé | Jeanne Sauvé Catholic Elementary School | ELE | 4300 | 7891 | 7891-B01 | 8 GRANGE ST | STRATFORD | N5A3P6 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3686 | -80.9793 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1286037 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140637 | 140637 | 1145400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1145400 | 1286037 | 1286037 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-007 | 36-007 | 36 | N/A | 67016 | Huron Perth CDSB | Precious Blood | Precious Blood Catholic Elementary School | ELE | 3207 | 7109 | 7109-B01 | 133 SANDERS ST W SS 2 | EXETER | N0M1S2 | 35-15-52-407 | South Huron | South Huron M | Huron Co | HURON | Southwest | South | 43.3466 | -81.4855 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1303662 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84569 | 84569 | 1219093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1219093 | 1303662 | 1303662 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-008 | 36-008 | 36 | N/A | 67016 | Huron Perth CDSB | Precious Blood | Precious Blood Catholic Elementary School | ELE | 3207 | 7109 | 7109-B01 | 133 SANDERS ST W SS 2 | EXETER | N0M1S2 | 35-15-52-407 | South Huron | South Huron M | Huron Co | HURON | Southwest | South | 43.3466 | -81.4855 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Not Required | - | 1067393 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481998 | 0 | 262720 | 0 | 0 | 0 | 0 | 0 | 744718 | 744718 | 1067393 | 322675 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 262720
36-009 | 36-009 | 36 | N/A | 67016 | Huron Perth CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 4598 | 8099 | 8099-B01 | 225 CORNYN ST | WINGHAM | N0G2W0 | 35-15-52-620 | North Huron | North Huron Tp | Huron Co | HURON | Southwest | South | 43.8799 | -81.308 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1395239 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102508 | 102508 | 0 | 0 | 479844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479844 | 582352 | 1395239 | 812887 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-010 | 36-010 | 36 | N/A | 67016 | Huron Perth CDSB | St. Anne's | St. Anne's Catholic Secondary School | SEC | 3737 | 7481 | 7481-B01 | 353 ONTARIO ST | CLINTON | N0M1L0 | 35-15-52-617 | Central Huron | Central Huron M | Huron Co | HURON | Southwest | South | 43.6138 | -81.5288 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2328851 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59675 | 59675 | 2269176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2269176 | 2328851 | 2328851 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-011 | 36-011 | 36 | N/A | 67016 | Huron Perth CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4130 | 7774 | 7774-B01 | 363 ST VINCENT ST S | STRATFORD | N5A2Y2 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.3626 | -80.9975 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2389538 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103210 | 103210 | 2286328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2286328 | 2389538 | 2389538 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-012 | 36-012 | 36 | N/A | 67016 | Huron Perth CDSB | St. Joseph's | St. Joseph's Catholic Elementary School | ELE | 10764 | 11978 | 11978-B01 | 297 SMITH ST N | CLINTON | N0M1L0 | 35-15-52-617 | Central Huron | Central Huron M | Huron Co | HURON | Southwest | South | 43.6156 | -81.5284 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4100926 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100926 | 4100926 | 4100926 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-013 | 36-013 | 36 | N/A | 67016 | Huron Perth CDSB | St. Joseph's | St. Joseph's Catholic Elementary School | ELE | 10764 | 11978 | 11978-B01 | 297 SMITH ST N | CLINTON | N0M1L0 | 35-15-52-617 | Central Huron | Central Huron M | Huron Co | HURON | Southwest | South | 43.6156 | -81.5284 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 78 | - | - | N | - | Not Required | - | 926428 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768705 | 0 | 0 | 0 | 0 | 0 | 1768705 | 1768705 | 926428 | -842277 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1768705
36-014 | 36-014 | 36 | N/A | 67016 | Huron Perth CDSB | St. Marys | St. Marys Catholic Elementary School | ELE | 4259 | 7866 | 7866-B01 | 70 BENNETT ST E | GODERICH | N7A1A4 | 35-15-52-403 | Goderich | Goderich T | Huron Co | HURON | Southwest | South | 43.7332 | -81.7076 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2429532 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 819342 | 819342 | 1610190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610190 | 2429532 | 2429532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-015 | 36-015 | 36 | N/A | 67016 | Huron Perth CDSB | St. Marys | St. Marys Catholic Elementary School | ELE | 4259 | 7866 | 7866-B01 | 70 BENNETT ST E | GODERICH | N7A1A4 | 35-15-52-403 | Goderich | Goderich T | Huron Co | HURON | Southwest | South | 43.7332 | -81.7076 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 549633 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101607 | 101607 | 0 | 0 | 448026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448026 | 549633 | 549633 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-016 | 36-016 | 36 | N/A | 67016 | Huron Perth CDSB | St. Mary's | St. Mary's Catholic Elementary School | ELE | 10765 | 11979 | 11979-B01 | 1209 TREMAINE AVE S RR 4 | LISTOWEL | N4W3G9 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.718 | -80.9509 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4011691 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815098 | 815098 | 3196593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3196593 | 4011691 | 4011691 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-017 | 36-017 | 36 | N/A | 67016 | Huron Perth CDSB | St. Mary's | St. Mary's Catholic Elementary School | ELE | 10765 | 11979 | 11979-B01 | 1209 TREMAINE AVE S RR 4 | LISTOWEL | N4W3G9 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.718 | -80.9509 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Not Required | - | 742881 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478024 | 0 | 570910 | 0 | 0 | 0 | 0 | 0 | 1048934 | 1048934 | 742881 | -306053 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 570910
36-018 | 36-018 | 36 | N/A | 67016 | Huron Perth CDSB | St. Michael | St. Michael Catholic Secondary School | SEC | 4298 | 8389 | 8389-B02 | 240 OAKDALE AVE | STRATFORD | N5A7W2 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.386 | -80.9953 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3408641 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3408641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3408641 | 3408641 | 3408641 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-019 | 36-019 | 36 | N/A | 67016 | Huron Perth CDSB | St. Michael | St. Michael Catholic Secondary School | SEC | 4298 | 8389 | 8389-B02 | 240 OAKDALE AVE | STRATFORD | N5A7W2 | 35-15-65-101 | Stratford | Stratford C | Perth Co | PERTH | Southwest | South | 43.386 | -80.9953 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3273276 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3273276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3273276 | 3273276 | 3273276 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-020 | 36-020 | 36 | N/A | 67016 | Huron Perth CDSB | Holy Name of Mary | Holy Name of Mary Catholic Elementary School | ELE | 3299 | 7167 | 7167-B01 | 161 PEEL ST N | ST MARYS | N4X1B2 | 35-15-65-301 | St. Marys | St. Marys ST | Perth Co | PERTH | Southwest | South | 43.2643 | -81.1398 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168000 | 1168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168000 | 1168000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
36-021 | 36-021 | 36 | 210 - CMSM Stratford | 67016 | Huron Perth CDSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 10765 | 11979 | 11979-B01 | 1209 TREMAINE AVE S RR 4 | LISTOWEL | N4W3G9 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.718 | -80.9509 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 49 | 4 | 64 | Y | 1 | Approved | 43621 | 3937720 | Construction Complete | Addition | Accommodation Pressure | 2020-21 | 44082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265616 | 0 | 2137683 | 534421 | 0 | 0 | 3937720 | 3937720 | 3937720 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3937720
37-001 | 37-001 | 37 | N/A | 67024 | Windsor-Essex CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 10666 | 8929 | 8929-B01 | 1325 CALIFORNIA AVE | WINDSOR | N9B3Y6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2956 | -83.0618 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524 | 0 | 0 | 0 | 0 | 0 | 524 | 524 | 0 | -524 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 524
37-002 | 37-002 | 37 | N/A | 67024 | Windsor-Essex CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 10666 | 8929 | 8929-B01 | 1325 CALIFORNIA AVE | WINDSOR | N9B3Y6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2956 | -83.0618 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 14694686 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15017440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15017440 | 15017440 | 14694686 | -322754 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-003 | 37-003 | 37 | N/A | 67024 | Windsor-Essex CDSB | Assumption | Assumption College Catholic Secondary School | SEC | 7844 | 8929 | 8929-B01 | 1100 HURON CHURCH RD | WINDSOR | N9C2K7 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2949 | -83.0616 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17482303 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 1800000 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 14382303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14382303 | 17482303 | 17482303 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-004 | 37-004 | 37 | N/A | 67024 | Windsor-Essex CDSB | FJ Brennan | FJ Brennan Catholic Secondary School | SEC | 7846 | 8931 | 8931-B01 | 910 RAYMO RD | WINDSOR | N8Y4A6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3253 | -82.976 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 13489405 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13489405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13489405 | 13489405 | 13489405 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-005 | 37-005 | 37 | N/A | 67024 | Windsor-Essex CDSB | HJ Lassaline | HJ Lassaline Catholic Elementary School | ELE | 7813 | 8899 | 8899-B01 | 3145 WILDWOOD DR | WINDSOR | N8R1Y1 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.302 | -82.9203 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1996188 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996188 | 1996188 | 1996188 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-006 | 37-006 | 37 | N/A | 67024 | Windsor-Essex CDSB | Holy Cross | Holy Cross Catholic Elementary School | ELE | 10165 | 10439 | 10439-B01 | 2555 SANDWICH WEST PKY | LASALLE | N9H2P7 | 35-15-45-408 | LaSalle | LaSalle T | Essex Co | ESSEX | Southwest | South | 42.2359 | -83.0225 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9180250 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9180250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9180250 | 9180250 | 9180250 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-007 | 37-007 | 37 | N/A | 67024 | Windsor-Essex CDSB | Holy Cross | Holy Cross Catholic Elementary School | ELE | 10165 | 10439 | 10439-B01 | 2555 SANDWICH WEST PKY | LASALLE | N9H2P7 | 35-15-45-408 | LaSalle | LaSalle T | Essex Co | ESSEX | Southwest | South | 42.2359 | -83.0225 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 827015 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827015 | 827015 | 827015 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-009 | 37-009 | 37 | N/A | 67024 | Windsor-Essex CDSB | Holy Name Essex | Holy Name Essex Catholic Elementary School | ELE | 10563 | 8469 | 8469-B01 | 200 FAIRVIEW AVE W | ESSEX | N8M1Y1 | 35-15-45-410 | Essex | Essex T | Essex Co | ESSEX | Southwest | South | 42.1647 | -82.8208 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8797759 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8797759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8797759 | 8797759 | 8797759 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-011 | 37-011 | 37 | N/A | 67024 | Windsor-Essex CDSB | Holy Names | Holy Names Catholic Secondary School | SEC | 7847 | 8932 | 8932-B01 | 1400 NORTHWOOD ST | WINDSOR | N9E1A4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2771 | -83.0332 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 62598 | Construction Complete | Retrofit | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62598 | 62598 | 62598 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-012 | 37-012 | 37 | N/A | 67024 | Windsor-Essex CDSB | Immaculate Conception | Immaculate Conception Catholic Elementary School | ELE | 7857 | 8940 | 8940-B01 | 465 VICTORIA AVE | WINDSOR | N9A3M7 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3148 | -83.0403 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 829273 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75148 | 0 | 754125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829273 | 829273 | 829273 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-014 | 37-014 | 37 | N/A | 67024 | Windsor-Essex CDSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 7819 | 8904 | 8904-B01 | 2751 PARTINGTON AVE | WINDSOR | N9E3A9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2691 | -83.0353 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3454827 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3454827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3454827 | 3454827 | 3454827 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-016 | 37-016 | 37 | N/A | 67024 | Windsor-Essex CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 7821 | 8906 | 8906-B01 | 1400 COUSINEAU RD | WINDSOR | N9G1V9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2434 | -83.0121 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 40641 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40641 | 40641 | 40641 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-017 | 37-017 | 37 | N/A | 67024 | Windsor-Essex CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 7821 | 8906 | 8906-B01 | 1400 COUSINEAU RD | WINDSOR | N9G1V9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2434 | -83.0121 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4835274 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4835274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4835274 | 4835274 | 4835274 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-018 | 37-018 | 37 | N/A | 67024 | Windsor-Essex CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 7821 | 8906 | 8906-B01 | 1400 COUSINEAU RD | WINDSOR | N9G1V9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2434 | -83.0121 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1190013 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190013 | 1190013 | 1190013 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-020-1 | 37-020 | 37 | N/A | 67024 | Windsor-Essex CDSB | Cardinal Carter | Cardinal Carter Catholic Secondary School | SEC | 3108 | 7043 | 7043-B01 | 120 ELLISON AVE | LEAMINGTON | N8H5C7 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0393 | -82.6135 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42828 | 3928642 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3796013 | 0 | 0 | 0 | 0 | 0 | 3796013 | 3796013 | 3796013 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3796013
37-020-2 | 37-020 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Louis | St. Louis Catholic Elementary School | ELE | 4172 | 7805 | 7805-B01 | 176 TALBOT ST E | LEAMINGTON | N8H1M2 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0545 | -82.5891 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44595 | 390520 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390520 | 0 | 0 | 0 | 0 | 0 | 390520 | 390520 | 390520 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 390520
37-023 | 37-023 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 7823 | 8908 | 8908-B01 | 1140 MONMOUTH RD | WINDSOR | N8Y3L9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3166 | -83.005 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 900000 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000 | 900000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-025 | 37-025 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 7823 | 8908 | 8908-B01 | 1140 MONMOUTH RD | WINDSOR | N8Y3L9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3166 | -83.005 | 41353 | 2012-13 | 2012-13 | 41353 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Cancelled | - | 45000 | Cancelled | Cancelled | Other | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-026 | 37-026 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Anne's | St. Anne's Catholic Secondary School | SEC | 10564 | 11170 | 11170-B01 | 1200 OAKWOOD AVE | BELLE RIVER | N0R1A0 | 35-15-45-412 | Lakeshore | Lakeshore T | Essex Co | ESSEX | Southwest | South | 42.289 | -82.7655 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 37958595 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500000 | 29458595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29458595 | 37958595 | 37958595 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-027 | 37-027 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 10565 | 3020 | 3020-B01 | 166 CENTRE ST W | HARROW | N0R1G0 | 35-15-45-410 | Essex | Essex T | Essex Co | ESSEX | Southwest | South | 42.0371 | -82.9213 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6295446 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6295446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6295446 | 6295446 | 6295446 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-028-01 | 37-028 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Teresa of Calcutta | St. Teresa of Calcutta Catholic Elementary School | ELE | 21881 | 8912 | 8912-B02 | 1860 CHANDLER RD | WINDSOR | N8W0A9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3076 | -82.9855 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 400 | - | - | N | - | Approved | 42612 | 8900040 | Construction Complete | New Construction | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489244 | 0 | 8410796 | 0 | 0 | 0 | 0 | 0 | 8900040 | 8900040 | 8900040 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8410796
37-028-02 | 37-028 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Teresa of Calcutta | St. Teresa of Calcutta Catholic Elementary School | ELE | 21881 | 8912 | 8912-L02 | 1860 CHANDLER RD | WINDSOR | N8W0A9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3076 | -82.9855 | 41921 | 2014-15 | 2014-15 | 41921 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41921 | 300000 | Construction Complete | Land Acquisition | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 572218 | 272218 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 300000
37-029 | 37-029 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Christopher | St. Christopher Catholic Elementary School | ELE | 7849 | 8934 | 8934-B01 | 1213 E C ROW AVE E | WINDSOR | N8W1Y6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2805 | -82.9931 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5069986 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5069986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5069986 | 5069986 | 5069986 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-032 | 37-032 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. James | St. James Catholic Elementary School | ELE | 7833 | 8918 | 8918-B01 | 1601 ST JAMES ST | WINDSOR | N9C3P6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2839 | -83.0613 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1418604 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1418604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1418604 | 1418604 | 1418604 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-033-1 | 37-033 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. James | St. James Catholic Elementary School | ELE | 7833 | 8918 | 8918-B01 | 1601 ST JAMES ST | WINDSOR | N9C3P6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2839 | -83.0613 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Approved | 43266 | 1289198 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518998 | 0 | 770200 | 0 | 0 | 0 | 0 | 0 | 1289198 | 1289198 | 1289198 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 770200
37-033-2 | 37-033 | 37 | N/A | 67024 | Windsor-Essex CDSB | Assumption | Assumption Catholic Secondary School | SEC | 7844 | 8929 | 8929-B01 | 1100 HURON CHURCH RD | WINDSOR | N9C2K7 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2949 | -83.0616 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 247283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247283 | 0 | 0 | 0 | 0 | 1832186 | 0 | 0 | 0 | 0 | 0 | 1832186 | 2079469 | 2079469 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1832186
37-034 | 37-034 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. John | St. John Facility Holding | HFA | 7834 | 8919 | 8919-B01 | 1920 GROVE AVE | WINDSOR | N9B1P6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3002 | -83.0539 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 749436 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749436 | 749436 | 749436 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-035 | 37-035 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. John de Brebeuf | St. John de Brebeuf Catholic Elementary School | ELE | 10522 | 7729 | 7729-B01 | 43 SPRUCE ST S | KINGSVILLE | N9Y1T8 | 35-15-45-411 | Kingsville | Kingsville T | Essex Co | ESSEX | Southwest | South | 42.0367 | -82.7345 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7970375 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7970375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7970375 | 7970375 | 7970375 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-037 | 37-037 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. John Vianney | St. John Vianney Catholic Elementary School | ELE | 7835 | 8920 | 8920-B01 | 8405 CEDARVIEW ST | WINDSOR | N8S1K9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.337 | -82.9397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4732728 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4732728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4732728 | 4732728 | 4732728 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-039 | 37-039 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Joseph's | St. Joseph's Catholic Secondary School | SEC | 10749 | 11964 | 11964-B01 | 2425 CLOVER AVE | WINDSOR | N8P2A3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.317 | -82.9118 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 44567795 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44567795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44567795 | 44567795 | 44567795 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-043 | 37-043 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Michael (Rhodes) | St. Michael (Rhodes) Catholic Secondary School | SEC | 11545 | 12219 | 12219-B01 | 3600 RHODES DR | WINDSOR | N8W5A4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2826 | -82.9668 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 733095 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733095 | 733095 | 733095 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-046 | 37-046 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Rose | St. Rose Catholic Elementary School | ELE | 7840 | 8925 | 8925-B01 | 871 ST ROSE AVE | WINDSOR | N8S1X4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.33 | -82.9542 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1282824 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282824 | 1282824 | 1282824 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-048 | 37-048 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Thomas of Villanova | St. Thomas of Villanova Catholic Secondary School | SEC | 4571 | 8084 | 8084-B01 | 2800 COUNTRY RD 8 | LASALLE | N9A6Z6 | 35-15-45-408 | LaSalle | LaSalle T | Essex Co | ESSEX | Southwest | South | 42.186 | -83.0397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 234864 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234864 | 234864 | 234864 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-049 | 37-049 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. Thomas of Villanova | St. Thomas of Villanova Catholic Secondary School | SEC | 4571 | 8084 | 8084-B01 | 2800 COUNTRY RD 8 | LASALLE | N9A6Z6 | 35-15-45-408 | LaSalle | LaSalle T | Essex Co | ESSEX | Southwest | South | 42.186 | -83.0397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4101457 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4101457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4101457 | 4101457 | 4101457 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-050 | 37-050 | 37 | N/A | 67024 | Windsor-Essex CDSB | St. William | St. William Catholic Elementary School | ELE | 4538 | 8058 | 8058-B01 | 1217 FAITH DR | EMERYVILLE | N0R1C0 | 35-15-45-412 | Lakeshore | Lakeshore T | Essex Co | ESSEX | Southwest | South | 42.2943 | -82.7607 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2417948 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2417948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2417948 | 2417948 | 2417948 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
37-053 | 37-053 | 37 | N/A | 67024 | Windsor-Essex CDSB | Stella Maris | Stella Maris Catholic Elementary School | ELE | 4540 | 8060 | 8060-B01 | 140 GIRARD ST | AMHERSTBURG | N9V2X3 | 35-15-45-409 | Amherstburg | Amherstburg T | Essex Co | ESSEX | Southwest | South | 42.1156 | -83.1067 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Approved | 42509 | 1755427 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349743 | 0 | 0 | 0 | 0 | 0 | 1349743 | 1349743 | 1349743 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1349743
37-054-01 | 37-054 | 37 | N/A | 67024 | Windsor-Essex CDSB | Catholic Central | Catholic Central Catholic Secondary School | SEC | 24591 | 19597 | 19597-B01 | 2465 MCDOUGALL ST | WINDSOR | N8X3N9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.29 | -83.0185 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 850 | - | - | N | - | Approved | 45075 | 31265793 | Under Construction | New Construction | Condition | 2022-23 | 44810 | 0 | 0 | 2015687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2015687 | 0 | 0 | 0 |  | 28557410 | 0 | 0 | 0 | 0 | 0 | 28557410 | 30573097 | 31265793 | 692696 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 28557410
37-054-02 | 37-054 | 37 | N/A | 67024 | Windsor-Essex CDSB | Catholic Central | Catholic Central Catholic Secondary School | SEC | 24591 | 19597 | 19597-L01 | 2465 MCDOUGALL ST | WINDSOR | N8X3N9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.29 | -83.0185 | 43630 | 2018-19 | 2019-20 | 43630 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43630 | 8084079 | Construction Complete | Land Acquisition | Condition | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8084079 | 0 | 0 | 0 | 0 | 0 | 0 | 8084079 | 8084079 | 8084079 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 8084079
37-055 | 37-055 | 37 | 212 - CMSM Windsor | 67024 | Windsor-Essex CDSB | St. Louis | St. Louis Catholic Elementary School | ELE | 4172 | 7805 | 7805-B01 | 176 TALBOT ST E | LEAMINGTON | N8H1M2 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0545 | -82.5891 | 43050 | 2017-18 | 2017-18 | - | - | - | 43921 | 2019-20 | 2019-20 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 147 | 3 | 63 | Y | - | Approved | 44890 | 7589289 | Under Construction | Addition | Accommodation Pressure | 2023-24 | 45170 | 124765 | 0 | 957060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1081825 | 0 | 0 | 0 | 0 | 4418614 | 0 | 2088850 | 0 | 0 | 0 | 6507464 | 7589289 | 7589289 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 6507464
37-056 | 37-056 | 37 | 212 - CMSM Windsor | 67024 | Windsor-Essex CDSB | Stella Maris | Stella Maris Catholic Elementary School | ELE | 4540 | 8060 | 8060-B01 | 140 GIRARD ST | AMHERSTBURG | N9V2X3 | 35-15-45-409 | Amherstburg | Amherstburg T | Essex Co | ESSEX | Southwest | South | 42.1156 | -83.1067 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43836 | 2117516 | Construction Complete | Addition | Child Care | 2021-22 | 44564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2117517 | 0 | 0 | 0 | 2117517 | 2117517 | 2117517 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2117517
37-057 | 37-057 | 37 | 212 - CMSM Windsor | 67024 | Windsor-Essex CDSB | St. Teresa of Calcutta | St. Teresa of Calcutta Catholic Elementary School | ELE | 21881 | 8912 | 8912-B02 | 1860 CHANDLER RD | WINDSOR | N8W0A9 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3076 | -82.9855 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 44574 | 2281554 | Under Construction | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281554 | 0 | 0 | 0 | 2281554 | 2281554 | 2281554 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2281554
38-001 | 38-001 | 38 | N/A | 67032 | London DCSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16130 | 7385 | 7385-B02 | 5200 WELLINGTON RD S | LONDON | N6E3X8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.8944 | -81.2013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-002 | 38-002 | 38 | N/A | 67032 | London DCSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16130 | 7385 | 7385-B02 | 5200 WELLINGTON RD S | LONDON | N6E3X8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.8944 | -81.2013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7112354 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848647 | 7848647 | 7112354 | -736293 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-003 | 38-003 | 38 | N/A | 67032 | London DCSB | Assumption | Assumption Catholic Elementary School | ELE | 3038 | 6995 | 6995-B01 | 42 SOUTH ST E | AYLMER | N5H1P6 | 35-15-44-401 | Aylmer | Aylmer T | Elgin Co | ELGIN | Southwest | South | 42.7701 | -80.9835 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2151871 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2151871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2151871 | 2151871 | 2151871 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-005 | 38-005 | 38 | N/A | 67032 | London DCSB | Catholic Central | Catholic Central Catholic Secondary School | SEC | 3119 | 7048 | 7048-B01 | 450 DUNDAS ST | LONDON | N6B3K3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9873 | -81.2395 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9657452 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9657452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9657452 | 9657452 | 9657452 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-006 | 11-103+38-006 | 38 | N/A | 67032 | London DCSB | Holy Cross | Holy Cross Catholic Secondary School | SEC | 10175 | 10446 | 10446-B01 | 367 SECOND ST | STRATHROY | N7G4K6 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.9806 | -81.6068 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12813709 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12813709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12813709 | 12813709 | 12813709 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-008 | 38-008 | 38 | N/A | 67032 | London DCSB | Holy Family | Holy Family Catholic Elementary School | ELE | 3288 | 7160 | 7160-B01 | 329 HUDSON DR | LONDON | N5V1E4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9916 | -81.1566 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1291463 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250596 | 40867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1291463 | 1291463 | 1291463 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-010 | 38-010 | 38 | N/A | 67032 | London DCSB | Jean Vanier | Jean Vanier Catholic Elementary School | ELE | 3351 | 7197 | 7197-B01 | 1019 VISCOUNT RD | LONDON | N6K1H5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9455 | -81.2938 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4214490 | Construction Complete | Addition | Other | 2007-08 | 39326 | 426465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281668 | 2708133 | 1457957 | 48400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506357 | 4214490 | 4214490 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-012 | 38-012 | 38 | N/A | 67032 | London DCSB | LDCSB Head Office | Administrative Office | OFF-ADM | 16130 | 7385 | 7385-B02 | 5200 WELLINGTON RD S | LONDON | N6E3X8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.8944 | -81.2013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9479883 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9479883 | 9479883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9479883 | 9479883 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-013 | 38-013 | 38 | N/A | 67032 | London DCSB | Monsignor Morrison | Monsignor Morrison Catholic Elementary School | ELE | 4601 | 8102 | 8102-B01 | 10 SOUTH EDGEWARE RD | ST THOMAS | N5P2H2 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7937 | -81.183 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 630492 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630492 | 630492 | 630492 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-014 | 38-014 | 38 | N/A | 67032 | London DCSB | Mother Teresa | Mother Teresa Catholic Secondary School | SEC | 10071 | 10382 | 10382-B01 | 1065 SUNNINGDALE RD E | LONDON | N5X4B1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0491 | -81.2519 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 26397688 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26397688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26397688 | 26397688 | 26397688 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-015 | 38-015 | 38 | N/A | 67032 | London DCSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 5884 | 8480 | 8480-B01 | 767 VALETTA ST | LONDON | N6H4N1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9755 | -81.301 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 61 | - | - | N | - | Not Required | - | 1775976 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895469 | 0 | 880507 | 0 | 0 | 0 | 0 | 0 | 1775976 | 1775976 | 1775976 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 880507
38-017 | 38-017 | 38 | N/A | 67032 | London DCSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 12019 | 12310 | 12310-B01 | 103 WELLINGTON ST | DELAWARE | N0L1E0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.9107 | -81.4095 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8421133 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 487297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487297 | 7933836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7933836 | 8421133 | 8421133 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-018 | 38-018 | 38 | N/A | 67032 | London DCSB | Regina Mundi | Regina Mundi Catholic Secondary School | SEC | 24858 | 7385 | 7385-B02 | 5250 WELLINGTON RD S | LONDON | N6E3X8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.8944 | -81.2013 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 700 | - | - | N | - | Approved | 45112 | 51605781 | Planned | New Construction | Condition | 2024-25 | 45538 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 50305781 | 0 | 0 | 0 | 0 | 0 | 50305781 | 51605781 | 51605781 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 50305781
38-020 | 38-020 | 38 | N/A | 67032 | London DCSB | Saint André Bessette | Saint André Bessette Catholic Secondary School | SEC | 24208 | 19200 | 19200-B01 | 2727 TOKALA TRAIL | LONDON | N6G0L8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0151 | -81.3284 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 27952157 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27952157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27952157 | 27952157 | 27952157 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-023 | 38-023 | 38 | N/A | 67032 | London DCSB | St. Anne's | St. Anne's Catholic Elementary School | ELE | 11078 | 7981 | 7981-B01 | 84 PARK AVE | ST THOMAS | N5R4W1 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7677 | -81.1703 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8763706 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 382678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382678 | 8381028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8381028 | 8763706 | 8763706 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-025-01 | 38-025 | 38 | N/A | 67032 | London DCSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 3745 | 7486 | 7486-B01 | 1380 ERNEST AVE | LONDON | N6E2H8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9311 | -81.2352 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 282 | - | - | N | - | Approved | 42139 | 7357027 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3768431 | 0 | 1235710 | 0 | 2352886 | 0 | 0 | 0 | 0 | 0 | 7357027 | 7357027 | 7357027 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2352886
38-025-02 | 38-025 | 38 | N/A | 67032 | London DCSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 3745 | 7486 | 7486-L01 | 1380 ERNEST AVE | LONDON | N6E2H8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9311 | -81.2352 | 42139 | 2014-15 | 2015-16 | 42139 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42139 | 129870 | Construction Complete | Land Acquisition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129870 | 0 | 0 | 0 | 0 | 0 | 0 | 129870 | 129870 | 129870 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 129870
38-027 | 38-027 | 38 | N/A | 67032 | London DCSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 10621 | 11242 | 11242-B01 | 2140 QUARRIER RD | LONDON | N6G5L4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0315 | -81.2902 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7239088 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7239088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7239088 | 7239088 | 7239088 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-028 | 38-028 | 38 | N/A | 67032 | London DCSB | St. Charles | St. Charles Catholic Elementary School | ELE | 3846 | 7562 | 7562-B01 | 257 ELIZABETH ST | GLENCOE | N0L1M0 | 35-15-59-620 | Southwest Middlesex | Southwest Middlesex M | Middlesex Co | MIDDLESEX | Southwest | South | 42.7531 | -81.7112 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1745695 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1690705 | 54990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1745695 | 1745695 | 1745695 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-029 | 38-029 | 38 | N/A | 67032 | London DCSB | St. David | St. David Catholic Elementary School | ELE | 3883 | 7591 | 7591-B01 | 3966 CATHERINE ST | DORCHESTER | N0G1G0 | 35-15-59-622 | Thames Centre | Thames Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.9891 | -81.0708 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1896305 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1896305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1896305 | 1896305 | 1896305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-030 | 38-030 | 38 | N/A | 67032 | London DCSB | St. David | St. David Catholic Elementary School | ELE | 3883 | 7591 | 7591-B01 | 3966 CATHERINE ST | DORCHESTER | N0G1G0 | 35-15-59-622 | Thames Centre | Thames Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.9891 | -81.0708 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 896920 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896920 | 896920 | 896920 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-032 | 38-032 | 38 | 206 - CMSM London | 67032 | London DCSB | St. Francis | St. Francis Catholic Elementary School | ELE | 3937 | 7634 | 7634-B01 | 690 OSGOODE DR | LONDON | N6E2G2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9439 | -81.2084 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | N | 3 | Not Required | - | 0 | Construction Complete | Retrofit | Condition | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163665 | 163665 | 0 | 0 | 0 | 0 | 440975 | 0 | 0 | 741427 | 0 | 0 | 1182402 | 1346067 | 1346067 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1182402
38-035-01 | 38-035 | 38 | 206 - CMSM London | 67032 | London DCSB | St. John | St. John Catholic Elementary School | ELE | 24287 | 19279 | 19279-B01 | 1212 CORONATION DR | LONDON | N6G0G5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9958 | -81.3232 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 504 | 5 | 88 | N | - | Approved | 42284 | 12062320 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425858 | 0 | 8165100 | 0 | 2422961 | 0 | 0 | 0 | 12013919 | 12013919 | 12013919 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10588061
38-035-02 | 38-035 | 38 | N/A | 67032 | London DCSB | St. John | St. John Catholic Elementary School | ELE | 24287 | 19279 | 19279-L01 | 1212 CORONATION DR | LONDON | N6G0G5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9958 | -81.3232 | 41850 | 2013-14 | 2014-15 | 41850 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41850 | 1398589 | Construction Complete | Land Acquisition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398589 | 0 | 0 | 0 | 0 | 0 | 0 | 1398589 | 1398589 | 1398589 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1398589
38-037 | 38-037 | 38 | N/A | 67032 | London DCSB | St. Joseph's | St. Joseph's Catholic Secondary School | SEC | 4119 | 7767 | 7767-B01 | 100 BILL MARTYN PKY | ST THOMAS | N5R6A7 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7544 | -81.1693 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4826614 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4826614 | 0 | 0 | 0 | 0 | 4826614 | 4826614 | 4826614 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-038 | 38-038 | 38 | N/A | 67032 | London DCSB | St. Joseph's | St. Joseph's Catholic Elementary School | ELE | 4146 | 7786 | 7786-B01 | 31 FRANCES ST | TILLSONBURG | N4G1E8 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8739 | -80.722 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1928278 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928278 | 1928278 | 1928278 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-040 | 38-040 | 38 | N/A | 67032 | London DCSB | St. Jude | St. Jude Catholic Elementary School | ELE | 4152 | 7790 | 7790-B01 | 690 VISCOUNT RD | LONDON | N6J2Y5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9491 | -81.2691 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1208693 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1208693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1208693 | 1208693 | 1208693 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-042 | 38-042 | 38 | N/A | 67032 | London DCSB | St. Jude's | St. Jude's Catholic Elementary School | ELE | 4151 | 7789 | 7789-B01 | 30 CAFFYN ST | INGERSOLL | N5C3T9 | 35-15-37-401 | Ingersoll | Ingersoll T | Oxford Co | OXFORD | Southwest | South | 43.0296 | -80.8659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4234842 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4234842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4234842 | 4234842 | 4234842 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-046 | 38-046 | 38 | N/A | 67032 | London DCSB | St. Mark | St. Mark Catholic Elementary School | ELE | 4217 | 7835 | 7835-B01 | 1440 GLENORA DR | LONDON | N5X1V2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0351 | -81.2361 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1228584 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228584 | 1228584 | 1228584 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-049 | 38-049 | 38 | N/A | 67032 | London DCSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 4284 | 5032 | 5032-B01 | 431 JULIANA DR | WOODSTOCK | N4V1E8 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1139 | -80.7507 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1795761 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1795761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1795761 | 1795761 | 1795761 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-051 | 38-051 | 38 | N/A | 67032 | London DCSB | St. Michael's | St. Michael's Catholic Elementary School | ELE | 4286 | 7878 | 7878-B01 | 1085 DEVONSHIRE AVE | WOODSTOCK | N4S5S1 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1471 | -80.7322 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2755420 | Construction Complete | Addition | Other | 2008-09 | 39692 | 643326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643326 | 2112094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112094 | 2755420 | 2755420 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-053 | 38-053 | 38 | N/A | 67032 | London DCSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 24194 | 19186 | 19186-B01 | 1956 SHORE RD | LONDON | N6K0E8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9689 | -81.3623 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 401 | - | - | N | - | Not Required | - | 8299910 | Construction Complete | New Construction | Condition | 2014-15 | 41885 | 0 | 0 | 157265 | 0 | 712470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869735 | 0 | 0 | 470 | 0 | 7429705 | 0 | 0 | 0 | 0 | 0 | 7430175 | 8299910 | 8299910 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7429705
38-055 | 38-055 | 38 | N/A | 67032 | London DCSB | St. Patrick's | St. Patrick's Catholic Elementary School | ELE | 4353 | 7928 | 7928-B01 | 344 PARKINSON RD | WOODSTOCK | N4S2N6 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1168 | -80.7581 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3765677 | Construction Complete | Addition | Other | 2008-09 | 39692 | 1559556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559556 | 2206121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2206121 | 3765677 | 3765677 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-056 | 38-056 | 38 | N/A | 67032 | London DCSB | St. Paul | St. Paul Catholic Elementary School | ELE | 4375 | 7940 | 7940-B01 | 1090 GUILDWOOD BLVD | LONDON | N6H4G6 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.978 | -81.3186 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3932603 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3908403 | 24200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932603 | 3932603 | 3932603 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-061 | 38-061 | 38 | N/A | 67032 | London DCSB | St. Theresa | St. Theresa Catholic Elementary School | ELE | 3397 | 7232 | 7232-B01 | 108 FAIRLANE AVE | LONDON | N6K3E6 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9483 | -81.3391 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1422515 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422515 | 1422515 | 1422515 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-064 | 38-064 | 38 | 209 - CMSM St. Thomas | 67032 | London DCSB | Assumption | Assumption Catholic Elementary School | ELE | 3038 | 6995 | 6995-B01 | 42 SOUTH ST E | AYLMER | N5H1P6 | 35-15-44-401 | Aylmer | Aylmer T | Elgin Co | ELGIN | Southwest | South | 42.7701 | -80.9835 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | Y | - | Approved | 44858 | 3128734 | Under Construction | Retrofit | Child Care | 2022-23 | 44927 | 100000 | 0 | 29607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129607 | 0 | 0 | 533321 | 0 | 0 | 0 | 2465806 | 0 | 0 | 0 | 2999127 | 3128734 | 3128734 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2465806
38-065 | 38-065 | 38 | 206 - CMSM London | 67032 | London DCSB | Blessed Sacrament | Blessed Sacrament Catholic Elementary School | ELE | 3076 | 7019 | 7019-B01 | 1063 OXFORD ST E | LONDON | N5Y3L4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0053 | -81.2182 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181583 | 0 | 0 | 0 | 181583 | 181583 | 181583 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 181583
38-066 | 38-066 | 38 | N/A | 67032 | London DCSB | North London | North London Catholic Elementary School | ELE | 24839 | 19845 | 19845-B01 | 3055 BUROAK DR | LONDON | TBD | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.032 | -81.2921 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 504 | - | - | N | - | Approved | 45093 | 22352581 | Under Construction | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028507 | 0 | 21324074 | 0 | 0 | 0 | 0 | 0 | 22352581 | 22352581 | 22352581 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 21324074
38-067 | 38-067 | 38 | N/A | 67032 | London DCSB | St. Bernadette | St. Bernadette Catholic Elementary School | ELE | 3799 | 7529 | 7529-B01 | 155 TWEEDSMUIR AVE | LONDON | N5W1K9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9818 | -81.1834 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 69 | - | - | N | - | Approved | 43621 | 3427507 | Construction Complete | Addition | Consolidation | 2021-22 | 44446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3719304 | 0 | 0 | 0 | 0 | 0 | 3719304 | 3719304 | 3719304 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3719304
38-068-1 | 38-068-1 | 38 | N/A | 67032 | London DCSB | Assumption | Assumption Catholic Elementary School | ELE | 3038 | 6995 | 6995-B01 | 42 SOUTH ST E | AYLMER | N5H1P6 | 35-15-44-401 | Aylmer | Aylmer T | Elgin Co | ELGIN | Southwest | South | 42.7701 | -80.9835 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 60000 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000 | 60000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 60000
38-068-10 | 38-068-10 | 38 | N/A | 67032 | London DCSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 10621 | 11242 | 11242-B01 | 2140 QUARRIER RD | LONDON | N6G5L4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0315 | -81.2902 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 29000 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | 0 | 0 | 0 | 0 | 0 | 29000 | 29000 | 29000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 29000
38-068-11 | 38-068-11 | 38 | N/A | 67032 | London DCSB | St. Francis | St. Francis Catholic Elementary School | ELE | 3937 | 7634 | 7634-B01 | 690 OSGOODE DR | LONDON | N6E2G2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9439 | -81.2084 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 270587 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270587 | 0 | 0 | 0 | 0 | 0 | 270587 | 270587 | 270587 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 270587
38-068-12 | 38-068-12 | 38 | N/A | 67032 | London DCSB | St. John | St. John Catholic Elementary School | ELE | 24287 | 19279 | 19279-B01 | 1212 CORONATION DR | LONDON | N6G0G5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9958 | -81.3232 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 22000 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 22000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 22000
38-068-13 | 38-068-13 | 38 | N/A | 67032 | London DCSB | St. Joseph's | St. Joseph's Catholic Elementary School | ELE | 4146 | 7786 | 7786-B01 | 31 FRANCES ST | TILLSONBURG | N4G1E8 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8739 | -80.722 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 122793 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122793 | 0 | 0 | 0 | 0 | 0 | 122793 | 122793 | 122793 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 122793
38-068-14 | 38-068-14 | 38 | N/A | 67032 | London DCSB | St. Jude's | St. Jude's Catholic Elementary School | ELE | 4151 | 7789 | 7789-B01 | 30 CAFFYN ST | INGERSOLL | N5C3T9 | 35-15-37-401 | Ingersoll | Ingersoll T | Oxford Co | OXFORD | Southwest | South | 43.0296 | -80.8659 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 58934 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58934 | 0 | 0 | 0 | 0 | 0 | 58934 | 58934 | 58934 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 58934
38-068-15 | 38-068-15 | 38 | N/A | 67032 | London DCSB | St. Kateri | St. Kateri Catholic Elementary School | ELE | 3072 | 7015 | 7015-B01 | 220 SUNNYSIDE DR | LONDON | N5X3R1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0237 | -81.2643 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 33442 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33442 | 0 | 0 | 0 | 0 | 0 | 33442 | 33442 | 33442 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 33442
38-068-16 | 38-068-16 | 38 | N/A | 67032 | London DCSB | St. Marguerite d’Youville | St. Marguerite d’Youville Catholic Elementary School | ELE | 4207 | 7828 | 7828-B01 | 170 HAWTHORNE RD | LONDON | N6G4Z9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0066 | -81.321 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 128381 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128381 | 0 | 0 | 0 | 0 | 0 | 128381 | 128381 | 128381 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 128381
38-068-17 | 38-068-17 | 38 | N/A | 67032 | London DCSB | St. Mark | St. Mark Catholic Elementary School | ELE | 4217 | 7835 | 7835-B01 | 1440 GLENORA DR | LONDON | N5X1V2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0351 | -81.2361 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 213969 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213969 | 0 | 0 | 0 | 0 | 0 | 213969 | 213969 | 213969 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 213969
38-068-18 | 38-068-18 | 38 | N/A | 67032 | London DCSB | St. Michael's | St. Michael's Catholic Elementary School | ELE | 4286 | 7878 | 7878-B01 | 1085 DEVONSHIRE AVE | WOODSTOCK | N4S5S1 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1471 | -80.7322 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 74793 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74793 | 0 | 0 | 0 | 0 | 0 | 74793 | 74793 | 74793 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 74793
38-068-19 | 38-068-19 | 38 | N/A | 67032 | London DCSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4301 | 7892 | 7892-B01 | 926 MAITLAND ST | LONDON | N5Y2X1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0042 | -81.2446 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 101626 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101626 | 0 | 0 | 0 | 0 | 0 | 101626 | 101626 | 101626 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 101626
38-068-2 | 38-068-2 | 38 | N/A | 67032 | London DCSB | Blessed Sacrament | Blessed Sacrament Catholic Elementary School | ELE | 3076 | 7019 | 7019-B01 | 1063 OXFORD ST E | LONDON | N5Y3L4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0053 | -81.2182 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 42793 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42793 | 0 | 0 | 0 | 0 | 0 | 42793 | 42793 | 42793 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 42793
38-068-20 | 38-068-20 | 38 | N/A | 67032 | London DCSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 24194 | 19186 | 19186-B01 | 1956 SHORE RD | LONDON | N6K0E8 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9689 | -81.3623 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 16346 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16346 | 0 | 0 | 0 | 0 | 0 | 16346 | 16346 | 16346 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 16346
38-068-21 | 38-068-21 | 38 | N/A | 67032 | London DCSB | St. Patrick's | St. Patrick's Catholic Elementary School | ELE | 4353 | 7928 | 7928-B01 | 344 PARKINSON RD | WOODSTOCK | N4S2N6 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1168 | -80.7581 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 59793 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59793 | 0 | 0 | 0 | 0 | 0 | 59793 | 59793 | 59793 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 59793
38-068-22 | 38-068-22 | 38 | N/A | 67032 | London DCSB | St. Pius X | St. Pius X Catholic Elementary School | ELE | 4432 | 7976 | 7976-B01 | 255 VANCOUVER ST | LONDON | N5W4R9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9938 | -81.1854 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 42793 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42793 | 0 | 0 | 0 | 0 | 0 | 42793 | 42793 | 42793 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 42793
38-068-23 | 38-068-23 | 38 | N/A | 67032 | London DCSB | St. Theresa | St. Theresa Catholic Elementary School | ELE | 3397 | 7232 | 7232-B01 | 108 FAIRLANE AVE | LONDON | N6K3E6 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9483 | -81.3391 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 105587 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105587 | 0 | 0 | 0 | 0 | 0 | 105587 | 105587 | 105587 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 105587
38-068-24 | 38-068-24 | 38 | N/A | 67032 | London DCSB | St. Thomas More | St. Thomas More Catholic Elementary School | ELE | 4507 | 8033 | 8033-B01 | 18 WYCHWOOD PK | LONDON | N6G1R5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.999 | -81.2896 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 42793 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42793 | 0 | 0 | 0 | 0 | 0 | 42793 | 42793 | 42793 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 42793
38-068-3 | 38-068-3 | 38 | N/A | 67032 | London DCSB | Jean Vanier | Jean Vanier Catholic Elementary School | ELE | 3351 | 7197 | 7197-B01 | 1019 VISCOUNT RD | LONDON | N6K1H5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9455 | -81.2938 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 97999 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97999 | 0 | 0 | 0 | 0 | 0 | 97999 | 97999 | 97999 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 97999
38-068-4 | 38-068-4 | 38 | N/A | 67032 | London DCSB | Monsignor JH O'Neil | Monsignor JH O'Neil Catholic Elementary School | ELE | 3427 | 7252 | 7252-B01 | 250 QUARTER TOWN LINE RR 3 | TILLSONBURG | N4G4G8 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8707 | -80.7501 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 63174 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63174 | 0 | 0 | 0 | 0 | 0 | 63174 | 63174 | 63174 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 63174
38-068-5 | 38-068-5 | 38 | N/A | 67032 | London DCSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 5884 | 8480 | 8480-B01 | 767 VALETTA ST | LONDON | N6H4N1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9755 | -81.301 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 9000 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9000
38-068-6 | 38-068-6 | 38 | N/A | 67032 | London DCSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 12019 | 12310 | 12310-B01 | 103 WELLINGTON ST | DELAWARE | N0L1E0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 42.9107 | -81.4095 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 42793 | Construction Complete | Other | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42793 | 0 | 0 | 0 | 0 | 0 | 42793 | 42793 | 42793 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 42793
38-068-7 | 38-068-7 | 38 | N/A | 67032 | London DCSB | Sir Arthur Carty | Sir Arthur Carty Catholic Elementary School | ELE | 3671 | 7433 | 7433-B01 | 1655 ERNEST AVE | LONDON | N6E2S3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9377 | -81.2391 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 17469 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17469 | 0 | 0 | 0 | 0 | 0 | 17469 | 17469 | 17469 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 17469
38-068-8 | 38-068-8 | 38 | N/A | 67032 | London DCSB | St. Anne's | St. Anne's Catholic Elementary School | ELE | 11078 | 7981 | 7981-B01 | 84 PARK AVE | ST THOMAS | N5R4W1 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7677 | -81.1703 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 10000 | Construction Complete | Retrofit | Other | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10000
38-068-9 | 38-068-9 | 38 | N/A | 67032 | London DCSB | St. Bernadette | St. Bernadette Catholic Elementary School | ELE | 3799 | 7529 | 7529-B01 | 155 TWEEDSMUIR AVE | LONDON | N5W1K9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9818 | -81.1834 | 43433 | 2018-19 | 2018-19 | - | - | - | 43433 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 85586 | Construction Complete | Other | Other | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85586 | 0 | 0 | 0 | 0 | 0 | 85586 | 85586 | 85586 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 85586
38-069-1 | 38-069-1 | 38 | N/A | 67032 | London DCSB | Jean Vanier | Jean Vanier Catholic Elementary School | ELE | 3351 | 7197 | 7197-B01 | 1019 VISCOUNT RD | LONDON | N6K1H5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9455 | -81.2938 | 43903 | 2019-20 | 2019-20 | - | - | - | 43903 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 104000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 104000 | 104000 | 104000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 104000
38-069-10 | 38-069-10 | 38 | N/A | 67032 | London DCSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 4342 | 7920 | 7920-B01 | 33654 ROMAN LINE | LUCAN | N0M2J0 | 35-15-59-617 | Lucan Biddulph | Lucan Biddulph Tp | Middlesex Co | MIDDLESEX | Southwest | South | 43.1746 | -81.3692 | 44068 | 2019-20 | 2020-21 | - | - | - | 44068 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 52000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 52000 | 52000 | 52000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 52000
38-069-11 | 38-069-11 | 38 | N/A | 67032 | London DCSB | St. Patrick's | St. Patrick's Catholic Elementary School | ELE | 4353 | 7928 | 7928-B01 | 344 PARKINSON RD | WOODSTOCK | N4S2N6 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1168 | -80.7581 | 44068 | 2019-20 | 2020-21 | - | - | - | 44068 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 412000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 314212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314212 | 0 | 0 | 0 | 0 | 97788 | 0 | 0 | 0 | 0 | 0 | 97788 | 412000 | 412000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 97788
38-069-12 | 38-069-12 | 38 | N/A | 67032 | London DCSB | St. Joseph's | St. Joseph's Catholic Elementary School | ELE | 4146 | 7786 | 7786-B01 | 31 FRANCES ST | TILLSONBURG | N4G1E8 | 35-15-37-402 | Tillsonburg | Tillsonburg T | Oxford Co | OXFORD | Southwest | South | 42.8739 | -80.722 | 44068 | 2019-20 | 2020-21 | - | - | - | 44068 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 104000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 104000 | 104000 | 104000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 104000
38-069-2 | 38-069-2 | 38 | N/A | 67032 | London DCSB | St. Anne's | St. Anne's Catholic Elementary School | ELE | 11078 | 7981 | 7981-B01 | 84 PARK AVE | ST THOMAS | N5R4W1 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7677 | -81.1703 | 43903 | 2019-20 | 2019-20 | - | - | - | 43903 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 104000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 104000 | 104000 | 104000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 104000
38-069-3 | 38-069-3 | 38 | N/A | 67032 | London DCSB | St. Kateri | St. Kateri Catholic Elementary School | ELE | 3072 | 7015 | 7015-B01 | 220 SUNNYSIDE DR | LONDON | N5X3R1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0237 | -81.2643 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled | - | 0 | Cancelled | Cancelled | Other | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-069-4 | 38-069-4 | 38 | N/A | 67032 | London DCSB | St. John | St. John Catholic Elementary School | ELE | 24287 | 19279 | 19279-B01 | 1212 CORONATION DR | LONDON | N6G0G5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9958 | -81.3232 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled | - | 0 | Cancelled | Cancelled | Other | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-069-5 | 38-069-5 | 38 | N/A | 67032 | London DCSB | St. Mark | St. Mark Catholic Elementary School | ELE | 4217 | 7835 | 7835-B01 | 1440 GLENORA DR | LONDON | N5X1V2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0351 | -81.2361 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled | - | 0 | Cancelled | Cancelled | Other | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-069-6 | 38-069-6 | 38 | N/A | 67032 | London DCSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4301 | 7892 | 7892-B01 | 926 MAITLAND ST | LONDON | N5Y2X1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0042 | -81.2446 | 43903 | 2019-20 | 2019-20 | - | - | - | 43903 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 52000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 52000 | 52000 | 52000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 52000
38-069-7 | 38-069-7 | 38 | N/A | 67032 | London DCSB | St. Michael's | St. Michael's Catholic Elementary School | ELE | 4286 | 7878 | 7878-B01 | 1085 DEVONSHIRE AVE | WOODSTOCK | N4S5S1 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1471 | -80.7322 | 43903 | 2019-20 | 2019-20 | - | - | - | 43903 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 52000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 52000 | 52000 | 52000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 52000
38-069-8 | 38-069-8 | 38 | N/A | 67032 | London DCSB | Blessed Sacrament | Blessed Sacrament Catholic Elementary School | ELE | 3076 | 7019 | 7019-B01 | 1063 OXFORD ST E | LONDON | N5Y3L4 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0053 | -81.2182 | 44068 | 2019-20 | 2020-21 | - | - | - | 44068 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 104000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | 104000 | 104000 | 104000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 104000
38-069-9 | 38-069-9 | 38 | N/A | 67032 | London DCSB | St. Theresa | St. Theresa Catholic Elementary School | ELE | 3397 | 7232 | 7232-B01 | 108 FAIRLANE AVE | LONDON | N6K3E6 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9483 | -81.3391 | 44068 | 2019-20 | 2020-21 | - | - | - | 44068 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44068 | 52000 | Construction Complete | Other | Other | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 52000 | 52000 | 52000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 52000
38-070 | 38-070 | 38 | 206 - CMSM London | 67032 | London DCSB | Northeast London | Northeast London Catholic Elementary School | ELE | 25387 | 20393 | 20393-B01 | TBD | LONDON | TBD | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 400 | 5 | 88 | N | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2025-26 | 45902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9067814 | 0 | 2674120 | 0 | 0 | 0 | 11741934 | 11741934 | 11741934 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11741934
38-071 | 38-065 | 38 | 206 - CMSM London | 67032 | London DCSB | St. Anne | St. Anne Catholic Elementary School | ELE | 3731 | 7476 | 7476-B01 | 1366 HURON ST | LONDON | N5V2E2 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0213 | -81.2129 | 44222 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44222 | 2020-21 | 2020-21 | 44222 | 2020-21 | 2020-21 | - | - | - | - | 5 | 88 | Y | 2 | Approved | 44685 | 6110158 | Under Construction | Addition | Child Care | 2022-23 | 44931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5041317 | 1068841 | 0 | 0 | 6110158 | 6110158 | 6110158 | 0 | - | TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 6110158
38-072 | 38-072 | 38 | 209 - CMSM St. Thomas | 67032 | London DCSB | Monsignor Morrison | Monsignor Morrisson Catholic Elementary School | ELE | 4601 | 8102 | 8102-B01 | 10 SOUTH EDGEWARE RD | ST THOMAS | N5P2H2 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7937 | -81.183 | 44222 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 44222 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2021-22 | 44470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524337 | 0 | 0 | 524337 | 524337 | 524337 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 524337
38-074 | 38-074 | 38 | 209 - CMSM St. Thomas | 67032 | London DCSB | St. Mary's | St. Mary's Catholic Elementary School | ELE | 4235 | 7848 | 7848-B01 | 128 WILLIAM ST | WEST LORNE | N0L2P0 | 35-15-44-613 | West Elgin | West Elgin M | Elgin Co | ELGIN | Southwest | South | 42.6053 | -81.6022 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 1 | 15 | N | - | Approved | 44931 | 1440826 | Planned | Retrofit | Child Care | 2023-24 | 45175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440826 | 0 | 0 | 0 | 1440826 | 1440826 | 1440826 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1440826
38-075 | 38-075 | 38 | N/A | 67032 | London DCSB | St. Anne's | St. Anne's Catholic Elementary School | ELE | 11078 | 7981 | 7981-B01 | 84 PARK AVE | ST THOMAS | N5R4W1 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7677 | -81.1703 | 44413 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44413 | 284074 | Construction Complete | Retrofit | FDK | 2021-22 | 44440 | 0 | 0 | 284074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284074 | 284074 | 0 | - | TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
38-076 | 38-066 | 38 | N/A | 67032 | London DCSB | North London | North London Catholic Elementary School | ELE | 24839 | 19845 | 19845-L01 | 3055 BUROAK DR | LONDON | TBD | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.032 | -81.2921 | 44441 | 2021-22 | 2021-22 | 44441 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | 504 | - | - | N | - | Planned | - | 0 | Planned | Land Acquisition | Accommodation Pressure | 2024-25 | 45538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7052075 | 0 | 0 | 0 | 0 | 0 | 0 | 7052075 | 7052075 | 7052075 | 0 | - | TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 7052075
38-077 | 38-077 | 38 | N/A | 67032 | London DCSB | St. Anne's | St. Anne's Catholic Elementary School | ELE | 11078 | 7981 | 7981-B01 | 84 PARK AVE | ST THOMAS | N5R4W1 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.768 | -81.1707 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 210 | - | - | N | - | Approved | 45029 | 5718667 | Planned | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5718667 | 0 | 0 | 0 | 0 | 0 | 5718667 | 5718667 | 5718667 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5718667
38-078 | 38-078 | 38 | 222 - CMSM Oxford | 67032 | London DCSB | St. Michael's | St. Michael's Catholic Elementary School | ELE | 4286 | 7878 | 7878-B01 | 1085 DEVONSHIRE AVE | WOODSTOCK | N4S5S1 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1471 | -80.7322 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 230 | 5 | 88 | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7773690 | 0 | 3324941 | 0 | 0 | 0 | 11098631 | 11098631 | 11098631 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11098631
38-079 | 38-079 | 38 | 222 - CMSM Oxford | 67032 | London DCSB | [41 empty] | Planned | [9 empty] | 1834630 | [12 empty] | 1834630 | [10 empty] | 0 | 1834630 | 1834630 | 0
39-001 | 39-001 | 39 | N/A | 67040 | St. Clair CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 3535 | 7326 | 7326-B01 | 420 CREEK ST | WALLACEBURG | N8A4C4 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.597 | -82.3863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-002 | 39-002 | 39 | N/A | 67040 | St. Clair CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 3535 | 7326 | 7326-B01 | 420 CREEK ST | WALLACEBURG | N8A4C4 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.597 | -82.3863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3911730 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3625480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3625480 | 3625480 | 3911730 | 286250 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-003 | 39-003 | 39 | N/A | 67040 | St. Clair CDSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 3535 | 7326 | 7326-B01 | 420 CREEK ST | WALLACEBURG | N8A4C4 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.597 | -82.3863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 363659 | Construction Complete | Other | Other | 2002-03 | 37500 | 363659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363659 | 363659 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-004 | 39-004 | 39 | N/A | 67040 | St. Clair CDSB | Christ the King | Christ the King Catholic Elementary School | ELE | 3138 | 7063 | 7063-B01 | 227 THOMAS AVE | WALLACEBURG | N8A2B9 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.5991 | -82.3702 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 496435 | Construction Complete | Addition | Other | 2000-01 | 36770 | 496435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496435 | 496435 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-007 | 39-007 | 39 | N/A | 67040 | St. Clair CDSB | Good Shepherd | Good Shepherd Catholic Elementary School | ELE | 4386 | 7947 | 7947-B01 | 4 EDITH ST | THAMESVILLE | N0P2K0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.5572 | -81.9771 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3294878 | Construction Complete | Addition | Other | 2005-06 | 38596 | 1366911 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27967 | 3294878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3294878 | 3294878 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-008 | 39-008 | 39 | N/A | 67040 | St. Clair CDSB | Gregory A Hogan | Gregory A Hogan Catholic Elementary School | ELE | 3254 | 7139 | 7139-B01 | 1825 HOGAN DR | SARNIA | N7S6G9 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 43.0109 | -82.3598 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1258774 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593174 | 593174 | 665600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665600 | 1258774 | 1258774 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-009 | 39-009 | 39 | N/A | 67040 | St. Clair CDSB | Gregory A Hogan | Gregory A Hogan Catholic Elementary School | ELE | 3254 | 7139 | 7139-B01 | 1825 HOGAN DR | SARNIA | N7S6G9 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 43.0109 | -82.3598 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 144 | - | - | N | - | Not Required | - | 2880543 | Construction Complete | Addition | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 937439 | 0 | 1943104 | 0 | 0 | 0 | 0 | 0 | 2880543 | 2880543 | 2880543 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1943104
39-010 | 39-010 | 39 | N/A | 67040 | St. Clair CDSB | Holy Trinity | Holy Trinity Catholic Elementary School | ELE | 13127 | 7523 | 7523-B01 | 60 LORNE CRES | SARNIA | N7S0C3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9693 | -82.3724 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9360836 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 2166921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166921 | 6754850 | 0 | 439065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7193915 | 9360836 | 9360836 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-012 | 39-012 | 39 | N/A | 67040 | St. Clair CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 3523 | 7316 | 7316-B01 | 545 BALDOON RD | CHATHAM | N7L5A9 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4102 | -82.2206 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 647913 | Construction Complete | Retrofit | Other | 2002-03 | 37500 | 647913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647913 | 647913 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-015 | 39-015 | 39 | N/A | 67040 | St. Clair CDSB | SCCDSB Head Office | Administrative Office | OFF-ADM | 3535 | 7326 | 7326-B01 | 420 CREEK ST | WALLACEBURG | N8A4C4 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.597 | -82.3863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1171631 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1171631 | 1171631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1171631 | 1171631 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-016 | 39-016 | 39 | N/A | 67040 | St. Clair CDSB | St. Agnes | St. Agnes Catholic Elementary School | ELE | 3687 | 7444 | 7444-B01 | 55 CROYDON ST | CHATHAM | N7L1L5 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.405 | -82.1997 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 496435 | Construction Complete | Addition | Other | 2000-01 | 36770 | 496435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496435 | 496435 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-018 | 39-018 | 39 | N/A | 67040 | St. Clair CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 3732 | 7477 | 7477-B01 | 183 SNOW AVE | BLENHEIM | N0P1A0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.3282 | -81.9938 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1744870 | Construction Complete | Addition | Other | 2009-10 | 40057 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 644870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644870 | 1744870 | 1744870 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-022 | 39-022 | 39 | N/A | 67040 | St. Clair CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4430 | 7975 | 7975-B01 | 25 RALEIGH ST | CHATHAM | N7M2M6 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4032 | -82.1879 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 479933 | Construction Complete | Retrofit | Other | 2002-03 | 37500 | 479933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479933 | 479933 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-023 | 39-023 | 39 | N/A | 67040 | St. Clair CDSB | St. Matthew | St. Matthew Catholic Elementary School | ELE | 13106 | 8019 | 8019-B01 | 720 ELM AVE | SARNIA | N7T4H3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9723 | -82.3819 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9671739 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 2477824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477824 | 6754850 | 0 | 439065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7193915 | 9671739 | 9671739 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-024 | 39-024 | 39 | N/A | 67040 | St. Clair CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4304 | 7894 | 7894-B01 | 25 MAPLE ST S | RIDGETOWN | N0P2C0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4331 | -81.8896 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 298753 | Construction Complete | Retrofit | Other | 2002-03 | 37500 | 298753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298753 | 298753 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-026 | 39-026 | 39 | N/A | 67040 | St. Clair CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4315 | 7903 | 7903-B01 | 1930 WILDWOOD DR | BRIGHT'S GROVE | N0N1C0 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 43.0287 | -82.2625 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 559789 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59789 | 59789 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 559789 | 559789 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-027 | 39-027 | 39 | N/A | 67040 | St. Clair CDSB | St. Patrick's | St. Patrick's Catholic Secondary School | SEC | 3859 | 7572 | 7572-B01 | 1001 THE RAPIDS PKY | SARNIA | N7S6K2 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9949 | -82.3515 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 462 | - | - | N | - | Not Required | - | 14551055 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 402024 | 0 | 1232499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904369 | 2538892 | 0 | 0 | 0 | 0 | 12012163 | 0 | 0 | 0 | 0 | 0 | 12012163 | 14551055 | 14551055 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12012163
39-028 | 39-028 | 39 | N/A | 67040 | St. Clair CDSB | St. Peter Canisius | St. Peter Canisius Catholic Elementary School | ELE | 4400 | 7953 | 7953-B01 | 424 VICTORIA ST | WATFORD | N0M2S0 | 35-15-54-612 | Warwick | Warwick Tp | Lambton Co | LAMBTON | Southwest | South | 42.9526 | -81.8831 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 677384 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163766 | 163766 | 513618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513618 | 677384 | 677384 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-030 | 39-030 | 39 | N/A | 67040 | St. Clair CDSB | St. Peter CES | St. Peter CES Catholic Elementary School | ELE | 4407 | 7958 | 7958-B01 | 696 OXFORD ST | SARNIA | N7T6Z8 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9817 | -82.3838 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 599742 | Construction Complete | Addition | Other | 2013-14 | 41518 | 599742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599742 | 599742 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-031 | 39-031 | 39 | N/A | 67040 | St. Clair CDSB | St. Philip CES | St. Philip CES Catholic Elementary School | ELE | 4424 | 7969 | 7969-B01 | 420 QUEEN ST | PETROLIA | N0N1R0 | 35-15-54-402 | Petrolia | Petrolia T | Lambton Co | LAMBTON | Southwest | South | 42.8807 | -82.1507 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1687083 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679961 | 679961 | 1007122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007122 | 1687083 | 1687083 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-036 | 39-036 | 39 | N/A | 67040 | St. Clair CDSB | Ursuline College Chatham | Ursuline College Chatham Catholic Secondary School | SEC | 4575 | 8087 | 8087-B01 | 85 GRAND AVE W | CHATHAM | N7L1B6 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4066 | -82.1941 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6662263 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1858560 | 1858560 | 4803703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4803703 | 6662263 | 6662263 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-037 | 39-037 | 39 | N/A | 67040 | St. Clair CDSB | Ursuline College Chatham | Ursuline College Chatham Catholic Secondary School | SEC | 4575 | 8087 | 8087-B01 | 85 GRAND AVE W | CHATHAM | N7L1B6 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4066 | -82.1941 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 163840 | Construction Complete | Addition | Other | 2004-05 | 38231 | 163840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163840 | 163840 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-038-01 | 39-038 | 39 | 227 - CMSM Chatham-Kent | 67040 | St. Clair CDSB | St. Angela Merici | St. Angela Merici Catholic Elementary School | ELE | 24676 | 19683 | 19683-B01 | 801 MCNAUGHTON AVE W | CHATHAM-KENT | N7L0E5 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.3982 | -82.2252 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | - | - | - | 564 | 3 | 49 | Y | - | Approved | 43375 | 15460410 | Construction Complete | New Construction | Consolidation | 2020-21 | 44075 | 0 | 0 | 694384 | 299529 | 0 | 0 | 0 | 0 | 0 | 259881 | 0 | 0 | 0 | 0 | 0 | 1253794 | 0 | 0 | 1048675 | 0 | 11584931 | 0 | 1573010 | 0 | 0 | 0 | 14206616 | 15460410 | 15460410 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13157941
39-038-02 | 39-038 | 39 | N/A | 67040 | St. Clair CDSB | St. Angela Merici | St. Angela Merici Catholic Elementary School | ELE | 24676 | 19683 | 19683-L01 | 801 MCNAUGHTON AVE W | CHATHAM | N7L0E5 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.3982 | -82.2252 | 43227 | 2017-18 | 2018-19 | 43227 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43227 | 622563 | Construction Complete | Land Acquisition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622563 | 0 | 0 | 0 | 0 | 0 | 0 | 622563 | 622563 | 622563 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 622563
39-039 | 39-039 | 39 | 227 - CMSM Chatham-Kent | 67040 | St. Clair CDSB | South Chatham | South Chatham Catholic Elementary School | ELE | 24677 | 19684 | 19684-B01 | TBD | CHATHAM-KENT | TBD | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | TBD | TBD | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | - | - | - | 564 | 3 | 49 | Y | - | Approved | 44726 | 23634288 | Under Construction | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 2007440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2007440 | 0 | 0 | 1048675 | 0 | 18095828 | 0 | 2482345 | 0 | 0 | 0 | 21626848 | 23634288 | 23634288 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 20578173
39-040 | 39-040 | 39 | 218 - CMSM Lambton | 67040 | St. Clair CDSB | Holy Trinity | Holy Trinity Catholic Elementary School | ELE | 13127 | 7523 | 7523-B01 | 60 LORNE CRES | SARNIA | N7S0C3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9693 | -82.3724 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390077 | 0 | 0 | 0 | 390077 | 390077 | 390077 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 390077
39-041 | 39-041 | 39 | 218 - CMSM Lambton | 67040 | St. Clair CDSB | Gregory A Hogan | Gregory A Hogan Catholic Elementary School | ELE | 24841 | 19847 | 19847-B01 | 900 THE RAPIDS PKY | SARNIA | N7S6K3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | TBD | TBD | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 659 | 5 | 88 | Y | - | Approved | 44726 | 24243249 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | 1362772 | 0 | 19456656 | 0 | 3223821 | 0 | 0 | 0 | 24043249 | 24243249 | 24243249 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 22680477
39-042 | 39-042 | 39 | N/A | 67040 | St. Clair CDSB | St. Matthew | St. Matthew Catholic Elementary School | ELE | 13106 | 8019 | 8019-B01 | 720 ELM AVE | SARNIA | N7T4H3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9723 | -82.3819 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
39-043 | 39-043 | 39 | N/A | 67040 | St. Clair CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4123 | 7770 | 7770-B01 | 43 ST CLAIR ST | TILBURY | N0P2L0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.2594 | -82.4391 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43717 | 137078 | Construction Complete | Retrofit | Child Care | 2019-20 | 43831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137078 | 0 | 0 | 0 | 0 | 0 | 137078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137078 | 137078 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
39-044 | 39-044 | 39 | 218 - CMSM Lambton | 67040 | St. Clair CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3649 | 7417 | 7417-B01 | 434 JOHN ST | PORT LAMBTON | N0P2B0 | 35-15-54-614 | St. Clair | St. Clair Tp | Lambton Co | LAMBTON | Southwest | South | 42.6578 | -82.5005 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 46 | 3 | 49 | - | - | Approved | 44726 | 5653650 | Under Construction | Addition | Condition | 2023-24 | 45170 | 416430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416430 | 0 | 0 | 0 | 0 | 1420655 | 0 | 3816565 | 0 | 0 | 0 | 5237220 | 5653650 | 5653650 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5237220
39-045 | 39-039 | 39 | N/A | 67040 | St. Clair CDSB | South Chatham | South Chatham Catholic Elementary School | ELE | 24677 | 19684 | 19684-L01 | TBD | CHATHAM-KENT | TBD | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | TBD | TBD | 43928 | 2019-20 | 2020-21 | 43928 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44726 | 1886584 | Construction Complete | Land Acquisition | Consolidation | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1886584 | 0 | 0 | 0 | 0 | 0 | 0 | 1886584 | 1886584 | 1886584 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1886584
39-046 | 39-041 | 39 | N/A | 67040 | St. Clair CDSB | Gregory A Hogan | Gregory A Hogan Catholic Elementary School | ELE | 24841 | 19847 | 19847-L01 | 900 THE RAPIDS PKY | SARNIA | N7S6K3 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | TBD | TBD | 44088 | 2020-21 | 2020-21 | 44088 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44726 | 4422132 | Construction Complete | Land Acquisition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4422132 | 0 | 0 | 0 | 0 | 0 | 0 | 4422132 | 4422132 | 4422132 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4422132
39-047 | 39-047 | 39 |  | 67040 | St. Clair CDSB |  |  | ELE | [12 empty] | South | [29 empty] | Retrofit
40-001 | 40-001 | 40 | N/A | 67059 | Toronto CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 5816 | 11492 | 11492-B01 | 80 SHEPPARD AVE E | NORTH YORK | M2N6E8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7634 | -79.4078 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467082 | 0 | 0 | 0 | 0 | 0 | 467082 | 467082 | 0 | -467082 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 467082
40-002 | 40-002 | 40 | N/A | 67059 | Toronto CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 5816 | 11492 | 11492-B01 | 80 SHEPPARD AVE E | NORTH YORK | M2N6E8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7634 | -79.4078 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 47050443 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 2734564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2734564 | 0 | 0 | 44253882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44253882 | 46988446 | 44576435 | -2412011 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-003 | 40-003 | 40 | N/A | 67059 | Toronto CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 5816 | 11492 | 11492-B01 | 80 SHEPPARD AVE E | NORTH YORK | M2N6E8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7634 | -79.4078 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1834300 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834300 | 1834300 | 1834300 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-004 | 40-004 | 40 | N/A | 67059 | Toronto CDSB | St. Joseph Morrow Park | St. Joseph Morrow Park Catholic Secondary School | SEC | 24329 | 7021 | 7021-L0- | 3336 BAYVIEW AVE | NORTH YORK | M2K1G3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7867 | -79.3925 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3274034 | Construction Complete | Land Acquisition | Other | 2014-15 | 41883 | 0 | 0 | 3274034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274034 | 3274034 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-005 | 40-005 | 40 | N/A | 67059 | Toronto CDSB | All Saints | All Saints Catholic Elementary School | ELE | 10318 | 11066 | 11066-B01 | 1435 ROYAL YORK RD | ETOBICOKE | M9P3A7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6853 | -79.5279 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8618697 | Construction Complete | New Construction | Consolidation | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8618697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8618697 | 8618697 | 8618697 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-008 | 40-008 | 40 | N/A | 67059 | Toronto CDSB | Appian | Administrative Office | OFF-ADM | 5816 | 11492 | 11492-B01 | 80 SHEPPARD AVE E | NORTH YORK | M2N6E8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7634 | -79.4078 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2726111 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 2726111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2726111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2726111 | 2726111 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-009 | 40-009 | 40 | N/A | 67059 | Toronto CDSB | Bishop Allen Academy | Bishop Allen Academy Catholic Secondary School | SEC | 3054 | 5216 | 5216-B01 | 721 ROYAL YORK RD | ETOBICOKE | M8Y2T3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.634 | -79.5054 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2651537 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2651537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2651537 | 2651537 | 2651537 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-010-01 | 40-010 | 40 | N/A | 67059 | Toronto CDSB | Blessed Cardinal Newman | Blessed Cardinal Newman Catholic Secondary School | SEC | 24526 | 19531 | 19531-B0- | 100 BRIMLEY RD S | SCARBOROUGH | M1M3X4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7129 | -79.2427 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 1110 | - | - | N | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30576050 | 0 | 0 | 0 | 0 | 0 | 30576050 | 30576050 | 30576050 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 30576050
40-010-02 | 40-010 | 40 | N/A | 67059 | Toronto CDSB | Blessed Cardinal Newman | Blessed Cardinal Newman Catholic Secondary School | SEC | 24526 | 19531 | 19531-L0- | 100 BRIMLEY RD S | SCARBOROUGH | M1M3X4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7129 | -79.2427 | 42391 | 2015-16 | 2015-16 | 42391 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42391 | 17452257 | Construction Complete | Land Acquisition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17452257 | 0 | 0 | 0 | 0 | 0 | 0 | 17452257 | 17452257 | 17452257 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 17452257
40-011 | 40-011 | 40 | N/A | 67059 | Toronto CDSB | Blessed Pier Giorgo Frassati | Blessed Pier Giorgo Frassati Catholic Elementary School | ELE | 15036 | 12065 | 12065-B02 | 8 SEASONS DR | SCARBOROUGH | M1X1X4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8295 | -79.2333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10166492 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89416 | 89416 | 10112912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10112912 | 10202328 | 10202328 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-013 | 40-013 | 40 | N/A | 67059 | Toronto CDSB | Brebeuf College | Brebeuf College Catholic Secondary School | SEC | 10323 | 7027 | 7027-B02 | 211 STEELES AVE E | NORTH YORK | M2M3Y6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8006 | -79.4024 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 28004304 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28004304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28004304 | 28004304 | 28004304 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-014 | 40-014 | 40 | N/A | 67059 | Toronto CDSB | Canadian Martyrs | Canadian Martyrs Catholic Elementary School | ELE | 3101 | 7038 | 7038-B01 | 520 PLAINS RD | EAST YORK | M4C2Z1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.698 | -79.3194 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3458942 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3458942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3458942 | 3458942 | 3458942 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-015 | 40-015 | 40 | N/A | 67059 | Toronto CDSB | Cardinal Carter for the Arts (Annex) | Cardinal Carter for the Arts (Annex) Catholic Secondary School | SEC | 19949 | 11492 | 11492-B01 | 80 SHEPPARD AVE E | NORTH YORK | M2N6E8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7634 | -79.4078 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1900633 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900633 | 1900633 | 1900633 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-016 | 40-016 | 40 | N/A | 67059 | Toronto CDSB | Cardinal Leger | Cardinal Leger Catholic Elementary School | ELE | 3118 | 7047 | 7047-B01 | 600 MORRISH RD | SCARBOROUGH | M1C4Y1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7935 | -79.1747 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1935172 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329281 | 157865 | 448026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935172 | 1935172 | 1935172 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-017 | 40-017 | 40 | N/A | 67059 | Toronto CDSB | Dante Alighieri | Dante Alighieri Catholic Secondary School | SEC | 25103 | 7087 | 7087-B02 | 60 PLAYFAIR AVE | NORTH YORK | M6B2P9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7102 | -79.458 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 650 | - | - | N | - | Approved | 45198 | 60656214 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45538 | 0 | 0 | 0 | 0 | 1437196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1437196 | 0 | 0 | 0 | 0 | 59219018 | 0 | 0 | 0 | 0 | 0 | 59219018 | 60656214 | 60656214 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 59219018
40-018 | 40-018 | 40 | N/A | 67059 | Toronto CDSB | Dante Alighieri | Dante Alighieri Catholic Secondary School | SEC | 3167 | 7087 | 7087-B01 | 60 PLAYFAIR AVE | NORTH YORK | M6B2P9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7102 | -79.458 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1964239 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1964239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1964239 | 1964239 | 1964239 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-019 | 40-019 | 40 | N/A | 67059 | Toronto CDSB | Father Henry Carr | Father Henry Carr Catholic Secondary School | SEC | 9507 | 5051 | 5051-B01 | 1760 MARTIN GROVE RD | ETOBICOKE | M9V3S4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7362 | -79.5916 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 13863505 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13863505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13863505 | 13863505 | 13863505 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-020 | 40-020 | 40 | N/A | 67059 | Toronto CDSB | Father John Redmond | Father John Redmond Catholic Secondary School | SEC | 10310 | 11059 | 11059-B01 | 28 COLONEL SAMUEL SMITH PARK DR | ETOBICOKE | M8V4B7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.5946 | -79.5162 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 29605882 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29605882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29605882 | 29605882 | 29605882 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-021 | 40-021 | 40 | N/A | 67059 | Toronto CDSB | Father Serra | Father Serra Catholic Elementary School | ELE | 9504 | 5047 | 5047-B01 | 111 SUN ROW DR | ETOBICOKE | M9P3J3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6857 | -79.5375 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4215913 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2682911 | 197214 | 1335788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4215913 | 4215913 | 4215913 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-022 | 40-022 | 40 | N/A | 67059 | Toronto CDSB | Francis Libermann | Francis Libermann Catholic Secondary School | SEC | 10557 | 7119 | 7119-B01 | 4640 FINCH AVE E | SCARBOROUGH | M1S4G2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8072 | -79.2742 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4714279 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4714279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4714279 | 4714279 | 4714279 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-024 | 40-024 | 40 | N/A | 67059 | Toronto CDSB | Holy Cross | Holy Cross Catholic Elementary School | ELE | 3279 | 7155 | 7155-B01 | 299A DONLANDS AVE | EAST YORK | M4J3R7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.69 | -79.3411 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2694818 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2694818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2694818 | 2694818 | 2694818 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-025 | 40-025 | 40 | N/A | 67059 | Toronto CDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 3287 | 7159 | 7159-B01 | 141 CLOSE AVE | TORONTO | M6K2V6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6384 | -79.435 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2431381 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2431381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2431381 | 2431381 | 2431381 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-027 | 40-027 | 40 | N/A | 67059 | Toronto CDSB | Immaculate Conception | Immaculate Conception Catholic Elementary School | ELE | 10311 | 11060 | 11060-B01 | 23 COMAY RD | NORTH YORK | M6M2K9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6976 | -79.4786 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8964333 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8964333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8964333 | 8964333 | 8964333 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-028 | 40-028 | 40 | N/A | 67059 | Toronto CDSB | James Cardinal McGuigan | James Cardinal McGuigan Catholic Secondary School | SEC | 3343 | 7192 | 7192-B01 | 1440 FINCH AVE W | NORTH YORK | M3J3G3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7632 | -79.493 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 14287213 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 2557551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2557551 | 11729662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11729662 | 14287213 | 14287213 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-029 | 40-029 | 40 | N/A | 67059 | Toronto CDSB | Josyf Cardinal Slipyj | Josyf Cardinal Slipyj Catholic Elementary School | ELE | 3107 | 5045 | 5045-B01 | 35 WEST DEANE PARK DR | ETOBICOKE | M9B2R5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6601 | -79.5655 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2524197 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1694363 | 0 | 829834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2524197 | 2524197 | 2524197 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-030 | 40-030 | 40 | N/A | 67059 | Toronto CDSB | Loretto Abbey | Loretto Abbey Catholic Secondary School | SEC | 3387 | 7226 | 7226-B01 | 101 MASON BLVD | NORTH YORK | M5M3E2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7409 | -79.4111 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 25860735 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 25860735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25860735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25860735 | 25860735 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-031 | 40-031 | 40 | N/A | 67059 | Toronto CDSB | Loretto College | Loretto College Catholic Secondary School | SEC | 10325 | 7391 | 7391-B01 | 151 ROSEMOUNT AVE | TORONTO | M6H2N1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6648 | -79.4111 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 19577429 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19577429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19577429 | 19577429 | 19577429 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-032 | 40-032 | 40 | N/A | 67059 | Toronto CDSB | Loretto Abbey | Loretto Abbey Catholic Secondary School | SEC | 3387 | 7226 | 7226-B01 | 101 MASON BLVD | NORTH YORK | M5M3E2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7409 | -79.4111 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 39865 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39865 | 39865 | 39865 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-033 | 40-033 | 40 | N/A | 67059 | Toronto CDSB | Marshall McLuhan | Marshall McLuhan Catholic Secondary School | SEC | 5893 | 8485 | 8485-B01 | 1107 AVENUE RD | TORONTO | M5N3B1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7077 | -79.4101 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17678568 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17678568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17678568 | 17678568 | 17678568 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-034 | 40-034 | 40 | N/A | 67059 | Toronto CDSB | Monsignor Fraser College (Isabelle North) | Monsignor Fraser College (Isabelle North) Catholic Secondary School | SEC | 24252 | 7404 | 7404-B01 | 25 LINDEN ST | TORONTO | M4Y1V5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6706 | -79.3768 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2826008 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 2826008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2826008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2826008 | 2826008 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-035 | 40-035 | 40 | N/A | 67059 | Toronto CDSB | Monsignor Percy Johnson | Monsignor Percy Johnson Catholic Secondary School | SEC | 10654 | 5054 | 5054-B01 | 2170 KIPLING AVE | ETOBICOKE | M9W4K9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7217 | -79.5715 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 23354721 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23354721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23354721 | 23354721 | 23354721 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-036 | 40-036 | 40 | N/A | 67059 | Toronto CDSB | Nativity of our Lord | Nativity of our Lord Catholic Elementary School | ELE | 3448 | 11062 | 11062-B01 | 35 SAFFRON CRES | ETOBICOKE | M9C3T8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6535 | -79.5758 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2964909 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918740 | 126000 | 920169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2964909 | 2964909 | 2964909 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-037 | 40-037 | 40 | N/A | 67059 | Toronto CDSB | Neil McNeil | Neil McNeil Catholic Secondary School | SEC | 3449 | 7268 | 7268-B01 | 127 VICTORIA PARK AVE | SCARBOROUGH | M4E3S2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6791 | -79.2831 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12615125 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 7144932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144932 | 5470193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5470193 | 12615125 | 12615125 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-038 | 40-038 | 40 | N/A | 67059 | Toronto CDSB | Our Lady of Wisdom | Our Lady of Wisdom Catholic Elementary School | ELE | 3575 | 7357 | 7357-B01 | 10 JAPONICA RD | SCARBOROUGH | M1R4R7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7616 | -79.3082 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3406063 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 417183 | 0 | 924471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341654 | 0 | 0 | 2064409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2064409 | 3406063 | 3406063 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-039 | 40-039 | 40 | N/A | 67059 | Toronto CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 10314 | 7314 | 7314-B01 | 3176 ST CLAIR AVE E | SCARBOROUGH | M1L1V6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7095 | -79.2931 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10025240 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10025240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10025240 | 10025240 | 10025240 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-040 | 40-040 | 40 | N/A | 67059 | Toronto CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 10313 | 7334 | 7334-B01 | 444 SHERBOURNE ST | TORONTO | M4X1K2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6662 | -79.3744 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 15379549 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15379549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15379549 | 15379549 | 15379549 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-041 | 40-041 | 40 | N/A | 67059 | Toronto CDSB | Our Lady of Peace | Our Lady of Peace Catholic Elementary School | ELE | 3555 | 7341 | 7341-B01 | 70 MATTICE AVE | ETOBICOKE | M9B1T6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6465 | -79.5409 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3441180 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3441180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3441180 | 3441180 | 3441180 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-044 | 40-044 | 40 | N/A | 67059 | Toronto CDSB | Our Lady of Sorrows | Our Lady of Sorrows Catholic Elementary School | ELE | 10324 | 11069 | 11069-B01 | 32 MONTGOMERY RD | ETOBICOKE | M8X1Z4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6489 | -79.5188 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11561369 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11561369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11561369 | 11561369 | 11561369 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-047 | 40-047 | 40 | N/A | 67059 | Toronto CDSB | Our Lady of Victory | Our Lady of Victory Catholic Elementary School | ELE | 10501 | 7354 | 7354-B01 | 70 GUESTVILLE AVE | YORK | M6N4N3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6833 | -79.4893 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11404106 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11404106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11404106 | 11404106 | 11404106 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-049 | 40-049 | 40 | N/A | 67059 | Toronto CDSB | Senator O'Connor College | Senator O'Connor College Catholic Secondary School | SEC | 10315 | 11063 | 11063-B01 | 60 ROWENA DR | NORTH YORK | M3A3R2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7507 | -79.3167 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24718305 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24718305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24718305 | 24718305 | 24718305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-050 | 40-050 | 40 | N/A | 67059 | Toronto CDSB | St. Agatha | St. Agatha Catholic Elementary School | ELE | 3685 | 7442 | 7442-B01 | 49 CATHEDRAL BLUFFS DR | SCARBOROUGH | M1M2T6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7236 | -79.2299 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5191042 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4059130 | 698526 | 433386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5191042 | 5191042 | 5191042 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-052 | 40-052 | 40 | N/A | 67059 | Toronto CDSB | St. Albert | St. Albert Catholic Elementary School | ELE | 3694 | 7451 | 7451-B01 | 1125 MIDLAND AVE | SCARBOROUGH | M1K4H2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7438 | -79.2613 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5839674 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762130 | 416209 | 1661335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5839674 | 5839674 | 5839674 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-053 | 40-053 | 40 | N/A | 67059 | Toronto CDSB | St. Ambrose | St. Ambrose Catholic Elementary School | ELE | 14791 | 7461 | 7461-B02 | 20 COULES CRT | ETOBICOKE | M8W2N9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6082 | -79.5499 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9843840 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9843840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9843840 | 9843840 | 9843840 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-054 | 40-054 | 40 | N/A | 67059 | Toronto CDSB | St. Andre | St. Andre Catholic Elementary School | ELE | 14796 | 10050 | 10050-B02 | 36 YVONNE AVE | NORTH YORK | M3L1C9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7236 | -79.5175 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11038530 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10615278 | 0 | 434467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11049745 | 11049745 | 11049745 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-056 | 40-056 | 40 | N/A | 67059 | Toronto CDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 10316 | 11064 | 11064-B01 | 130 SHANLY ST | TORONTO | M6H1L9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6634 | -79.4348 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9902032 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9902032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9902032 | 9902032 | 9902032 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-057 | 40-057 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Augustine of Canterbury | St. Augustine of Canterbury Catholic Elementary School | ELE | 3775 | 7510 | 7510-B01 | 98 SHOREHAM DR | NORTH YORK | M3N1S9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7681 | -79.5248 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 92 | 3 | 49 | N | - | Approved | 43061 | 7965495 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43709 | 655306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655306 | 0 | 0 | 0 | 0 | 5797680 | 0 | 1512509 | 0 | 0 | 0 | 7310189 | 7965495 | 7965495 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7310189
40-058 | 40-058 | 40 | N/A | 67059 | Toronto CDSB | St. Basil The Great | St. Basil The Great Catholic Secondary School | SEC | 5896 | 8486 | 8486-B01 | 20 STARVIEW LANE | NORTH YORK | M9M3B2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7274 | -79.5329 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 212903 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212903 | 212903 | 212903 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-060 | 40-060 | 40 | N/A | 67059 | Toronto CDSB | St. Bernard | St. Bernard Catholic Elementary School | ELE | 3808 | 7537 | 7537-B01 | 12 DUCKWORTH ST | NORTH YORK | M6M4W4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7027 | -79.5 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4898336 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3321849 | 308200 | 1268287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4898336 | 4898336 | 4898336 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-061 | 40-061 | 40 | N/A | 67059 | Toronto CDSB | St. Bonaventure | St. Bonaventure Catholic Elementary School | ELE | 3817 | 7544 | 7544-B01 | 1340 LESLIE ST | NORTH YORK | M3C2K9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7331 | -79.3558 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5718312 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3484033 | 861415 | 1372864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5718312 | 5718312 | 5718312 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-064 | 40-064 | 40 | N/A | 67059 | Toronto CDSB | St. Cecilia | St. Cecilia Catholic Elementary School | ELE | 3840 | 7559 | 7559-B01 | 355 ANNETTE ST | TORONTO | M6P1R3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6606 | -79.4745 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 45392 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45392 | 45392 | 45392 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-066 | 40-066 | 40 | N/A | 67059 | Toronto CDSB | St. Charles Garnier | St. Charles Garnier Catholic Elementary School | ELE | 3853 | 7568 | 7568-B01 | 20 STONG CRT | NORTH YORK | M3N2X9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7623 | -79.5178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3248968 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592814 | 268130 | 388024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3248968 | 3248968 | 3248968 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-068 | 40-068 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Clement | St. Clement Catholic Elementary School | ELE | 3868 | 7578 | 7578-B01 | 4319 BLOOR ST W | ETOBICOKE | M9C2A2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6326 | -79.5739 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 170 | 3 | 49 | N | - | Approved | 42998 | 7488299 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43466 | 435230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435230 | 0 | 0 | 479924 | 0 | 4491427 | 0 | 1512510 | 0 | 0 | 0 | 6483861 | 6919091 | 7488299 | 569208 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 6003937
40-069 | 40-069 | 40 | N/A | 67059 | Toronto CDSB | St. Conrad | St. Conrad Catholic Elementary School | ELE | 14793 | 5056 | 5056-B02 | 5 EXBURY RD | NORTH YORK | M3M0A8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7302 | -79.4927 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12050206 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12050206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12050206 | 12050206 | 12050206 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-073 | 40-073 | 40 | N/A | 67059 | Toronto CDSB | St. Edward | St. Edward Catholic Elementary School | ELE | 15201 | 18046 | 18046-B01 | 1 BOTHAM RD | NORTH YORK | M2N2J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7531 | -79.4135 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 458 | - | - | N | - | Not Required | - | 11391298 | Construction Complete | New Construction | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513624 | 513624 | 0 | 0 | 0 | 0 | 10877674 | 0 | 0 | 0 | 0 | 0 | 10877674 | 11391298 | 11391298 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 10877674
40-075 | 40-075 | 40 | N/A | 67059 | Toronto CDSB | St. Eugene | St. Eugene Catholic Elementary School | ELE | 3924 | 7622 | 7622-B01 | 30 WESTROYAL RD | ETOBICOKE | M9P2C3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6924 | -79.5369 | 42382 | 2015-16 | 2015-16 | - | - | - | 42382 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 308 | - | - | N | - | Approved | 42382 | 9432474 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 7628602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7628602 | 0 | 0 | 529130 | 0 | 1274742 | 0 | 0 | 0 | 0 | 0 | 1803872 | 9432474 | 7593917 | -1838557 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1274742
40-076-01 | 40-076 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Fidelis | St. Fidelis Catholic Elementary School | ELE | 25015 | 10001 | 10001-B01 | 155 FALSTAFF AVE | NORTH YORK | M6L2E5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7177 | -79.4958 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 648 | 2 | 25 | N | - | Approved | 45057 | 28893491 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 684365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684365 | 0 | 0 | 998260 | 0 | 24291436 | 0 | 2919430 | 0 | 0 | 0 | 28209126 | 28893491 | 28893491 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 27210866
40-076-02 | 40-076 | 40 | N/A | 67059 | Toronto CDSB | St. Fidelis | St. Fidelis Catholic Elementary School | ELE | 25015 | 10001 | 10001-L01 | 155 FALSTAFF AVE | NORTH YORK | M6L2E5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7177 | -79.4958 | 43496 | 2018-19 | 2018-19 | 43496 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43496 | 15750000 | Construction Complete | Land Acquisition | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15750000 | 0 | 0 | 0 | 0 | 0 | 0 | 15750000 | 15750000 | 15750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 15750000
40-077 | 40-077 | 40 | N/A | 67059 | Toronto CDSB | St. Fidelis | St. Fidelis Catholic Elementary School | ELE | 3926 | 7624 | 7624-B01 | 9 BANNERMAN ST | NORTH YORK | M6L2S5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7172 | -79.4852 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 172314 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172314 | 172314 | 172314 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-078 | 40-078 | 40 | N/A | 67059 | Toronto CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 4178 | 7809 | 7809-B01 | 80 CLINTON ST | TORONTO | M6G2Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6563 | -79.4146 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3617715 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3617715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3617715 | 3617715 | 3617715 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-081 | 40-081 | 40 | N/A | 67059 | Toronto CDSB | St. Henry | St. Henry Catholic Elementary School | ELE | 3995 | 7676 | 7676-B01 | 100 BAMBURGH CIR | SCARBOROUGH | M1W3R3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8137 | -79.3278 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2473591 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866571 | 243400 | 363620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2473591 | 2473591 | 2473591 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-083 | 40-083 | 40 | N/A | 67059 | Toronto CDSB | St. Jane Frances | St. Jane Frances Catholic Elementary School | ELE | 4023 | 7695 | 7695-B01 | 2745 JANE ST | NORTH YORK | M3L2E8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.742 | -79.5132 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11970307 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11970307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11970307 | 11970307 | 11970307 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-085 | 40-085 | 40 | N/A | 67059 | Toronto CDSB | St. Joachim | St. Joachim Catholic Elementary School | ELE | 4037 | 7708 | 7708-B01 | 3395 ST CLAIR AVE E | SCARBOROUGH | M1L1W3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7132 | -79.2755 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4644861 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2881690 | 867120 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4644861 | 4644861 | 4644861 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-087 | 40-087 | 40 | N/A | 67059 | Toronto CDSB | St. John Paul II | St. John Paul II Catholic Secondary School | SEC | 3597 | 7373 | 7373-B01 | 685 MILITARY TRAIL | SCARBOROUGH | M1E4P6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7903 | -79.199 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1316825 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316825 | 1316825 | 1316825 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-088 | 40-088 | 40 | N/A | 67059 | Toronto CDSB | St. John the Evangelist | St. John the Evangelist Catholic Elementary School | ELE | 24649 | 7721 | 7721-B02 | 23 GEORGE ST | YORK | M9N2B4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7033 | -79.5205 | 40786 | 2010-11 | 2011-12 | - | - | - | 40786 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 600 | - | - | N | - | Approved | 42828 | 19563160 | Construction Complete | New Construction | Condition | 2019-20 | 43711 | 0 | 0 | 0 | 0 | 4665843 | 0 | 0 | 0 | 0 | 2368583 |  | 229569 | 0 | 0 | 0 | 7263995 | 0 | 0 | 959851 | 0 | 10769089 | 0 | 0 | 0 | 0 | 0 | 11728940 | 18992935 | 18992935 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10769089
40-089 | 40-089 | 40 | N/A | 67059 | Toronto CDSB | St. John Vianney | St. John Vianney Catholic Elementary School | ELE | 9513 | 5151 | 5151-B01 | 105 THISTLE DOWN BLVD | ETOBICOKE | M9V1J5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7384 | -79.5539 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6466306 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 4814052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4814052 | 1652254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652254 | 6466306 | 6466306 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-090 | 40-090 | 40 | N/A | 67059 | Toronto CDSB | St. Joseph | St. Joseph Catholic Secondary School | SEC | 4140 | 7781 | 7781-B01 | 74 WELLESLEY ST W | TORONTO | M5S1C4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6642 | -79.3886 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10484768 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 6303569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6303569 | 4181199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4181199 | 10484768 | 10484768 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-091 | 40-091 | 40 | N/A | 67059 | Toronto CDSB | St. Joseph Morrow Park | St. Joseph Morrow Park Catholic Secondary School | SEC | 4142 | 7783 | 7783-B01 | 3379 BAYVIEW AVE | NORTH YORK | M2M3S4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7967 | -79.3945 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 52286 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52286 | 52286 | 52286 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-092 | 40-092 | 40 | N/A | 67059 | Toronto CDSB | St. Joseph Morrow Park | St. Joseph Morrow Park Catholic Secondary School | SEC | 14205 | 7021 | 7021-B01 | 3336 BAYVIEW AVE | NORTH YORK | M2M3R9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7867 | -79.3925 | 40492 | 2010-11 | 2010-11 | - | - | - | 40492 | 2010-11 | 2010-11 | - | - | - | - | - | - | - | - | - | 800 | - | - | N | - | Approved | 42989 | 31855760 | Construction Complete | New Construction | Accommodation Pressure | 2020-21 | 44201 | 0 | 0 | 0 | 0 | 9311823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9311823 | 0 | 0 | 0 | 0 | 22543937 | 0 | 0 | 0 | 0 | 0 | 22543937 | 31855760 | 31855760 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 22543937
40-095 | 40-095 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Leo | St. Leo Catholic Elementary School | ELE | 24653 | 10115 | 10115-B02 | 165 STANLEY AVE | ETOBICOKE | M8V1P1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6142 | -79.4963 | 42508 | 2015-16 | 2016-17 | - | - | - | 42508 | 2015-16 | 2016-17 | 42509 | 2015-16 | 2016-17 | 43090 | 2017-18 | 2017-18 | - | - | - | 500 | 3 | 49 | N | 1 | Approved | 44677 | 25791932 | Under Construction | New Construction | Consolidation | 2023-24 | 45170 | 270200 | 0 | 630000 | 0 | 2595222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3495422 | 0 | 0 | 1008390 | 0 | 18048851 | 0 | 2725015 | 514254 | 0 | 0 | 22296510 | 25791932 | 25791932 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 21288120
40-096 | 40-096 | 40 | N/A | 67059 | Toronto CDSB | Pope Francis | Pope Francis Catholic Elementary School | ELE | 4185 | 7814 | 7814-B01 | 319 OSSINGTON AVE | TORONTO | M6J3A6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6516 | -79.421 | 42508 | 2015-16 | 2016-17 | - | - | - | 42508 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42508 | 254556 | Construction Complete | Retrofit | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254556 | 0 | 0 | 0 | 0 | 0 | 254556 | 254556 | 129826 | -124730 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 254556
40-097 | 40-097 | 40 | N/A | 67059 | Toronto CDSB | St. Malachy | St. Malachy Catholic Secondary School | SEC | 4186 | 7815 | 7815-B01 | 80 BENNETT RD | SCARBOROUGH | M1E3Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7713 | -79.1658 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 190 | - | - | N | - | Approved | 41759 | 3980731 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351299 | 0 | 3481601 | 0 | 0 | 0 | 0 | 0 | 3832900 | 3832900 | 3832900 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3481601
40-103 | 40-103 | 40 | N/A | 67059 | Toronto CDSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 14743 | 7913 | 7913-B02 | 33 AMARILLO DR | SCARBOROUGH | M1J2P7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7481 | -79.2331 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9255537 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9255537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9255537 | 9255537 | 9255537 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-104 | 40-104 | 40 | N/A | 67059 | Toronto CDSB | St. Nicholas of Bari | St. Nicholas of Bari Catholic Elementary School | ELE | 4338 | 7916 | 7916-B01 | 363 ROGERS RD | YORK | M6E1R6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6833 | -79.4607 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4565032 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4565032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4565032 | 4565032 | 4565032 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-106 | 40-106 | 40 | N/A | 67059 | Toronto CDSB | St. Norbert | St. Norbert Catholic Elementary School | ELE | 4339 | 7917 | 7917-B01 | 60 MANIZA RD | NORTH YORK | M3K1R6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7346 | -79.4643 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 536 | - | - | N | - | Not Required | - | 2261844 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250782 | 592690 | 418372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2261844 | 2261844 | 2261844 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-107 | 40-107 | 40 | N/A | 67059 | Toronto CDSB | St. Paschal Baylon | St. Paschal Baylon Catholic Elementary School | ELE | 4340 | 7918 | 7918-B01 | 15 ST. PASCHAL CRT | NORTH YORK | M2M1X6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7919 | -79.4316 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 404 | - | - | N | - | Approved | 44278 | 14545973 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43344 | 179100 | 0 | 12209664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12388764 | 0 | 0 | 0 | 0 | 2157209 | 0 | 0 | 0 | 0 | 0 | 2157209 | 14545973 | 14545973 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2157209
40-108 | 40-108 | 40 | N/A | 67059 | Toronto CDSB | St. Pius X | St. Pius X Catholic Elementary School | ELE | 4428 | 7973 | 7973-B01 | 71 JANE ST | TORONTO | M6S3Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6511 | -79.485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4375593 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272984 | 310000 | 792609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375593 | 4375593 | 4375593 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-109-01 | 40-109 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Raymond | St. Raymond Catholic Elementary School | ELE | 24702 | 7985 | 7985-B02 | 270 BARTON AVE | TORONTO | M6G1R4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6659 | -79.4232 | 42508 | 2015-16 | 2016-17 | - | - | - | 42508 | 2015-16 | 2016-17 | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | 350 | 3 | 49 | N | - | Approved | 44761 | 24464362 | Under Construction | New Construction | Consolidation | 2022-23 | 44929 | 0 | 0 | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630000 | 0 | 0 | 518998 | 0 | 18895038 | 0 | 4420326 | 0 | 0 | 0 | 23834362 | 24464362 | 24464362 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23315364
40-109-03 | 40-109 | 40 | N/A | 67059 | Toronto CDSB | St. Raymond | St. Raymond Catholic Elementary School | ELE | 4444 | 7985 | 7985-B01 | 270 BARTON AVE | TORONTO | M6G1R4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6659 | -79.4232 | 43073 | 2017-18 | 2017-18 | - | - | - | 43073 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43220 | 1573027 | Construction Complete | Demolition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573027 | 0 | 0 | 0 | 0 | 0 | 1573027 | 1573027 | 1573027 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1573027
40-110 | 40-110 | 40 | N/A | 67059 | Toronto CDSB | St. Richard | St. Richard Catholic Elementary School | ELE | 4447 | 7988 | 7988-B01 | 960 BELLAMY RD N | SCARBOROUGH | M1H1H1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7684 | -79.2397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 336159 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 167000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167000 | 0 | 0 | 169159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169159 | 336159 | 336159 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-111 | 40-111 | 40 | N/A | 67059 | Toronto CDSB | St. Robert | St. Robert Catholic Elementary School | ELE | 10319 | 8455 | 8455-B01 | 70 BAINBRIDGE AVE | NORTH YORK | M3H2K2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7496 | -79.4443 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8142943 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8142943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8142943 | 8142943 | 8142943 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-113 | 40-113 | 40 | N/A | 67059 | Toronto CDSB | St. Simon | St. Simon Catholic Elementary School | ELE | 4464 | 8001 | 8001-B01 | 20 WALLASEY AVE | NORTH YORK | M9M1E2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7196 | -79.5358 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 103806 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103806 | 103806 | 103806 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-114 | 40-114 | 40 | N/A | 67059 | Toronto CDSB | St. Simon | St. Simon Catholic Elementary School | ELE | 4464 | 8001 | 8001-B01 | 20 WALLASEY AVE | NORTH YORK | M9M1E2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7196 | -79.5358 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1481000 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1481000 | 1481000 | 1481000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-115 | 40-115 | 40 | N/A | 67059 | Toronto CDSB | St. Simon | St. Simon Catholic Elementary School | ELE | 24631 | 9998 | 9998-B02 | 24 STRATHBURN BLVD | NORTH YORK | M9M2K3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7187 | -79.5334 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 542 | - | - | N | - | Approved | 42211 | 12445827 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 822563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822563 | 0 | 0 | 479025 | 0 | 11240773 | 0 | 0 | 0 | 0 | 0 | 11719798 | 12542361 | 12636416 | 94055 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11240773
40-116 | 40-116 | 40 | N/A | 67059 | Toronto CDSB | St. Stephen | St. Stephen Catholic Elementary School | ELE | 4467 | 8004 | 8004-B01 | 55 GOLFDOWN DR | ETOBICOKE | M9W2H8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.722 | -79.5544 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3106578 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2097722 | 560830 | 448026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3106578 | 3106578 | 3106578 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-118 | 40-118 | 40 | N/A | 67059 | Toronto CDSB | St. Thomas More | St. Thomas More Catholic Elementary School | ELE | 4505 | 8031 | 8031-B01 | 2300 ELLESMERE RD | SCARBOROUGH | M1G3M7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7784 | -79.225 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3961947 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3209202 | 304719 | 448026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3961947 | 3961947 | 3961947 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-119 | 40-119 | 40 | N/A | 67059 | Toronto CDSB | St. Timothy | St. Timothy Catholic Elementary School | ELE | 10317 | 11065 | 11065-B01 | 25 ROCHELLE CRES | NORTH YORK | M2J1Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7745 | -79.3508 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9791515 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9791515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9791515 | 9791515 | 9791515 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-120 | 40-120 | 40 | N/A | 67059 | Toronto CDSB | St. Ursula | St. Ursula Catholic Elementary School | ELE | 4519 | 8044 | 8044-B01 | 215 LIVINGSTON RD | SCARBOROUGH | M1E1L8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7498 | -79.1997 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 69 | - | - | N | - | Approved | 42633 | 3013889 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 359142 | 0 | 1312351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1671493 | 0 | 0 | 1018260 | 0 | 324136 | 0 | 0 | 0 | 0 | 0 | 1342396 | 3013889 | 3013889 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 324136
40-121-01 | 40-121 | 40 | N/A | 67059 | Toronto CDSB | St. Victor | St. Victor Catholic Elementary School | ELE | 4525 | 8049 | 8049-B01 | 20 BERNADINE ST | SCARBOROUGH | M1P4M2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7691 | -79.2591 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 245 | - | - | N | - | Approved | 42216 | 5542529 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 181683 | 0 | 4362586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4544269 | 0 | 0 | 998260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998260 | 5542529 | 5542529 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-121-02 | 40-121 | 40 | N/A | 67059 | Toronto CDSB | St. Victor | St. Victor Catholic Elementary School | ELE | 4525 | 8049 | 8049-L01 | 20 BERNADINE ST | SCARBOROUGH | M1P4M2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7691 | -79.2591 | 42205 | 2014-15 | 2015-16 | 42205 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42205 | 711901 | Construction Complete | Land Acquisition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711901 | 0 | 0 | 0 | 0 | 0 | 0 | 711901 | 711901 | 617846 | -94055 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 711901
40-123 | 40-123 | 40 | N/A | 67059 | Toronto CDSB | Sts. Cosmas & Damian | Sts. Cosmas & Damian Catholic Elementary School | ELE | 9519 | 5046 | 5046-B01 | 111 DANESBURY AVE | TORONTO | M6B3L3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7067 | -79.4445 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4294751 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3414771 | 424714 | 455266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4294751 | 4294751 | 4294751 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-124-01 | 40-124 | 40 | N/A | 67059 | Toronto CDSB | The Holy Trinity | The Holy Trinity Catholic Elementary School | ELE | 15531 | 18069 | 18069-B01 | 6 COLONEL SAMUEL SMITH PARK DR | ETOBICOKE | M8V4B7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.5976 | -79.5169 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 536 | - | - | N | - | Approved | 42265 | 12371386 | Construction Complete | New Construction | Consolidation | 2017-18 | 43160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80500 | 80500 | 0 | 0 | 959851 | 0 | 9292477 | 0 | 0 | 0 | 0 | 0 | 10252328 | 10332828 | 10332828 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9292477
40-124-02 | 40-124 | 40 | N/A | 67059 | Toronto CDSB | The Holy Trinity | The Holy Trinity Catholic Elementary School | ELE | 15531 | 18069 | 18069-L01 | 6 COLONEL SAMUEL SMITH PARK DR | ETOBICOKE | M8V4B7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.5976 | -79.5169 | 42265 | 2015-16 | 2015-16 | 42265 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42265 | 517846 | Construction Complete | Land Acquisition | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 2570698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2570698 | 0 | 0 | 0 | 517846 | 0 | 0 | 0 | 0 | 0 | 0 | 517846 | 3088544 | 3088544 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 517846
40-126 | 40-126 | 40 | N/A | 67059 | Toronto CDSB | Venerable John Merlini | Venerable John Merlini Catholic Elementary School | ELE | 9520 | 5048 | 5048-B01 | 123 WHITFIELD AVE | NORTH YORK | M9L1G9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7569 | -79.5798 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3936269 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 2282846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2282846 | 1653423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1653423 | 3936269 | 3936269 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-127 | 40-127 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Antoine Daniel | St. Antoine Daniel Catholic Elementary School | ELE | 24654 | 7589 | 7589-B02 | 160 FINCH AVE W | NORTH YORK | M2N2J2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7776 | -79.4298 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 510 | 5 | 88 | Y | - | Approved | 45135 | 30043752 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45293 | 0 | 0 | 0 | 0 | 2579386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2579386 | 0 | 0 | 771380 | 0 | 23384241 | 0 | 3308745 | 0 | 0 | 0 | 27464366 | 30043752 | 30043752 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 26692986
40-128 | 40-128 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Regina Mundi | Regina Mundi Catholic Elementary School | ELE | 3609 | 7087 | 7087-B02 | 70 PLAYFAIR AVE | NORTH YORK | M6B2P9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7101 | -79.4593 | 42695 | 2015-16 | 2016-17 | - | - | - | 44263 | 2020-21 | 2020-21 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 5 | 88 | N | - | Approved | 44533 | 8784730 | Under Construction | Retrofit | Condition | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5948100 | 0 | 2836630 | 0 | 0 | 0 | 8784730 | 8784730 | 8784730 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 8784730
40-129 | 40-129 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 3287 | 7159 | 7159-B01 | 141 CLOSE AVE | TORONTO | M6K2V6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6384 | -79.435 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Retrofit | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794068 | 0 | 0 | 0 | 794068 | 794068 | 794068 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 794068
40-130 | 40-130 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Nativity of Our Lord | Nativity of Our Lord Catholic Elementary School | ELE | 3448 | 11062 | 11062-B01 | 35 SAFFRON CRES | ETOBICOKE | M9C3T8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6535 | -79.5758 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571267 | 0 | 0 | 0 | 2571267 | 2571267 | 2571267 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2571267
40-131 | 40-131 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Albert | St. Albert Catholic Elementary School | ELE | 3694 | 7451 | 7451-B01 | 1125 MIDLAND AVE | SCARBOROUGH | M1K4H2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7438 | -79.2613 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571267 | 0 | 0 | 0 | 2571267 | 2571267 | 2571267 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2571267
40-132 | 40-132 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. John Vianney | St. John Vianney Catholic Elementary School | ELE | 9513 | 5151 | 5151-B01 | 105 THISTLE DOWN BLVD | ETOBICOKE | M9V1J5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7384 | -79.5539 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Retrofit | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771381 | 0 | 0 | 0 | 771381 | 771381 | 771381 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 771381
40-133 | 40-133 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Elementary School | ELE | 4503 | 8029 | 8029-B01 | 636 GLENHOLME AVE | YORK | M6E3G9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6959 | -79.4451 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571267 | 0 | 0 | 0 | 2571267 | 2571267 | 2571267 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2571267
40-134 | 12-220+40-134 | 40 | N/A | 67059 | Toronto CDSB | Bishop Macdonell | Bishop Macdonell Catholic Elementary School | ELE | 24632 | 19639 | 19639-B01 | 20 BRUNEL CRT | TORONTO | M5V0R5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6395 | -79.3945 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 536 | - | - | N | - | Approved | 42912 | 19624176 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19624176 | 19624176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19624176 | 19624176 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-135 | 40-135 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Blessed Pope Paul VI | Blessed Pope Paul VI Catholic Elementary School | ELE | 3593 | 7370 | 7370-B01 | 270 LAUGHTON AVE | TORONTO | M6N2X8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6743 | -79.4575 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 45166 | 2162934 | Planned | Retrofit | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2162934 | 0 | 0 | 0 | 2162934 | 2162934 | 2009044 | -153890 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2162934
40-136 | 40-136 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Barbara | St. Barbara Catholic Elementary School | ELE | 3779 | 7514 | 7514-B01 | 25 JANRAY DR | SCARBOROUGH | M1G1Y2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7624 | -79.2188 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-137-01 | 40-137 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Bernard | St. Bernard Catholic Elementary School | ELE | 3808 | 7537 | 7537-B01 | 12 DUCKWORTH ST | NORTH YORK | M6M4W4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7027 | -79.5 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-137-02 | 40-137 | 40 | N/A | 67059 | Toronto CDSB | St. Bernard | St. Bernard Catholic Elementary School | ELE | 3808 | 7537 | 7537-B01 | 12 DUCKWORTH ST | NORTH YORK | M6M4W4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7027 | -79.5 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Other | Other | - | - | 0 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 2600000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-138 | 40-138 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Edmund Campion | St. Edmund Campion Catholic Elementary School | ELE | 3905 | 7607 | 7607-B01 | 30 HIGHCASTLE RD | SCARBOROUGH | M1E4N1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7881 | -79.2156 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2024-25 | 45658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-139 | 40-139 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Gerald | St. Gerald Catholic Elementary School | ELE | 3975 | 7663 | 7663-B01 | 200 OLD SHEPPARD AVE | NORTH YORK | M2J3L9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7804 | -79.3263 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-140 | 40-140 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Jean de Brébeuf | St. Jean de Brébeuf Catholic Elementary School | ELE | 4029 | 7701 | 7701-B01 | 101 DEAN PARK RD | SCARBOROUGH | M1B2X2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8023 | -79.1739 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-141 | 40-141 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Jude | St. Jude Catholic Elementary School | ELE | 4154 | 7792 | 7792-B01 | 3251 WESTON RD | NORTH YORK | M9M2T9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7403 | -79.5394 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514254 | 0 | 0 | 0 | 514254 | 514254 | 514254 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 514254
40-142-01 | 40-142 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Kevin | St. Kevin Catholic Elementary School | ELE | 4158 | 7795 | 7795-B01 | 15 MURRAY GLEN DR | SCARBOROUGH | M1R3J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7511 | -79.3064 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-142-02 | 40-142 | 40 | N/A | 67059 | Toronto CDSB | St. Kevin | St. Kevin Catholic Elementary School | ELE | 4158 | 7795 | 7795-B01 | 15 MURRAY GLEN DR | SCARBOROUGH | M1R3J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7511 | -79.3064 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Other | Other | - | - | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 1900000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-143 | 40-143 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Pope Francis | Pope Francis Catholic Elementary School | ELE | 4185 | 7814 | 7814-B01 | 319 OSSINGTON AVE | TORONTO | M6J3A6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6516 | -79.421 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Retrofit | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794069 | 0 | 0 | 0 | 794069 | 794069 | 794069 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 794069
40-144 | 40-144 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Nicholas of Bari | St. Nicholas of Bari Catholic Elementary School | ELE | 4338 | 7916 | 7916-B01 | 363 ROGERS RD | YORK | M6E1R6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6833 | -79.4607 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-145 | 40-145 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Santa Maria | Santa Maria Catholic Elementary School | ELE | 5984 | 8518 | 8518-B01 | 25 AVON AVE | TORONTO | M6N4X8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6813 | -79.4778 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028508 | 0 | 0 | 0 | 1028508 | 1028508 | 1028508 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1028508
40-147-01 | 40-147 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Father Serra | Father Serra Catholic Elementary School | ELE | 9504 | 5047 | 5047-B01 | 111 SUN ROW DR | ETOBICOKE | M9P3J3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6857 | -79.5375 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-147-02 | 40-147 | 40 | N/A | 67059 | Toronto CDSB | Father Serra | Father Serra Catholic Elementary School | ELE | 9504 | 5047 | 5047-B01 | 111 SUN ROW DR | ETOBICOKE | M9P3J3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6857 | -79.5375 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Other | Other | - | - | 0 | 0 | 3900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 3900000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-148 | 40-148 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Dominic Savio | St. Dominic Savio Catholic Elementary School | ELE | 9549 | 10195 | 10195-B01 | 50 TIDESWELL BLVD | SCARBOROUGH | M1B5X3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7983 | -79.1555 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-149 | 40-149 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Andre | St. Andre Catholic Elementary School | ELE | 14796 | 10050 | 10050-B02 | 36 YVONNE AVE | NORTH YORK | M3L1C9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7236 | -79.5175 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 1542762 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
40-151 | 40-151 | 40 | N/A | 67059 | Toronto CDSB | St. Michael's Choir | St. Michael's Choir Catholic Elementary School | ELE | 24777 | 19784 | 19784-B01 | TBD | TORONTO | TBD | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | TBD | TBD | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 300 | - | - | N | - | Planned | - | 0 | Planned | New Construction | Condition | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11155222 | 0 | 0 | 0 | 0 | 0 | 11155222 | 11155222 | 11155222 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11155222
40-152 | 40-152 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Holy Angels | Holy Angels Catholic Elementary School | ELE | 24778 | 7147 | 7147-B02 | 65 JUTLAND RD | ETOBICOKE | M8Z2G6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6282 | -79.5177 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 600 | 5 | 88 | Y | - | Approved | 44543 | 20360797 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17299294 | 0 | 3061503 | 0 | 0 | 0 | 20360797 | 20360797 | 20360797 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 20360797
40-153 | 40-153 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Matthias | St. Matthias Catholic Elementary School | ELE | 24779 | 7880 | 7880-B02 | 101 VAN HORNE AVE | NORTH YORK | M2J2S8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7845 | -79.3595 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 525 | 5 | 88 | Y | - | Approved | 44881 | 27329038 | Planned | New Construction | Consolidation | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049077 | 0 | 22299904 | 0 | 3980057 | 0 | 0 | 0 | 27329038 | 27329038 | 27329038 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 26279961
40-154 | 40-154 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Margaret | St. Margaret Catholic Elementary School | ELE | 4196 | 7823 | 7823-B01 | 85 CARMICHAEL AVE | NORTH YORK | M5M2X1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7361 | -79.4267 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 67 | 3 | 49 | Y | - | Planned | - | 0 | Planned | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 2397818 | 0 | 0 | 0 | 0 | 0 | 0 | 596214 | 0 | 0 | 0 | 0 | 0 | 2994032 | 0 | 0 | 399304 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1942066 | 4936098 | 4936098 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CP (CP+CC) | YES | 1542762
40-155 | 40-155 | 40 | N/A | 67059 | Toronto CDSB | All Saints | All Saints Catholic Elementary School | ELE | 10318 | 11066 | 11066-B01 | 1435 ROYAL YORK RD | ETOBICOKE | M9P3A7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6853 | -79.5279 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
40-156 | 40-156 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Baycrest | Baycrest Catholic Elementary School | ELE | 25122 | 9911 | 9911-B02 | 145 BAYCREST AVE | NORTH YORK | M6A1W4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7267 | -79.4443 | 43796 | 2019-20 | 2019-20 | - | - | - | - | - | - | 43796 | 2019-20 | 2019-20 | - | - | - | - | - | - | 504 | 3 | 49 | Y | - | Approved | 43796 | 12339687 | Under Construction | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 9199709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9199709 | 0 | 0 | 1597216 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 3139978 | 12339687 | 12339687 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CP (CP+CC) | YES | 1542762
40-157 | 40-157 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | Buttonwood | Buttonwood Catholic Elementary School | ELE | 25050 | 9534 | 9534-B02 | 100 ALLANHURST DR | TORONTO | M9A4K4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6803 | -79.5193 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 600 | 5 | 88 | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2025-26 | 46023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13159951 | 0 | 2727603 | 0 | 0 | 0 | 15887554 | 15887554 | 15887554 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15887554
40-158 | 40-158 | 40 | N/A | 67059 | Toronto CDSB | Buttonwood | Buttonwood Catholic Secondary School | SEC | 25050 | 9534 | 9534-B03 | 100 ALLANHURST DR | ETOBICOKE | M9A4K4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6807 | -79.5191 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 900 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26355588 | 0 | 0 | 0 | 0 | 0 | 26355588 | 26355588 | 26355588 | 0 | - | No, Site to be acquired. Sign installation planned for November 1, 2023 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 26355588
40-159 | 40-159 | 40 | N/A | 67059 | Toronto CDSB | Bishop Allen Academy | Bishop Allen Academy Catholic Secondary School | SEC | 25490 | 5216 | 5216-B02 | 721 ROYAL YORK RD | ETOBICOKE | M8Y2T3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.634 | -79.5054 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 1300 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36013876 | 0 | 0 | 0 | 0 | 0 | 36013876 | 36013876 | 36013876 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 36013876
40-160 | 40-160 | 40 | N/A | 67059 | Toronto CDSB | Lorreto Abbey | Lorreto Abbey Catholic Secondary School | SEC | 3387 | 7226 | 7226-B01 | 101 MASON BLVD | NORTH YORK | M5M3E2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7409 | -79.4111 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 620 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2024-25 | 45663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24088380 | 0 | 0 | 0 | 0 | 0 | 24088380 | 24088380 | 24088380 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 24088380
40-161 | 40-161 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Marguerite Bourgeoys | St. Marguerite Bourgeoys Catholic Elementary School | ELE | 3067 | 7010 | 7010-B01 | 75 ALEXMUIR BLVD | SCARBOROUGH | M1V1H6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8081 | -79.2855 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Child Care | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545521 | 0 | 0 | 0 | 545521 | 545521 | 545521 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 545521
40-162 | 40-162 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Florence | St. Florence Catholic Elementary School | ELE | 3928 | 7626 | 7626-B01 | 101 MURISON BLVD | SCARBOROUGH | M1B2L6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7987 | -79.2073 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | - | Planned | Retrofit | Child Care | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 818281 | 0 | 0 | 0 | 818281 | 818281 | 818281 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 818281
40-163 | 40-163 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Malachy | St. Malachy Catholic Secondary School | ELE | 4186 | 7815 | 7815-B01 | 80 BENNETT RD | SCARBOROUGH | M1E3Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7713 | -79.1658 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Child Care | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636562 | 0 | 0 | 0 | 1636562 | 1636562 | 1636562 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1636562
40-164 | 40-152 | 40 | N/A | 67059 | Toronto CDSB | Holy Angels | Holy Angels Catholic Elementary School | ELE | 24778 | 7147 | 7147-L02 | 65 JUTLAND RD | ETOBICOKE | M8Z2G6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6282 | -79.5177 | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44543 | 1240631 | Construction Complete | Land Acquisition | Accommodation Pressure | 2015-16 | 42490 | 0 | 0 | 0 | 0 | 1240631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240631 | 1240631 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-165 | 40-152 | 40 | N/A | 67059 | Toronto CDSB | Holy Angels | Holy Angels Catholic Elementary School | ELE | 24778 | 7147 | 7147-B02 | 65 JUTLAND RD | ETOBICOKE | M8Z2G6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6282 | -79.5177 | 43131 | 2017-18 | 2017-18 | - | - | - | 44543 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44543 | 992200 | Under Construction | Demolition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992200 | 0 | 0 | 0 | 0 | 0 | 992200 | 992200 | 992200 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 992200
40-166 | 40-095 | 40 | N/A | 67059 | Toronto CDSB | St. Leo | St. Leo Catholic Elementary School | ELE | 24653 | 10115 | 10115-B01 | 165 STANLEY AVE | ETOBICOKE | M8V1P1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6142 | -79.4963 | 44677 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44677 | 3061514 | Under Construction | Demolition | Consolidation | 2022-23 | 45169 | 0 | 0 | 0 | 0 | 2916698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916698 | 0 | 0 | 0 | 0 | 144816 | 0 | 0 | 0 | 0 | 0 | 144816 | 3061514 | 3061514 | 0 | - |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 144816
40-167 | 40-167 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Elizabeth | St. Elizabeth Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | ETOBICOKE | M9B1J8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 600 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16041997 | 0 | 3324941 | 0 | 0 | 0 | 19366938 | 19366938 | 19366938 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19366938
40-168 | 40-168 | 40 | 211 - CMSM Toronto | 67059 | Toronto CDSB | St. Monica | St. Monica Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | TORONTO | M4P1T4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 550 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15212297 | 0 | 3422733 | 0 | 0 | 0 | 18635030 | 18635030 | 18635030 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 18635030
40-169 | 40-153 | 40 | N/A | 67059 | Toronto CDSB | St. Matthias | St. Matthias Catholic Elementary School | ELE | 4289 | 7880 | 7880-B01 | 101 VAN HORNE AVE | NORTH YORK | M2J2S8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7845 | -79.3595 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44881 | 759440 | Planned | Demolition | Consolidation | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759440 | 0 | 0 | 0 | 0 | 0 | 759440 | 759440 | 759440 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 759440
40-170 | 40-076 | 40 | N/A | 67059 | Toronto CDSB | St. Fidelis | St. Fidelis Catholic Elementary School | ELE | 25015 | 10001 | 10001-L01 | 155 FALSTAFF AVE | NORTH YORK | M6L2E5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7177 | -79.4958 | [6 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - |  | 45057 | 2098195 | Planned | Demolition | Accommodation Pressure |  |  | 0 | 0 | 0 | 0 | 1933864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933864 | 0 | 0 | 0 | 0 | 913133 | 0 | 0 | 0 | 0 | 0 | 913133 | 2846997 | 2846997 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 913133
40-171 | 40-127 | 40 | N/A | 67059 | Toronto CDSB | St. Antoine Daniel CES | St. Antoine Daniel Catholic Elementary School | ELE | [7 empty] | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | [8 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - |  |  |  | Planned | Demolition | Accommodation Pressure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670455 | 0 | 0 | 0 | 0 | 0 | 670455 | 670455 | 670455 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 670455
40-172 | 40-017 | 40 | N/A | 67059 | Toronto CDSB | Dante Alighieri | Dante Alighieri Catholic Secondary School | SEC | 25103 | 7087 | 7087-B02 | 70 PLAYFAIR AVE | NORTH YORK | M6B2P9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7102 | -79.458 | 40731 | [8 empty] | - | - | - | - | - | - | - | - | - |  |  |  |  | - | Planned | - | 0 | Planned | Demolition | Accommodation Pressure |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 0
40-173 | 40-160 | 40 | N/A | 67059 | Toronto CDSB |  |  | ELE | 3387 |  |  |  | NORTH YORK |  |  | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | [8 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - |  |  | 2098195 | Planned | Demolition | Accommodation Pressure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
40-174 | 40-010 | 40 | N/A | 67059 | Toronto CDSB | Blessed Cardinal Newman | Blessed Cardinal Newman Catholic Secondary School | SEC | 24526 | 19531 | 19531-B0- | 100 BRIMLEY RD S | SCARBOROUGH | M1M3X4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7129 | -79.2427 | 42317 | 2015-16 | 2015-16 | - | - | - |  |  |  | - | - | - | - | - | - | - | - | - |  | - | - | N | - | Planned | - | 0 | Planned | Demolition | Accommodation Pressure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 0
40-175 | 40-169 | 40 | N/A | 67059 | Toronto CDSB | Block 9 Concord Place |  | ELE |  |  |  | Sheppard/Leslie area | NORTH YORK |  |  | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | [20 empty] | 450 |  |  | N |  | Planned |  |  | Planned | New Construction | Accommodation Pressure | 2028-29 | [5 empty] | 35000000 | [10 empty] | 35000000 | [10 empty] | 0 | 35000000 | 35000000 | 0
41-001 | 41-001 | 41 | N/A | 67067 | Peterborough VNCCDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 24595 | 10105 | 10105-B01 | 1355 LANSDOWNE ST W | PETERBOROUGH | K9J7M3 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2794 | -78.3559 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361498 | 0 | 0 | 0 | 0 | 0 | 361498 | 361498 | 0 |  | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 361498
41-002 | 41-002 | 41 | N/A | 67067 | Peterborough VNCCDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 24595 | 10105 | 10105-B01 | 1355 LANSDOWNE ST W | PETERBOROUGH | K9J7M3 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2794 | -78.3559 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3613497 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3705590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3705590 | 3705590 | 3613497 | -92093 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-003 | 41-003 | 41 | N/A | 67067 | Peterborough VNCCDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24595 | 10105 | 10105-B01 | 1355 LANSDOWNE ST W | PETERBOROUGH | K9J7M3 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2794 | -78.3559 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 20487 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20487 | 20487 | 20487 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-004 | 41-004 | 41 | N/A | 67067 | Peterborough VNCCDSB | Good Shepherd | Good Shepherd Catholic Elementary School | ELE | 9904 | 10319 | 10319-B01 | 20 FARMINGTON DR | COURTICE | L1E3B9 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9036 | -78.7798 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8749592 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 332969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419567 | 752536 | 7997056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7997056 | 8749592 | 8749592 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-005 | 41-005 | 41 | N/A | 67067 | Peterborough VNCCDSB | Holy Cross | Holy Cross Catholic Secondary School | SEC | 9277 | 10105 | 10105-B01 | 1355 LANSDOWNE ST W | PETERBOROUGH | K9J7M3 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2794 | -78.3559 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10619435 | Construction Complete | Addition | Other | 2010-11 | 40422 | 1360000 | 0 | 241848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 2351848 | 8267587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8267587 | 10619435 | 10619435 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-006 | 41-006 | 41 | N/A | 67067 | Peterborough VNCCDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 10815 | 12050 | 12050-B01 | 125 ASPEN SPRINGS DR | BOWMANVILLE | L1C0C6 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9023 | -78.7071 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 13205763 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278585 | 278585 | 12927178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12927178 | 13205763 | 13205763 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-007 | 41-007 | 41 | N/A | 67067 | Peterborough VNCCDSB | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 10263 | 10319 | 10319-B02 | 2260 COURTICE RD | COURTICE | L1E2M8 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9019 | -78.7734 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16870854 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 129410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998633 | 1128043 | 15742811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15742811 | 16870854 | 16870854 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-008 | 41-008 | 41 | N/A | 67067 | Peterborough VNCCDSB | Immaculate Conception | Immaculate Conception Catholic Elementary School | ELE | 9281 | 10106 | 10106-B01 | 76 ROBINSON ST | PETERBOROUGH | K9H1E8 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3048 | -78.31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2333468 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333468 | 2333468 | 2333468 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-010 | 41-010 | 41 | N/A | 67067 | Peterborough VNCCDSB | Monsignor Leo Cleary | Monsignor Leo Cleary Catholic Elementary School | ELE | 9271 | 10099 | 10099-B01 | 3820 COURTICE RD | COURTICE | L1E2L5 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9319 | -78.7898 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 26 | - | - | N | - | Not Required | - | 942923 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 422315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422315 | 0 | 0 | 520608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520608 | 942923 | 942923 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-011 | 41-011 | 41 | N/A | 67067 | Peterborough VNCCDSB | Monsignor O`Donoghue | Monsignor O`Donoghue Catholic Elementary School | ELE | 9861 | 10299 | 10299-B01 | 2400 MARSDALE DR | PETERBOROUGH | K9L1Z2 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3007 | -78.2922 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6193707 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 263526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 663526 | 5530181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5530181 | 6193707 | 6193707 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-014 | 41-014 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. John | St. John Catholic Elementary School | ELE | 10605 | 5623 | 5623-B01 | 746 PARK ST S | PETERBOROUGH | K9J3T4 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2845 | -78.3205 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2993387 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 928400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 928400 | 2064987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2064987 | 2993387 | 2993387 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-016 | 41-016 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 9244 | 10073 | 10073-B01 | 240 BELLEVUE ST | PETERBOROUGH | K9H5E5 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3212 | -78.3275 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6340331 | Construction Complete | Addition | Other | 2011-12 | 40787 | 800000 | 0 | 943000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2743000 | 2000000 | 0 | 1597331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3597331 | 6340331 | 6340331 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-017 | 41-017 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 9266 | 10095 | 10095-B01 | 74 TORONTO RD | PORT HOPE | L1A3R9 | 35-12-61-409 | Port Hope | Port Hope M | Northumberland Co | NORTHUMBERLAND | East | South | 43.9534 | -78.3136 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5090491 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012301 | 1012301 | 4078190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4078190 | 5090491 | 5090491 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-018 | 41-018 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Catherine | St. Catherine Catholic Elementary School | ELE | 9245 | 10074 | 10074-B01 | 1575 GLENFOREST BLVD | PETERBOROUGH | K9K2J6 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2959 | -78.3654 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 193 | - | - | N | - | Not Required | - | 2753837 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1382877 | 0 | 1370960 | 0 | 0 | 0 | 0 | 0 | 2753837 | 2753837 | 2753837 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1370960
41-020 | 41-020 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 10264 | 10471 | 10471-B01 | 1774 RUDELL RD | NEWCASTLE | L1B1E2 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9105 | -78.5996 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7196790 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579407 | 579407 | 6617383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6617383 | 7196790 | 7196790 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-022 | 41-022 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 9268 | 10097 | 10097-B01 | 90 PARKWAY CRES | BOWMANVILLE | L1C1C3 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9028 | -78.6751 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2948435 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2948435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2948435 | 2948435 | 2948435 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-023 | 41-023 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 9268 | 10097 | 10097-B01 | 90 PARKWAY CRES | BOWMANVILLE | L1C1C3 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9028 | -78.6751 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 147 | - | - | N | - | Not Required | - | 3390188 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453753 | 0 | 1936435 | 0 | 0 | 0 | 0 | 0 | 3390188 | 3390188 | 3390188 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1936435
41-024 | 41-024 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 9253 | 10082 | 10082-B01 | 531 ENNIS RD | ENNISMORE | K0L1T0 | 35-12-66-623 | Selwyn | Selwyn Tp | Peterborough Co | PETERBOROUGH | East | South | 44.4101 | -78.4277 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1781586 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781586 | 1781586 | 1781586 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-025 | 41-025 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 9253 | 10082 | 10082-B01 | 531 ENNIS RD | ENNISMORE | K0L1T0 | 35-12-66-623 | Selwyn | Selwyn Tp | Peterborough Co | PETERBOROUGH | East | South | 44.4101 | -78.4277 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2412587 | Construction Complete | Addition | Other | 2013-14 | 41518 | 880000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880000 | 0 | 0 | 1532587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532587 | 2412587 | 2412587 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-028 | 41-028 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Mary | St. Mary Catholic Secondary School | SEC | 9276 | 10104 | 10104-B01 | 1050 BIRCHWOOD TRAIL | COBOURG | K9A5S9 | 35-12-61-403 | Cobourg | Cobourg T | Northumberland Co | NORTHUMBERLAND | East | South | 43.9833 | -78.1696 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2540624 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40624 | 40624 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2540624 | 2540624 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-030 | 41-030 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 9247 | 10076 | 10076-B01 | 300 OTONABEE DR | PETERBOROUGH | K9J8L9 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2767 | -78.3083 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1014768 | Construction Complete | Addition | Other | 2013-14 | 41518 | 150000 | 0 | 0 | 0 | 0 | 0 | 122000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272000 | 0 | 0 | 742768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742768 | 1014768 | 1014768 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-031 | 41-031 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Paul | St. Paul Catholic Elementary School | ELE | 9248 | 10077 | 10077-B01 | 1101 HILLIARD ST | PETERBOROUGH | K9H5S3 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3329 | -78.3254 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1060921 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 665000 | 0 | 0 | 395921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395921 | 1060921 | 1060921 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-033 | 41-033 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Paul | St. Paul Catholic Elementary School | ELE | 9255 | 10084 | 10084-B01 | 55 OAK ST | NORWOOD | K0L2V0 | 35-12-66-615 | Asphodel-Norwood | Asphodel-Norwood Tp | Peterborough Co | PETERBOROUGH | East | South | 44.3781 | -77.9833 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 200 | - | - | N | - | Not Required | - | 4599147 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969170 | 0 | 3629977 | 0 | 0 | 0 | 0 | 0 | 4599147 | 4599147 | 4599147 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3629977
41-034 | 41-034 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Stephen | St. Stephen Catholic Secondary School | SEC | 9275 | 10103 | 10103-B01 | 300 SCUGOG ST | BOWMANVILLE | L1C3K2 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.928 | -78.6986 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9353482 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9353482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9353482 | 9353482 | 9353482 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-036 | 41-036 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 10037 | 10372 | 10372-B01 | 260 ANGELINE ST S | LINDSAY | K9V0J8 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.3348 | -78.7423 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15058942 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 21698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66727 | 88425 | 14553326 | 417191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14970517 | 15058942 | 15058942 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
41-037 | 41-037 | 41 | N/A | 67067 | Peterborough VNCCDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 9252 | 10081 | 10081-B01 | 405 DOURO FOURTH LINE | DOURO-DUMMER | K0L2H0 | 35-12-66-618 | Douro-Dummer | Peterborough Co | Peterborough Co | PETERBOROUGH | East | South | 44.3768 | -78.1918 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 92 | - | - | - | - | Approved | 45093 | 6066798 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 45017 | 281009 | 674126 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455135 | 0 | 0 | 0 | 0 | 4611663 | 0 | 0 | 0 | 0 | 0 | 4611663 | 6066798 | 6066798 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4611663
42-001 | 42-001 | 42 | N/A | 67075 | York CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15762 | 18080 | 18080-B01 | 320 BLOOMINGTON RD | AURORA | L4G0M1 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9608 | -79.4695 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-002 | 42-002 | 42 | N/A | 67075 | York CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15762 | 18080 | 18080-B01 | 320 BLOOMINGTON RD | AURORA | L4G0M1 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9608 | -79.4695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 20135775 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21766652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21766652 | 21766652 | 20482750 | -1283902 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-003 | 42-003 | 42 | N/A | 67075 | York CDSB | All Saints | All Saints Catholic Elementary School | ELE | 9845 | 10295 | 10295-B01 | 130 CASTLEMORE AVE | MARKHAM | L6C2P9 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8963 | -79.3075 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6540300 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6540300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6540300 | 6540300 | 6540300 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-004 | 42-004 | 42 | N/A | 67075 | York CDSB | Blessed Trinity | Blessed Trinity Catholic Elementary School | ELE | 9769 | 5135 | 5135-B01 | 230 HAWKER RD | MAPLE | L6A2R2 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8439 | -79.5252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12688618 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12688618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12688618 | 12688618 | 12688618 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-006 | 42-006 | 42 | N/A | 67075 | York CDSB | Cardinal Carter | Cardinal Carter Catholic Secondary School | SEC | 3393 | 5052 | 5052-B01 | 210 BLOOMINGTON RD | AURORA | L4G0P9 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9616 | -79.4664 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4767955 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4767955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4767955 | 4767955 | 4767955 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-007 | 42-007 | 42 | N/A | 67075 | York CDSB | Cardinal Carter | Cardinal Carter Catholic Secondary School | SEC | 3393 | 5052 | 5052-B01 | 210 BLOOMINGTON RD | AURORA | L4G0P9 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9616 | -79.4664 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2082938 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 2082938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082938 | 2082938 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-008 | 42-008 | 42 | N/A | 67075 | York CDSB | Corpus Christi | Corpus Christi Catholic Elementary School | ELE | 9777 | 10261 | 10261-B01 | 35 SQUIRE DR | RICHMOND HILL | L4S1C6 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8974 | -79.4381 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5370300 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5370300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5370300 | 5370300 | 5370300 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-009 | 42-009 | 42 | N/A | 67075 | York CDSB | Divine Mercy | Divine Mercy Catholic Elementary School | ELE | 6065 | 8554 | 8554-B01 | 251 MELVILLE AVE | MAPLE | L6A1Z1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8575 | -79.5327 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3048325 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3048325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3048325 | 3048325 | 3048325 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-010 | 42-010 | 42 | N/A | 67075 | York CDSB | Father Bressani | Father Bressani Catholic Secondary School | SEC | 4457 | 7996 | 7996-B01 | 250 ANSLEY GROVE RD | WOODBRIDGE | L4L3W4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7986 | -79.5635 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 880921 | Construction Complete | Retrofit | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880921 | 880921 | 880921 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-011 | 42-011 | 42 | N/A | 67075 | York CDSB | Father Frederick McGinn | Father Frederick McGinn Catholic Elementary School | ELE | 10918 | 12080 | 12080-B01 | 61 BROCKDALE ST | RICHMOND HILL | L4E4W2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9351 | -79.4768 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11313080 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11313080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11313080 | 11313080 | 11313080 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-013 | 42-013 | 42 | N/A | 67075 | York CDSB | Father John Kelly | Father John Kelly Catholic Elementary School | ELE | 3247 | 7136 | 7136-B01 | 1-9350 KEELE ST | MAPLE | L6A1P4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8403 | -79.5092 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1521000 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 1521000 | 1521000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-014 | 42-014 | 42 | N/A | 67075 | York CDSB | Father Michael McGivney | Father Michael McGivney Catholic Secondary School | SEC | 3212 | 7111 | 7111-B01 | 5300 14TH AVE | MARKHAM | L3S3K8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8497 | -79.2784 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5551516 | Construction Complete | Retrofit | Other | 2016-17 | 42614 | 0 | 0 | 5551516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5551516 | 5551516 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-015 | 42-015 | 42 | N/A | 67075 | York CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 24310 | 19302 | 19302-B01 | 200 CHATFIELD DR | WOODBRIDGE | L4H0Z5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8489 | -79.5694 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 694 | - | - | N | - | Approved | 44280 | 11645676 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 42018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272946 | 0 | 10247835 | 0 | 0 | 0 | 0 | 0 | 10520781 | 10520781 | 10520781 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10247835
42-016 | 42-016 | 42 | N/A | 67075 | York CDSB | Holy Jubilee | Holy Jubilee Catholic Elementary School | ELE | 9844 | 10294 | 10294-B01 | 400 ST. JOAN OF ARC AVE | MAPLE | L6A2S8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8699 | -79.5236 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9849103 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9558317 | 0 | 290786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9849103 | 9849103 | 9849103 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-017 | 42-017 | 42 | N/A | 67075 | York CDSB | Holy Name | Holy Name Catholic Elementary School | ELE | 11110 | 12315 | 12315-B01 | 65 SPRING HILL DR | KING CITY | L7B0B6 | 35-11-27-603 | King | King Tp | York R | YORK | GTA | South | 43.9292 | -79.5084 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 14004844 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 1658085 | 0 | 1685085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3343170 | 10661674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10661674 | 14004844 | 14004844 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-019 | 42-019 | 42 | N/A | 67075 | York CDSB | Jean Vanier | Jean Vanier Catholic Secondary School | SEC | 11007 | 12140 | 12140-B01 | 10475 BAYVIEW AVE | RICHMOND HILL | L4C3P2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8865 | -79.4179 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 31972000 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31972000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31972000 | 31972000 | 31972000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-020 | 42-020 | 42 | N/A | 67075 | York CDSB | Light of Christ | Light of Christ Catholic Elementary School | ELE | 3382 | 7221 | 7221-B01 | 290 MCCLELLAN WAY | AURORA | L4G6P3 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9708 | -79.4846 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2340000 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340000 | 2340000 | 2340000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-022 | 42-022 | 42 | N/A | 67075 | York CDSB | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 3441 | 7264 | 7264-B01 | 7100 BIRCHMOUNT RD | MARKHAM | L3R4H2 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8257 | -79.318 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 760500 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760500 | 760500 | 760500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-024 | 42-024 | 42 | N/A | 67075 | York CDSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 9768 | 10253 | 10253-B01 | 715 KINGSMERE AVE | NEWMARKET | L3X1L4 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0393 | -79.4368 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8132554 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8132554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8132554 | 8132554 | 8132554 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-025 | 42-025 | 42 | N/A | 67075 | York CDSB | Our Lady Help of Christians | Our Lady Help of Christians Catholic Elementary School | ELE | 10556 | 11166 | 11166-B01 | 275 REDSTONE RD | RICHMOND HILL | L4S2H1 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8919 | -79.3997 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7255310 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7255310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7255310 | 7255310 | 7255310 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-026 | 42-026 | 42 | N/A | 67075 | York CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 3524 | 7317 | 7317-B01 | 191 CROFTERS RD | WOODBRIDGE | L4L7G3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8117 | -79.6014 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3428100 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3428100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3428100 | 3428100 | 3428100 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-028-01 | 42-028 | 42 | 234 - CMSM York | 67075 | York CDSB | Our Lady of Good Counsel | Our Lady of Good Counsel Catholic Elementary School | ELE | 24471 | 19474 | 19474-B01 | 801 MURRELL BLVD | SHARON | L9N0P6 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.1046 | -79.4432 | 41879 | 2013-14 | 2014-15 | - | - | - | 41879 | 2013-14 | 2014-15 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 461 | 3 | 72 | N | - | Approved | 42650 | 15737938 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484592 | 0 | 8727656 | 0 | 1453777 | 0 | 0 | 0 | 10666025 | 10666025 | 10666025 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10181433
42-028-02 | 42-028 | 42 | N/A | 67075 | York CDSB | Our Lady of Good Counsel | Our Lady of Good Counsel Catholic Elementary School | ELE | 24471 | 19474 | 19474-L01 | 801 MURRELL BLVD | SHARON | L9N0P6 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.1046 | -79.4432 | 42650 | 2016-17 | 2016-17 | 42650 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42650 | 5093965 | Construction Complete | Land Acquisition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 5071913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5071913 | 0 | 0 | 0 | 5093965 | 0 | 0 | 0 | 0 | 0 | 0 | 5093965 | 10165878 | 10165878 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 5093965
42-029 | 42-029 | 42 | N/A | 67075 | York CDSB | Our Lady of Hope | Our Lady of Hope Catholic Elementary School | ELE | 10227 | 10465 | 10465-B01 | 80 RED CARDINAL TRAIL | RICHMOND HILL | L4E4B8 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9548 | -79.4762 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5850000 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5850000 | 5850000 | 5850000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-031 | 42-031 | 42 | N/A | 67075 | York CDSB | Our Lady of Peace | Our Lady of Peace Catholic Elementary School | ELE | 3512 | 7307 | 7307-B01 | 301 BARRHILL RD | MAPLE | L6A1J5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8475 | -79.5039 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2281500 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281500 | 2281500 | 2281500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-033 | 42-033 | 42 | N/A | 67075 | York CDSB | Our Lady of the Annunciation | Our Lady of the Annunciation Catholic Elementary School | ELE | 3498 | 7296 | 7296-B01 | 30 BAYSWATER AVE | RICHMOND HILL | L4E2L3 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9525 | -79.448 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3079804 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2183753 | 0 | 896051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3079804 | 3079804 | 3079804 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-034 | 42-034 | 42 | N/A | 67075 | York CDSB | Our Lady of the Lake | Our Lady of the Lake Catholic Secondary School | SEC | 9846 | 10296 | 10296-B01 | 185 GLENWOODS AVE | KESWICK | L4P2W6 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.2133 | -79.4602 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 516117 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516117 | 516117 | 516117 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-035 | 42-035 | 42 | N/A | 67075 | York CDSB | Our Lady of the Lake | Our Lady of the Lake Catholic Secondary School | SEC | 9846 | 10296 | 10296-B01 | 185 GLENWOODS AVE | KESWICK | L4P2W6 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.2133 | -79.4602 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 14547891 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14547891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14547891 | 14547891 | 14547891 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-037 | 42-037 | 42 | N/A | 67075 | York CDSB | Pope Francis | Pope Francis Catholic Elementary School | ELE | 24434 | 19436 | 19436-B01 | 15 AV SECORD | KLEINBURG | L4H3Z3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8302 | -79.6556 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 602 | - | - | N | - | Approved | 44280 | 12267015 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42619 | 0 | 0 | 2953997 | 0 | 553600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3507597 | 0 | 0 | 1397841 | 0 | 7361577 | 0 | 0 | 0 | 0 | 0 | 8759418 | 12267015 | 12267015 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7361577
42-039 | 42-039 | 42 | N/A | 67075 | York CDSB | Sacred Heart | Sacred Heart Catholic Secondary School | SEC | 3639 | 7411 | 7411-B01 | 908 LEMAR RD | NEWMARKET | L3Y1R9 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0578 | -79.4409 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 13861979 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13861979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13861979 | 13861979 | 13861979 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-040 | 42-040 | 42 | N/A | 67075 | York CDSB | San Lorenzo Ruiz | San Lorenzo Ruiz Catholic Elementary School | ELE | 10797 | 12002 | 12002-B01 | 840 BUR OAK AVE | MARKHAM | L6E0E1 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.897 | -79.2826 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10040305 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10040305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10040305 | 10040305 | 10040305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-041 | 42-041 | 42 | N/A | 67075 | York CDSB | San Lorenzo Ruiz | San Lorenzo Ruiz Catholic Elementary School | ELE | 10797 | 12002 | 12002-B01 | 840 BUR OAK AVE | MARKHAM | L6E0E1 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.897 | -79.2826 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Not Required | - | 2091118 | Construction Complete | Addition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 0 | 833790 | 0 | 0 | 0 | 0 | 0 | 1765684 | 1765684 | 2091118 | 325434 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 833790
42-042 | 42-042 | 42 | N/A | 67075 | York CDSB | Sir Richard W Scott | Sir Richard W Scott Catholic Elementary School | ELE | 9547 | 10193 | 10193-B01 | 90 ROXBURY ST | MARKHAM | L3S3S8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8589 | -79.2468 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 397987 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397987 | 397987 | 397987 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-043 | 42-043 | 42 | N/A | 67075 | York CDSB | Sir Richard W Scott | Sir Richard W Scott Catholic Elementary School | ELE | 9547 | 10193 | 10193-B01 | 90 ROXBURY ST | MARKHAM | L3S3S8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8589 | -79.2468 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 247618 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247618 | 247618 | 247618 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-045 | 42-045 | 42 | N/A | 67075 | York CDSB | St. Agnes of Assisi | St. Agnes of Assisi Catholic Elementary School | ELE | 10224 | 10464 | 10464-B01 | 120 LA ROCCA AVE | WOODBRIDGE | L4H2A9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8298 | -79.5621 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7310000 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7310000 | 7310000 | 7310000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-046 | 42-046 | 42 | N/A | 67075 | York CDSB | St. Agnes of Assisi | St. Agnes of Assisi Catholic Elementary School | ELE | 10224 | 10464 | 10464-B01 | 120 LA ROCCA AVE | WOODBRIDGE | L4H2A9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8298 | -79.5621 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1198982 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198982 | 1198982 | 1198982 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-047 | 42-047 | 42 | N/A | 67075 | York CDSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 9889 | 10313 | 10313-B01 | 151 FOREST FOUNTAIN DR | WOODBRIDGE | L4H1S4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8183 | -79.6122 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7335900 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7335900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7335900 | 7335900 | 7335900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-048 | 42-048 | 42 | N/A | 67075 | York CDSB | St. Angela Merici | St. Angela Merici Catholic Elementary School | ELE | 9843 | 10293 | 10293-B01 | 8881 MARTIN GROVE RD | WOODBRIDGE | L4H1C3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8008 | -79.6233 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4492800 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492800 | 4492800 | 4492800 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-049 | 42-049 | 42 | N/A | 67075 | York CDSB | St. Angela Merici | St. Angela Merici Catholic Elementary School | ELE | 9843 | 10293 | 10293-B01 | 8881 MARTIN GROVE RD | WOODBRIDGE | L4H1C3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8008 | -79.6233 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 944433 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944433 | 944433 | 944433 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-051 | 42-051 | 42 | N/A | 67075 | York CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 3765 | 7501 | 7501-B01 | 105 DON HEAD VILLAGE BLVD | RICHMOND HILL | L4C7N1 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8643 | -79.4537 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1708200 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708200 | 1708200 | 1708200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-053 | 42-053 | 42 | N/A | 67075 | York CDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 3756 | 7495 | 7495-B01 | 141 KIRK DR | THORNHILL | L3T3L3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8291 | -79.4153 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1991518 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991518 | 1991518 | 1991518 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-054 | 42-054 | 42 | N/A | 67075 | York CDSB | St. Augustine | St. Augustine Catholic Secondary School | SEC | 9879 | 10309 | 10309-B01 | 2188 RODICK RD | MARKHAM | L6C1S3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8751 | -79.3578 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21294000 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21294000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21294000 | 21294000 | 21294000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-055 | 42-055 | 42 | N/A | 67075 | York CDSB | St. Benedict | St. Benedict Catholic Elementary School | ELE | 3793 | 7525 | 7525-B01 | 50 ALDERGROVE DR | MARKHAM | L3R7E6 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8315 | -79.2905 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1333800 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1333800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1333800 | 1333800 | 1333800 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-056 | 42-056 | 42 | N/A | 67075 | York CDSB | St. Brendan | St. Brendan Catholic Elementary School | ELE | 19720 | 19110 | 19110-B01 | 751 HOOVER PARK DR | STOUFFVILLE | L4A0Z6 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9633 | -79.2542 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 550 | - | - | N | - | Not Required | - | 9589479 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 8089479 | 0 | 0 | 0 | 0 | 0 | 9589479 | 9589479 | 9589479 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8089479
42-057 | 42-057 | 42 | N/A | 67075 | York CDSB | St. Brigid | St. Brigid Catholic Elementary School | ELE | 9885 | 10311 | 10311-B01 | 223 MILLARD ST | STOUFFVILLE | L4A5S2 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9783 | -79.2428 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6300300 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300300 | 6300300 | 6300300 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-059 | 42-059 | 42 | N/A | 67075 | York CDSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 3836 | 7557 | 7557-B01 | 80 TERRA RD | WOODBRIDGE | L4L3J5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7784 | -79.5727 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 573300 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573300 | 573300 | 573300 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-060 | 42-060 | 42 | N/A | 67075 | York CDSB | St. Cecilia | St. Cecilia Catholic Elementary School | ELE | 11262 | 12247 | 12247-B01 | 300 AV PETER RUPERT | MAPLE | L6A4P3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8495 | -79.494 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12224515 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12224515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12224515 | 12224515 | 12224515 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-062 | 42-062 | 42 | N/A | 67075 | York CDSB | St. Clement | St. Clement Catholic Elementary School | ELE | 3858 | 7571 | 7571-B01 | 40 BAINBRIDGE AVE | WOODBRIDGE | L4L3Y1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7854 | -79.6081 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1521000 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 1521000 | 1521000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-064 | 42-064 | 42 | N/A | 67075 | York CDSB | St. David | St. David Catholic Elementary School | ELE | 3886 | 7594 | 7594-B01 | 240 KILLIAN RD | MAPLE | L6A1A8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.858 | -79.5192 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1521000 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 1521000 | 1521000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-065 | 42-065 | 42 | N/A | 67075 | York CDSB | St. Edward | St. Edward Catholic Elementary School | ELE | 3909 | 7609 | 7609-B01 | 33 CAIRNS DR | MARKHAM | L3P7M8 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8812 | -79.2791 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1708200 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1708200 | 1708200 | 1708200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-066 | 42-066 | 42 | N/A | 67075 | York CDSB | St. Elizabeth | St. Elizabeth Catholic Secondary School | SEC | 3910 | 7610 | 7610-B01 | 525 NEW WESTMINSTER DR | THORNHILL | L4J7X3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8033 | -79.457 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8430573 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8430573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8430573 | 8430573 | 8430573 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-068 | 42-068 | 42 | N/A | 67075 | York CDSB | St. Emily | St. Emily Catholic Elementary School | ELE | 10223 | 10463 | 10463-B01 | 60 VELLORE WOODS BLVD | WOODBRIDGE | L4H2K8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8303 | -79.5519 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9427443 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9427443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9427443 | 9427443 | 9427443 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-069 | 42-069 | 42 | N/A | 67075 | York CDSB | St. Francis Xavier | St. Francis Xavier Catholic Elementary School | ELE | 3954 | 7644 | 7644-B01 | 223 HIGHGLEN AVE | MARKHAM | L3S1Y4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8443 | -79.2874 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3229200 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3229200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3229200 | 3229200 | 3229200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-070 | 42-070 | 42 | N/A | 67075 | York CDSB | St. Gregory the Great | St. Gregory the Great Catholic Elementary School | ELE | 3985 | 7670 | 7670-B01 | 140 GREENPARK BLVD | WOODBRIDGE | L4L6Z6 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8104 | -79.5581 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 726083 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726083 | 726083 | 726083 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-071 | 42-071 | 42 | N/A | 67075 | York CDSB | St. James | St. James Catholic Elementary School | ELE | 10220 | 10461 | 10461-B01 | 171 MAST RD | MAPLE | L6A3J7 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8539 | -79.5465 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6394760 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6394760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6394760 | 6394760 | 6394760 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-072 | 42-072 | 42 | N/A | 67075 | York CDSB | St. James | St. James Catholic Elementary School | ELE | 10220 | 10461 | 10461-B01 | 171 MAST RD | MAPLE | L6A3J7 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8539 | -79.5465 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 849744 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849744 | 849744 | 849744 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-073 | 42-073 | 42 | N/A | 67075 | York CDSB | St. Jean de Brébeuf | St. Jean de Brébeuf Catholic Secondary School | SEC | 10377 | 11087 | 11087-B01 | 2 DAVOS RD | WOODBRIDGE | L4H2Y1 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8349 | -79.5595 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24103251 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24103251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24103251 | 24103251 | 24103251 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-074 | 42-074 | 42 | N/A | 67075 | York CDSB | St. Jerome | St. Jerome Catholic Elementary School | ELE | 10686 | 11245 | 11245-B01 | 20 BRIDGENORTH DR | AURORA | L4G7P3 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.0146 | -79.4526 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10958850 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9034452 | 0 | 1924398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10958850 | 10958850 | 10958850 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-075 | 42-075 | 42 | N/A | 67075 | York CDSB | St. Joan of Arc | St. Joan of Arc Catholic Secondary School | SEC | 4040 | 7711 | 7711-B01 | 1 ST. JOAN OF ARC AVE | MAPLE | L6A1W9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8615 | -79.5198 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7281864 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7281864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7281864 | 7281864 | 7281864 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-076 | 42-076 | 42 | N/A | 67075 | York CDSB | St. Joan of Arc | St. Joan of Arc Catholic Secondary School | SEC | 4040 | 7711 | 7711-B01 | 1 ST. JOAN OF ARC AVE | MAPLE | L6A1W9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8615 | -79.5198 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1703955 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 688410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688410 | 1015545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015545 | 1703955 | 1703955 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-077 | 42-077 | 42 | N/A | 67075 | York CDSB | St. John Chrysostom | St. John Chrysostom Catholic Elementary School | ELE | 9880 | 10310 | 10310-B01 | 800 JOE PERSECHINI DR | NEWMARKET | L3X2S6 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0297 | -79.4773 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6801000 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6801000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6801000 | 6801000 | 6801000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-078 | 42-078 | 42 | N/A | 67075 | York CDSB | St. John Paul II | St. John Paul II Catholic Elementary School | ELE | 10228 | 10387 | 10387-B01 | 155 RED MAPLE RD | RICHMOND HILL | L4B4P9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8451 | -79.4241 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5966028 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5966028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5966028 | 5966028 | 5966028 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-081 | 42-081 | 42 | N/A | 67075 | York CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4087 | 7744 | 7744-B01 | 2 GLASS DR | AURORA | L4G2E8 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9829 | -79.475 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1866144 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866144 | 1866144 | 1866144 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-082 | 42-082 | 42 | N/A | 67075 | York CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4110 | 7759 | 7759-B01 | 301 RONEY AVE | RICHMOND HILL | L4C2H4 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8696 | -79.4178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1907100 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1907100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1907100 | 1907100 | 1907100 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-083-01 | 42-083 | 42 | N/A | 67075 | York CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 24311 | 19303 | 19303-B01 | 388 WHITE'S HILL AVE | MARKHAM | L6B0J3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8967 | -79.2234 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 519 | - | - | N | - | Approved | 44280 | 10554808 | Construction Complete | New Construction | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315923 | 0 | 0 | 0 | 0 | 315923 | 5700000 | 0 | 465947 | 0 | 5072938 | 0 | 0 | 0 | 0 | 0 | 11238885 | 11554808 | 11554808 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5072938
42-083-02 | 42-083 | 42 | N/A | 67075 | York CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 24311 | 19303 | 19303-L01 | 388 WHITE'S HILL AVE | MARKHAM | L6B0J3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8967 | -79.2234 | 42591 | 2015-16 | 2016-17 | 42591 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42591 | 3201003 | Construction Complete | Land Acquisition | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 1208857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1208857 | 0 | 0 | 0 | 1992146 | 0 | 0 | 0 | 0 | 0 | 0 | 1992146 | 3201003 | 3201003 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1992146
42-084 | 42-084 | 42 | N/A | 67075 | York CDSB | St. Joseph the Worker | St. Joseph the Worker Catholic Elementary School | ELE | 4144 | 7784 | 7784-B01 | 475 BROWNRIDGE DR | THORNHILL | L4J5Y6 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8012 | -79.4706 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2281500 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281500 | 2281500 | 2281500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-086 | 42-086 | 42 | N/A | 67075 | York CDSB | St. Julia Billiart | St. Julia Billiart Catholic Elementary School | ELE | 10689 | 11246 | 11246-B01 | 2070 BUR OAK AVE | MARKHAM | L6E1X5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9031 | -79.2533 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8223052 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8223052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8223052 | 8223052 | 8223052 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-087 | 42-087 | 42 | N/A | 67075 | York CDSB | St. Julia Billiart | St. Julia Billiart Catholic Elementary School | ELE | 10689 | 11246 | 11246-B01 | 2070 BUR OAK AVE | MARKHAM | L6E1X5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.9031 | -79.2533 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 190 | - | - | N | - | Not Required | - | 2425485 | Construction Complete | Addition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896051 | 0 | 1529434 | 0 | 0 | 0 | 0 | 0 | 2425485 | 2425485 | 2425485 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1529434
42-088 | 42-088 | 42 | N/A | 67075 | York CDSB | St. Kateri Tekakwitha | St. Kateri Tekakwitha Catholic Elementary School | ELE | 3367 | 7210 | 7210-B01 | 230 FINCHAM AVE | MARKHAM | L3P4B5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8906 | -79.2474 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1801800 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801800 | 1801800 | 1801800 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-090 | 42-090 | 42 | N/A | 67075 | York CDSB | St. Marguerite d'Youville | St. Marguerite d'Youville Catholic Elementary School | ELE | 10687 | 11247 | 11247-B01 | 121 ROLLINGHILL RD | RICHMOND HILL | L4E4L2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9117 | -79.4589 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7283384 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7283384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7283384 | 7283384 | 7283384 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-091 | 42-091 | 42 | N/A | 67075 | York CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 4280 | 7875 | 7875-B01 | 75 GREENSIDE DR | NOBLETON | L0G1N0 | 35-11-27-603 | King | King Tp | York R | YORK | GTA | South | 43.9076 | -79.6461 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 190 | - | - | N | - | Not Required | - | 4014945 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448025 | 0 | 3566920 | 0 | 0 | 0 | 0 | 0 | 4014945 | 4014945 | 4014945 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3566920
42-092 | 42-092 | 42 | N/A | 67075 | York CDSB | St. Mary Immaculate | St. Mary Immaculate Catholic Elementary School | ELE | 4252 | 7861 | 7861-B01 | 161 REGENT ST | RICHMOND HILL | L4C9N9 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8828 | -79.4509 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3872175 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20876 | 1020876 | 2851299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2851299 | 3872175 | 3872175 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-093 | 42-093 | 42 | N/A | 67075 | York CDSB | St. Mary of the Angels | St. Mary of the Angels Catholic Elementary School | ELE | 11111 | 12245 | 12245-B01 | 351 AV VELLORE PARK | WOODBRIDGE | L4H0E4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8547 | -79.5593 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10408651 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10408651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10408651 | 10408651 | 10408651 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-094 | 42-094 | 42 | N/A | 67075 | York CDSB | St. Matthew | St. Matthew Catholic Elementary School | ELE | 4294 | 7885 | 7885-B01 | 75 WATERBRIDGE LANE | UNIONVILLE | L3R4G3 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8748 | -79.306 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1521000 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1521000 | 1521000 | 1521000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-095 | 42-095 | 42 | N/A | 67075 | York CDSB | St. Maximilian Kolbe | St. Maximilian Kolbe Catholic Secondary School | SEC | 11004 | 12139 | 12139-B01 | 278 WELLINGTON ST E | AURORA | L4G1J5 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 44.0031 | -79.4539 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 35050905 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35050905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35050905 | 35050905 | 35050905 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-096 | 42-096 | 42 | N/A | 67075 | York CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4321 | 7907 | 7907-B01 | 41 SIMONSTON BLVD | THORNHILL | L3T4R6 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8135 | -79.3652 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9814994 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9814994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9814994 | 9814994 | 9814994 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-097 | 42-097 | 42 | N/A | 67075 | York CDSB | St. Michael the Archangel | St. Michael the Archangel Catholic Elementary School | ELE | 19721 | 19111 | 19111-B01 | 161 VIA CAMPANILE | WOODBRIDGE | L4H3K5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8267 | -79.576 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 600 | - | - | N | - | Not Required | - | 10406817 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397843 | 0 | 9008974 | 0 | 0 | 0 | 0 | 0 | 10406817 | 10406817 | 10406817 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9008974
42-100 | 42-100 | 42 | N/A | 67075 | York CDSB | St. Padre Pio | St. Padre Pio Catholic Elementary School | ELE | 10688 | 11248 | 11248-B01 | 770 NAPA VALLEY AVE | WOODBRIDGE | L4H1W9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8243 | -79.6151 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7932171 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931500 | 931500 | 7000671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000671 | 7932171 | 7932171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-102 | 42-102 | 42 | N/A | 67075 | York CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 4352 | 7927 | 7927-B01 | 51 WESTERN AVE | SCHOMBERG | L0G1T0 | 35-11-27-603 | King | King Tp | York R | YORK | GTA | South | 44.0011 | -79.6875 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3077166 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1957102 | 0 | 1120064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3077166 | 3077166 | 3077166 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-104 | 42-104 | 42 | N/A | 67075 | York CDSB | St. Raphael the Archangel | St. Raphael the Archangel Catholic Elementary School | ELE | 11260 | 12246 | 12246-B01 | 131 RAVINEVIEW DR | MAPLE | L6A3T6 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8915 | -79.5145 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8699532 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8699532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8699532 | 8699532 | 8699532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-105 | 42-105 | 42 | N/A | 67075 | York CDSB | St. Rene Goupil-St. Luke | St. Rene Goupil-St. Luke Catholic Elementary School | ELE | 4446 | 7987 | 7987-B01 | 135 GREEN LANE | THORNHILL | L3T6K7 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8241 | -79.3877 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1025949 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8049 | 8049 | 1017900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017900 | 1025949 | 1025949 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-106 | 42-106 | 42 | N/A | 67075 | York CDSB | St. Robert | St. Robert Catholic Secondary School | SEC | 4454 | 7994 | 7994-B01 | 8101 LESLIE ST | THORNHILL | L3T7P4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8346 | -79.3796 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1446551 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446551 | 1446551 | 1446551 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-107 | 42-107 | 42 | N/A | 67075 | York CDSB | St. Stephen | St. Stephen Catholic Elementary School | ELE | 10221 | 10462 | 10462-B01 | 451 NAPA VALLEY AVE | WOODBRIDGE | L4H1Y8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8206 | -79.6253 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7310000 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7310000 | 7310000 | 7310000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-108 | 42-108 | 42 | N/A | 67075 | York CDSB | St. Stephen | St. Stephen Catholic Elementary School | ELE | 10221 | 10462 | 10462-B01 | 451 NAPA VALLEY AVE | WOODBRIDGE | L4H1Y8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8206 | -79.6253 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1010157 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1010157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1010157 | 1010157 | 1010157 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-109 | 42-109 | 42 | N/A | 67075 | York CDSB | St. Theresa of Lisieux | St. Theresa of Lisieux Catholic Secondary School | SEC | 9878 | 10308 | 10308-B01 | 230 SHAFTSBURY AVE | RICHMOND HILL | L4C0E8 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8951 | -79.4662 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24361187 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24361187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24361187 | 24361187 | 24361187 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-110 | 42-110 | 42 | N/A | 67075 | York CDSB | St. Theresa of Lisieux | St. Theresa of Lisieux Catholic Secondary School | SEC | 9878 | 10308 | 10308-B01 | 230 SHAFTSBURY AVE | RICHMOND HILL | L4C0E8 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8951 | -79.4662 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1792688 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1792688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1792688 | 1792688 | 1792688 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-111 | 42-111 | 42 | N/A | 67075 | York CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Elementary School | ELE | 10219 | 8083 | 8083-B01 | 262 OLD HOMESTEAD RD | KESWICK | L4P3C8 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.2491 | -79.4821 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6133500 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6133500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6133500 | 6133500 | 6133500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-113 | 42-113 | 42 | N/A | 67075 | York CDSB | St. Veronica | St. Veronica Catholic Elementary School | ELE | 10776 | 11984 | 11984-B01 | 171 MARIA ANTONIA RD | WOODBRIDGE | L4H2S8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8395 | -79.5658 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9238561 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9238561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9238561 | 9238561 | 9238561 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-114 | 42-114 | 42 | N/A | 67075 | York CDSB | St. Veronica | St. Veronica Catholic Elementary School | ELE | 10776 | 11984 | 11984-B01 | 171 MARIA ANTONIA RD | WOODBRIDGE | L4H2S8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8395 | -79.5658 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1090840 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090840 | 1090840 | 1090840 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-118 | 42-118 | 42 | 234 - CMSM York | 67075 | York CDSB | Blessed Chiara Badano / St. Katherine Drexel | Blessed Chiara Badano / St. Katherine Drexel Catholic Elementary and Secondary School | ELE/SEC | 24436-25412 | 19439 | 19439-B01 | NINTH LINE | STOUFFVILLE | TBD | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9815 | -79.2582 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 1400 | 3 | 49 | Y | - | Approved | 44365 | 42629165 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 5040439 | 0 | 1549430 | 0 | 577000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7166869 | 0 | 0 | 1512510 | 0 | 32437276 | 0 | 1512510 | 0 | 0 | 0 | 35462296 | 42629165 | 42629165 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 33949786
42-119 | 42-119 | 42 | 234 - CMSM York | 67075 | York CDSB | Pope Francis | Pope Francis Catholic Elementary School | ELE | 24434 | 19436 | 19436-B01 | 15 SECORD AVE | KLEINBURG | L4H3Z3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8302 | -79.6556 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 43110 | 2068570 | Construction Complete | Addition | Child Care | 2018-19 | 43525 | 0 | 0 | 0 | 0 | 0 | 0 | 356060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356060 | 0 | 0 | 0 | 0 | 0 | 0 | 1712510 | 0 | 0 | 0 | 1712510 | 2068570 | 2068570 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1712510
42-120 | 42-120 | 42 | 234 - CMSM York | 67075 | York CDSB | St. Rene Goupil-St. Luke | St. Rene Goupil-St. Luke Catholic Elementary School | ELE | 4446 | 7987 | 7987-B01 | 135 GREEN LANE | THORNHILL | L3T6K7 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8241 | -79.3877 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 44678 | 2405966 | Under Construction | Addition | Child Care | 2022-23 | 44927 | 371199 | 0 | 0 | 0 | 0 | 0 | 1595353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1966552 | 0 | 0 | 0 | 0 | 0 | 0 | 1951469 | 0 | 0 | 0 | 1951469 | 3918021 | 3918021 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1951469
42-121 | 42-121 | 42 | N/A | 67075 | York CDSB | St. Francis Xavier | St. Francis Xavier Catholic Elementary School | ELE | 3954 | 7644 | 7644-B01 | 223 HIGHGLEN AVE | MARKHAM | L3S1Y4 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8443 | -79.2874 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44280 | 780900 | Construction Complete | Retrofit | Consolidation | 2018-19 | 43361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780900 | 0 | 0 | 0 | 0 | 0 | 780900 | 780900 | 780900 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 780900
42-122 | 42-122 | 42 | N/A | 67075 | York CDSB | St. Bernadette | St. Bernadette Catholic Elementary School | ELE | 3759 | 5021 | 5021-B01 | 5279 BLACK RIVER RD | SUTTON WEST | L0E1R0 | 35-11-27-408 | Georgina | Georgina T | York R | YORK | GTA | South | 44.3093 | -79.3683 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43173 | 300000 | Construction Complete | FDK | FDK | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-123 | 42-123 | 42 | N/A | 67075 | York CDSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 3836 | 7557 | 7557-B01 | 80 TERRA RD | WOODBRIDGE | L4L3J5 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7784 | -79.5727 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43173 | 400000 | Construction Complete | FDK | FDK | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 400000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-124 | 42-124 | 42 | N/A | 67075 | York CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 4280 | 7875 | 7875-B01 | 75 GREENSIDE DR | NOBLETON | L0G1N0 | 35-11-27-603 | King | King Tp | York R | YORK | GTA | South | 43.9076 | -79.6461 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43227 | 1500000 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43344 | 400000 | 400000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-125 | 42-125 | 42 | N/A | 67075 | York CDSB | St. Theresa of Lisieux | St Theresa of Lisieux Catholic Elementary School | SEC | 9878 | 10308 | 10308-B01 | 230 SHAFTSBURY AVE | RICHMOND HILL | L4C0E8 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8948 | -79.4656 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Planned | - | 0 | Planned | Addition | Accommodation Pressure | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370150 | 0 | 0 | 0 | 0 | 0 | 370150 | 370150 | 370150 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 370150
42-126 | 42-126 | 42 | N/A | 67075 | York CDSB | Demolition of Portables | Demolition of Portables | OFF-ADM | 15762 | 18080 | 18080-B01 | 320 BLOOMINGTON RD | AURORA | L4G0M1 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9608 | -79.4695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43847 | 225000 | Construction Complete | Demolition | Other | 2020-21 | 44075 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 225000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-127 | 42-127 | 42 | N/A | 67075 | York CDSB | Safe Reopening of Schools | Safe Reopening of Schools | OFF-ADM | 15762 | 18080 | 18080-B01 | 320 BLOOMINGTON RD | AURORA | L4G0M1 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9608 | -79.4695 | 44222 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44222 | 9000000 | Construction Complete | Other | Other | 2021-22 | 44440 | 0 | 0 | 14975167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14975167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14975167 | 14975167 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
42-128 | 42-128 | 42 | 234 - CMSM York | 67075 | York CDSB | Queensville | Queensville Catholic Elementary School | ELE | TBD | TBD | TBD | LESLIE ST / JIM MORTSON DR | QUEENSVILLE | TBD | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.1283 | -79.4481 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 409 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9699437 | 0 | 1700737 | 0 | 0 | 0 | 11400174 | 11400174 | 11400174 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11400174
42-129 | 42-129 | 42 |  | 67075 | York CDSB | [45 empty] | Other | Other |  |  | 0 | 0 | 2522933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2522933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 0
42-130 | 42-130 |  |  | 67075 | York CDSB | POD Use for Operating Expenses | Exemption to O. Reg 193/10: POD Use for Operating Expenses |  | TBD | TBD | TBD | [39 empty] | Other | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 0
43-001 | 43-001 | 43 | N/A | 67083 | Dufferin Peel CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18305 | 19061 | 19061-B01 | 40 MATHESON BLVD W | MISSISSAUGA | L5R1C5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6192 | -79.6721 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982162 | 0 | 824109 | 0 | 0 | 0 | 1806271 | 1806271 | 0 | -1806271 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | NO | YES | 1806271
43-002 | 43-002 | 43 | N/A | 67083 | Dufferin Peel CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18305 | 19061 | 19061-B01 | 40 MATHESON BLVD W | MISSISSAUGA | L5R1C5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6192 | -79.6721 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13381672 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26477830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26477830 | 26477830 | 13483788 | -12994042 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-003 | 43-003 | 43 | N/A | 67083 | Dufferin Peel CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18305 | 19061 | 19061-B01 | 40 MATHESON BLVD W | MISSISSAUGA | L5R1C5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6192 | -79.6721 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 222337 | Construction Complete | Other | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222337 | 222337 | 222337 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-004 | 43-004 | 43 | N/A | 67083 | Dufferin Peel CDSB | All Saints | All Saints Catholic Elementary School | ELE | 6492 | 8749 | 8749-B01 | 4105 COLONIAL DR | MISSISSAUGA | L5L4E8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5316 | -79.7106 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2359105 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359105 | 2359105 | 2359105 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-005 | 43-005 | 43 | N/A | 67083 | Dufferin Peel CDSB | Ascension of Our Lord | Ascension of Our Lord Catholic Secondary School | SEC | 10589 | 8748 | 8748-B01 | 7640 ANAKA DR | MISSISSAUGA | L4T3H7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.7234 | -79.6535 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 18920795 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18920795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18920795 | 18920795 | 18920795 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-006 | 43-006 | 43 | N/A | 67083 | Dufferin Peel CDSB | Bishop Scalabrini | Bishop Scalabrini Catholic Elementary School | ELE | 3015 | 6984 | 6984-B01 | 225 CENTRAL PKY W | MISSISSAUGA | L5B3J5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5839 | -79.6359 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17495 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17495 | 17495 | 17495 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-007 | 43-007 | 43 | N/A | 67083 | Dufferin Peel CDSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 18305 | 19061 | 19061-B01 | 40 MATHESON BLVD W | MISSISSAUGA | L5R1C5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6192 | -79.6721 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1200000 | Construction Complete | Other | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792000 | 792000 | 408000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408000 | 1200000 | 1200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-008 | 43-008 | 43 | N/A | 67083 | Dufferin Peel CDSB | Canadian Martyrs | Canadian Martyrs Catholic Elementary School | ELE | 3096 | 7036 | 7036-B01 | 1185 MISSISSAUGA VALLEY BLVD | MISSISSAUGA | L5A3R7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.599 | -79.6219 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2427337 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2427337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2427337 | 2427337 | 2427337 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-010 | 43-010 | 43 | N/A | 67083 | Dufferin Peel CDSB | Cardinal Ambrozic | Cardinal Ambrozic Catholic Secondary School | SEC | 11028 | 12172 | 12172-B01 | 10 CASTLE OAKS CROSS | BRAMPTON | L6P3A2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7877 | -79.6831 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 30139628 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30139628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30139628 | 30139628 | 30139628 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-011 | 43-011 | 43 | N/A | 67083 | Dufferin Peel CDSB | Cardinal Leger | Cardinal Leger Catholic Secondary School | SEC | 4468 | 7850 | 7850-B02 | 75 MARY ST | BRAMPTON | L6W3K5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6841 | -79.7505 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1450000 | Construction Complete | Retrofit | Other | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328316 | 0 | 0 | 0 | 0 | 0 | 1328316 | 1328316 | 1328316 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 1328316
43-012 | 43-012 | 43 | N/A | 67083 | Dufferin Peel CDSB | Cardinal Newman | Cardinal Newman Catholic Elementary School | ELE | 3353 | 7199 | 7199-B01 | 698 BALMORAL DR | BRAMPTON | L6T1X1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7216 | -79.6992 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 20417 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20417 | 20417 | 20417 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-013 | 43-013 | 43 | N/A | 67083 | Dufferin Peel CDSB | Cardinal Newman | Cardinal Newman Catholic Elementary School | ELE | 3353 | 7199 | 7199-B01 | 698 BALMORAL DR | BRAMPTON | L6T1X1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7216 | -79.6992 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1483555 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1483555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1483555 | 1483555 | 1483555 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-014 | 43-014 | 43 | N/A | 67083 | Dufferin Peel CDSB | Christ The King | Christ The King Catholic Elementary School | ELE | 3134 | 7060 | 7060-B01 | 3240 GARTHWOOD RD | MISSISSAUGA | L5L5A3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.524 | -79.695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1367105 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1367105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1367105 | 1367105 | 1367105 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-015 | 43-015 | 43 | N/A | 67083 | Dufferin Peel CDSB | Divine Mercy | Divine Mercy Catholic Elementary School | ELE | 6067 | 8555 | 8555-B01 | 2840 DUNCAIRN DR | MISSISSAUGA | L5M5C6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5595 | -79.7238 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1846739 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1846739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1846739 | 1846739 | 1846739 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-016 | 43-016 | 43 | N/A | 67083 | Dufferin Peel CDSB | Father Francis McSpiritt | Father Francis McSpiritt Catholic Elementary School | ELE | 10966 | 12114 | 12114-B01 | 55 LEXINGTON RD | BRAMPTON | L6P2B1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7751 | -79.6981 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9320858 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9154176 | 0 | 166682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9320858 | 9320858 | 9320858 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-017 | 43-017 | 43 | N/A | 67083 | Dufferin Peel CDSB | Father Michael Goetz | Father Michael Goetz Catholic Secondary School | SEC | 6493 | 8750 | 8750-B01 | 330 CENTRAL PKY W | MISSISSAUGA | L5B3K6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5819 | -79.6358 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4544430 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4544430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4544430 | 4544430 | 4544430 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-018 | 43-018 | 43 | N/A | 67083 | Dufferin Peel CDSB | Good Shepherd | Good Shepherd Catholic Elementary School | ELE | 9799 | 10274 | 10274-B01 | 28 RED RIVER DR | BRAMPTON | L6R2H9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.756 | -79.7463 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7388717 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7388717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7388717 | 7388717 | 7388717 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-019 | 43-019 | 43 | N/A | 67083 | Dufferin Peel CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 10361 | 11043 | 11043-B01 | 62 HEATHERDALE DR | BRAMPTON | L7A2H4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6868 | -79.8196 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7212639 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7212639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7212639 | 7212639 | 7212639 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-020 | 43-020 | 43 | N/A | 67083 | Dufferin Peel CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 10361 | 11043 | 11043-B01 | 62 HEATHERDALE DR | BRAMPTON | L7A2H4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6868 | -79.8196 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10321 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10321 | 10321 | 10321 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-022 | 43-022 | 43 | N/A | 67083 | Dufferin Peel CDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 10588 | 7161 | 7161-B01 | 61 ALLAN DR | BOLTON | L7E1P7 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8737 | -79.7261 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7445928 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7445928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7445928 | 7445928 | 7445928 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-023 | 43-023 | 43 | N/A | 67083 | Dufferin Peel CDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 10588 | 7161 | 7161-B01 | 61 ALLAN DR | BOLTON | L7E1P7 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8737 | -79.7261 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 28467 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28467 | 28467 | 28467 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-024 | 43-024 | 43 | N/A | 67083 | Dufferin Peel CDSB | Holy Spirit | Holy Spirit Catholic Elementary School | ELE | 10639 | 11255 | 11255-B01 | 25 BLOOMSBURY AVE | BRAMPTON | L6P1W9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7843 | -79.7292 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8136745 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8136745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8136745 | 8136745 | 8136745 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-025 | 43-025 | 43 | N/A | 67083 | Dufferin Peel CDSB | Iona | Iona Catholic Secondary School | SEC | 3342 | 7191 | 7191-B01 | 2170 SOUTH SHERIDAN WAY | MISSISSAUGA | L5J2M4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5206 | -79.6472 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11691 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11691 | 11691 | 11691 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-026 | 43-026 | 43 | N/A | 67083 | Dufferin Peel CDSB | John Cabot | John Cabot Catholic Secondary School | SEC | 10384 | 8092 | 8092-B02 | 635 WILLOWBANK TRAIL | MISSISSAUGA | L4W3L6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6126 | -79.6208 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21017686 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21017686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21017686 | 21017686 | 21017686 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-027 | 43-027 | 43 | N/A | 67083 | Dufferin Peel CDSB | Lester B Pearson | Lester B Pearson Catholic Elementary School | ELE | 11304 | 7223 | 7223-B02 | 140 HOWDEN BLVD | BRAMPTON | L6S2G1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.723 | -79.7293 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7966348 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7966348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7966348 | 7966348 | 7966348 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-028 | 43-028 | 43 | N/A | 67083 | Dufferin Peel CDSB | Loyola | Loyola Catholic Secondary School | SEC | 10783 | 11990 | 11990-B01 | 4010 SLADEVIEW CRES | MISSISSAUGA | L5L6B1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.526 | -79.7128 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 26024692 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26024692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26024692 | 26024692 | 26024692 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-029 | 43-029 | 43 | N/A | 67083 | Dufferin Peel CDSB | Metropolitan Andrei | Metropolitan Andrei Catholic Elementary School | ELE | 3415 | 7245 | 7245-B01 | 515 MISSISSAUGA VALLEY BLVD | MISSISSAUGA | L5A3G6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5925 | -79.613 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3604619 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3604619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3604619 | 3604619 | 3604619 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-030 | 43-030 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | St. Daniel Comboni | St. Daniel Comboni Catholic Elementary School | ELE | 24216 | 19208 | 19208-B01 | 120 VETERANS DR | BRAMPTON | L7A3Z7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.681 | -79.8412 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 553 | 2 | 39 | N | - | Approved | 44490 | 11503828 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235711 | 0 | 9304053 | 0 | 964064 | 0 | 0 | 0 | 11503828 | 11503828 | 11503828 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10268117
43-031 | 43-031 | 43 | N/A | 67083 | Dufferin Peel CDSB | Notre Dame | Notre Dame Catholic Secondary School | SEC | 3079 | 7022 | 7022-B01 | 2 NOTRE DAME AVE | BRAMPTON | L6Z4L5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7194 | -79.7793 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3274876 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274876 | 3274876 | 3274876 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-032 | 43-032 | 43 | N/A | 67083 | Dufferin Peel CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 3507 | 7303 | 7303-B01 | 39 SUNSET BLVD | BRAMPTON | L6X1X1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6881 | -79.7775 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 445 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445 | 445 | 445 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-033 | 43-033 | 43 | N/A | 67083 | Dufferin Peel CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 12085 | 12318 | 12318-B01 | 25 MOUNT ROYAL CIR | BRAMPTON | L6P1W3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7918 | -79.7472 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 504 | - | - | N | - | Not Required | - | 9303189 | Construction Complete | New Construction | Other | 2011-12 | 40792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9262955 | 0 | 0 | 0 | 0 | 0 | 9262955 | 9262955 | 9262955 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 9262955
43-034 | 43-034 | 43 | N/A | 67083 | Dufferin Peel CDSB | Our Lady of Mercy | Our Lady of Mercy Catholic Elementary School | ELE | 6040 | 8542 | 8542-B01 | 5820 GLEN ERIN DR | MISSISSAUGA | L5M5J9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5693 | -79.733 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1356686 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356686 | 1356686 | 1356686 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-035 | 43-035 | 43 | N/A | 67083 | Dufferin Peel CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Secondary School | SEC | 3510 | 7305 | 7305-B01 | 3700 TRELAWNY CIR | MISSISSAUGA | L5N5J7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5746 | -79.7719 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4341693 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4341693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4341693 | 4341693 | 4341693 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-036 | 43-036 | 43 | N/A | 67083 | Dufferin Peel CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Secondary School | SEC | 3510 | 7305 | 7305-B01 | 3700 TRELAWNY CIR | MISSISSAUGA | L5N5J7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5746 | -79.7719 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3467 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3467 | 3467 | 3467 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-038 | 43-038 | 43 | N/A | 67083 | Dufferin Peel CDSB | Our Lady of Providence | Our Lady of Providence Catholic Elementary School | ELE | 5988 | 8520 | 8520-B01 | 35 BLACK OAK DR | BRAMPTON | L6R1B9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7438 | -79.7597 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2601769 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601769 | 2601769 | 2601769 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-039 | 43-039 | 43 | N/A | 67083 | Dufferin Peel CDSB | Queen of Heaven | Queen of Heaven Catholic Elementary School | ELE | 3601 | 7377 | 7377-B01 | 1198 ALEXANDRA AVE | MISSISSAUGA | L5E2A5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.578 | -79.5666 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6966460 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6966460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6966460 | 6966460 | 6966460 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-040 | 43-040 | 43 | N/A | 67083 | Dufferin Peel CDSB | Robert F Hall | Robert F Hall Catholic Secondary School | SEC | 3620 | 7394 | 7394-B01 | 6500 OLD CHURCH RD | CALEDON EAST | L7C0H3 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8809 | -79.8555 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4957143 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4957143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4957143 | 4957143 | 4957143 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-041 | 43-041 | 43 | N/A | 67083 | Dufferin Peel CDSB | Robert F Hall | Robert F Hall Catholic Secondary School | SEC | 3620 | 7394 | 7394-B01 | 6500 OLD CHURCH RD | CALEDON EAST | L7C0H3 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8809 | -79.8555 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 54453 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54453 | 54453 | 54453 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-042 | 43-042 | 43 | N/A | 67083 | Dufferin Peel CDSB | San Lorenzo Ruiz | San Lorenzo Ruiz Catholic Elementary School | ELE | 9792 | 10270 | 10270-B01 | 100 BARONDALE DR | MISSISSAUGA | L4Z3R1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6178 | -79.6636 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6750452 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750452 | 6750452 | 6750452 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-043 | 43-043 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Aidan | St. Aidan Catholic Elementary School | ELE | 10968 | 12115 | 12115-B01 | 34 BUICK BLVD | BRAMPTON | L7A3B9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6963 | -79.8371 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7845249 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7845249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7845249 | 7845249 | 7845249 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-045 | 43-045 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Albert of Jerusalem | St. Albert of Jerusalem Catholic Elementary School | ELE | 9483 | 10175 | 10175-B01 | 7185 ROSEHURST DR | MISSISSAUGA | L5N7G6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5803 | -79.7892 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4446945 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4446945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4446945 | 4446945 | 4446945 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-047 | 43-047 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Aloysius Gonzaga | St. Aloysius Gonzaga Catholic Secondary School | SEC | 9733 | 10237 | 10237-B01 | 2800 ERIN CENTRE BLVD | MISSISSAUGA | L5M6R5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5564 | -79.7173 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 28681375 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28681375 | 28681375 | 28681375 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-048 | 43-048 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Alphonsa | St. Alphonsa Catholic Elementary School | ELE | 24508 | 19513 | 19513-B01 | 60 OLIVIA MARIE RD | BRAMPTON | L6Y0M4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6352 | -79.7718 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 553 | - | - | N | - | Approved | 42174 | 10461800 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 4766115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4766115 | 0 | 0 | 969184 | 0 | 4726501 | 0 | 0 | 0 | 0 | 0 | 5695685 | 10461800 | 10461800 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4726501
43-049 | 43-049 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. André Bessette | St. André Bessette Catholic Elementary School | ELE | 17840 | 19043 | 19043-B01 | 25 RIVERSTONE DR | BRAMPTON | L6P2V7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7657 | -79.6746 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 505 | - | - | N | - | Not Required | - | 10856280 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37337 | 0 | 1995951 | 0 | 8751861 | 0 | 0 | 0 | 0 | 0 | 10785149 | 10785149 | 10785149 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8751861
43-051 | 43-051 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 6035 | 8540 | 8540-B01 | 50 MEADOW DR | ORANGEVILLE | L9W4C8 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9189 | -80.1171 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4280102 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4280462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4280462 | 4280462 | 4280462 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-053 | 43-053 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Angela Merici | St. Angela Merici Catholic Elementary School | ELE | 10585 | 11251 | 11251-B01 | 83 EDENBROOK HILL DR | BRAMPTON | L7A2N7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6954 | -79.8106 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7509370 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7509370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7509370 | 7509370 | 7509370 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-054 | 43-054 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Angela Merici | St. Angela Merici Catholic Elementary School | ELE | 10585 | 11251 | 11251-B01 | 83 EDENBROOK HILL DR | BRAMPTON | L7A2N7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6954 | -79.8106 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 35130 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35130 | 35130 | 35130 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-055 | 43-055 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 11303 | 7491 | 7491-B01 | 950 NORTH PARK DR | BRAMPTON | L6S3L5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.736 | -79.7415 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 41739 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41739 | 41739 | 41739 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-056 | 43-056 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 11303 | 7491 | 7491-B01 | 950 NORTH PARK DR | BRAMPTON | L6S3L5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.736 | -79.7415 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6383049 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6383049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6383049 | 6383049 | 6383049 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-057 | 43-057 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Augustine | St. Augustine Catholic Secondary School | SEC | 3777 | 7512 | 7512-B01 | 27 DRINKWATER RD | BRAMPTON | L6Y4T6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6581 | -79.7646 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4418872 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4418872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4418872 | 4418872 | 4418872 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-058 | 43-058 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Augustine | St. Augustine Catholic Secondary School | SEC | 3777 | 7512 | 7512-B01 | 27 DRINKWATER RD | BRAMPTON | L6Y4T6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6581 | -79.7646 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8940 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8940 | 8940 | 8940 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-059 | 43-059 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Barbara | St. Barbara Catholic Elementary School | ELE | 9800 | 10275 | 10275-B01 | 1455 SAMUELSON CIR | MISSISSAUGA | L5N7Z2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6241 | -79.7461 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7033968 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033968 | 7033968 | 7033968 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-060 | 43-060 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Benedict | St. Benedict Catholic Elementary School | ELE | 9484 | 10176 | 10176-B01 | 345 BLIND LINE | ORANGEVILLE | L9W4X1 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9305 | -80.116 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2104442 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2104442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2104442 | 2104442 | 2104442 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-061 | 43-061 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Bernard of Clairvaux | St. Bernard of Clairvaux Catholic Elementary School | ELE | 10782 | 11989 | 11989-B01 | 3345 ESCADA DR | MISSISSAUGA | L5M7V5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5482 | -79.734 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8858085 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8858085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8858085 | 8858085 | 8858085 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-062 | 43-062 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Bonaventure | St. Bonaventure Catholic Elementary School | ELE | 10964 | 12113 | 12113-B01 | 35 MCCRIMMON DR | BRAMPTON | L7A2Z5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6875 | -79.8291 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8813426 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8813426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8813426 | 8813426 | 8813426 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-064 | 43-064 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Brigid | St. Brigid Catholic Elementary School | ELE | 3823 | 7550 | 7550-B01 | 81 TORRANCE WOODS | BRAMPTON | L6Y2X4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6582 | -79.7593 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2078618 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078618 | 2078618 | 2078618 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-065 | 43-065 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 9823 | 5155 | 5155-B01 | 2350 HURONTARIO ST | MISSISSAUGA | L5B1N1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5743 | -79.6093 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6808662 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6808662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6808662 | 6808662 | 6808662 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-066 | 43-066 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Cornelius | St. Cornelius Catholic Elementary School | ELE | 3874 | 7583 | 7583-B01 | 16066 INNIS LAKE RD | CALEDON EAST | L7C2Z2 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8792 | -79.8581 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2643074 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2643074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2643074 | 2643074 | 2643074 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-068 | 43-068 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. David of Wales | St. David of Wales Catholic Elementary School | ELE | 3885 | 7593 | 7593-B01 | 4200 BEACON LANE | MISSISSAUGA | L5C3V9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5748 | -79.666 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2689906 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689906 | 2689906 | 2689906 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-069 | 43-069 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Dominic | St. Dominic Catholic Elementary School | ELE | 3896 | 7601 | 7601-B01 | 515 HARTSDALE AVE | MISSISSAUGA | L5G2G7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5733 | -79.5794 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2144000 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330046 | 330046 | 1813954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813954 | 2144000 | 2144000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-070 | 43-070 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Dunstan | St. Dunstan Catholic Elementary School | ELE | 3902 | 7605 | 7605-B01 | 1525 CUTHBERT AVE | MISSISSAUGA | L5M3R6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5788 | -79.6877 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1668344 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668344 | 1668344 | 1668344 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-071 | 43-071 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Edmund | St. Edmund Catholic Elementary School | ELE | 3904 | 7606 | 7606-B01 | 1250 MELTON DR | MISSISSAUGA | L4Y1L5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5986 | -79.5767 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 78877 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78877 | 78877 | 78877 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-072 | 43-072 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Edmund | St. Edmund Catholic Elementary School | ELE | 3904 | 7606 | 7606-B01 | 1250 MELTON DR | MISSISSAUGA | L4Y1L5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5986 | -79.5767 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1390000 | Construction Complete | Retrofit | Other | 2014-15 | 41890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084870 | 0 | 0 | 0 | 0 | 0 | 1084870 | 1084870 | 1084870 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 1084870
43-073 | 43-073 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Edmund Campion | St. Edmund Campion Catholic Secondary School | SEC | 10583 | 11257 | 11257-B01 | 275 BRISDALE DR | BRAMPTON | L7A3C7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6943 | -79.8301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 31050723 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31050723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31050723 | 31050723 | 31050723 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-074 | 43-074 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Elizabeth Seton | St. Elizabeth Seton Catholic Elementary School | ELE | 3919 | 7618 | 7618-B01 | 6133 GLEN ERIN DR | MISSISSAUGA | L5N2T7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5775 | -79.7406 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 164 | - | - | N | - | Approved | 43679 | 3090000 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3090000 | 0 | 0 | 0 | 0 | 0 | 3090000 | 3090000 | 2786244 | -303756 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 3090000
43-075 | 43-075 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Faustina | St. Faustina Catholic Elementary School | ELE | 10344 | 11077 | 11077-B01 | 3420 MCDOWELL DR | MISSISSAUGA | L5M6R7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5569 | -79.7504 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7750297 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750297 | 7750297 | 7750297 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-076 | 43-076 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Faustina | St. Faustina Catholic Elementary School | ELE | 10344 | 11077 | 11077-B01 | 3420 MCDOWELL DR | MISSISSAUGA | L5M6R7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5569 | -79.7504 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1100651 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100651 | 1100651 | 1100651 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-077 | 43-077 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 3949 | 7641 | 7641-B01 | 2480 THORNE LODGE DR | MISSISSAUGA | L5K1K5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5264 | -79.6717 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6361798 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6230022 | 0 | 131776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6361798 | 6361798 | 6361798 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-078 | 43-078 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Francis Xavier | St. Francis Xavier Catholic Secondary School | SEC | 3958 | 7648 | 7648-B01 | 50 BRISTOL RD W | MISSISSAUGA | L5R3K3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6125 | -79.6638 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4140389 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140389 | 4140389 | 4140389 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-079 | 43-079 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Francis Xavier | St. Francis Xavier Catholic Secondary School | SEC | 3958 | 7648 | 7648-B01 | 50 BRISTOL RD W | MISSISSAUGA | L5R3K3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6125 | -79.6638 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 61403 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61403 | 61403 | 61403 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-080 | 43-080 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Francis Xavier | St. Francis Xavier Catholic Elementary School | ELE | 10381 | 7647 | 7647-B01 | 111 BARTLEY BULL PKY | BRAMPTON | L6W2J8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6745 | -79.7381 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7327336 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7327336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7327336 | 7327336 | 7327336 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-081 | 43-081 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Gerard | St. Gerard Catholic Elementary School | ELE | 3977 | 7664 | 7664-B01 | 1300 MCBRIDE AVE | MISSISSAUGA | L5C1M8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5586 | -79.6562 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3236621 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3236621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3236621 | 3236621 | 3236621 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-082 | 43-082 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Gertrude | St. Gertrude Catholic Elementary School | ELE | 3751 | 7490 | 7490-B01 | 815 CEREMONIAL DR | MISSISSAUGA | L5R3S2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.602 | -79.676 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2855623 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2855623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2855623 | 2855623 | 2855623 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-083 | 43-083 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Gregory | St. Gregory Catholic Elementary School | ELE | 6045 | 8545 | 8545-B01 | 1075 SWINBOURNE DR | MISSISSAUGA | L5V1B9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6092 | -79.7074 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1978004 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1978004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1978004 | 1978004 | 1978004 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-085 | 43-085 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Herbert | St. Herbert Catholic Elementary School | ELE | 9794 | 10271 | 10271-B01 | 5180 FALLINGBROOK DR | MISSISSAUGA | L5V2C6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5859 | -79.6847 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6501331 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6501331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6501331 | 6501331 | 6501331 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-086 | 43-086 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Hilary | St. Hilary Catholic Elementary School | ELE | 3997 | 7678 | 7678-B01 | 5070 FAIRWIND DR | MISSISSAUGA | L5R2N4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6037 | -79.6607 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1888333 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1888333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1888333 | 1888333 | 1888333 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-087 | 43-087 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Isaac Jogues | St. Isaac Jogues Catholic Elementary School | ELE | 10345 | 11078 | 11078-B01 | 300 GREAT LAKES DR | BRAMPTON | L6R2W7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7361 | -79.7695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7791370 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7791370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7791370 | 7791370 | 7791370 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-089 | 43-089 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Jean-Marie Vianney | St. Jean-Marie Vianney Catholic Elementary School | ELE | 17839 | 19042 | 19042-B01 | 75 JORDENSEN DR | BRAMPTON | L6X0S1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6694 | -79.8014 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 555 | - | - | N | - | Not Required | - | 10641583 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111353 | 0 | 9389068 | 0 | 0 | 0 | 0 | 0 | 10500421 | 10500421 | 10500421 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9389068
43-090 | 43-090 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Joan of Arc | St. Joan of Arc Catholic Secondary School | SEC | 10709 | 11254 | 11254-B01 | 3801 THOMAS ST | MISSISSAUGA | L5M7G2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5531 | -79.7466 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 28496062 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28496062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28496062 | 28496062 | 28496062 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-091 | 43-091 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. John Fisher | St. John Fisher Catholic Elementary School | ELE | 4062 | 7731 | 7731-B01 | 330 BALMORAL DR | BRAMPTON | L6T1V6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7103 | -79.7116 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8708 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8708 | 8708 | 8708 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-093 | 43-093 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. John Paul II | St. John Paul II Catholic Elementary School | ELE | 3586 | 7366 | 7366-B01 | 9094 BOLTON HEIGHTS RD | BOLTON | L7E4E2 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8898 | -79.7468 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6676333 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6676333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6676333 | 6676333 | 6676333 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-095 | 43-095 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. John the Baptist | St. John the Baptist Catholic Elementary School | ELE | 9795 | 10272 | 10272-B01 | 299 LANDSBRIDGE ST | BOLTON | L7E2K4 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8708 | -79.7125 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9209762 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9209762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9209762 | 9209762 | 9209762 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-096 | 43-096 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. John XXIII | St. John XXIII Catholic Elementary School | ELE | 3358 | 7203 | 7203-B01 | 915 MCBRIDE AVE | MISSISSAUGA | L5C1M1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5654 | -79.6444 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2093361 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093361 | 2093361 | 2093361 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-097 | 43-097 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Josephine Bahkita | St. Josephine Bahkita Catholic Elementary School | ELE | 11043 | 12159 | 12159-B01 | 430 VAN KIRK DR | BRAMPTON | L7A0J2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7209 | -79.8258 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7440077 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7440077 | 7440077 | 7440077 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-099 | 43-099 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Julia | St. Julia Catholic Elementary School | ELE | 10586 | 11252 | 11252-B01 | 6770 HISTORIC TRAIL | MISSISSAUGA | L5W1J3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6203 | -79.7236 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8094443 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8094443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8094443 | 8094443 | 8094443 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-100 | 43-100 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Kevin | St. Kevin Catholic Elementary School | ELE | 4160 | 7797 | 7797-B01 | 103 MALTA AVE | BRAMPTON | L6Y4C8 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6606 | -79.7314 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2441776 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2441776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2441776 | 2441776 | 2441776 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-101 | 43-101 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Lucy | St. Lucy Catholic Elementary School | ELE | 10781 | 11988 | 11988-B01 | 25 KANATA RD | BRAMPTON | L7A3R2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7079 | -79.8214 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8266997 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8266997 | 8266997 | 8266997 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-102 | 43-102 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Luke | St. Luke Catholic Elementary School | ELE | 10366 | 11048 | 11048-B01 | 1280 COBALT ST | MISSISSAUGA | L5H4L8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5466 | -79.6054 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6887769 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6887769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6887769 | 6887769 | 6887769 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-103 | 43-103 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Marcellinus | St. Marcellinus Catholic Secondary School | SEC | 10362 | 11081 | 11081-B01 | 730 COURTNEYPARK DR W | MISSISSAUGA | L5W1L9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6241 | -79.7102 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 28344629 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28344629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28344629 | 28344629 | 28344629 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-104 | 43-104 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Marguerite d'Youville | St. Marguerite d'Youville Catholic Secondary School | SEC | 9798 | 10273 | 10273-B01 | 10815 DIXIE RD | BRAMPTON | L6R2W5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7522 | -79.7753 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 29622627 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29622627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29622627 | 29622627 | 29622627 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-105 | 43-105 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Mark | St. Mark Catholic Elementary School | ELE | 4216 | 7834 | 7834-B01 | 3675 SAWMILL VALLEY DR | MISSISSAUGA | L5L2Z5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5513 | -79.6796 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2908237 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908237 | 2908237 | 2908237 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-106 | 43-106 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Martin | St. Martin Catholic Secondary School | SEC | 4229 | 7844 | 7844-B01 | 2470 ROSEMARY DR | MISSISSAUGA | L5C1X2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5566 | -79.6356 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 13339549 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13339549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13339549 | 13339549 | 13339549 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-107 | 43-107 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 4239 | 7850 | 7850-B01 | 66 MAIN ST S | BRAMPTON | L6W2C6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6837 | -79.7541 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 607305 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607305 | 607305 | 607305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-108 | 43-108 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Michael | St. Michael Catholic Secondary School | SEC | 11029 | 12235 | 12235-B01 | 9130 COLUMBIA WAY | BOLTON | L7E4G6 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8952 | -79.7517 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 30846394 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30846394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30846394 | 30846394 | 30846394 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-109 | 43-109 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 10360 | 11042 | 11042-B01 | 120 HARVEST MOON DR | BOLTON | L7E2W1 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8714 | -79.7591 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6857509 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6857509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6857509 | 6857509 | 6857509 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-110 | 43-110 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 10360 | 11042 | 11042-B01 | 120 HARVEST MOON DR | BOLTON | L7E2W1 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8714 | -79.7591 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1280868 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280868 | 1280868 | 1280868 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-112 | 43-112 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 4357 | 7931 | 7931-B01 | 11948 THE GORE RD | BRAMPTON | L6P0A2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.8174 | -79.7264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2488894 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488894 | 2488894 | 2488894 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-113 | 43-113 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Paul | St. Paul Catholic Secondary School | SEC | 4380 | 7943 | 7943-B01 | 815 ATWATER AVE | MISSISSAUGA | L5E1L8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5773 | -79.5709 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16414957 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16414957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16414957 | 16414957 | 16414957 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-114 | 43-114 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Peter | St. Peter Catholic Elementary School | ELE | 4402 | 7955 | 7955-B01 | 46 DAWSON RD | ORANGEVILLE | L9W2W3 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.912 | -80.1035 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2364115 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364115 | 2364115 | 2364115 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-115 | 43-115 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Pio of Pietrelcina | St. Pio of Pietrelcina Catholic Elementary School | ELE | 10364 | 11082 | 11082-B01 | 4765 HURON HEIGHTS DR | MISSISSAUGA | L4Z4G9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6082 | -79.6427 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8081848 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8081848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8081848 | 8081848 | 8081848 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-117 | 43-117 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Raymond | St. Raymond Catholic Elementary School | ELE | 9802 | 10277 | 10277-B01 | 5735 WHITEHORN AVE | MISSISSAUGA | L5V2A9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5949 | -79.7016 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7488252 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7488252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7488252 | 7488252 | 7488252 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-118 | 43-118 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Richard | St. Richard Catholic Elementary School | ELE | 4448 | 7989 | 7989-B01 | 7270 COPENHAGEN RD | MISSISSAUGA | L5N2C3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5935 | -79.7701 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1546924 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1546924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1546924 | 1546924 | 1546924 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-119 | 43-119 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Rita | St. Rita Catholic Elementary School | ELE | 10365 | 11047 | 11047-B01 | 30 SUMMER VALLEY DR | BRAMPTON | L6Z4V6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7372 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7600103 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600103 | 7600103 | 7600103 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-120 | 43-120 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Rita | St. Rita Catholic Elementary School | ELE | 10365 | 11047 | 11047-B01 | 30 SUMMER VALLEY DR | BRAMPTON | L6Z4V6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7372 | -79.8244 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1406205 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1406205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1406205 | 1406205 | 1406205 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-121 | 43-121 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Roch | St. Roch Catholic Secondary School | SEC | 11042 | 12173 | 12173-B01 | 200 VALLEYWAY DR | BRAMPTON | L6X0N3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6719 | -79.8071 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 29153866 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29153866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29153866 | 29153866 | 29153866 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-123 | 43-123 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Sebastian | St. Sebastian Catholic Elementary School | ELE | 10587 | 11253 | 11253-B01 | 3460 AQUINAS AVE | MISSISSAUGA | L5M7L2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5409 | -79.7223 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7490604 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7490604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7490604 | 7490604 | 7490604 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-125 | 43-125 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Simon Stock | St. Simon Stock Catholic Elementary School | ELE | 10346 | 11079 | 11079-B01 | 6440 LISGAR DR | MISSISSAUGA | L5N6X3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5656 | -79.77 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7746791 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7746791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7746791 | 7746791 | 7746791 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-126 | 43-126 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Sofia | St. Sofia Catholic Elementary School | ELE | 4465 | 8002 | 8002-B01 | 3540 HAVENWOOD DR | MISSISSAUGA | L4X2M9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6216 | -79.596 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12891 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12891 | 12891 | 12891 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-127 | 43-127 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Sofia | St. Sofia Catholic Elementary School | ELE | 4465 | 8002 | 8002-B01 | 3540 HAVENWOOD DR | MISSISSAUGA | L4X2M9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6216 | -79.596 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 216 | - | - | N | - | Not Required | - | 7190000 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 0 | 6122104 | 0 | 0 | 0 | 0 | 0 | 7053998 | 7053998 | 7053998 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6122104
43-128 | 43-128 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Teresa of Avila | St. Teresa of Avila Catholic Elementary School | ELE | 4476 | 8011 | 8011-B01 | 6675 MONTEVIDEO RD | MISSISSAUGA | L5N4E8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.591 | -79.7512 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2624470 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2624470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2624470 | 2624470 | 2624470 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-129 | 43-129 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Therese of the Child Jesus | St. Therese of the Child Jesus Catholic Elementary School | ELE | 4484 | 8018 | 8018-B01 | 6930 FOREST PARK DR | MISSISSAUGA | L5N6X7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5794 | -79.7773 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1126653 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126653 | 1126653 | 1126653 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-130 | 43-130 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 4498 | 8026 | 8026-B01 | 25 CORPORATION DR | BRAMPTON | L6S6A2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7387 | -79.7104 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5111559 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5111559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5111559 | 5111559 | 5111559 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-131 | 43-131 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 4498 | 8026 | 8026-B01 | 25 CORPORATION DR | BRAMPTON | L6S6A2 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7387 | -79.7104 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 56969 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56969 | 56969 | 56969 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-132 | 43-132 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Thomas More | St. Thomas More Catholic Elementary School | ELE | 4511 | 8037 | 8037-B01 | 3270 TOMKEN RD | MISSISSAUGA | L4Y2Y7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6054 | -79.6013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1025989 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025989 | 1025989 | 1025989 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-134 | 43-134 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Timothy | St. Timothy Catholic Elementary School | ELE | 10780 | 8042 | 8042-B01 | 2214 CLIFF RD | MISSISSAUGA | L5A2N9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.58 | -79.5991 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8626961 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8626961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8626961 | 8626961 | 8626961 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-135 | 43-135 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Ursula | St. Ursula Catholic Elementary School | ELE | 10347 | 11080 | 11080-B01 | 11 DWELLERS RD | BRAMPTON | L6X5C1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6891 | -79.7999 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7636542 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7636542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7636542 | 7636542 | 7636542 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-136 | 43-136 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Valentine | St. Valentine Catholic Elementary School | ELE | 9801 | 10276 | 10276-B01 | 5610 HEATHERLEIGH AVE | MISSISSAUGA | L5V2V7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6007 | -79.6894 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8222342 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8222342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8222342 | 8222342 | 8222342 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-137 | 43-137 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Veronica | St. Veronica Catholic Elementary School | ELE | 10363 | 11045 | 11045-B01 | 680 NOVO STAR DR | MISSISSAUGA | L5W1C7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6311 | -79.7178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7610787 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7610787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7610787 | 7610787 | 7610787 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-138 | 43-138 | 43 | N/A | 67083 | Dufferin Peel CDSB | Streetsville Holding | Streetsville Holding Catholic Elementary School | ELE | 10141 | 5212 | 5212-B01 | 6341 MISSISSAUGA RD | MISSISSAUGA | L5N1A5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5954 | -79.7304 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9812925 | Construction Complete | Retrofit | Accommodation Pressure | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9812925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9812925 | 9812925 | 9812925 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-139 | 43-139 | 43 | N/A | 67083 | Dufferin Peel CDSB | Sts. Martha and Mary | Sts. Martha and Mary Catholic Elementary School | ELE | 4567 | 8080 | 8080-B01 | 1760 BOUGH BEECHES BLVD | MISSISSAUGA | L4W2B9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6358 | -79.6016 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4448672 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448672 | 4448672 | 4448672 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-140 | 43-140 | 43 | N/A | 67083 | Dufferin Peel CDSB | Venerable Michael J McGivney | Venerable Michael J McGivney Catholic Elementary School | ELE | 10584 | 11249 | 11249-B01 | 450 FERNFOREST DR | BRAMPTON | L6R2P7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7529 | -79.7679 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8004628 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8004628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8004628 | 8004628 | 8004628 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
43-141 | 43-141 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | St. Evan | St. Evan Catholic Elementary School | ELE | 24590 | 19596 | 19596-B01 | 500 DOUGALL AVE | CALEDON | L7C4C5 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.7522 | -79.8361 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 504 | 2 | 39 | Y | - | Approved | 43073 | 12474008 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43472 | 0 | 0 | 0 | 0 | 1088004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088004 | 0 | 0 | 1008340 | 0 | 9369324 | 0 | 1008340 | 0 | 0 | 0 | 11386004 | 12474008 | 12474008 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10377664
43-142 | 43-142 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | St. Jacinta Marto | St. Jacinta Marto Catholic Elementary School | ELE | 24589 | 19595 | 19595-B01 | 40 FALLOWFIELD RD | BRAMPTON | L6X0W1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6572 | -79.7976 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 504 | 2 | 39 | Y | - | Approved | 43679 | 13595574 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43711 | 0 | 0 | 0 | 0 | 1409570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409570 | 0 | 0 | 1008340 | 0 | 10169324 | 0 | 1008340 | 0 | 0 | 0 | 12186004 | 13595574 | 13595574 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11177664
43-143 | 43-143 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Bernadette | St. Bernadette Catholic Elementary School | ELE | 3798 | 7528 | 7528-B01 | 1060 WHITE CLOVER WAY | MISSISSAUGA | L5V1G7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5816 | -79.673 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2019-20 | 43711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945000 | 0 | 0 | 0 | 0 | 0 | 945000 | 945000 | 945000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 945000
43-144 | 43-144 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Gregory | St. Gregory Catholic Elementary School | ELE | 6045 | 8545 | 8545-B01 | 1075 SWINBOURNE DR | MISSISSAUGA | L5V1B9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6092 | -79.7074 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Consolidation | 2018-19 | 43374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560000 | 0 | 0 | 0 | 0 | 0 | 560000 | 560000 | 560000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 560000
43-145 | 43-145 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Herbert | St. Herbert Catholic Elementary School | ELE | 9794 | 10271 | 10271-B01 | 5180 FALLINGBROOK DR | MISSISSAUGA | L5V2C6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5859 | -79.6847 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Retrofit | Consolidation | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 190000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 190000
43-146 | 43-146 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Valentine | St. Valentine Catholic Elementary School | ELE | 9801 | 10276 | 10276-B01 | 5610 HEATHERLEIGH AVE | MISSISSAUGA | L5V2V7 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6007 | -79.6894 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Consolidation | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1335000 | 0 | 0 | 0 | 0 | 0 | 1335000 | 1335000 | 1335000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1335000
43-147 | 43-147 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | St. Edith Stein | St. Edith Stein Catholic Elementary School | ELE | 3071 | 7014 | 7014-B01 | 6234 OSPREY BLVD | MISSISSAUGA | L5N5V5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5662 | -79.7586 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 34 | Y | - | Approved | 43879 | 1008341 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008341 | 0 | 0 | 0 | 1008341 | 1008341 | 1008341 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1008341
43-148 | 43-148 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | Father Michael Goetz | Father Michael Goetz Catholic Secondary School | SEC | 6493 | 8750 | 8750-B01 | 330 CENTRAL PKY W | MISSISSAUGA | L5B3K6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5819 | -79.6358 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44490 | 1125502 | Construction Complete | Retrofit | Child Care | 2020-21 | 44298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205845 | 0 | 0 | 0 | 1205845 | 1205845 | 1205845 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1205845
43-149 | 43-149 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | St. Albert of Jerusalem | St. Albert of Jerusalem Catholic Elementary School | ELE | 9483 | 10175 | 10175-B01 | 7185 ROSEHURST DR | MISSISSAUGA | L5N7G6 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5803 | -79.7892 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 44490 | 1257116 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000882 | 0 | 0 | 0 | 2000882 | 2000882 | 2000882 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2000882
43-150 | 43-150 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | Holy Spirit | Holy Spirit Catholic Elementary School | ELE | 10639 | 11255 | 11255-B01 | 25 BLOOMSBURY AVE | BRAMPTON | L6P1W9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7843 | -79.7292 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44490 | 1700591 | Construction Complete | Retrofit | Child Care | 2021-22 | 44634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700591 | 0 | 0 | 0 | 1700591 | 1700591 | 1700591 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1700591
43-151 | 43-151 | 43 | N/A | 67083 | Dufferin Peel CDSB | Holy Name of Mary | Holy Name of Mary Catholic Secondary School | SEC | 4209 | 7830 | 7830-B01 | 115 GLENVALE BLVD | BRAMPTON | L6S3J7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7338 | -79.7167 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 357 | - | - | N | - | Approved | 43621 | 11009943 | Construction Complete | Addition | Condition | 2020-21 | 44243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11009943 | 0 | 0 | 0 | 0 | 0 | 11009943 | 11009943 | 11009943 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11009943
43-152 | 43-152 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Cornelius | St. Cornelius Catholic Elementary School | ELE | 3874 | 7583 | 7583-B01 | 16066 INNIS LAKE RD | CALEDON EAST | L7C2Z2 | 35-11-21-401 | Caledon | Caledon T | Peel R | PEEL | GTA | South | 43.8792 | -79.8581 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 184 | - | - | N | - | Approved | 43433 | 3736881 | Construction Complete | Addition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3736881 | 0 | 0 | 0 | 0 | 0 | 3736881 | 3736881 | 3736881 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3736881
43-153 | 43-153 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | San Lorenzo Ruiz | San Lorenzo Ruiz Catholic Elementary School | ELE | 9792 | 10270 | 10270-B01 | 100 BARONDALE DR | MISSISSAUGA | L4Z3R1 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6178 | -79.6636 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 73 | N | - | Planned | - | - | Planned | Retrofit | Child Care | 2022-23 | 44929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604472 | 0 | 0 | 0 | 1604472 | 1604472 | 1604472 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1604472
43-154 | 43-154 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | Our Lady of Mercy | Our Lady of Mercy Catholic Elementary School | ELE | 6040 | 8542 | 8542-B01 | 5820 GLEN ERIN DR | MISSISSAUGA | L5M5J9 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5693 | -79.733 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 73 | N | - | Planned | - | - | Planned | Retrofit | Child Care | 2022-23 | 44929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1604472 | 0 | 0 | 0 | 1604472 | 1604472 | 1604472 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1604472
43-155 | 43-155 | 43 | N/A | 67083 | Dufferin Peel CDSB | St. Leonard | St. Leonard Catholic Elemenary School | ELE | 4165 | 7801 | 7801-B01 | 185 CONESTOGA DR | BRAMPTON | L6Z2Z7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7231 | -79.7903 | 44376 | 2020-21 | 2021-22 | - | - | - | 44376 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2022-23 | 44927 | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 0 | 4029513 | 0 | 0 | 0 | 0 | 0 | 4029513 | 4779513 | 4779513 | 0 | - | TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4029513
43-156 | 43-156 | 43 | 232 - CMSM Peel | 67083 | Dufferin Peel CDSB | Mount Pleasant | Mount Pleasant Catholic Elementary School | ELE | TBD | TBD | TBD | ROBERT PARKINSON DR / SEINCLIFF RD | BRAMPTON | TBD | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6969 | -79.852 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 435 | 4 | 73 | N | - | Approved | 45064 | 19284840 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 386340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386340 | 0 | 0 | 0 | 0 | 16308683 | 0 | 2589817 | 0 | 0 | 0 | 18898500 | 19284840 | 19284840 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 18898500
43-157 | 43-157 | 43 | N/A | 67083 | Dufferin-Peel CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | BRAMPTON | L6V1M5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 504 | - | - | N | - | Approved | 45076 | 19203274 | Planned | New Construction | Condition | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19203274 | 0 | 0 | 0 | 0 | 0 | 19203274 | 19203274 | 19203274 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 19203274
43-158 | 43-157 | 43 | N/A | 67083 | Dufferin-Peel CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | BRAMPTON | L6V1M5 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - |  | - | - | N | - | Approved | 45076 | 927126 | Planned | Demolition | Condition | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927126 | 0 | 0 | 0 | 0 | 0 | 927126 | 927126 | 927126 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 927126
43-159 | 43-159 | 43 |  | 67083 | Dufferin-Peel CDSB | Ascension of Our Lord | Ascension of Our Lord Catholic Secondary School | SEC | 10589 | 8748 |  | 7640 ANAKA DRIVE | MISSISAUGA | L4T3H7 |  | Mississauga | Mississauga C | Peel R |  | GTA | South | 43.72 | -79.65 | [26 empty] | Planned | New Construction | Other |  |  | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 0
44-001 | 44-001 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15763 | 18081 | 18081-B01 | 46 ALLIANCE BLVD | BARRIE | L4M5K3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4109 | -79.681 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52852 | 0 | 0 | 0 | 0 | 0 | 52852 | 52852 | 0 | -52852 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 52852
44-002 | 44-002 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15763 | 18081 | 18081-B01 | 46 ALLIANCE BLVD | BARRIE | L4M5K3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4109 | -79.681 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3282910 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4290318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4290318 | 4290318 | 3282910 | -1007408 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-003 | 44-003 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 15763 | 18081 | 18081-B01 | 46 ALLIANCE BLVD | BARRIE | L4M5K3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4109 | -79.681 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1510235 | Construction Complete | Other | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510235 | 1510235 | 1510235 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-004 | 44-004 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 15763 | 18081 | 18081-B01 | 46 ALLIANCE BLVD | BARRIE | L4M5K3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4109 | -79.681 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5163941 | Construction Complete | Other | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5163941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5163941 | 5163941 | 5163941 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-005 | 44-005 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Canadian Martyrs | Canadian Martyrs Catholic Elementary School | ELE | 9590 | 10203 | 10203-B01 | 7 BELLISLE RD | PENETANGUISHENE | L9M1N6 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7641 | -79.9373 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4233750 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4233750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4233750 | 4233750 | 4233750 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-007 | 44-007 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Father F.X. O'Reilly | Father F.X. O'Reilly Catholic Elementary School | ELE | 8287 | 9328 | 9328-B01 | 235 QUEEN ST N | TOTTENHAM | L0G1W0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0322 | -79.8088 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4581674 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 436000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299536 | 735536 | 748212 | 0 | 0 | 0 | 0 | 3097926 | 0 | 0 | 0 | 0 | 3846138 | 4581674 | 4581674 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-008 | 44-008 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Foley | Foley Catholic Elementary School | ELE | 8288 | 9329 | 9329-B01 | 2162 CONCESSION ROAD 4 | BRECHIN | L0K1B0 | 35-11-70-622 | Ramara | Ramara Tp | Simcoe Co | SIMCOE | Central | South | 44.5481 | -79.1729 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2438268 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2438268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2438268 | 2438268 | 2438268 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-009 | 44-009 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Holy Cross | Holy Cross Catholic Elementary School | ELE | 9791 | 10269 | 10269-B01 | 910 LESLIE DR | INNISFIL | L9S1A7 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.3226 | -79.5467 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5028517 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5028517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5028517 | 5028517 | 5028517 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-010 | 44-010 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 8290 | 9331 | 9331-B01 | 180 KING ST S | ALLISTON | L9R1B9 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.1425 | -79.8769 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1879644 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879644 | 1879644 | 1879644 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-011 | 44-011 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 8291 | 9332 | 9332-B01 | 100 MELBOURNE DR | BRADFORD | L3Z2B3 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1073 | -79.5797 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12071902 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12071902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12071902 | 12071902 | 12071902 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-012 | 44-012 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Jean Vanier | Jean Vanier Catholic Secondary School | SEC | 8292 | 9333 | 9333-B01 | 160 COLLINS ST | COLLINGWOOD | L9Y4R1 | 35-11-70-403 | Collingwood | Collingwood T | Simcoe Co | SIMCOE | Central | South | 44.4898 | -80.2073 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3773442 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3773442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3773442 | 3773442 | 3773442 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-013 | 44-013 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Monsignor Clair | Monsignor Clair Catholic Elementary School | ELE | 8295 | 9336 | 9336-B01 | 345 LIVINGSTONE ST E | BARRIE | L4M7B5 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4143 | -79.6854 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5183540 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5183540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5183540 | 5183540 | 5183540 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-014 | 44-014 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Monsignor Clair | Monsignor Clair Catholic Elementary School | ELE | 8295 | 9336 | 9336-B01 | 345 LIVINGSTONE ST E | BARRIE | L4M7B5 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4143 | -79.6854 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2415000 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 1056000 | 0 | 296328 | 1062672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415000 | 2415000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-015 | 44-015 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Monsignor JE Ronan | Monsignor JE Ronan Catholic Elementary School | ELE | 9404 | 10156 | 10156-B01 | 10 LILLY ST E | BEETON | L0G1A0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0917 | -79.7875 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4817690 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4817690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4817690 | 4817690 | 4817690 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-016 | 44-016 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Monsignor Lee | Monsignor Lee Catholic Elementary School | ELE | 14450 | 9337 | 9337-B02 | 14 FITTONS RD E | ORILLIA | L3V2H9 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6236 | -79.4299 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9966117 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 139925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273427 | 1413352 | 8100259 | 0 | 452506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8552765 | 9966117 | 9966117 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-017 | 44-017 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Our Lady of Grace | Our Lady of Grace Catholic Elementary School | ELE | 8299 | 9340 | 9340-B01 | 24 ROTH ST | ANGUS | L0M1B2 | 35-11-70-602 | Essa | Essa Tp | Simcoe Co | SIMCOE | Central | South | 44.325 | -79.8859 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 403 | - | - | N | - | Approved | 41117 | 10793352 | Construction Complete | Addition | Condition | 2014-15 | 41883 | 50148 | 0 | 0 | 0 | 1425040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1475188 | 0 | 0 | 484585 | 0 | 8833579 | 0 | 0 | 0 | 0 | 0 | 9318164 | 10793352 | 10793352 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8833579
44-018 | 44-018 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 8300 | 9341 | 9341-B01 | 34 KERR ST | ELMVALE | L0L1P0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.5863 | -79.8631 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 924148 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 814148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 814148 | 924148 | 924148 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-019 | 44-019 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Patrick Fogarty | Patrick Fogarty Catholic Secondary School | SEC | 8303 | 9344 | 9344-B01 | 15 COMMERCE RD | ORILLIA | L3V0Z2 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6263 | -79.4317 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8631247 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6931247 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8631247 | 8631247 | 8631247 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-020 | 44-020 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Saint Gabriel the Archangel | Saint Gabriel the Archangel Catholic Elementary School | ELE | 10935 | 12090 | 12090-B01 | 130 PRINCE WILLIAM WAY | BARRIE | L4M7G4 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3559 | -79.6126 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10444510 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453 | 453 | 10444057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10444057 | 10444510 | 10444510 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-022 | 44-022 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Saint Mary's | Saint Mary's Catholic Elementary School | ELE | 3270 | 5141 | 5141-B01 | 36 SILVERWOOD DR | HUNTSVILLE | P1H1N1 | 35-11-33-403 | Huntsville | Huntsville T | Muskoka D | MUSKOKA | Central | South | 45.3299 | -79.2341 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 79795 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79795 | 79795 | 79795 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-023 | 44-023 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Sister Catherine Donnelly | Sister Catherine Donnelly Catholic Elementary School | ELE | 10282 | 10480 | 10480-B01 | 123 HANMER ST E | BARRIE | L4M6W2 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4196 | -79.7044 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5793624 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793624 | 5793624 | 5793624 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-024 | 44-024 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Angela Merici | St. Angela Merici Catholic Elementary School | ELE | 14411 | 18010 | 18010-B01 | 109 WEST PARK AVE | BRADFORD | L3Z0A7 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1011 | -79.5867 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 470 | - | - | N | - | Not Required | - | 10957211 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42255 | 0 | 0 | 0 | 0 | 1584359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584359 | 0 | 0 | 969170 | 0 | 8403682 | 0 | 0 | 0 | 0 | 0 | 9372852 | 10957211 | 10957211 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8403682
44-025 | 44-025 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Antoine Daniel | St. Antoine Daniel Catholic Elementary School | ELE | 8330 | 9367 | 9367-B01 | 460 PARK ST | VICTORIA HARBOUR | L0K2A0 | 35-11-70-625 | Tay | Tay Tp | Simcoe Co | SIMCOE | Central | South | 44.7464 | -79.7613 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 72822 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72822 | 72822 | 72822 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-026 | 44-026 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Bernadette | St. Bernadette Catholic Elementary School | ELE | 10108 | 10395 | 10395-B01 | 101 MARSELLUS DR | BARRIE | L4N8R6 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3326 | -79.7213 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5682230 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5682230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5682230 | 5682230 | 5682230 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-027 | 44-027 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Bernard's | St. Bernard's Catholic Elementary School | ELE | 22521 | 9349 | 9349-B02 | 255 OXFORD ST | ORILLIA | L3V1H6 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6005 | -79.3961 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10850384 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 1147245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150898 | 2298143 | 8099735 | 0 | 452506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8552241 | 10850384 | 10850384 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-028 | 44-028 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 9944 | 10339 | 10339-B01 | 111 SUMMERSET DR | BARRIE | L4N0A6 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3572 | -79.724 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5510551 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5510551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5510551 | 5510551 | 5510551 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-029 | 44-029 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 9944 | 10339 | 10339-B01 | 111 SUMMERSET DR | BARRIE | L4N0A6 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3572 | -79.724 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1106086 | Construction Complete | Addition | Other | 2014-15 | 41883 | 118500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118500 | 0 | 0 | 987586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987586 | 1106086 | 1106086 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-030 | 44-030 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Dominic's | St. Dominic's Catholic Secondary School | SEC | 9406 | 10158 | 10158-B01 | 955 CEDAR LANE | BRACEBRIDGE | P1L0A1 | 35-11-33-401 | Bracebridge | Bracebridge T | Muskoka D | MUSKOKA | Central | South | 45.048 | -79.2958 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9794540 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9794540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9794540 | 9794540 | 9794540 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-031 | 44-031 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Dominic's | St. Dominic's Catholic Secondary School | SEC | 9406 | 10158 | 10158-B01 | 955 CEDAR LANE | BRACEBRIDGE | P1L0A1 | 35-11-33-401 | Bracebridge | Bracebridge T | Muskoka D | MUSKOKA | Central | South | 45.048 | -79.2958 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3549392 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3549392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3549392 | 3549392 | 3549392 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-032 | 44-032 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 8312 | 9352 | 9352-B01 | 1067 ANNA MARIA AVE | INNISFIL | L9S1W2 | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | 44.3035 | -79.5513 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1787092 | Construction Complete | Addition | Other | 2014-15 | 41883 | 84500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84500 | 0 | 0 | 1702592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1702592 | 1787092 | 1787092 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-033 | 44-033 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. James | St. James Catholic Elementary School | ELE | 8313 | 9353 | 9353-B01 | 7332 ST JAMES LANE RR 1 | TOTTENHAM | L0G1W0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0269 | -79.848 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1768834 | Construction Complete | Addition | Other | 2014-15 | 41883 | 335000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335000 | 0 | 0 | 1433834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1433834 | 1768834 | 1768834 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-034 | 44-034 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Joan of Arc | St. Joan of Arc Catholic Secondary School | SEC | 10111 | 10396 | 10396-B01 | 460 MAPLETON AVE | BARRIE | L4N9C2 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3492 | -79.7331 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6108584 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 155000 | 0 | 0 | 0 | 0 | 0 | 5953584 | 0 | 0 | 0 | 0 | 5953584 | 6108584 | 6108584 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-035 | 44-035 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Joan of Arc | St. Joan of Arc Catholic Secondary School | SEC | 10111 | 10396 | 10396-B01 | 460 MAPLETON AVE | BARRIE | L4N9C2 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3492 | -79.7331 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 20096901 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20096901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20096901 | 20096901 | 20096901 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-036 | 44-036 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. John Paul II | St. John Paul II Catholic Elementary School | ELE | 8305 | 9345 | 9345-B01 | 211 ASHFORD DR | BARRIE | L4N6A3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3563 | -79.6397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2575040 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575040 | 2575040 | 2575040 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-037 | 44-037 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. John Vianney | St. John Vianney Catholic Elementary School | ELE | 8315 | 9355 | 9355-B01 | 393 INNISFIL ST | BARRIE | L4N3G7 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3671 | -79.6915 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 936940 | Construction Complete | Addition | Other | 2014-15 | 41883 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 0 | 0 | 882940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882940 | 936940 | 936940 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-038 | 44-038 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Joseph's | St. Joseph's Catholic Secondary School | SEC | 8317 | 9356 | 9356-B01 | 243 CUNDLES RD E | BARRIE | L4M6L1 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4127 | -79.6844 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8496415 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8496415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8496415 | 8496415 | 8496415 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-039 | 44-039 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Marie of the Incarnation | St. Marie of the Incarnation Catholic Elementary School | ELE | 8293 | 9334 | 9334-B01 | 105 COLBORNE ST | BRADFORD | L3Z1C4 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.1184 | -79.5608 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 242 | - | - | N | - | Not Required | - | 8005162 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42450 | 487710 | 0 | 0 | 0 | 1210636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | 1736346 | 122625 | 0 | 2111752 | 0 | 4334439 | 0 | 0 | 0 | 0 | 0 | 6568816 | 8305162 | 8305162 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4334439
44-040 | 44-040 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Michael the Archangel | St. Michael the Archangel Catholic Elementary School | ELE | 9790 | 10268 | 10268-B01 | 349 BIG BAY POINT RD | BARRIE | L4N8A2 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3537 | -79.6598 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5478356 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5478356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5478356 | 5478356 | 5478356 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-041 | 44-041 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Monica's | St. Monica's Catholic Elementary School | ELE | 8322 | 9361 | 9361-B01 | 90 STEEL ST | BARRIE | L4M2E9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4026 | -79.6659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5179927 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179927 | 5179927 | 5179927 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-042 | 44-042 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Noel Chabanel | St. Noel Chabanel Catholic Elementary School | ELE | 9407 | 10159 | 10159-B01 | 425 RAMBLEWOOD DR | WASAGA BEACH | L9Z1P3 | 35-11-70-408 | Wasaga Beach | Wasaga Beach T | Simcoe Co | SIMCOE | Central | South | 44.4615 | -80.0906 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5065819 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5065819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5065819 | 5065819 | 5065819 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-043 | 44-043 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Patrick's | St. Patrick's Facility Holding | HFA | 8323 | 9362 | 9362-B01 | 1588 FLOS RD 4 E RR 1 | PHELPSTON | L0L2K0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.5177 | -79.85 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 200000 | Construction Complete | Retrofit | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-044 | 44-044 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Paul | St. Paul Catholic Elementary School | ELE | 10936 | 12091 | 12091-B01 | 100 JAMES A MCCAGUE AVE | ALLISTON | L9R0G5 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.165 | -79.8685 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9604502 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376575 | 1376575 | 8227927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8227927 | 9604502 | 9604502 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-045 | 44-045 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Peter's | St. Peter's Catholic Secondary School | SEC | 8325 | 9345 | 9345-B02 | 201 ASHFORD DR | BARRIE | L4N6A3 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3549 | -79.6398 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11353200 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171588 | 171588 | 6220292 | 0 | 0 | 0 | 0 | 4961320 | 0 | 0 | 0 | 0 | 11181612 | 11353200 | 11353200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-046 | 44-046 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Theresa's | St. Theresa's Catholic Secondary School | SEC | 9585 | 10201 | 10201-B01 | 347 GALLOWAY BLVD | MIDLAND | L4R5B2 | 35-11-70-404 | Midland | Midland T | Simcoe Co | SIMCOE | Central | South | 44.739 | -79.87 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5454230 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5454230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5454230 | 5454230 | 5454230 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-047 | 44-047 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 8327 | 9365 | 9365-B01 | 2 NOLAN RD | TOTTENHAM | L0G1W0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.0351 | -79.8087 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9436465 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9436465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9436465 | 9436465 | 9436465 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-048 | 44-048 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | St. Charles | St. Charles Catholic Elementary School | ELE | 24622 | 9350 | 9350-B02 | 691 SIMCOE RD | BRADFORD | L3Z4B4 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | 44.0933 | -79.5671 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 470 | 3 | 49 | Y | - | Approved | 44124 | 18244650 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 6746715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6746715 | 0 | 0 | 1008340 | 0 | 8977085 | 0 | 1512510 | 0 | 0 | 0 | 11497935 | 18244650 | 18244650 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10489595
44-049 | 44-049 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | St. Bernard's | St. Bernard's Catholic Elementary School | ELE | 22521 | 9349 | 9349-B02 | 255 OXFORD ST | ORILLIA | L3V1H6 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6005 | -79.3961 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | N | 1 | Approved | 43228 | 3100002 | Construction Complete | Addition | Child Care | 2019-20 | 43836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2585748 | 514254 | 0 | 0 | 3100002 | 3100002 | 3100002 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 3100002
44-050 | 44-050 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | St. Paul's | St. Paul's Catholic Elementary School | ELE | 10936 | 12091 | 12091-B01 | 100 JAMES A MCCAGUE AVE | ALLISTON | L9R0G5 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.165 | -79.8685 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 45118 | 3679552 | Under Construction | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3679552 | 0 | 0 | 0 | 3679552 | 3679552 | 3679552 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3679552
44-051 | 44-051 | 44 | 226 - CMSM Muskoka | 67091 | Simcoe Muskoka CDSB | St. Mary's | St. Mary's Catholic Elementary School | ELE | 3270 | 5141 | 5141-B01 | 36 SILVERWOOD DR | HUNTSVILLE | P1H1N1 | 35-11-33-403 | Huntsville | Huntsville T | Muskoka D | MUSKOKA | Central | South | 45.3299 | -79.2341 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 39 | N | - | Approved | 43152 | 1159591 | Under Construction | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159591 | 0 | 0 | 0 | 1159591 | 1159591 | 1159591 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1159591
44-052 | 44-052 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | St. Antoine Daniel | St. Antoine Daniel Catholic Elementary School | ELE | 8330 | 9367 | 9367-B01 | 460 PARK ST | VICTORIA HARBOUR | L0K2A0 | 35-11-70-625 | Tay | Tay Tp | Simcoe Co | SIMCOE | Central | South | 44.7464 | -79.7613 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Planned | - | 0 | Planned | Addition | Consolidation | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 1058757 | 0 | 0 | 0 | 1198757 | 1198757 | 1198757 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 1198757
44-053 | 44-053 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 8289 | 9330 | 9330-B01 | 125 WEST ST N | ORILLIA | L3V5C4 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6117 | -79.4231 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Demolition | Other | 2017-18 | 42979 | 0 | 0 | 437989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437989 | 437989 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-054 | 44-054 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 8300 | 9341 | 9341-B01 | 34 KERR ST | ELMVALE | L0L1P0 | 35-11-70-624 | Springwater | Springwater Tp | Simcoe Co | SIMCOE | Central | South | 44.5863 | -79.8631 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058759 | 0 | 0 | 0 | 1058759 | 1058759 | 1058759 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1058759
44-056 | 44-056 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | St. Monica's | St. Monica's Catholic Elementary School | ELE | 8322 | 9361 | 9361-B01 | 90 STEEL ST | BARRIE | L4M2E9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.4026 | -79.6659 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028508 | 0 | 0 | 0 | 1028508 | 1028508 | 1028508 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1028508
44-057 | 44-057 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | Alliston | Alliston Catholic Elementary School | ELE | 24844 | 19850 | 19850-B01 | WILLOUGHBY WAY | ALLISTON | TBD | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | 44.1608 | -79.792 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 470 | 3 | 49 | Y | - | Approved | 44166 | 14977046 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44810 | 0 | 0 | 575115 | 0 | 2469225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3044340 | 0 | 0 | 1079932 | 0 | 9264637 | 0 | 1588138 | 0 | 0 | 0 | 11932707 | 14977047 | 11932708 | -3044339 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10852775
44-058 | 44-058 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 8298 | 9339 | 9339-B01 | 140 ATLANTIS DR | ORILLIA | L3V0A8 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6103 | -79.4622 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43258 | 856800 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856800 | 0 | 0 | 0 | 0 | 0 | 856800 | 856800 | 856800 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 856800
44-059 | 44-059 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | Innisfil South | Innisfil South Catholic Elementary School | ELE | 14413 | 18012 | 18012-B01 | MCMASTER AVE | INNISFIL | TBD | 35-11-70-409 | Innisfil | Innisfil T | Simcoe Co | SIMCOE | Central | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 493 | 3 | 49 | - | - | Approved | 45077 | 22610121 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 4897901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4897901 | 0 | 0 | 0 | 0 | 15508879 | 0 | 2203341 | 0 | 0 | 0 | 17712220 | 22610121 | 22610121 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 17712220
44-060 | 44-060 | 44 | N/A | 67091 | Simcoe Muskoka CDSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 8298 | 9339 | 9339-B01 | 140 ATLANTIS DR | ORILLIA | L3V0A8 | 35-11-70-102 | Orillia | Orillia C | Simcoe Co | SIMCOE | Central | South | 44.6103 | -79.4622 | 44306 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | N | - | Approved | 44306 | 249520 | Construction Complete | Other | Other | 2021-22 | 44440 | 149075 | 0 | 100445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249520 | 249520 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
44-061 | 44-061 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | Bradford | Bradford Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | BRADFORD | L3Z0G4 | 35-11-70-410 | Bradford West Gwillimbury | Bradford-West Gwillimbury T | Simcoe Co | SIMCOE | Central | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 516 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14257909 | 0 | 2053640 | 0 | 0 | 0 | 16311549 | 16311549 | 16311549 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16311549
44-062 | 44-062 | 44 | 224 - CMSM Simcoe | 67091 | Simcoe Muskoka CDSB | Tottenham | Tottenham Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | TOTTENHAM | L0G1W0 | 35-11-70-411 | New Tecumseth | New Tecumseth T | Simcoe Co | SIMCOE | Central | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 516 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14257909 | 0 | 2053640 | 0 | 0 | 0 | 16311549 | 16311549 | 16311549 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16311549
45-001 | 45-001 | 45 | N/A | 67105 | Durham CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15780 | 18091 | 18091-B01 | 650 ROSSLAND RD W | OSHAWA | L1J7C4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.911 | -78.8958 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 0
45-002 | 45-002 | 45 | N/A | 67105 | Durham CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15780 | 18091 | 18091-B01 | 650 ROSSLAND RD W | OSHAWA | L1J7C4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.911 | -78.8958 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6914966 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7428013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7428013 | 7428013 | 6914966 | -513047 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-003 | 45-003 | 45 | N/A | 67105 | Durham CDSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 15780 | 18091 | 18091-B01 | 650 ROSSLAND RD W | OSHAWA | L1J7C4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.911 | -78.8958 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2700000 | Construction Complete | Other | Other | 2010-11 | 40422 | 0 | 0 | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 2700000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-004 | 45-004 | 45 | N/A | 67105 | Durham CDSB | BWE (OTH) | Board Wide Expense (Other) | OFF-ADM | 15780 | 18091 | 18091-B01 | 650 ROSSLAND RD W | OSHAWA | L1J7C4 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.911 | -78.8958 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2142338 | Construction Complete | Other | Other | 2011-12 | 40787 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 142338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142338 | 2142338 | 2142338 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-005 | 45-005 | 45 | N/A | 67105 | Durham CDSB | All Saints | All Saints Catholic Secondary School | SEC | 9907 | 10321 | 10321-B01 | 3001 COUNTRY LANE | WHITBY | L1P1M1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8951 | -78.9656 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21635268 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331232 | 1331232 | 20304036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20304036 | 21635268 | 21635268 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-006 | 45-006 | 45 | N/A | 67105 | Durham CDSB | Archbishop Denis O'Connor | Archbishop Denis O'Connor Catholic Secondary School | SEC | 8759 | 9655 | 9655-B01 | 80 MANDRAKE ST | AJAX | L1S5H4 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8581 | -79.02 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6033017 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2387659 | 2387659 | 3645358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3645358 | 6033017 | 6033017 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-008 | 45-008 | 45 | N/A | 67105 | Durham CDSB | St. John Paul II | St. John Paul II Catholic Elementary School | ELE | 18327 | 19068 | 19068-B01 | 160 CACHET BLVD | WHITBY | L1M2L9 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9664 | -78.9432 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Not Required | - | 8119870 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465947 | 0 | 8195365 | 0 | 0 | 0 | 0 | 0 | 8661312 | 8661312 | 8119870 | -541442 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8195365
45-009 | 45-009 | 45 | N/A | 67105 | Durham CDSB | St. André Bessette | St. André Bessette Catholic Elementary School | ELE | 10608 | 11258 | 11258-B01 | 60 SEGGAR AVE | AJAX | L1T4Y4 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8836 | -79.0441 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7711707 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7711707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7711707 | 7711707 | 7711707 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-010 | 45-010 | 45 | N/A | 67105 | Durham CDSB | Father Fenelon | Father Fenelon Catholic Elementary School | ELE | 24315 | 9668 | 9668-B02 | 795 EYER DR | PICKERING | L1W2K2 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8158 | -79.1093 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 409 | - | - | N | - | Not Required | - | 9527847 | Construction Complete | New Construction | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969184 | 0 | 7836124 | 0 | 0 | 0 | 0 | 0 | 8805308 | 8805308 | 9520450 | 715142 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7836124
45-011 | 45-011 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | Father Fenelon | Father Fenelon Catholic Elementary School | ELE | 24315 | 9668 | 9668-B02 | 795 EYER DR | PICKERING | L1W2K2 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8158 | -79.1093 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 42510 | 1317124 | Construction Complete | Addition | Child Care | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482852 | 0 | 0 | 0 | 1482852 | 1482852 | 1529569 | 46717 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1482852
45-012 | 45-012 | 45 | N/A | 67105 | Durham CDSB | Father Leo J Austin | Father Leo J Austin Catholic Secondary School | SEC | 8762 | 9658 | 9658-B02 | 1020 DRYDEN BLVD | WHITBY | L1R2A2 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9119 | -78.9377 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1617168 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617168 | 1617168 | 1617168 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-014 | 45-014 | 45 | N/A | 67105 | Durham CDSB | Monsignor J Pereyma | Monsignor J Pereyma Catholic Secondary School | SEC | 8768 | 9664 | 9664-B01 | 316 CONANT ST | OSHAWA | L1H3S6 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8803 | -78.8434 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3887385 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3887385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3887385 | 3887385 | 3887385 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-015 | 45-015 | 45 | N/A | 67105 | Durham CDSB | Monsignor Paul Dwyer | Monsignor Paul Dwyer Catholic Secondary School | SEC | 8769 | 9665 | 9665-B01 | 700 STEVENSON RD N | OSHAWA | L1J5P5 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9113 | -78.8931 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3328532 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121986 | 1121986 | 2206546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2206546 | 3328532 | 3328532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-017 | 45-017 | 45 | N/A | 67105 | Durham CDSB | St. Teresa of Calcutta | St. Teresa of Calcutta Catholic Elementary School | ELE | 9903 | 10318 | 10318-B01 | 15 FISHLOCK ST | AJAX | L1Z1H1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8762 | -79.0302 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4702291 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390991 | 390991 | 4311300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4311300 | 4702291 | 4702291 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-018 | 45-018 | 45 | N/A | 67105 | Durham CDSB | Notre Dame | Notre Dame Catholic Secondary School | SEC | 9910 | 10322 | 10322-B01 | 1375 HARWOOD AVE N | AJAX | L1T4G8 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8846 | -79.028 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 26599195 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4392413 | 4392413 | 22206782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22206782 | 26599195 | 26599195 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-021 | 45-021 | 45 | N/A | 67105 | Durham CDSB | St. Bernadette | St. Bernadette Catholic Elementary School | ELE | 11883 | 9670 | 9670-B01 | 41 BAYLY ST E | AJAX | L1S1P2 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8435 | -79.0159 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12454314 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12454314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12454314 | 12454314 | 12454314 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-022 | 45-022 | 45 | N/A | 67105 | Durham CDSB | St. Bridget | St. Bridget Catholic Elementary School | ELE | 10561 | 11169 | 11169-B01 | 200 CARNWITH DR W | WHITBY | L1M2J8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9618 | -78.9753 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6256760 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6256760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6256760 | 6256760 | 6256760 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-023 | 45-023 | 45 | N/A | 67105 | Durham CDSB | St. Bridget | St. Bridget Catholic Elementary School | ELE | 10561 | 11169 | 11169-B01 | 200 CARNWITH DR W | WHITBY | L1M2J8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9618 | -78.9753 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 464 | - | - | N | - | Not Required | - | 2144352 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931894 | 0 | 1719681 | 0 | 0 | 0 | 0 | 0 | 2651575 | 2651575 | 2144352 | -507223 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1719681
45-024 | 45-024 | 45 | N/A | 67105 | Durham CDSB | St. Catherine of Siena | St. Catherine of Siena Catholic Elementary School | ELE | 8777 | 9672 | 9672-B01 | 15 BENNETT AVE | AJAX | L1T3P1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8739 | -79.0362 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1439163 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439163 | 1439163 | 1439163 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-026 | 45-026 | 45 | N/A | 67105 | Durham CDSB | St. Elizabeth Seton | St. Elizabeth Seton Catholic Elementary School | ELE | 8779 | 9674 | 9674-B01 | 490 STROUDS LANE | PICKERING | L1V6W7 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8267 | -79.1309 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2509255 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509255 | 2509255 | 2509255 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-029 | 45-029 | 45 | N/A | 67105 | Durham CDSB | St. Isaac Jogues | St. Isaac Jogues Catholic Elementary School | ELE | 8784 | 9679 | 9679-B01 | 1166 FINCH AVE | PICKERING | L1V1J6 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8448 | -79.1012 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1328756 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328756 | 1328756 | 1328756 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-030 | 45-030 | 45 | N/A | 67105 | Durham CDSB | St. James | St. James Catholic Elementary School | ELE | 8785 | 9680 | 9680-B01 | 10 CLOVER RIDGE DR W | AJAX | L1S3E5 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8266 | -79.0145 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Not Required | - | 0 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394000 | 394000 | 0 | 0 | 0 | 0 | 2910201 | 0 | 0 | 0 | 0 | 0 | 2910201 | 3304201 | 5056976 | 1752775 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2910201
45-031 | 45-031 | 45 | N/A | 67105 | Durham CDSB | St. John Bosco | St. John Bosco Catholic Elementary School | ELE | 9353 | 10129 | 10129-B01 | 1600 CLEARBROOK DR | OSHAWA | L1K2P6 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9453 | -78.8582 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5900541 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5900541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5900541 | 5900541 | 5900541 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-033 | 45-033 | 45 | N/A | 67105 | Durham CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 8788 | 9682 | 9682-B01 | 25 QUAKER VILLAGE DR | UXBRIDGE | L9P1A1 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.1067 | -79.1387 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1576373 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576373 | 1576373 | 1576373 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-034 | 45-034 | 45 | N/A | 67105 | Durham CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 10726 | 11259 | 11259-B01 | 1200 SUMMERWOOD HTS | OSHAWA | L1K0C2 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9352 | -78.8495 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8484755 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8484755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8484755 | 8484755 | 8484755 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-035 | 45-035 | 45 | N/A | 67105 | Durham CDSB | St. Josephine Bakhita | St. Josephine Bakhita Catholic Elementary School | ELE | 15652 | 18073 | 18073-B01 | 51 WILLIAMSON DR E | AJAX | L1T0B4 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8913 | -79.032 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9063194 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8565415 | 0 | 497779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9063194 | 9063194 | 9063194 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-037 | 45-037 | 45 | N/A | 67105 | Durham CDSB | St. Kateri Tekakwitha | St. Kateri Tekakwitha Catholic Elementary School | ELE | 24273 | 19265 | 19265-B01 | 1425 COLDSTREAM DR | OSHAWA | L1K0B5 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9464 | -78.8401 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 406 | - | - | N | - | Not Required | - | 9099261 | Construction Complete | New Construction | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 377619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778113 | 1155732 | 0 | 0 | 465947 | 0 | 7477582 | 0 | 0 | 0 | 0 | 0 | 7943529 | 9099261 | 9117309 | 18048 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7477582
45-038 | 45-038 | 45 | N/A | 67105 | Durham CDSB | St. Leo | St. Leo Catholic Elementary School | ELE | 9354 | 10130 | 10130-B01 | 120 WATFORD ST | WHITBY | L1M1H2 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9642 | -78.9507 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1814407 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400486 | 400486 | 1413921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1413921 | 1814407 | 1814407 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-040 | 45-040 | 45 | N/A | 67105 | Durham CDSB | St. Luke the Evangelist | St. Luke the Evangelist Catholic Elementary School | ELE | 9906 | 10320 | 10320-B01 | 55 TWIN STREAMS RD | WHITBY | L1P1N9 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9038 | -78.969 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6021431 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6021431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6021431 | 6021431 | 6021431 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-041 | 45-041 | 45 | N/A | 67105 | Durham CDSB | St. Mark the Evangelist | St. Mark the Evangelist Catholic Elementary School | ELE | 8794 | 9688 | 9688-B01 | 95 WALLER ST | WHITBY | L1R1Z7 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9141 | -78.9211 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1070646 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070646 | 1070646 | 1070646 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-042 | 45-042 | 45 | N/A | 67105 | Durham CDSB | St. Mary | St. Mary Catholic Secondary School | SEC | 8795 | 9689 | 9689-B01 | 1918 WHITES RD | PICKERING | L1V1R9 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.835 | -79.1232 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8598984 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8598984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8598984 | 8598984 | 8598984 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-045 | 45-045 | 45 | N/A | 67105 | Durham CDSB | St. Monica | St. Monica Catholic Elementary School | ELE | 8798 | 9692 | 9692-B01 | 275 TWYN RIVERS DR | PICKERING | L1V1E3 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8172 | -79.1378 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2776917 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2776917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2776917 | 2776917 | 2776917 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-050 | 45-050 | 45 | N/A | 67105 | Durham CDSB | St. Wilfrid | St. Wilfrid Catholic Elementary School | ELE | 8803 | 9697 | 9697-B01 | 2360 SOUTHCOTT RD | PICKERING | L1X2S9 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8661 | -79.081 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1938248 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1938248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1938248 | 1938248 | 1938248 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-051 | 45-051 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 24596 | 19602 | 19602-B01 | 2465 BRIDLE RD | OSHAWA | L1L0H9 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9657 | -78.8903 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 412 | 4 | 73 | Y | 1 | Approved | 43369 | 13920628 | Construction Complete | New Construction | Accommodation Pressure | 2020-21 | 44088 | 0 | 0 | 1542635 | 0 | 714500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257135 | 0 | 0 | 1502930 | 0 | 7639713 | 0 | 2016680 | 504170 | 0 | 0 | 11663493 | 13920628 | 13920628 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10160563
45-052 | 45-052 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Josephine Bakhita | St. Josephine Bakhita Catholic Elementary School | ELE | 15652 | 18073 | 18073-B01 | 51 WILLIAMSON DR E | AJAX | L1T0B4 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8913 | -79.032 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 42590 | 2405382 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 650031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650031 | 0 | 0 | 0 | 0 | 0 | 0 | 1482852 | 0 | 0 | 0 | 1482852 | 2132883 | 2405382 | 272499 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1482852
45-053 | 45-053 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Kateri Tekakwitha | St. Kateri Tekakwitha Catholic Elementary School | ELE | 24273 | 19265 | 19265-B01 | 1425 COLDSTREAM DR | OSHAWA | L1K0B5 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9464 | -78.8401 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 3 | 49 | N | - | Approved | 42510 | 1346199 | Construction Complete | Addition | Child Care | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482852 | 0 | 0 | 0 | 1482852 | 1482852 | 1346199 | -136653 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1482852
45-054 | 45-054 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | Sir Albert Love | Sir Albert Love Catholic Elementary School | ELE | 8773 | 9669 | 9669-B01 | 425 WILSON RD N | OSHAWA | L1G6E6 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9128 | -78.8481 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | N | 1 | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252085 | 0 | 0 | 252085 | 252085 | 252085 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 252085
45-055 | 45-055 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Elizabeth Seton | St. Elizabeth Seton Catholic Elementary School | ELE | 8779 | 9674 | 9674-B01 | 490 STROUDS LANE | PICKERING | L1V6W7 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8267 | -79.1309 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252085 | 0 | 0 | 0 | 252085 | 252085 | 252085 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 252085
45-056 | 45-056 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 8788 | 9682 | 9682-B01 | 25 QUAKER VILLAGE DR | UXBRIDGE | L9P1A1 | 35-11-10-603 | Uxbridge | Uxbridge Tp | Durham R | DURHAM | GTA | South | 44.1067 | -79.1387 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257127 | 0 | 0 | 0 | 257127 | 257127 | 257127 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 257127
45-057 | 45-057 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Leo | St. Leo Catholic Elementary School | ELE | 9354 | 10130 | 10130-B01 | 120 WATFORD ST | WHITBY | L1M1H2 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9642 | -78.9507 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2018-19 | 43466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008340 | 0 | 0 | 0 | 1008340 | 1008340 | 1008340 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1008340
45-058 | 45-058 | 45 | N/A | 67105 | Durham CDSB | Monsignor J Pereyma | Monsignor J Pereyma Catholic Secondary School | SEC | 8768 | 9664 | 9664-B01 | 316 CONANT ST | OSHAWA | L1H3S6 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8803 | -78.8434 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42404 | 2092411 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 2092411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092411 | 2092411 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
45-059 | 45-059 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | Monsignor Philip Coffey | Monsignor Philip Coffey Catholic Elementary School | ELE | 8770 | 9666 | 9666-B01 | 1324 OXFORD ST | OSHAWA | L1J3W6 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.8617 | -78.854 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 43879 | 3279037 | Construction Complete | Addition | Child Care | 2021-22 | 44562 | 210378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210378 | 0 | 0 | 0 | 0 | 0 | 0 | 3068660 | 0 | 0 | 0 | 3068660 | 3279038 | 3279038 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3068660
45-060 | 45-060 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Theresa | St. Theresa Catholic Elementary School | ELE | 8801 | 9695 | 9695-B01 | 173 CRAWFORTH ST | WHITBY | L1N3S4 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8867 | -78.9219 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43728 | 504170 | Construction Complete | Retrofit | Child Care | 2020-21 | 44197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504171 | 0 | 0 | 0 | 504171 | 504171 | 504171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 504171
45-061 | 45-061 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | Good Shepherd | Good Shepherd Catholic Elementary School | ELE | 9330 | 10128 | 10128-B01 | 1650 REACH ST | PORT PERRY | L9L1T1 | 35-11-10-602 | Scugog | Scugog Tp | Durham R | DURHAM | GTA | South | 44.1097 | -78.9607 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 44048 | 2386869 | Construction Complete | Addition | Child Care | 2021-22 | 44562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2386869 | 0 | 0 | 0 | 2386869 | 2386869 | 2386869 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2386869
45-062 | 45-062 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Teresa of Calcutta | St. Teresa of Calcutta Catholic Elementary School | ELE | 9903 | 10318 | 10318-B01 | 15 FISHLOCK ST | AJAX | L1Z1H1 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8762 | -79.0302 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 44048 | 2304653 | Construction Complete | Addition | Child Care | 2021-22 | 44562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2304653 | 0 | 0 | 0 | 2304653 | 2304653 | 2304653 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2304653
45-063 | 45-063 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. Marguerite D'Youville | St. Marguerite D'Youville Catholic Elementary School | ELE | 24846 | 19852 | 19852-B01 | 250 MICHAEL BLVD | WHITBY | L1N6B1 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8716 | -78.9523 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 323 | 1 | 24 | Y | 1 | Approved | 43700 | 11512493 | Construction Complete | New Construction | Condition | 2021-22 | 44440 | 0 | 0 | 993771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993771 | 0 | 0 | 0 | 0 | 9479305 | 0 | 535248 | 504171 | 0 | 0 | 10518724 | 11512495 | 11512495 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10518724
45-064 | 45-064 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | St. John Paul II | St. John Paul II Catholic Elementary School | ELE | 18327 | 19068 | 19068-B01 | 160 CACHET BLVD | WHITBY | L1M2L9 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9664 | -78.9432 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | N | 1 | Not Required | - | 0 | Construction Complete | Addition | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252085 | 0 | 0 | 252085 | 252085 | 252085 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 252085
45-065 | 45-065 | 45 | N/A | 67105 | Durham CDSB | Monsignor Paul Dwyer | Monsignor Paul Dwyer Catholic Secondary School | ELE/SEC | 25392-25391 | 20398 | 20398-B01 | GREENHILL AVE / HARMONY RD N | OSHAWA | TBD | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9515 | -78.8548 | 43921 | 2019-20 | 2019-20 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 1061 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Condition | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29405627 | 0 | 0 | 0 | 0 | 0 | 29405627 | 29405627 | 29405627 | 0 | - | No, Site to be acquired. Sign installation planned for January 31, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 29405627
45-066 | 45-066 | 45 | 229 - CMSM Durham | 67105 | Durham CDSB | Seaton 1 | Seaton 1 Catholic Elementary School | ELE | TBD | TBD | TBD | BURKHOLDER DR / HIBISCUS ST | PICKERING | TBD | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8713 | -79.1139 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 622 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14121555 | 0 | 2834561 | 0 | 0 | 0 | 16956116 | 16956116 | 16956116 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 16956116
45-067 | 45-067 | 45 | N/A | 67105 | Durham CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 24596 | 19602 | 19602-B01 | 2465 BRIDLE RD | OSHAWA | L1L0H9 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9608 | -78.8907 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 184 | 8 | - | N | - | Approved | 44985 | 4801755 | Planned | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4801755 | 0 | 0 | 0 | 0 | 0 | 4801755 | 4801755 | 4801755 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4801755
45-068 | 45-065 | 45 | N/A | 67105 | Durham CDSB | Monsignor Paul Dwyer | Monsignor Paul Dwyer Catholic Secondary School | ELE/SEC | 25392-25391 | 20398 | 20398-L01 | GREENHILL AVE / HARMONY RD N | OSHAWA | TBD | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9515 | -78.8548 | 44494 | 2021-22 | 2021-22 | 44494 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44494 | 2393460 | Under Construction | Land Acquisition | Condition | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 2037299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037299 | 0 | 0 | 0 | 356161 | 0 | 0 | 0 | 0 | 0 | 0 | 356161 | 2393460 | 2393460 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 356161
46-001 | 46-001 | 46 | N/A | 67113 | Halton CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18309 | 19064 | 19064-B01 | 802 DRURY LANE | BURLINGTON | L7R2Y2 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3415 | -79.8033 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-002 | 46-002 | 46 | N/A | 67113 | Halton CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18309 | 19064 | 19064-B01 | 802 DRURY LANE | BURLINGTON | L7R2Y2 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3415 | -79.8033 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3688885 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6785912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6785912 | 6785912 |  | -6785912 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-003 | 46-003 | 46 | N/A | 67113 | Halton CDSB | Ascension | Ascension Catholic Elementary School | ELE | 8111 | 9175 | 9175-B01 | 5205 NEW ST | BURLINGTON | L7L1V3 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3732 | -79.7481 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3160703 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3160703 | 3160703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3160703 | 3160703 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-004 | 46-004 | 46 | N/A | 67113 | Halton CDSB | Assumption | Assumption Catholic Secondary School | SEC | 8134 | 9198 | 9198-B01 | 3230 WOODWARD AVE | BURLINGTON | L7N3P1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3484 | -79.7837 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4734987 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445087 | 445087 | 4289900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4289900 | 4734987 | 4734987 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-005 | 46-005 | 46 | N/A | 67113 | Halton CDSB | Christ The King | Christ The King Catholic Secondary School | SEC | 10024 | 10369 | 10369-B01 | 161 GUELPH ST | GEORGETOWN | L7G4A1 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6511 | -79.9094 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 25758453 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25758453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25758453 | 25758453 | 25758453 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-006 | 46-006 | 46 | N/A | 67113 | Halton CDSB | Christ The King | Christ The King Catholic Secondary School | SEC | 10024 | 10369 | 10369-B01 | 161 GUELPH ST | GEORGETOWN | L7G4A1 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6511 | -79.9094 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1886025 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1886025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1886025 | 1886025 | 1886025 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-007 | 46-007 | 46 | N/A | 67113 | Halton CDSB | Corpus Christi | Corpus Christi Catholic Secondary School | SEC | 11033 | 12155 | 12155-B01 | 5150 UPPER MIDDLE RD | BURLINGTON | L7L0E5 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3977 | -79.7844 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 31393428 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5862736 | 5862736 | 25530692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25530692 | 31393428 | 31393428 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-008 | 46-008 | 46 | N/A | 67113 | Halton CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 10595 | 11179 | 11179-B01 | 650 BENNETT BLVD | MILTON | L9T6B1 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5185 | -79.8437 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8134843 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8134843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8134843 | 8134843 | 8134843 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-009 | 46-009 | 46 | N/A | 67113 | Halton CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 10595 | 11179 | 11179-B01 | 650 BENNETT BLVD | MILTON | L9T6B1 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5185 | -79.8437 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2309221 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45038 | 45038 | 0 | 0 | 2264183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264183 | 2309221 | 2309221 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-010 | 46-010 | 46 | N/A | 67113 | Halton CDSB | Holy Rosary | Holy Rosary Catholic Elementary School | ELE | 8115 | 9179 | 9179-B01 | 261 PLAINS RD E | BURLINGTON | L7T2C7 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3134 | -79.845 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2305896 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283556 | 283556 | 2022340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022340 | 2305896 | 2305896 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-011 | 46-011 | 46 | N/A | 67113 | Halton CDSB | Holy Rosary | Holy Rosary Catholic Elementary School | ELE | 8116 | 9180 | 9180-B01 | 141 MARTIN ST | MILTON | L9T2R3 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5175 | -79.8856 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5356378 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106378 | 106378 | 5250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250000 | 5356378 | 5356378 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-012 | 46-012 | 46 | N/A | 67113 | Halton CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18309 | 19064 | 19064-B01 | 802 DRURY LANE | BURLINGTON | L7R2Y2 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3415 | -79.8033 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 933624 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 933624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 933624 | 933624 | 933624 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-013 | 46-013 | 46 | N/A | 67113 | Halton CDSB | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 10025 | 10370 | 10370-B01 | 2420 SIXTH LINE | OAKVILLE | L6H5Z8 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4721 | -79.7242 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 26419175 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26419175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26419175 | 26419175 | 26419175 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-014 | 46-014 | 46 | N/A | 67113 | Halton CDSB | Jean Vanier | Jean Vanier Catholic Secondary School | SEC | 22647 | 19148 | 19148-B01 | 1145 BRONTE ST S | MILTON | L9T8B4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4871 | -79.8572 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 32417507 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 4076134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4076134 | 28341373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28341373 | 32417507 | 32417507 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-015 | 46-015 | 46 | N/A | 67113 | Halton CDSB | Lumen Christi | Lumen Christi Catholic Elementary School | ELE | 15759 | 18077 | 18077-B01 | 841 SAVOLINE BLVD | MILTON | L9T0Z1 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4848 | -79.8727 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10547741 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9217105 | 0 | 1330636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10547741 | 10547741 | 10547741 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-016 | 46-016 | 46 | N/A | 67113 | Halton CDSB | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 9809 | 10279 | 10279-B01 | 1190 WESTVIEW TERR | OAKVILLE | L6M3N2 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.451 | -79.7357 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6874383 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6874383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6874383 | 6874383 | 6874383 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-017 | 46-017 | 46 | N/A | 67113 | Halton CDSB | Notre Dame | Notre Dame Catholic Secondary School | SEC | 8103 | 9168 | 9168-B01 | 2333 HEADON FOREST DR | BURLINGTON | L7M3X6 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3781 | -79.8307 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1039404 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171404 | 171404 | 868000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 868000 | 1039404 | 1039404 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-018 | 46-018 | 46 | N/A | 67113 | Halton CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 11241 | 12183 | 12183-B01 | 709 BOLINGBROKE DR | MILTON | L9T6Z3 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5051 | -79.8488 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9917870 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9917870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9917870 | 9917870 | 9917870 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-019 | 46-019 | 46 | N/A | 67113 | Halton CDSB | Our Lady of Victory | Our Lady of Victory Catholic Elementary School | ELE | 8118 | 9182 | 9182-B01 | 540 COMMERCIAL ST | MILTON | L9T4Z3 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5037 | -79.8671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2265547 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1469830 | 1469830 | 795717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795717 | 2265547 | 2265547 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-020 | 46-020 | 46 | N/A | 67113 | Halton CDSB | Queen of Heaven | Queen of Heaven Catholic Elementary School | ELE | 24301 | 19293 | 19293-B01 | 311 SAVOLINE BLVD | MILTON | L9T7M4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.495 | -79.8881 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 671 | - | - | N | - | Not Required | - | 11730614 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950532 | 0 | 10607507 | 0 | 0 | 0 | 0 | 0 | 11558039 | 11558039 | 11558039 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10607507
46-021 | 46-021 | 46 | N/A | 67113 | Halton CDSB | Sacred Heart of Jesus | Sacred Heart of Jesus Catholic Elementary School | ELE | 9810 | 10280 | 10280-B01 | 2222 COUNTRY CLUB DR | BURLINGTON | L7M4S5 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3873 | -79.8122 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7030955 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7030955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7030955 | 7030955 | 7030955 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-022 | 46-022 | 46 | N/A | 67113 | Halton CDSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 9813 | 10282 | 10282-B01 | 145 MILLBANK DR | OAKVILLE | L6H6G3 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4752 | -79.7195 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7255509 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7255509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7255509 | 7255509 | 7255509 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-023 | 46-023 | 46 | N/A | 67113 | Halton CDSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 9813 | 10282 | 10282-B01 | 145 MILLBANK DR | OAKVILLE | L6H6G3 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4752 | -79.7195 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 691316 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49666 | 49666 | 0 | 0 | 641650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641650 | 691316 | 691316 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-024 | 46-024 | 46 | N/A | 67113 | Halton CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 24219 | 19211 | 19211-B01 | 4675 DOUG WRIGHT DR | BURLINGTON | L7M0N9 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4071 | -79.8246 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 543 | - | - | N | - | Not Required | - | 11622062 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950532 | 0 | 10025468 | 0 | 0 | 0 | 0 | 0 | 10976000 | 10976000 | 10976000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10025468
46-025 | 46-025 | 46 | N/A | 67113 | Halton CDSB | St. Anthony of Padua | St. Anthony of Padua Catholic Elementary School | ELE | 11026 | 12147 | 12147-B01 | 1240 TUPPER DR | MILTON | L9T6T7 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.528 | -79.8526 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9281229 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281229 | 9281229 | 9281229 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-027 | 46-027 | 46 | N/A | 67113 | Halton CDSB | St. Benedict | St. Benedict Catholic Elementary School | ELE | 24302 | 19294 | 19294-B01 | 80 MCLAUGHLIN AVE | MILTON | L9T8N2 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4955 | -79.8663 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 671 | - | - | N | - | Not Required | - | 11268219 | Construction Complete | New Construction | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950532 | 0 | 10769850 | 0 | 0 | 0 | 0 | 0 | 11720382 | 11720382 | 11720382 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10769850
46-028 | 46-028 | 46 | N/A | 67113 | Halton CDSB | St. Brigid | St. Brigid Catholic Elementary School | ELE | 8121 | 9185 | 9185-B01 | 73 MILLER DR | GEORGETOWN | L7G5T2 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6317 | -79.8907 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1262728 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65792 | 65792 | 952036 | 0 | 244900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196936 | 1262728 | 1262728 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-029 | 46-029 | 46 | N/A | 67113 | Halton CDSB | St. Catherine of Alexandria | St. Catherine of Alexandria Catholic Elementary School | ELE | 10023 | 10368 | 10368-B01 | 407 BARBER DR | GEORGETOWN | L7G5H7 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6341 | -79.8741 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7914532 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7914532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7914532 | 7914532 | 7914532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-030 | 46-030 | 46 | N/A | 67113 | Halton CDSB | St. Catherine of Alexandria | St. Catherine of Alexandria Catholic Elementary School | ELE | 10023 | 10368 | 10368-B01 | 407 BARBER DR | GEORGETOWN | L7G5H7 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6341 | -79.8741 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1990641 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37253 | 37253 | 1230683 | 0 | 722705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1953388 | 1990641 | 1990641 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-031 | 46-031 | 46 | N/A | 67113 | Halton CDSB | St. Christopher | St. Christopher Catholic Elementary School | ELE | 11027 | 12148 | 12148-B01 | 2400 SUTTON DR | BURLINGTON | L7L7N2 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.4061 | -79.786 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9544128 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9544128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9544128 | 9544128 | 9544128 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-032 | 46-032 | 46 | N/A | 67113 | Halton CDSB | St. Dominic | St. Dominic Catholic Elementary School | ELE | 8122 | 9186 | 9186-B01 | 2405 REBECCA ST | OAKVILLE | L6L2B1 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4007 | -79.7191 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 730187 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23899 | 23899 | 0 | 0 | 706288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706288 | 730187 | 730187 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-033 | 46-033 | 46 | N/A | 67113 | Halton CDSB | St. Elizabeth Seton | St. Elizabeth Seton Catholic Elementary School | ELE | 10270 | 10473 | 10473-B01 | 5070 DRYDEN AVE | BURLINGTON | L7L6Y3 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3998 | -79.7942 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7137082 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7137082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7137082 | 7137082 | 7137082 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-034 | 46-034 | 46 | N/A | 67113 | Halton CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 8123 | 9187 | 9187-B01 | 120 SINCLAIR AVE | GEORGETOWN | L7G5Z6 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6471 | -79.8951 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3669902 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2235250 | 2235250 | 1434652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1434652 | 3669902 | 3669902 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-035 | 46-035 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | St. Gregory the Great | St. Gregory the Great Catholic Elementary School | ELE | 24490 | 19495 | 19495-B01 | 138 SIXTEEN MILE DR | OAKVILLE | L6M0T7 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4769 | -79.7358 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 671 | 5 | 88 | N | - | Approved | 44684 | 14990744 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260424 | 0 | 11423525 | 0 | 2306795 | 0 | 0 | 0 | 14990744 | 14990744 | 14990744 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13730320
46-036 | 46-036 | 46 | N/A | 67113 | Halton CDSB | St. Ignatius of Loyola SS | St. Ignatius of Loyola SS Catholic Secondary School | SEC | 8136 | 9200 | 9200-B01 | 1550 NOTTINGHILL GATE | OAKVILLE | L6M1X7 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4447 | -79.7336 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40449 | 22921188 | Construction Complete | Addition | Other | 2013-14 | 41518 | 4425227 | 0 | 0 | 8015948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5529464 | 17970639 | 4863086 | 87463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950549 | 22921188 | 22921188 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-037 | 46-037 | 46 | N/A | 67113 | Halton CDSB | St. Joan of Arc | St. Joan of Arc Catholic Elementary School | ELE | 10271 | 10474 | 10474-B01 | 2912 WESTOAK TRAILS BLVD | OAKVILLE | L6M4T7 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4312 | -79.759 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7704963 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7704963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7704963 | 7704963 | 7704963 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-038 | 46-038 | 46 | N/A | 67113 | Halton CDSB | St. John | St. John Catholic Elementary School | ELE | 8127 | 9191 | 9191-B01 | 1480 MANSFIELD DR | OAKVILLE | L6H1K4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4588 | -79.7159 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 285471 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285471 | 285471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285471 | 285471 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-039 | 46-039 | 46 | N/A | 67113 | Halton CDSB | St. John Paul II | St. John Paul II Catholic Elementary School | ELE | 10828 | 12007 | 12007-B01 | 2130 KINGSRIDGE DR | OAKVILLE | L6M4Z2 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4424 | -79.7582 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8600943 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8600943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8600943 | 8600943 | 8600943 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-040 | 46-040 | 46 | N/A | 67113 | Halton CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 8128 | 9192 | 9192-B01 | 147 MILL ST W | ACTON | L7J1G7 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6243 | -80.045 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2211231 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291801 | 291801 | 1919430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919430 | 2211231 | 2211231 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-041 | 46-041 | 46 | N/A | 67113 | Halton CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 8128 | 9192 | 9192-B01 | 147 MILL ST W | ACTON | L7J1G7 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6243 | -80.045 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 961890 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239682 | 239682 | 0 | 0 | 722208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722208 | 961890 | 961890 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-042 | 46-042 | 46 | N/A | 67113 | Halton CDSB | St. Mark | St. Mark Catholic Elementary School | ELE | 8097 | 9162 | 9162-B01 | 2145 UPPER MIDDLE RD | BURLINGTON | L7P4G1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3594 | -79.8423 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 402630 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402630 | 402630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402630 | 402630 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-043 | 46-043 | 46 | N/A | 67113 | Halton CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 22568 | 19147 | 19147-B01 | 2175 COLONEL WILLIAM PKY | OAKVILLE | L6M0B7 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4235 | -79.7713 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 658 | - | - | N | - | Approved | 44657 | 10466766 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950532 | 0 | 9456234 | 0 | 0 | 0 | 0 | 0 | 10406766 | 10406766 | 10406766 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9456234
46-044 | 46-044 | 46 | N/A | 67113 | Halton CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 8100 | 9165 | 9165-B01 | 200 KENWOOD AVE | BURLINGTON | L7L4L8 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3696 | -79.7374 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3716647 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2136265 | 2136265 | 1580382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1580382 | 3716647 | 3716647 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-045 | 46-045 | 46 | N/A | 67113 | Halton CDSB | St. Paul | St. Paul Catholic Elementary School | ELE | 8101 | 9166 | 9166-B01 | 530 CUMBERLAND AVE | BURLINGTON | L7N2X2 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3474 | -79.7808 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1573776 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174946 | 1174946 | 398830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398830 | 1573776 | 1573776 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-046 | 46-046 | 46 | N/A | 67113 | Halton CDSB | St. Peter | St. Peter Catholic Elementary School | ELE | 11242 | 12182 | 12182-B01 | 137 DIXON DR | MILTON | L9T5P7 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5338 | -79.8643 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10545495 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 4375827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4375827 | 6169668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6169668 | 10545495 | 10545495 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-047 | 46-047 | 46 | N/A | 67113 | Halton CDSB | St. Raphael | St. Raphael Catholic Elementary School | ELE | 8130 | 9194 | 9194-B01 | 4056 NEW ST | BURLINGTON | L7L1S9 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3542 | -79.7672 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1919238 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1421780 | 1421780 | 497458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497458 | 1919238 | 1919238 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-048 | 46-048 | 46 | N/A | 67113 | Halton CDSB | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 24259 | 9169 | 9169-B02 | 124 DORVAL DR | OAKVILLE | L6K2W1 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4361 | -79.6803 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 37602806 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 4902111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1177660 | 6079771 | 31523035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31523035 | 37602806 | 37602806 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-049 | 46-049 | 46 | N/A | 67113 | Halton CDSB | St. Vincent | St. Vincent Catholic Elementary School | ELE | 8132 | 9196 | 9196-B01 | 1280 BRAESIDE DR | OAKVILLE | L6J2A4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4659 | -79.6565 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1159421 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517431 | 517431 | 641990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641990 | 1159421 | 1159421 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-050 | 46-050 | 46 | N/A | 67113 | Halton CDSB | St. Scholastica | St. Scholastica Catholic Elementary School | ELE | 24575 | 19581 | 19581-B01 | 170 WHITLOCK AVE | MILTON | L9E1K6 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.4836 | -79.8543 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 671 | - | - | N | - | Approved | 42975 | 13668474 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542760 | 0 | 12125714 | 0 | 0 | 0 | 0 | 0 | 13668474 | 13668474 | 13668474 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12125714
46-051 | 46-051 | 46 | N/A | 67113 | Halton CDSB | Holy Rosary | Holy Rosary Catholic Elementary School | ELE | 8116 | 9180 | 9180-B01 | 141 MARTIN ST | MILTON | L9T2R3 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5175 | -79.8856 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 130 | - | - | N | - | Approved | 44657 | 3458678 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3275000 | 0 | 1385409 | 0 | 0 | 0 | 0 | 0 | 4660409 | 4660409 | 4660409 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1385409
46-052-01 | 46-052 | 46 | N/A | 67113 | Halton CDSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 24693 | 9193 | 9193-B02 | 477 WARMINSTER DR | OAKVILLE | L6L4N4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4228 | -79.7032 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 527 | - | - | N | - | Approved | 43445 | 12111775 | Construction Complete | New Construction | Consolidation | 2019-20 | 43861 | 0 | 0 | 4523847 | 0 | 115330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4639177 | 0 | 0 | 0 | 0 | 7472598 | 0 | 0 | 0 | 0 | 0 | 7472598 | 12111775 | 12111775 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7472598
46-052-03 | 46-052 | 46 | N/A | 67113 | Halton CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 8129 | 9193 | 9193-B01 | 477 WARMINSTER DR | OAKVILLE | L6L4N4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4227 | -79.7038 | 43206 | 2017-18 | 2018-19 | - | - | - | 43206 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43206 | 413160 | Construction Complete | Demolition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413160 | 0 | 0 | 0 | 0 | 0 | 413160 | 413160 | 413160 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 413160
46-053 | 46-053 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | St. Mark | St. Mark Catholic Elementary School | ELE | 8097 | 9162 | 9162-B01 | 2145 UPPER MIDDLE RD | BURLINGTON | L7P4G1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3594 | -79.8423 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | 42951 | 2016-17 | 2017-18 | - | - | - | 124 | 3 | 49 | Y | 1 | Approved | 43258 | 3667880 | Construction Complete | Addition | Consolidation | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610867 | 0 | 1542760 | 514253 | 0 | 0 | 3667880 | 3667880 | 3667880 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3667880
46-054 | 46-054 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | St. Peter | St. Peter Catholic Elementary School | ELE | 11242 | 12182 | 12182-B01 | 137 DIXON DR | MILTON | L9T5P7 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5338 | -79.8643 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 44039 | 3067683 | Construction Complete | Addition | Child Care | 2020-21 | 44287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3067683 | 0 | 0 | 0 | 3067683 | 3067683 | 3067683 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 3067683
46-055 | 46-055 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | Bishop PF Reding | Bishop PF Reding Catholic Secondary School | SEC | 8135 | 9199 | 9199-B01 | 1120 MAIN ST E | MILTON | L9T6H7 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5309 | -79.8627 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 609 | 4 | 64 | Y | - | Approved | 43509 | 20130036 | Construction Complete | Addition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18073020 | 0 | 2057016 | 0 | 0 | 0 | 20130036 | 20130036 | 20130036 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 20130036
46-056 | 46-056 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 8099 | 9164 | 9164-B01 | 165 SEWELL DR | OAKVILLE | L6H1E3 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4632 | -79.6954 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 23 | 3 | 49 | Y | - | Approved | 43727 | 3122284 | Construction Complete | Addition | Consolidation | 2020-21 | 44197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579522 | 0 | 1542762 | 0 | 0 | 0 | 3122284 | 3122284 | 3122284 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 3122284
46-058 | 46-058 | 46 | N/A | 67113 | Halton CDSB | Assumption | Assumption Catholic Secondary School | SEC | 8134 | 9198 | 9198-B01 | 3230 WOODWARD AVE | BURLINGTON | L7N3P1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3484 | -79.7837 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 84 | - | - | N | - | Approved | 43433 | 2358102 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43889 | 0 | 0 | 2358102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2358102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2358102 | 2358102 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
46-059 | 46-059 | 46 | N/A | 67113 | Halton CDSB | St. Kateri Tekakwitha | St. Kateri Tekakwitha Catholic Secondary School | SEC | 25393 | 20399 | 20399-B01 | LOUIS ST. LAURENT AVE / KENNEDY CIR | MILTON | TBD | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 1611 | - | - | - | - | Approved | 44881 | 67076692 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 1400000 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 63576692 | 0 | 0 | 0 | 0 | 0 | 63576692 | 67076692 | 67076692 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 63576692
46-060 | 46-060 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | Milton 10 | Milton 10 Catholic Elementary School | ELE | 25394 | 20400 | 20400-B01 | WHITLOCK AVE / KENNEDY CIRCLE W | MILTON | TBD | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 671 | 5 | 88 | - | - | Approved | 44186 | 18727105 | Construction Complete | New Construction | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 14499502 | 0 | 2727603 | 0 | 0 | 0 | 17227105 | 18727105 | 18727105 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 17227105
46-061 | 46-061 | 46 | N/A | 67113 | Halton CDSB | North Oakville 4 | North Oakville 4 Catholic Elementary School | ELE | 25515 | 20521 | 20521-B01 | THRESHING MILL BLVD / POSTRIDGE DR | OAKVILLE | TBD | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | TBD | TBD | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 671 | - | - | N | - | Approved | 44911 | 24400157 | Under Construction | New Construction | Accommodation Pressure | 2022-23 | 44927 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 23400157 | 0 | 0 | 0 | 0 | 0 | 23400157 | 24400157 | 19587903 | -4812254 | - | No, Site to be acquired. Sign installation planned for December 1, 2021 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 23400157
46-063 | 46-063 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | Milton 9 | Milton 9 Catholic Elementary School | ELE | TBD | TBD | TBD | GORDON KRANTZ AVE / KOVACHIK BLVD | MILTON | TBD | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | TBD | TBD | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 671 | 5 | 88 | N | - | Approved | 44684 | 22715819 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 20204694 | 0 | 3737014 | 0 | 0 | 0 | 23941708 | 24841708 | 24841708 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23941708
46-064 | 46-064 | 46 | 230 - CMSM Halton | 67113 | Halton CDSB | Milton 11 | Milton 11 Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | MILTON | L9T7V8 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 763 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19977585 | 0 | 3324941 | 0 | 0 | 0 | 23302526 | 23302526 | 23302526 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 23302526
47-001 | 47-001 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 24246 | 19238 | 19238-B01 | 90 MULBERRY ST | HAMILTON | L8R2C8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2632 | -79.8705 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-002 | 47-002 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 24246 | 19238 | 19238-B01 | 90 MULBERRY ST | HAMILTON | L8R2C8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2632 | -79.8705 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12584511 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12146838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12146838 | 12146838 | 12584511 | 437673 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-003 | 47-003 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24246 | 19238 | 19238-B01 | 90 MULBERRY ST | HAMILTON | L8R2C8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2632 | -79.8705 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2537729 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2537729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2537729 | 2537729 | 2537729 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-004 | 47-004 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Annunciation of Our Lord | Annunciation of Our Lord Catholic Elementary School | ELE | 11662 | 7705 | 7705-B02 | 250 LIMERIDGE RD W | HAMILTON | L9C2V2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2237 | -79.896 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12879960 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2444199 | 2444199 | 9584512 | 0 | 851249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10435761 | 12879960 | 12879960 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-005 | 47-005 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Bishop Ryan | Bishop Ryan Catholic Secondary School | SEC | 11835 | 12326 | 12326-B01 | 1824 RYMAL RD | HANNON | L0R1P0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1816 | -79.8164 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 40273473 | Construction Complete | New Construction | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 7579345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7579345 | 32694128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32694128 | 40273473 | 40273473 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-006 | 47-006 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Bishop Tonnos | Bishop Tonnos Catholic Secondary School | SEC | 10651 | 11261 | 11261-B01 | 100 PANABAKER DR | ANCASTER | L9G5E3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2017 | -79.9952 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 26566907 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26566907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26566907 | 26566907 | 26566907 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-009 | 47-009 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Canadian Martyrs | Canadian Martyrs Catholic Elementary School | ELE | 3094 | 7034 | 7034-B01 | 1355 MAIN ST W | HAMILTON | L8S4M7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2574 | -79.9208 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2147732 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147732 | 2147732 | 2147732 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-010 | 47-010 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Cardinal Newman | Cardinal Newman Catholic Secondary School | SEC | 9411 | 5167 | 5167-B01 | 127 GRAY RD | STONEY CREEK | L8G3V3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2216 | -79.7455 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 400000 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 400000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-011 | 47-011 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Cardinal Newman | Cardinal Newman Catholic Secondary School | SEC | 9411 | 5167 | 5167-B01 | 127 GRAY RD | STONEY CREEK | L8G3V3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2216 | -79.7455 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 105 | - | - | N | - | Not Required | - | 925412 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 937199 | 0 | 0 | 0 | 0 | 0 | 937199 | 937199 | 925412 | -11787 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 937199
47-013 | 47-013 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 10115 | 10400 | 10400-B01 | 705 CENTRE RD RR 2 | HAMILTON | L8N2Z7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.3438 | -79.9143 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5969138 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5969138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5969138 | 5969138 | 5969138 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-015 | 47-015 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Holy Name of Jesus | Holy Name of Jesus Catholic Elementary School | ELE | 18488 | 8726 | 8726-B01 | 181 BELMONT AVE | HAMILTON | L8L7M5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2501 | -79.8222 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10609876 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 842192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2845995 | 3688187 | 6496065 | 0 | 425624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6921689 | 10609876 | 10609876 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-016 | 47-016 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Immaculate Conception | Immaculate Conception Catholic Elementary School | ELE | 11663 | 12254 | 12254-B01 | 470 KITTY MURRAY LANE | ANCASTER | L9K0C3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2095 | -79.9541 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11597242 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10745993 | 0 | 851249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11597242 | 11597242 | 11597242 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-017 | 47-017 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Immaculate Heart of Mary | Immaculate Heart of Mary Catholic Elementary School | ELE | 11073 | 12161 | 12161-B01 | 190 GLOVER RD | STONEY CREEK | L8E5J2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2086 | -79.6822 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8720754 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220754 | 220754 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500000 | 8720754 | 8720754 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-018 | 47-018 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 3541 | 7330 | 7330-B01 | 420 MOHAWK RD E | HAMILTON | L8V2H7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2225 | -79.8578 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1103844 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1103844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1103844 | 1103844 | 1103844 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-022 | 47-022 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Our Lady of the Assumption | Our Lady of the Assumption Catholic Elementary School | ELE | 24583 | 19589 | 19589-B01 | 103 FLETCHER RD | HANNON | L0R1P0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1775 | -79.8065 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 509 | - | - | N | - | Approved | 42499 | 12244823 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 43220 | 0 | 0 | 0 | 0 | 634205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634205 | 0 | 0 | 1260424 | 0 | 10591319 | 0 | 0 | 0 | 0 | 0 | 11851743 | 12485948 | 12485948 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10591319
47-024 | 47-024 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3635 | 7407 | 7407-B01 | 5 HAMILTON AVE | HAMILTON | L8V2S3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2411 | -79.8495 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2618144 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618144 | 2618144 | 2618144 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-028 | 47-028 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Ann | St. Ann Catholic Elementary School | ELE | 24251 | 7484 | 7484-B02 | 15 ST ANN ST | HAMILTON | L8L0B8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2553 | -79.8358 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 450 | - | - | N | - | Not Required | - | 11198695 | Construction Complete | New Construction | Condition | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475266 | 0 | 10723429 | 0 | 0 | 0 | 0 | 0 | 11198695 | 11198695 | 11198695 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10723429
47-032 | 47-032 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. David | St. David Catholic Elementary School | ELE | 3888 | 7596 | 7596-B01 | 95 OWEN PL | HAMILTON | L8G2H3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2242 | -79.7715 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2621471 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2621471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2621471 | 2621471 | 2621471 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-035 | 47-035 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Gabriel | St. Gabriel Catholic Elementary School | ELE | 23630 | 19152 | 19152-B01 | 1361 BARTON ST | STONEY CREEK | L8E5L1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2113 | -79.6431 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 504 | - | - | N | - | Not Required | - | 10730082 | Construction Complete | New Construction | Condition | 2015-16 | 42248 | 0 | 0 | 947366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947366 | 0 | 0 | 950532 | 0 | 8832184 | 0 | 0 | 0 | 0 | 0 | 9782716 | 10730082 | 10730082 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8832184
47-036 | 47-036 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Jean de Brébeuf | St. Jean de Brébeuf Catholic Secondary School | SEC | 4030 | 7702 | 7702-B01 | 200 ACADIA DR | HAMILTON | L8W1B8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2016 | -79.864 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3280156 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280156 | 3280156 | 3280156 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-037 | 47-037 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Jean de Brébeuf | St. Jean de Brébeuf Catholic Secondary School | SEC | 4030 | 7702 | 7702-B01 | 200 ACADIA DR | HAMILTON | L8W1B8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2016 | -79.864 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 105 | - | - | N | - | Approved | 42499 | 4037166 | Construction Complete | Addition | Condition | 2017-18 | 42979 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 2837166 | 0 | 0 | 0 | 0 | 0 | 2837166 | 4037166 | 4037166 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2837166
47-039 | 47-039 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. John Paul II | St. John Paul II Catholic Elementary School | ELE | 10472 | 11119 | 11119-B01 | 600 ACADIA DR | HAMILTON | L8W3A8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2027 | -79.8685 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6572505 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6572505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6572505 | 6572505 | 6572505 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-040 | 47-040 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. John the Baptist | St. John the Baptist Catholic Elementary School | ELE | 4069 | 7736 | 7736-B01 | 115 LONDON ST S | HAMILTON | L8K2G6 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2387 | -79.8198 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2168286 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168286 | 2168286 | 2168286 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-043 | 47-043 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Lawrence | St. Lawrence Catholic Elementary School | ELE | 4162 | 7799 | 7799-B01 | 88 MACAULAY ST E | HAMILTON | L8L3X3 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2695 | -79.8594 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7039796 | Construction Complete | Addition | Other | 2010-11 | 40422 | 103486 | 0 | 0 | 3433626 | 0 | 1942598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5479710 | 0 | 1347274 | 212812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560086 | 7039796 | 7039796 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-047 | 47-047 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Mark | St. Mark Catholic Elementary School | ELE | 10116 | 10401 | 10401-B01 | 43 WHITEDEER RD | STONEY CREEK | L8J2V8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1782 | -79.7861 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6485205 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229727 | 229727 | 6255478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255478 | 6485205 | 6485205 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-048 | 47-048 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Mark | St. Mark Catholic Elementary School | ELE | 10116 | 10401 | 10401-B01 | 43 WHITEDEER RD | STONEY CREEK | L8J2V8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1782 | -79.7861 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 692774 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692774 | 692774 | 692774 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-051 | 47-051 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Mathew | St. Mathew Catholic Elementary School | ELE | 11255 | 12189 | 12189-B01 | 200 WINDWOOD DR | BINBROOK | L0R1C0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1172 | -79.814 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13941286 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13090037 | 0 | 851249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13941286 | 13941286 | 13941286 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-054 | 47-054 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Therese of Lisieux | St. Therese of Lisieux Catholic Elementary School | ELE | 10652 | 11260 | 11260-B01 | 1760 GARTH ST | HAMILTON | L9B2X5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2059 | -79.916 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7551232 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7551232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7551232 | 7551232 | 7551232 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-055 | 47-055 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Therese of Lisieux | St. Therese of Lisieux Catholic Elementary School | ELE | 10652 | 11260 | 11260-B01 | 1760 GARTH ST | HAMILTON | L9B2X5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2059 | -79.916 | 41761 | 2013-14 | 2014-15 | - | - | - | 41761 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Not Required | - | 3952963 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1256430 | 0 | 2444470 | 0 | 0 | 0 | 0 | 0 | 3700900 | 3700900 | 3700900 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2444470
47-056 | 47-056 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Thomas More | St. Thomas More Catholic Secondary School | SEC | 4506 | 8032 | 8032-B01 | 1045 UPPER PARADISE RD | HAMILTON | L9B2N4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2137 | -79.9199 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 315 | - | - | N | - | Not Required | - | 6583353 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6583353 | 0 | 0 | 0 | 0 | 0 | 6583353 | 6583353 | 6583353 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6583353
47-057 | 47-057 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Thomas the Apostle | St. Thomas the Apostle Catholic Elementary School | ELE | 23945 | 19155 | 19155-B01 | 170 SKINNER RD | WATERDOWN | L0R2H7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.3391 | -79.877 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13171325 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13171325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13171325 | 13171325 | 13171325 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
47-059 | 47-059 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | Binbrook | Binbrook Catholic Elementary School | ELE | 24584 | 19590 | 19590-B01 | 400 PUMPKIN PASS | BINBROOK | L0R1C0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1303 | -79.8264 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 458 | 3 | 49 | Y | - | Approved | 43603 | 12759018 | Construction Complete | New Construction | Accommodation Pressure | 2020-21 | 44264 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 1028507 | 0 | 9687751 | 0 | 1542761 | 0 | 0 | 0 | 12259019 | 12759019 | 12759019 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11230512
47-060 | 47-060 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | St. Gabriel | St. Gabriel Catholic Elementary School | ELE | 23630 | 19152 | 19152-B01 | 1361 BARTON ST | STONEY CREEK | L8E5L1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2113 | -79.6431 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | 4 | 73 | N | - | Approved | 42899 | 2670102 | Construction Complete | Addition | Child Care | 2018-19 | 43347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2670102 | 0 | 0 | 0 | 2670102 | 2670102 | 2670102 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2670102
47-061 | 47-061 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | St. Augustine | St. Augustine Catholic Elementary School | ELE | 3778 | 7513 | 7513-B01 | 25 ALMA ST | DUNDAS | L9H2C9 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2709 | -79.9557 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 63 | Y | - | Approved | 43902 | 1285635 | Construction Complete | Retrofit | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285635 | 0 | 0 | 0 | 1285635 | 1285635 | 1285635 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1285635
47-062 | 47-062 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | St. Kateri Tekakwitha | St. Kateri Tekakwitha Catholic Elementary School | ELE | 4593 | 8096 | 8096-B01 | 22 QUEENSBURY DR | HAMILTON | L8W1Z6 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2016 | -79.8409 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 0 | -1542762 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1542762
47-063 | 47-063 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | Holy Name of Mary | Holy Name of Mary Catholic Elementary School | ELE | 9410 | 10161 | 10161-B01 | 161 MEADOWLANDS BLVD | ANCASTER | L9K1H8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2203 | -79.9453 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1542762 | 0 | -1542762 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1542762
47-064 | 47-064 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | St. Thomas the Apostle | St. Thomas the Apostle Catholic Elementary School | ELE | 23945 | 19155 | 19155-B01 | 170 SKINNER RD | WATERDOWN | L0R2H7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.3391 | -79.877 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44658 | 3098948 | Under Construction | Addition | Child Care | 2022-23 | 44986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3098948 | 0 | 0 | 0 | 3098948 | 3098948 | 3098948 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 3098948
47-065 | 47-065 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 24849 | 7932 | 7932-B02 | 20 EAST AVE S | HAMILTON | L8N3X1 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2524 | -79.8558 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 383 | 3 | 49 | Y | 2 | Approved | 44137 | 16241486 | Under Construction | New Construction | Consolidation | 2022-23 | 44805 | 0 | 0 | 1124397 | 434068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1558465 | 0 | 0 | 0 | 0 | 11767507 | 0 | 1887006 | 1028508 | 0 | 0 | 14683021 | 16241486 | 16241486 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14683021
47-066 | 47-066 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4310 | 7900 | 7900-B01 | 135 HESTER ST | HAMILTON | L9A2N9 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2243 | -79.8748 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
47-067 | 47-067 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | St. James the Apostle | St. James the Apostle Catholic Elementary School | ELE | 25396 | 7693 | 7693-B02 | 29 JOHN MURRAY ST | HAMILTON | L8J1C5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1916 | -79.7836 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 590 | 3 | 49 | - | - | Approved | 44474 | 17287079 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 589552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 589552 | 0 | 0 | 0 | 0 | 13604198 | 0 | 1888086 | 0 | 0 | 0 | 15492284 | 16081836 | 16081836 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15492284
47-068 | 47-068 | 47 | 203 - CMSM Hamilton | 67121 | Hamilton-Wentworth CDSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 10115 | 10400 | 10400-B01 | 705 CENTRE RD | HAMILTON | L8N2Z7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.344 | -79.9144 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 118 | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716356 | 0 | 1734752 | 0 | 0 | 0 | 4451108 | 4451108 | 4451108 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4451108
47-069 | 47-067 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. James the Apostle | St. James the Apostle Catholic Elementary School | ELE | 25396 | 7693 | 7693-L02 | 29 JOHN MURRAY ST | HAMILTON | L8J1C5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1916 | -79.7836 | 44474 | 2021-22 | 2021-22 | 44474 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44474 | 602989 | Planned | Land Acquisition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 541203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541203 | 0 | 0 | 0 | 602989 | 0 | 0 | 0 | 0 | 0 | 0 | 602989 | 1144192 | 1144192 | 0 | - | Yes | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 602989
47-070 | 47-067 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | St. James the Apostle | St. James the Apostle Catholic Elementary School | ELE | 25396 | 7693 | 7693-B01 | 29 JOHN MURRAY ST | HAMILTON | L8J1C5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1916 | -79.7836 | 44474 | 2021-22 | 2021-22 | - | - | - | 44474 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44474 | 664040 | Planned | Demolition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664040 | 0 | 0 | 0 | 0 | 0 | 664040 | 664040 | 664040 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 664040
47-071 | 47-071 | 47 | N/A | 67121 | Hamilton-Wentworth CDSB | Bishop Ryan | Bishop Ryan Catholic Secondary School | SEC | 11835 | 12326 | 12326-B01 | 1824 RYMAL RD | HANNON | L0R1P0 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1816 | -79.8164 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 253 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8449198 | 0 | 0 | 0 | 0 | 0 | 8449198 | 8449198 | 8449198 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8449198
48-001 | 48-001 | 48 | N/A | 67130 | Wellington CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16162 | 18109 | 18109-B02 | 75 WOOLWICH ST | GUELPH | N1H3V1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5476 | -80.2475 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509756 | 0 | 0 | 0 | 0 | 0 | 509756 | 509756 | 0 | -509756 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 509756
48-002 | 48-002 | 48 | N/A | 67130 | Wellington CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16162 | 18109 | 18109-B02 | 75 WOOLWICH ST | GUELPH | N1H3V1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5476 | -80.2475 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2409115 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2455937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2455937 | 2455937 | 2409115 | -46822 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-003 | 48-003 | 48 | N/A | 67130 | Wellington CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 16162 | 18109 | 18109-B02 | 75 WOOLWICH ST | GUELPH | N1H3V1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5476 | -80.2475 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 439722 | Construction Complete | Other | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439722 | 439722 | 439722 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-004 | 48-004 | 48 | N/A | 67130 | Wellington CDSB | Bishop Macdonell | Bishop Macdonell Catholic Secondary School | SEC | 10176 | 10448 | 10448-B01 | 200 CLAIR RD W | GUELPH | N1L1G1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.495 | -80.196 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 20467265 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 618326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618326 | 19848939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19848939 | 20467265 | 20467265 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-005 | 48-005 | 48 | N/A | 67130 | Wellington CDSB | Holy Trinity | Holy Trinity Catholic Elementary School | ELE | 10291 | 10487 | 10487-B01 | 487 GRANGE RD | GUELPH | N1E7C4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5698 | -80.2221 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5323834 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 160836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160836 | 5162998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5162998 | 5323834 | 5323834 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-006 | 48-006 | 48 | N/A | 67130 | Wellington CDSB | Holy Trinity | Holy Trinity Catholic Elementary School | ELE | 10291 | 10487 | 10487-B01 | 487 GRANGE RD | GUELPH | N1E7C4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5698 | -80.2221 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1680351 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680351 | 1680351 | 1680351 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-008 | 48-008 | 48 | N/A | 67130 | Wellington CDSB | Mary Phelan | Mary Phelan Catholic Elementary School | ELE | 3407 | 7239 | 7239-B01 | 8 BISHOP CRT | GUELPH | N1G2R9 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5126 | -80.2465 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2363561 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 71404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71404 | 2292157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2292157 | 2363561 | 2363561 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-009 | 48-009 | 48 | N/A | 67130 | Wellington CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Secondary School | SEC | 3540 | 5087 | 5087-B01 | 54 WESTMOUNT RD | GUELPH | N1H5H7 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5479 | -80.2678 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9897350 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 299004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299004 | 9598346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9598346 | 9897350 | 9897350 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-010 | 48-010 | 48 | N/A | 67130 | Wellington CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3634 | 7406 | 7406-B01 | 125 HURON ST | GUELPH | N1E5L5 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5474 | -80.2358 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2112599 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 63823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63823 | 2048776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2048776 | 2112599 | 2112599 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-011 | 48-011 | 48 | N/A | 67130 | Wellington CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 24405 | 19406 | 19406-B01 | 5146 7 HWY RR 4 | ROCKWOOD | N0B2K0 | 35-15-75-615 | Guelph-Eramosa | Guelph/Eramosa Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6241 | -80.1517 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 268 | - | - | N | - | Approved | 41934 | 6221591 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239382 | 0 | 470607 | 0 | 5511602 | 0 | 0 | 0 | 0 | 0 | 6221591 | 6221591 | 6221591 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5511602
48-012 | 48-012 | 48 | N/A | 67130 | Wellington CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 10177 | 10449 | 10449-B01 | 287 IMPERIAL RD S | GUELPH | N1K1Z4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5255 | -80.2826 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6319900 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 190927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190927 | 6128973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6128973 | 6319900 | 6319900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-013 | 48-013 | 48 | N/A | 67130 | Wellington CDSB | St. Ignatius of Loyola | St. Ignatius of Loyola Catholic Elementary School | ELE | 12017 | 12227 | 12227-B01 | 251 COLONIAL DR | GUELPH | N1L0G4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5167 | -80.1809 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8936235 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8936235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8936235 | 8936235 | 8936235 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-014 | 48-014 | 48 | N/A | 67130 | Wellington CDSB | St. James | St. James Catholic Secondary School | SEC | 4014 | 7689 | 7689-B02 | 57 VICTORIA RD N | GUELPH | N1E5G9 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5597 | -80.2336 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5385192 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 162689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162689 | 5222503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5222503 | 5385192 | 5385192 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-015 | 48-015 | 48 | N/A | 67130 | Wellington CDSB | St. John | St. John Catholic Elementary School | ELE | 4042 | 7689 | 7689-B01 | 63 VICTORIA RD N | GUELPH | N1E5G9 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.56 | -80.234 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2933248 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 88615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88615 | 2844633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2844633 | 2933248 | 2933248 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-017 | 48-017 | 48 | N/A | 67130 | Wellington CDSB | St. John Brebeuf | St. John Brebeuf Catholic Elementary School | ELE | 4059 | 7728 | 7728-B01 | 30 MILLWOOD RD SS 1 | ERIN | N0B1T0 | 35-15-75-405 | Erin | Erin T | Wellington Co | WELLINGTON | Southwest | South | 43.7709 | -80.0592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1746406 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 52771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52771 | 1693635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693635 | 1746406 | 1746406 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-019 | 48-019 | 48 | N/A | 67130 | Wellington CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 13242 | 7754 | 7754-B01 | 10 GUELPH ST | GUELPH | N1H5Y8 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5383 | -80.2674 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6094669 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6094669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6094669 | 6094669 | 6094669 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-020 | 48-020 | 48 | N/A | 67130 | Wellington CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 4241 | 7852 | 7852-B01 | 390 PARKSIDE DR | MOUNT FOREST | N0G2L3 | 35-15-75-617 | Wellington North | Wellington North Tp | Wellington Co | WELLINGTON | Southwest | South | 43.9786 | -80.7291 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2781004 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 84005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84005 | 2696999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2696999 | 2781004 | 2781004 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-021 | 48-021 | 48 | N/A | 67130 | Wellington CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 4242 | 7853 | 7853-B01 | 251 IRVINE ST | ELORA | N0B1S0 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6898 | -80.4274 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2004968 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 60571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60571 | 1944397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1944397 | 2004968 | 2004968 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-022 | 48-022 | 48 | N/A | 67130 | Wellington CDSB | St. Mary | St. Mary Catholic Elementary School | ELE | 4242 | 7853 | 7853-B01 | 251 IRVINE ST | ELORA | N0B1S0 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6898 | -80.4274 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1113534 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113534 | 1113534 | 1113534 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-023 | 48-023 | 48 | N/A | 67130 | Wellington CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4308 | 7898 | 7898-B01 | 9 MCELDERRY RD | GUELPH | N1G4W7 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5193 | -80.2229 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2375259 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 71758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71758 | 2303501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2303501 | 2375259 | 2375259 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-024 | 48-024 | 48 | N/A | 67130 | Wellington CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 4308 | 7898 | 7898-B01 | 9 MCELDERRY RD | GUELPH | N1G4W7 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5193 | -80.2229 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 300000 | Construction Complete | Retrofit | Other | 2011-12 | 40787 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-026 | 48-026 | 48 | N/A | 67130 | Wellington CDSB | St. Paul | St. Paul Catholic Elementary School | ELE | 10567 | 11172 | 11172-B01 | 182 CLAIRFIELDS DR E | GUELPH | N1L1N4 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5092 | -80.187 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6858521 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 207199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207199 | 6651322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6651322 | 6858521 | 6858521 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-027 | 48-027 | 48 | N/A | 67130 | Wellington CDSB | St. Peter | St. Peter Catholic Elementary School | ELE | 4599 | 8100 | 8100-B01 | 150 WESTWOOD RD | GUELPH | N1H7G1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5324 | -80.2834 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5236972 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 158212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158212 | 5078760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5078760 | 5236972 | 5236972 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-028 | 48-028 | 48 | N/A | 67130 | Wellington CDSB | WeCDSB Head Office | Administrative Office | OFF-ADM | 16162 | 18109 | 18109-B02 | 75 WOOLWICH ST | GUELPH | N1H3V1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5476 | -80.2475 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 588305 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 286477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286477 | 286477 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-029 | 48-029 | 48 | 225 - CMSM Wellington | 67130 | Wellington CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 24405 | 19406 | 19406-B01 | 5146 7 HWY RR 4 | ROCKWOOD | N0B2K0 | 35-15-75-615 | Guelph-Eramosa | Guelph/Eramosa Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6241 | -80.1517 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | 3 | 49 | Y | 2 | Approved | 44162 | 3261933 | Construction Complete | Addition | Child Care | 2021-22 | 44652 | 0 | 0 | 190803 | 25379 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 266182 | 0 | 0 | 0 | 0 | 0 | 0 | 1957160 | 1038591 | 0 | 0 | 2995751 | 3261933 | 3261933 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2995751
48-030 | 48-030 | 48 | N/A | 67130 | Wellington CDSB | WeCDSB Warehouse | Operational Office | OFF-OPS | 25061 | 20067 | 20067-B01 | 160 SOUTHGATE DR | GUELPH | N1G4P5 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.4984 | -80.2131 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42402 | 788100 | Construction Complete | New Construction | Other | 2016-17 | 42614 | 0 | 0 | 788100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788100 | 788100 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-031 | 48-031 | 48 | 225 - CMSM Wellington | 67130 | Wellington CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 4345 | 7922 | 7922-B01 | 391 VICTORIA RD N | GUELPH | N1E5J9 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5766 | -80.2578 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 64 | N | - | Approved | 44951 | 3887404 | Planned | Addition | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3887404 | 0 | 0 | 0 | 3887404 | 3887404 | 3887404 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 3887404
48-032 | 48-032 | 48 | N/A | 67130 | Wellington CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4098 | 7753 | 7753-B01 | 150 STRATHALLAN ST | FERGUS | N1M1A1 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.7122 | -80.387 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 190 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5205113 | 0 | 0 | 0 | 0 | 0 | 5205113 | 5205113 | 5205113 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5205113
48-033 | 48-033 | 48 | N/A | 67130 | Wellington CDSB | Education Centre | Education Centre | OFF-ADM | TBD | TBD | TBD | 512 WOOLWICH ST | GUELPH | N1H6N6 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.555 | -80.2641 | 44729 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44729 | 10201750 | Under Construction | Purchase | Other | 2021-22 | 44804 | 0 | 0 | 8504049 | 1697701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10201750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10201750 | 10201750 | 0 | EMBARGEOD | No | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
48-034 | 48-034 | 48 | N/A | 67130 | Wellington CDSB | Bishop Macdonell | Bishop Macdonell Catholic High School |  | TBD | TBD | TBD | [15 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - |  |  |  | Under Construction |  | Other |  |  | 0 | 0 | 0 | 2692751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2692751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2692751 | 2692751 | 0 | - | No | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-001 | 49-001 | 49 | N/A | 67148 | Waterloo CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 4288 | 7879 | 7879-B01 | 35 WEBER ST W | KITCHENER | N2H3Z1 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4523 | -80.4895 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131471 | 0 | 0 | 0 | 0 | 0 | 131471 | 131471 | 0 | -131471 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 131471
49-002 | 49-002 | 49 | N/A | 67148 | Waterloo CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 4288 | 7879 | 7879-B01 | 35 WEBER ST W | KITCHENER | N2H3Z1 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4523 | -80.4895 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5438368 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5928826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5928826 | 5928826 | 4611371 | -1317455 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-003 | 49-003 | 49 | N/A | 67148 | Waterloo CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 4288 | 7879 | 7879-B01 | 35 WEBER ST W | KITCHENER | N2H3Z1 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4523 | -80.4895 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 188731 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188731 | 188731 | 188731 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-004 | 49-004 | 49 | N/A | 67148 | Waterloo CDSB | Blessed Mother Teresa | Blessed Mother Teresa Catholic Elementary School | ELE | 6258 | 8639 | 8639-B01 | 520 SAGINAW PKY | CAMBRIDGE | N1T1W9 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3905 | -80.2831 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 600000 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000 | 600000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-006 | 49-006 | 49 | 233 - CMSM Waterloo | 67148 | Waterloo CDSB | Brigadoon-Huron | Brigadoon-Huron Catholic Elementary School | ELE | 24453 | 19456 | 19456-B01 | S HURON / E FISHER HALLMAN | KITCHENER | TBD | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.3824 | -80.4822 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 650 | 5 | 88 | N | - | Approved | 44533 | 19017116 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 917491 | 0 | 2043200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 3060691 | 0 | 0 | 465947 | 0 | 14086067 | 0 | 3289765 | 0 | 0 | 0 | 17841779 | 20902470 | 20902470 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 17375832
49-007 | 49-007 | 49 | N/A | 67148 | Waterloo CDSB | Canadian Martyrs | Canadian Martyrs Catholic Elementary School | ELE | 3095 | 7035 | 7035-B01 | 50 CONFEDERATION DR | KITCHENER | N2B2X5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4616 | -80.4463 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1275275 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475839 | 475839 | 0 | 0 | 850845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850845 | 1326684 | 1326684 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-009 | 49-009 | 49 | N/A | 67148 | Waterloo CDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 3294 | 7164 | 7164-B01 | 313 HURON ST | NEW HAMBURG | N3A1K3 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.3763 | -80.7143 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3012798 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3012798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3012798 | 3012798 | 3012798 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-010 | 49-010 | 49 | N/A | 67148 | Waterloo CDSB | Holy Rosary | Holy Rosary Catholic Elementary School | ELE | 3313 | 7177 | 7177-B01 | 485 THORNDALE DR | WATERLOO | N2T1W5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4453 | -80.5537 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Cancelled | - | 0 | Cancelled | Cancelled | Consolidation | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-011 | 49-011 | 49 | N/A | 67148 | Waterloo CDSB | Holy Spirit | Holy Spirit Catholic Elementary School | ELE | 10044 | 10374 | 10374-B01 | 15 GATEHOUSE DR | CAMBRIDGE | N1P1C7 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.344 | -80.2805 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6287678 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096746 | 1096746 | 5190932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5190932 | 6287678 | 6287678 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-012 | 49-012 | 49 | N/A | 67148 | Waterloo CDSB | Holy Spirit | Holy Spirit Catholic Elementary School | ELE | 10044 | 10374 | 10374-B01 | 15 GATEHOUSE DR | CAMBRIDGE | N1P1C7 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.344 | -80.2805 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1049600 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049600 | 1049600 | 1049600 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-013 | 49-013 | 49 | N/A | 67148 | Waterloo CDSB | Holy Spirit | Holy Spirit Catholic Elementary School | ELE | 10044 | 10374 | 10374-B01 | 15 GATEHOUSE DR | CAMBRIDGE | N1P1C7 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.344 | -80.2805 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 98 | - | - | N | - | Not Required | - | 1323421 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465947 | 0 | 910222 | 0 | 0 | 0 | 0 | 0 | 1376169 | 1376169 | 1376169 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 910222
49-014 | 49-014 | 49 | N/A | 67148 | Waterloo CDSB | John Sweeney | John Sweeney Catholic Elementary School | ELE | 10453 | 10286 | 10286-B01 | 185 ACTIVA AVE | KITCHENER | N2E4A1 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4075 | -80.5121 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7014049 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415788 | 415788 | 6598261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6598261 | 7014049 | 7014049 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-015 | 49-015 | 49 | N/A | 67148 | Waterloo CDSB | John Sweeney | John Sweeney Catholic Elementary School | ELE | 10453 | 10286 | 10286-B01 | 185 ACTIVA AVE | KITCHENER | N2E4A1 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4075 | -80.5121 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2773839 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1483525 | 0 | 1313277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796802 | 2796802 | 2796802 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-016 | 49-016 | 49 | N/A | 67148 | Waterloo CDSB | Monsignor Doyle | Monsignor Doyle Catholic Secondary School | SEC | 3425 | 7250 | 7250-B01 | 185 MYERS RD | CAMBRIDGE | N1R7H2 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3408 | -80.2977 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3661898 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3661898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3661898 | 3661898 | 3661898 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-018 | 49-018 | 49 | N/A | 67148 | Waterloo CDSB | Morrison Land | Morrison Land Land Holding | HLA | 24700 | 19177 | 19177-L0- | QUINTE CRESCENT / MORRISON RD | KITCHENER | TBD | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4317 | -80.415 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 650922 | Construction Complete | Land Acquisition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650922 | 650922 | 650922 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-019 | 49-019 | 49 | N/A | 67148 | Waterloo CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 3519 | 7313 | 7313-B01 | 55 HAMMET ST | CAMBRIDGE | N3C2H5 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4323 | -80.2993 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4977172 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4977172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4977172 | 4977172 | 4977172 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-020 | 49-020 | 49 | N/A | 67148 | Waterloo CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 3519 | 7313 | 7313-B01 | 55 HAMMET ST | CAMBRIDGE | N3C2H5 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4323 | -80.2993 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 170 | - | - | N | - | Not Required | - | 2804957 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774160 | 0 | 2334539 | 0 | 0 | 0 | 0 | 0 | 3108699 | 3108699 | 2804957 | -303742 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2334539
49-022 | 49-022 | 49 | N/A | 67148 | Waterloo CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 3546 | 7335 | 7335-B01 | 55 ROSLIN AVE S | WATERLOO | N2L6N5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.459 | -80.5301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2529567 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27645 | 27645 | 2501922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2501922 | 2529567 | 2529567 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-023 | 49-023 | 49 | N/A | 67148 | Waterloo CDSB | Saint John Paul II | Saint John Paul II Catholic Elementary School | ELE | 11306 | 12229 | 12229-L01 | 75 PEBBLECREEK DR | KITCHENER | N2A0E3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4489 | -80.4111 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1765241 | Construction Complete | Land Acquisition | Other | 2009-10 | 40057 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 15241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15241 | 1765241 | 1765241 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-024 | 49-024 | 49 | N/A | 67148 | Waterloo CDSB | Saint John Paul II | Saint John Paul II Catholic Elementary School | ELE | 11306 | 12229 | 12229-B01 | 75 PEBBLECREEK DR | KITCHENER | N2A0E3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4489 | -80.4111 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6863685 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 277315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277315 | 6586370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6586370 | 6863685 | 6863685 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-025 | 49-025 | 49 | N/A | 67148 | Waterloo CDSB | Saint John Paul II | Saint John Paul II Catholic Elementary School | ELE | 11306 | 12229 | 12229-B01 | 75 PEBBLECREEK DR | KITCHENER | N2A0E3 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4489 | -80.4111 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Not Required | - | 2217097 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575087 | 0 | 0 | 0 | 0 | 0 | 2575087 | 2575087 | 2217097 | -357990 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2575087
49-026 | 49-026 | 49 | N/A | 67148 | Waterloo CDSB | St. Agatha | St. Agatha Catholic Elementary School | ELE | 4596 | 8097 | 8097-B01 | 1869 NOTRE DAME DR RR 1 | ST AGATHA | N0B2L0 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | 43.4364 | -80.6299 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1298545 | Construction Complete | Retrofit | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616479 | 616479 | 682066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682066 | 1298545 | 1298545 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-028 | 49-028 | 49 | N/A | 67148 | Waterloo CDSB | St. Agnes | St. Agnes Catholic Elementary School | ELE | 3691 | 7448 | 7448-B01 | 254 NEILSON AVE | WATERLOO | N2J2M3 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.474 | -80.5018 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2169443 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2169443 | 2169443 | 2169443 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-030 | 49-030 | 49 | N/A | 67148 | Waterloo CDSB | St. Aloysius | St. Aloysius Catholic Elementary School | ELE | 3700 | 7454 | 7454-B01 | 504 CONNAUGHT ST | KITCHENER | N2C1C2 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4287 | -80.4449 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Not Required | - | 4268842 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 1477050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1477050 | 0 | 0 | 931894 | 0 | 2307122 | 0 | 0 | 0 | 0 | 0 | 3239016 | 4716066 | 4716066 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2307122
49-031 | 49-031 | 49 | N/A | 67148 | Waterloo CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 3728 | 7473 | 7473-B01 | 127 ELGIN ST N | CAMBRIDGE | N1R5H6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3655 | -80.2994 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1900000 | Construction Complete | Addition | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900000 | 1900000 | 1900000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-032 | 49-032 | 49 | N/A | 67148 | Waterloo CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 3728 | 7473 | 7473-L01 | 127 ELGIN ST N | CAMBRIDGE | N1R5H6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3655 | -80.2994 | 41976 | 2014-15 | 2014-15 | 41976 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1823988 | Construction Complete | Land Acquisition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15288 | 0 | 0 | 1808700 | 0 | 0 | 0 | 0 | 0 | 0 | 1823988 | 1823988 | 1823988 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1808700
49-033 | 49-033 | 49 | N/A | 67148 | Waterloo CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 3728 | 7473 | 7473-B01 | 127 ELGIN ST N | CAMBRIDGE | N1R5H6 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3655 | -80.2994 | 41734 | 2013-14 | 2014-15 | - | - | - | 41734 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 168 | - | - | N | - | Approved | 42102 | 4119827 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 0 | 0 | 633751 | 0 | 0 | 0 | 0 | 0 | 0 | 87718 | 0 | 0 | 0 | 0 | 0 | 721469 | 0 | 0 | 931894 | 0 | 2473702 | 0 | 0 | 0 | 0 | 0 | 3405596 | 4127065 | 4127065 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2473702
49-034 | 49-034 | 49 | N/A | 67148 | Waterloo CDSB | St. Anne | St. Anne Catholic Elementary School | ELE | 3730 | 7475 | 7475-B01 | 250 EAST AVE | KITCHENER | N2H1Z4 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4511 | -80.471 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2752727 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 752727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752727 | 2752727 | 2752727 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-035 | 49-035 | 49 | N/A | 67148 | Waterloo CDSB | St. Benedict | St. Benedict Catholic Secondary School | SEC | 3790 | 7522 | 7522-B01 | 50 SAGINAW PKY | CAMBRIDGE | N1R5W1 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3926 | -80.3 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5292083 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5292083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5292083 | 5292083 | 5292083 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-036-01 | 49-036 | 49 | 233 - CMSM Waterloo | 67148 | Waterloo CDSB | St. Boniface | St. Boniface Catholic Elementary School | ELE | 25101 | 20107 | 20107-B01 | 255 STARLIGHT AVE | WOOLWICH | TBD | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.4696 | -80.4157 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 257 | 5 | 88 | N | 3 | Approved | 43756 | 10383010 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465946 | 0 | 5962789 | 0 | 2471422 | 1482853 | 0 | 0 | 10383010 | 10383010 | 10383010 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9917064
49-036-02 | 49-036 | 49 | N/A | 67148 | Waterloo CDSB | St. Boniface | St. Boniface Catholic Elementary School | ELE | 25101 | 20107 | 20107-L01 | 255 STARLIGHT AVE | WOOLWICH | TBD | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.4696 | -80.4157 | 43404 | 2018-19 | 2018-19 | 43404 | 2018-19 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43756 | 3912431 | Construction Complete | Land Acquisition | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 2214092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214092 | 0 | 0 | 0 | 1698338 | 0 | 0 | 0 | 0 | 0 | 0 | 1698338 | 3912430 | 3912430 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1698338
49-037 | 49-037 | 49 | N/A | 67148 | Waterloo CDSB | St. Brigid | St. Brigid Catholic Elementary School | ELE | 9939 | 10338 | 10338-B01 | 50 BROOM ST | AYR | N0B1E0 | 35-15-25-601 | North Dumfries | North Dumfries Tp | Waterloo R | WATERLOO | Southwest | South | 43.2909 | -80.46 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 403532 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 403532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403532 | 403532 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-039 | 49-039 | 49 | 233 - CMSM Waterloo | 67148 | Waterloo CDSB | St. Brigid | St. Brigid Catholic Elementary School | ELE | 24656 | 10338 | 10338-B02 | 50 BROOM ST | AYR | N0B1E0 | 35-15-25-601 | North Dumfries | North Dumfries Tp | Waterloo R | WATERLOO | Southwest | South | 43.2903 | -80.4602 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 222 | 5 | 88 | N | - | Approved | 43186 | 8809937 | Construction Complete | New Construction | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612877 | 0 | 5345090 | 0 | 2545564 | 0 | 0 | 0 | 8503531 | 8503531 | 8903531 | 400000 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7890654
49-042 | 49-042 | 49 | N/A | 67148 | Waterloo CDSB | St. David | St. David Catholic Secondary School | SEC | 3889 | 7597 | 7597-B01 | 4 HIGH ST | WATERLOO | N2L3X5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.484 | -80.5288 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6002282 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6002282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6002282 | 6002282 | 6002282 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-043 | 49-043 | 49 | N/A | 67148 | Waterloo CDSB | St. Dominic Savio | St. Dominic Savio Catholic Elementary School | ELE | 9938 | 10337 | 10337-B01 | 3 WESTFOREST TRAIL | KITCHENER | N2N3A6 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4339 | -80.5397 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5200000 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 5200000 | 5200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-045 | 49-045 | 49 | N/A | 67148 | Waterloo CDSB | St. Gabriel | St. Gabriel Catholic Elementary School | ELE | 24266 | 19258 | 19258-B01 | 15 BALDWIN DR | CAMBRIDGE | N3C0G1 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4419 | -80.3132 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 350 | - | - | N | - | Not Required | - | 7827094 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 475390 | 0 | 6659976 | 0 | 0 | 0 | 0 | 0 | 7135366 | 7455366 | 7934477 | 479111 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6659976
49-046 | 49-046 | 49 | N/A | 67148 | Waterloo CDSB | St. John | St. John Catholic Elementary School | ELE | 4044 | 7715 | 7715-B01 | 99 STRANGE ST | KITCHENER | N2G1R4 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4488 | -80.509 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9607066 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 7676961 | 0 | 448868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8125829 | 9625829 | 9625829 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-049 | 49-049 | 49 | N/A | 67148 | Waterloo CDSB | St. Luke | St. Luke Catholic Elementary School | ELE | 10105 | 10394 | 10394-B01 | 550 CHESAPEAKE DR | WATERLOO | N2K4G5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.5095 | -80.5049 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8334877 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342755 | 342755 | 7992122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7992122 | 8334877 | 8334877 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-050 | 49-050 | 49 | N/A | 67148 | Waterloo CDSB | St. Luke | St. Luke Catholic Elementary School | ELE | 10105 | 10394 | 10394-B01 | 550 CHESAPEAKE DR | WATERLOO | N2K4G5 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.5095 | -80.5049 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 184 | - | - | N | - | Not Required | - | 2400948 | Construction Complete | Addition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637920 | 0 | 2327386 | 0 | 0 | 0 | 0 | 0 | 2965306 | 2965306 | 2402944 | -562362 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2327386
49-053 | 49-053 | 49 | N/A | 67148 | Waterloo CDSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 10136 | 10417 | 10417-B01 | 1500 BLOCK LINE RD | KITCHENER | N2C2S2 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4201 | -80.4671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 30275198 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605 | 605 | 30274593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30274593 | 30275198 | 30275198 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-054 | 49-054 | 49 | N/A | 67148 | Waterloo CDSB | St. Mary's | St. Mary's Catholic Secondary School | SEC | 10136 | 10417 | 10417-B01 | 1500 BLOCK LINE RD | KITCHENER | N2C2S2 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4201 | -80.4671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 371313 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 371313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371313 | 371313 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-055 | 49-055 | 49 | N/A | 67148 | Waterloo CDSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 10046 | 10375 | 10375-B01 | 525 LAURELWOOD DR | WATERLOO | N2V2N1 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4723 | -80.5875 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7703621 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020996 | 1020996 | 6682625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6682625 | 7703621 | 7703621 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-056 | 49-056 | 49 | N/A | 67148 | Waterloo CDSB | St. Nicholas | St. Nicholas Catholic Elementary School | ELE | 10046 | 10375 | 10375-B01 | 525 LAURELWOOD DR | WATERLOO | N2V2N1 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4723 | -80.5875 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 985004 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985004 | 985004 | 985004 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-059 | 49-059 | 49 | N/A | 67148 | Waterloo CDSB | St. Teresa | St. Teresa Catholic Elementary School | ELE | 4479 | 8013 | 8013-B01 | 69 FIRST ST W | ELMIRA | N3B1G5 | 35-15-25-604 | Woolwich | Woolwich Tp | Waterloo R | WATERLOO | Southwest | South | 43.5926 | -80.5712 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2232516 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 417058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417058 | 1817058 | 1817058 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-060 | 49-060 | 49 | N/A | 67148 | Waterloo CDSB | St. Teresa | St. Teresa Catholic Elementary School | ELE | 4474 | 8009 | 8009-B01 | 270 EDWIN ST | KITCHENER | N2H4P4 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4677 | -80.4879 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 225149 | Construction Complete | Demolition | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227644 | 0 | 0 | 0 | 0 | 0 | 227644 | 227644 | 227644 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 227644
49-062 | 49-062 | 49 | 233 - CMSM Waterloo | 67148 | Waterloo CDSB | St. Vincent de Paul | St. Vincent de Paul Catholic Elementary School | ELE | 24657 | 8053 | 8053-B02 | 30 FAIAL RD | CAMBRIDGE | N1R7C3 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.346 | -80.2904 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 550 | 5 | 88 | N | - | Approved | 42773 | 13455626 | Construction Complete | New Construction | Consolidation | 2012-13 | 41306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988568 | 0 | 9715434 | 0 | 2471420 | 0 | 0 | 0 | 13175422 | 13175422 | 13175422 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12186854
49-063 | 49-063 | 49 | N/A | 67148 | Waterloo CDSB | WaCDSB Head Office | Administrative Office | OFF-ADM | 4288 | 7879 | 7879-L01 | 35 WEBER ST W | KITCHENER | N2H3Z1 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4523 | -80.4895 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10789492 | Construction Complete | Land Acquisition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10789492 | 10789492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10789492 | 10789492 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
49-064 | 49-064 | 49 | 233 - CMSM Waterloo | 67148 | Waterloo CDSB | St. Francis | St. Francis Catholic Continued Education | ELE-CED | 3936 | 7633 | 7633-B01 | 154 GATEWOOD RD | KITCHENER | N2M4E4 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.433 | -80.5082 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | 43090 | 2017-18 | 2017-18 | - | - | - | - | 5 | 88 | Y | 3 | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2021-22 | 44593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520853 | 1512512 | 0 | 0 | 4033365 | 4033365 | 4033365 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 4033365
49-065 | 49-065 | 49 | N/A | 67148 | Waterloo CDSB | Southeast Galt | Southeast Galt Catholic Elementary School | ELE | 25398 | 20404 | 20404-B01 | TBD | CAMBRIDGE | TBD | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 354 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8652378 | 0 | 0 | 0 | 0 | 0 | 8652378 | 8652378 | 8652378 | 0 | - | No, Site to be acquired. Sign installation planned for January 31, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8652378
49-066 | 49-066 | 49 | N/A | 67148 | Waterloo CDSB | East Kitchener | East Kitchener Catholic Secondary School | ELE/SEC | 25399-25400 | 20405 | 20405-B01 | TBD | KITCHENER | TBD | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 1400 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37699818 | 0 | 0 | 0 | 0 | 0 | 37699818 | 37699818 | 37699818 | 0 | - | No, Site to be acquired. Sign installation planned for July 1, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 37699818
49-067 | 49-067 | 49 | N/A | 67148 | Waterloo CDSB | St. Agnes | St. Agnes Elementary School | ELE | 3691 | 7448 | 7448-B01 | 254 NEILSON AVE | WATERLOO | N2J2M3 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Central | South | 43.474 | -80.5018 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 167 | - | - | N | - | Approved | 44645 | 9445795 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44866 | 999703 | 700000 | 990000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689703 | 0 | 0 | 139419 | 0 | 6616673 | 0 | 0 | 0 | 0 | 0 | 6756092 | 9445795 | 9445795 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6616673
49-068 | 49-068 | 49 | N/A | 67148 | Waterloo CDSB | Rosenberg | Rosenberg Catholic Elementary School | ELE | TBD | TBD | TBD | ROSENBERG WAY / FOREST WALK ST | KITCHENER | TBD | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | TBD | TBD | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 527 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12142420 | 0 | 0 | 0 | 0 | 0 | 12142420 | 12142420 | 12142420 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12142420
49-069 | 49-069 | 49 | 233 - CMSM Waterloo | 67148 | Waterloo CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | TBD | TBD | TBD | S | KITCHENER | TBD | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4371 | -80.4337 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 527 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12142420 | 0 | 2834561 | 0 | 0 | 0 | 14976981 | 14976981 | 14976981 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14976981
49-070 | 49-070 | 49 | 233 - CMSM Waterloo | 67148 | Waterloo CDSB | Baden | Baden Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | BADEN | N3A2L9 | 35-15-25-603 | Wilmot | Wilmot Tp | Waterloo R | WATERLOO | Southwest | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 294 | 5 | 88 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8759588 | 0 | 3357538 | 0 | 0 | 0 | 12117126 | 12117126 | 12117126 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12117126
50-001 | 50-001 | 50 | N/A | 67156 | Niagara CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15821 | 18092 | 18092-B01 | 427 RICE RD | WELLAND | L3C7C1 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0221 | -79.2701 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-002 | 50-002 | 50 | N/A | 67156 | Niagara CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15821 | 18092 | 18092-B01 | 427 RICE RD | WELLAND | L3C7C1 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0221 | -79.2701 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3671095 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3222353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3222353 | 3222353 | 3671095 | 448742 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-003 | 50-003 | 50 | N/A | 67156 | Niagara CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 15821 | 18092 | 18092-B01 | 427 RICE RD | WELLAND | L3C7C1 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0221 | -79.2701 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1849065 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1849065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1849065 | 1849065 | 1849065 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-004 | 50-004 | 50 | N/A | 67156 | Niagara CDSB | Alexander Kuska KSG | Alexander Kuska KSG Catholic Elementary School | ELE | 3023 | 6986 | 6986-L01 | 333 RICE RD | WELLAND | L3C2V9 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0196 | -79.2705 | 41072 | 2011-12 | 2012-13 | 41072 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 166168 | Construction Complete | Land Acquisition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 1168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168 | 0 | 0 | 0 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 166168 | 166168 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 165000
50-005 | 50-005 | 50 | N/A | 67156 | Niagara CDSB | Assumption | Assumption Catholic Elementary School | ELE | 7960 | 9035 | 9035-B01 | 225 PARNELL RD | ST CATHARINES | L2M1W3 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.2127 | -79.2178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1593708 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1593708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1593708 | 1593708 | 1593708 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-006 | 50-006 | 50 | N/A | 67156 | Niagara CDSB | Blessed Trinity | Blessed Trinity Catholic Secondary School | SEC | 7961 | 9036 | 9036-B01 | 145 LIVINGSTON AVE | GRIMSBY | L3M5J6 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.1974 | -79.5805 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11682675 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 7774113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7774113 | 3908562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3908562 | 11682675 | 11682675 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-007 | 50-007 | 50 | N/A | 67156 | Niagara CDSB | Blessed Trinity | Blessed Trinity Catholic Secondary School | SEC | 7961 | 9036 | 9036-B01 | 145 LIVINGSTON AVE | GRIMSBY | L3M5J6 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.1974 | -79.5805 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11329915 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329915 | 329915 | 0 | 0 | 0 | 0 | 0 | 11000000 | 0 | 0 | 0 | 0 | 11000000 | 11329915 | 11329915 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-009 | 50-009 | 50 | N/A | 67156 | Niagara CDSB | Cardinal Newman | Cardinal Newman Catholic Elementary School | ELE | 3104 | 7041 | 7041-B01 | 8120 BEAVERDAMS RD | NIAGARA FALLS | L2H1R8 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0934 | -79.1325 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1603472 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1603472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1603472 | 1603472 | 1603472 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-010 | 50-010 | 50 | N/A | 67156 | Niagara CDSB | Cardinal Newman | Cardinal Newman Catholic Elementary School | ELE | 3104 | 7041 | 7041-B01 | 8120 BEAVERDAMS RD | NIAGARA FALLS | L2H1R8 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0934 | -79.1325 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2659261 | Construction Complete | Addition | Other | 2009-10 | 40057 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62812 | 862812 | 1796449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1796449 | 2659261 | 2659261 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-011 | 50-011 | 50 | N/A | 67156 | Niagara CDSB | Cardinal Newman | Cardinal Newman Catholic Elementary School | ELE | 3104 | 7041 | 7041-B01 | 8120 BEAVERDAMS RD | NIAGARA FALLS | L2H1R8 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0934 | -79.1325 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 485800 | Construction Complete | Addition | Other | 2012-13 | 41153 | 31881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31881 | 0 | 0 | 453919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453919 | 485800 | 485800 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-012 | 50-012 | 50 | N/A | 67156 | Niagara CDSB | Denis Morris | Denis Morris Catholic Secondary School | SEC | 7966 | 9041 | 9041-B01 | 40 GLEN MORRIS DR | ST CATHARINES | L2T2M9 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1393 | -79.2366 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4865227 | Construction Complete | Addition | Other | 2001-02 | 37135 | 695887 | 0 | 3240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3935887 | 929340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929340 | 4865227 | 4865227 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-013-01 | 50-013 | 50 | N/A | 67156 | Niagara CDSB | Lakeshore | Lakeshore Catholic Secondary School | SEC | 3380 | 7219 | 7219-B01 | 150 JANET ST | PORT COLBORNE | L3K2E7 | 35-11-18-102 | Port Colborne | Port Colborne C | Niagara R | NIAGARA | Central | South | 42.8963 | -79.2444 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 210 | - | - | N | - | Approved | 41758 | 5507666 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5501722 | 0 | 0 | 0 | 0 | 0 | 5501722 | 5501722 | 5501722 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5501722
50-013-02 | 50-013 | 50 | N/A | 67156 | Niagara CDSB | Lakeshore | Lakeshore Catholic Secondary School | SEC | 3380 | 7219 | 7219-L01 | 150 JANET ST | PORT COLBORNE | L3K2E7 | 35-11-18-102 | Port Colborne | Port Colborne C | Niagara R | NIAGARA | Central | South | 42.8963 | -79.2444 | 41153 | 2012-13 | 2012-13 | 41153 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 500000 | Construction Complete | Land Acquisition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 505944 | 5944 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 500000
50-014 | 50-014 | 50 | N/A | 67156 | Niagara CDSB | Loretto | Loretto Catholic Elementary School | ELE | 9593 | 5058 | 5058-B01 | 6855 KALAR RD | NIAGARA FALLS | L2H2T3 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0751 | -79.1371 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 50938 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50938 | 50938 | 50938 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-016 | 50-016 | 50 | N/A | 67156 | Niagara CDSB | Mary Ward | Mary Ward Catholic Elementary School | ELE | 3408 | 7240 | 7240-B01 | 2999 DORCHESTER RD | NIAGARA FALLS | L2J2Z9 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.1289 | -79.1132 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1083822 | Construction Complete | Addition | Other | 2013-14 | 41518 | 646787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646787 | 0 | 0 | 437035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437035 | 1083822 | 1083822 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-017 | 50-017 | 50 | N/A | 67156 | Niagara CDSB | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 10290 | 10486 | 10486-B01 | 125 FIRST ST LOUTH RR 3 | ST CATHARINES | L2R6P9 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1628 | -79.2769 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 36078 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36078 | 36078 | 36078 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-018 | 50-018 | 50 | N/A | 67156 | Niagara CDSB | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 10290 | 10486 | 10486-B01 | 125 FIRST ST LOUTH RR 3 | ST CATHARINES | L2R6P9 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1628 | -79.2769 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5378426 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5378426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5378426 | 5378426 | 5378426 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-019 | 50-019 | 50 | N/A | 67156 | Niagara CDSB | NCDSB Head Office | Administrative Office | OFF-ADM | 15821 | 18092 | 18092-B01 | 427 RICE RD | WELLAND | L3C7C1 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0221 | -79.2701 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 91072 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 91072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91072 | 91072 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-020 | 50-020 | 50 | N/A | 67156 | Niagara CDSB | Notre Dame College | Notre Dame College Catholic Secondary School | SEC | 3484 | 7288 | 7288-B01 | 64 SMITH ST | WELLAND | L3C4H4 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0004 | -79.2469 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4335491 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4335491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4335491 | 4335491 | 4335491 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-021-01 | 50-021 | 50 | 231 - CMSM Niagara | 67156 | Niagara CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 14749 | 9053 | 9053-B02 | 69 OLIVE ST | GRIMSBY | L3M2C3 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.2026 | -79.5667 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 138 | 3 | 49 | N | - | Approved | 42797 | 4391129 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 43101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2863790 | 0 | 1527339 | 0 | 0 | 0 | 4391129 | 4391129 | 4117251 | -273878 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4391129
50-021-03 | 50-021 | 50 | N/A | 67156 | Niagara CDSB | CyberQuest | CyberQuest Catholic Continued Education | ELE-CED | 7980 | 9053 | 9053-B01 | 69 OLIVE ST | GRIMSBY | L3M2C3 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.2018 | -79.5675 | 42803 | 2016-17 | 2016-17 | - | - | - | 42803 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42803 | 134100 | Construction Complete | Demolition | Other | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134100 | 0 | 0 | 0 | 0 | 0 | 134100 | 134100 | 134100 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 134100
50-022 | 50-022 | 50 | N/A | 67156 | Niagara CDSB | Our Lady of Fatima (Annex) | Our Lady of Fatima (Annex) Catholic Continued Education | ELE-CED | 7980 | 9053 | 9053-B01 | 69 OLIVE ST | GRIMSBY | L3M2C3 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.2018 | -79.5675 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 20108 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20108 | 20108 | 20108 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-023 | 50-023 | 50 | N/A | 67156 | Niagara CDSB | Our Lady of Fatima (Annex) | Our Lady of Fatima (Annex) Catholic Continued Education | ELE-CED | 7980 | 9053 | 9053-B01 | 69 OLIVE ST | GRIMSBY | L3M2C3 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.2018 | -79.5675 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8239131 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 347900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173869 | 521769 | 7717362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7717362 | 8239131 | 8239131 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-024 | 50-024 | 50 | N/A | 67156 | Niagara CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 3106 | 7042 | 7042-B01 | 6525 CARLTON AVE | NIAGARA FALLS | L2G5K4 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0806 | -79.1075 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 44 | - | - | N | - | Not Required | - | 2494752 | Construction Complete | Addition | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021197 | 0 | 1473555 | 0 | 0 | 0 | 0 | 0 | 2494752 | 2494752 | 2494752 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1473555
50-025 | 50-025 | 50 | N/A | 67156 | Niagara CDSB | Our Lady of Victory | Our Lady of Victory Catholic Elementary School | ELE | 3573 | 7355 | 7355-B02 | 300 CENTRAL AVE | FORT ERIE | L2A3T3 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.9186 | -78.917 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5839630 | Construction Complete | Addition | Other | 2011-12 | 40787 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276488 | 776488 | 0 | 500000 | 0 | 0 | 0 | 4563142 | 0 | 0 | 0 | 0 | 5063142 | 5839630 | 5839630 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-026 | 50-026 | 50 | N/A | 67156 | Niagara CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3651 | 7419 | 7419-B01 | 8450 OLIVER ST | NIAGARA FALLS | L2G6Z2 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0546 | -79.0527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1815670 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1815670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1815670 | 1815670 | 1815670 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-027 | 50-027 | 50 | N/A | 67156 | Niagara CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 3651 | 7419 | 7419-B01 | 8450 OLIVER ST | NIAGARA FALLS | L2G6Z2 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0546 | -79.0527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 638449 | Construction Complete | Addition | Other | 2012-13 | 41153 | 114732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114732 | 0 | 0 | 523717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523717 | 638449 | 638449 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-028 | 50-028 | 50 | N/A | 67156 | Niagara CDSB | Saint Michael | Saint Michael Catholic Secondary School | SEC | 10286 | 10484 | 10484-B01 | 8699 MCLEOD RD | NIAGARA FALLS | L2H0Z2 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0705 | -79.1429 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 85160 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85160 | 85160 | 85160 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-029 | 50-029 | 50 | N/A | 67156 | Niagara CDSB | Saint Michael | Saint Michael Catholic Secondary School | SEC | 10286 | 10484 | 10484-B01 | 8699 MCLEOD RD | NIAGARA FALLS | L2H0Z2 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0705 | -79.1429 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 210 | - | - | N | - | Not Required | - | 6166985 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 402028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402028 | 0 | 0 | 0 | 0 | 5527880 | 0 | 0 | 0 | 0 | 0 | 5527880 | 5929908 | 5929908 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5527880
50-030 | 50-030 | 50 | N/A | 67156 | Niagara CDSB | Saint Michael | Saint Michael Catholic Secondary School | SEC | 10286 | 10484 | 10484-B01 | 8699 MCLEOD RD | NIAGARA FALLS | L2H0Z2 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0705 | -79.1429 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16021924 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16021924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16021924 | 16021924 | 16021924 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-031 | 50-031 | 50 | N/A | 67156 | Niagara CDSB | Saint Paul | Saint Paul Catholic Secondary School | SEC | 3667 | 7431 | 7431-B01 | 3834 WINDERMERE RD | NIAGARA FALLS | L2J2Y5 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.1174 | -79.1102 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 70057 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70057 | 70057 | 70057 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-032 | 50-032 | 50 | N/A | 67156 | Niagara CDSB | St. Alexander | St. Alexander Catholic Elementary School | ELE | 3696 | 7452 | 7452-B01 | 26 HWY 20 E | FONTHILL | L0S1E0 | 35-11-18-405 | Pelham | Pelham T | Niagara R | NIAGARA | Central | South | 43.0463 | -79.2815 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 26850 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26850 | 26850 | 26850 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-033 | 50-033 | 50 | N/A | 67156 | Niagara CDSB | St. Alexander | St. Alexander Catholic Elementary School | ELE | 3696 | 7452 | 7452-B01 | 26 HWY 20 E | FONTHILL | L0S1E0 | 35-11-18-405 | Pelham | Pelham T | Niagara R | NIAGARA | Central | South | 43.0463 | -79.2815 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 582775 | Construction Complete | Addition | Other | 2013-14 | 41518 | 91644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91644 | 0 | 0 | 491131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491131 | 582775 | 582775 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-034 | 50-034 | 50 | N/A | 67156 | Niagara CDSB | St. Alfred | St. Alfred Catholic Elementary School | ELE | 7957 | 9032 | 9032-B01 | 280 VINE ST | ST CATHARINES | L2M4T3 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1811 | -79.2285 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 685818 | Construction Complete | Addition | Other | 2012-13 | 41153 | 134887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134887 | 0 | 0 | 550931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550931 | 685818 | 685818 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-035 | 50-035 | 50 | N/A | 67156 | Niagara CDSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 6195 | 8606 | 8606-B01 | 16 ST ANDREWS AVE | WELLAND | L3B1E1 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.9924 | -79.2277 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24746 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24746 | 24746 | 24746 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-036 | 50-036 | 50 | N/A | 67156 | Niagara CDSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 6195 | 8606 | 8606-B01 | 16 ST ANDREWS AVE | WELLAND | L3B1E1 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.9924 | -79.2277 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1302122 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224253 | 224253 | 1077869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077869 | 1302122 | 1302122 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-037 | 50-037 | 50 | N/A | 67156 | Niagara CDSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 6195 | 8606 | 8606-B01 | 16 ST ANDREWS AVE | WELLAND | L3B1E1 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.9924 | -79.2277 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 661047 | Construction Complete | Addition | Other | 2013-14 | 41518 | 134966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194150 | 329116 | 0 | 0 | 331931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331931 | 661047 | 661047 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-038 | 50-038 | 50 | N/A | 67156 | Niagara CDSB | St. Ann | St. Ann Catholic Elementary School | ELE | 3724 | 7470 | 7470-B01 | 832 CANBORO RD W | FENWICK | L0S1C0 | 35-11-18-405 | Pelham | Pelham T | Niagara R | NIAGARA | Central | South | 43.0234 | -79.3655 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 929363 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929363 | 929363 | 929363 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-039 | 50-039 | 50 | N/A | 67156 | Niagara CDSB | St. Ann | St. Ann Catholic Elementary School | ELE | 3724 | 7470 | 7470-B01 | 832 CANBORO RD W | FENWICK | L0S1C0 | 35-11-18-405 | Pelham | Pelham T | Niagara R | NIAGARA | Central | South | 43.0234 | -79.3655 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 53490 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53490 | 53490 | 53490 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-040 | 50-040 | 50 | N/A | 67156 | Niagara CDSB | St. Anthony | St. Anthony Catholic Elementary School | ELE | 7959 | 9034 | 9034-B01 | 81 RYKERT ST | ST CATHARINES | L2S1Z2 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1403 | -79.2565 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2115657 | Construction Complete | Addition | Other | 2011-12 | 40787 | 166700 | 0 | 0 | 78491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358012 | 603203 | 1077869 | 0 | 434585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512454 | 2115657 | 2115657 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-041 | 50-041 | 50 | N/A | 67156 | Niagara CDSB | St. Augustine | St. Augustine Catholic Elementary School | ELE | 3776 | 7511 | 7511-B01 | 300 SANTONE AVE | WELLAND | L3C2J8 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.97 | -79.2646 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1149789 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715204 | 0 | 434585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149789 | 1149789 | 1149789 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-042 | 50-042 | 50 | N/A | 67156 | Niagara CDSB | St. Charles | St. Charles Catholic Elementary School | ELE | 3847 | 7563 | 7563-B01 | 25 WHYTE AVE N | THOROLD | L2V2T4 | 35-11-18-105 | Thorold | Thorold C | Niagara R | NIAGARA | Central | South | 43.126 | -79.2086 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1242152 | Construction Complete | Addition | Other | 2012-13 | 41153 | 82095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82095 | 0 | 0 | 1160057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1160057 | 1242152 | 1242152 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-043 | 50-043 | 50 | N/A | 67156 | Niagara CDSB | St. Gabriel Lalemant | St. Gabriel Lalemant Catholic Elementary School | ELE | 3966 | 7655 | 7655-B01 | 6121 VINE ST | NIAGARA FALLS | L2J1L4 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.1222 | -79.0984 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1652531 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652531 | 1652531 | 1652531 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-044 | 50-044 | 50 | N/A | 67156 | Niagara CDSB | St. George | St. George Catholic Elementary School | ELE | 10078 | 10386 | 10386-B01 | 3800 WELLINGTON RD | CRYSTAL BEACH | L0S1B0 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.8746 | -79.0567 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4663676 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4663676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4663676 | 4663676 | 4663676 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-045 | 50-045 | 50 | N/A | 67156 | Niagara CDSB | St. James | St. James Catholic Elementary School | ELE | 7971 | 9046 | 9046-B01 | 615 GENEVA ST | ST CATHARINES | L2N2J3 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.2036 | -79.2434 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 72 | - | - | N | - | Not Required | - | 2721042 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 883353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883353 | 0 | 0 | 479928 | 0 | 1357761 | 0 | 0 | 0 | 0 | 0 | 1837689 | 2721042 | 2721042 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1357761
50-046 | 50-046 | 50 | N/A | 67156 | Niagara CDSB | St. John | St. John Catholic Elementary School | ELE | 7972 | 9047 | 9047-B01 | 5684 REGIONAL RD 81 | BEAMSVILLE | L0R1B0 | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1805 | -79.5097 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17867 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17867 | 17867 | 17867 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-047 | 50-047 | 50 | N/A | 67156 | Niagara CDSB | St. John | St. John Catholic Elementary School | ELE | 7972 | 9047 | 9047-B01 | 5684 REGIONAL RD 81 | BEAMSVILLE | L0R1B0 | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1805 | -79.5097 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1470321 | Construction Complete | Addition | Other | 2013-14 | 41518 | 42350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468121 | 510471 | 0 | 0 | 959850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959850 | 1470321 | 1470321 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-049 | 50-049 | 50 | N/A | 67156 | Niagara CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 7973 | 9048 | 9048-B02 | 5 ROBINSON ST N | GRIMSBY | L3M3C8 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.1929 | -79.5579 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7346699 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 236460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646204 | 882664 | 6464035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6464035 | 7346699 | 7346699 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-050 | 50-050 | 50 | N/A | 67156 | Niagara CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4104 | 7756 | 7756-B01 | 3650 NETHERBY RD | STEVENSVILLE | L0S1S0 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.9641 | -79.0528 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1308756 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308756 | 1308756 | 1308756 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-051 | 50-051 | 50 | N/A | 67156 | Niagara CDSB | St. Kevin | St. Kevin Catholic Elementary School | ELE | 4159 | 7288 | 7288-B02 | 182 AQUEDUCT ST | WELLAND | L3C1C4 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0017 | -79.2485 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1141307 | Construction Complete | Addition | Other | 2013-14 | 41518 | 378217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43202 | 421419 | 0 | 0 | 719888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719888 | 1141307 | 1141307 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-052 | 50-052 | 50 | N/A | 67156 | Niagara CDSB | St. Mark | St. Mark Catholic Elementary School | ELE | 10019 | 10367 | 10367-B01 | 4114 MOUNTAIN ST | BEAMSVILLE | L0R1B7 | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1578 | -79.4799 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1988383 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1437159 | 0 | 551224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1988383 | 1988383 | 1988383 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-053 | 50-053 | 50 | N/A | 67156 | Niagara CDSB | St. Mark | St. Mark Catholic Elementary School | ELE | 10019 | 10367 | 10367-B01 | 4114 MOUNTAIN ST | BEAMSVILLE | L0R1B7 | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1578 | -79.4799 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5945676 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5945676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5945676 | 5945676 | 5945676 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-054 | 50-054 | 50 | N/A | 67156 | Niagara CDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 7976 | 9051 | 9051-B01 | 186 MARGARET ST | SMITHVILLE | L0R2A0 | 35-11-18-602 | West Lincoln | West Lincoln Tp | Niagara R | NIAGARA | Central | South | 43.0993 | -79.5506 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1756350 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1756350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1756350 | 1756350 | 1756350 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-056-01 | 50-056 | 50 | N/A | 67156 | Niagara CDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 24298 | 19290 | 19290-B01 | 18 STREAMSIDE DR | SMITHVILLE | L0R2A0 | 35-11-18-602 | West Lincoln | West Lincoln Tp | Niagara R | NIAGARA | Central | South | 43.0947 | -79.5486 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 454 | - | - | N | - | Approved | 42327 | 9748099 | Construction Complete | New Construction | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959850 | 0 | 9339395 | 0 | 0 | 0 | 0 | 0 | 10299245 | 10299245 | 10003694 | -295551 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9339395
50-056-02 | 50-056 | 50 | N/A | 67156 | Niagara CDSB | St. Martin | St. Martin Catholic Elementary School | ELE | 24298 | 19290 | 19290-L01 | 18 STREAMSIDE DR | SMITHVILLE | L0R2A0 | 35-11-18-602 | West Lincoln | West Lincoln Tp | Niagara R | NIAGARA | Central | South | 43.0947 | -79.5486 | 41578 | 2013-14 | 2013-14 | 41578 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41578 | 2305000 | Construction Complete | Land Acquisition | Condition | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2305000 | 0 | 0 | 0 | 0 | 0 | 0 | 2305000 | 2305000 | 2115593 | -189407 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2305000
50-057 | 50-057 | 50 | N/A | 67156 | Niagara CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 7977 | 9052 | 9052-B01 | 387 LINE 3 RD | NIAGARA ON THE LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.2098 | -79.1364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2252649 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2252649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2252649 | 2252649 | 2252649 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-058 | 50-058 | 50 | N/A | 67156 | Niagara CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 7977 | 9052 | 9052-B01 | 387 LINE 3 RD | NIAGARA ON THE LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.2098 | -79.1364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 31648 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31648 | 31648 | 31648 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-059 | 50-059 | 50 | N/A | 67156 | Niagara CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 7977 | 9052 | 9052-B01 | 387 LINE 3 RD | NIAGARA ON THE LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.2098 | -79.1364 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 609251 | Construction Complete | Addition | Other | 2012-13 | 41153 | 92669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92669 | 0 | 0 | 516582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516582 | 609251 | 609251 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-060 | 50-060 | 50 | N/A | 67156 | Niagara CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 7977 | 9052 | 9052-L01 | 387 LINE 3 RD | NIAGARA ON THE LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.2098 | -79.1364 | 42018 | 2014-15 | 2014-15 | 42018 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15560 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 0 | 0 | 0 | 0 | 0 | 0 | 15560 | 15560 | 13964 | -1596 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 15560
50-061 | 50-061 | 50 | N/A | 67156 | Niagara CDSB | St. Philomena | St. Philomena Catholic Elementary School | ELE | 4425 | 7970 | 7970-B01 | 1332 PHILLIPS ST | FORT ERIE | L2A3C2 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.8957 | -78.9651 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 385863 | Construction Complete | Addition | Other | 2013-14 | 41518 | 87047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49862 | 136909 | 0 | 0 | 248954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248954 | 385863 | 385863 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-062 | 50-062 | 50 | N/A | 67156 | Niagara CDSB | St. Vincent de Paul | St. Vincent de Paul Catholic Elementary School | ELE | 10288 | 10485 | 10485-B01 | 3900 KALAR RD | NIAGARA FALLS | L2H0K2 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.1151 | -79.1371 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 36764 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36764 | 36764 | 36764 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-063 | 50-063 | 50 | N/A | 67156 | Niagara CDSB | St. Vincent de Paul | St. Vincent de Paul Catholic Elementary School | ELE | 10288 | 10485 | 10485-B01 | 3900 KALAR RD | NIAGARA FALLS | L2H0K2 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.1151 | -79.1371 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6697812 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6697812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6697812 | 6697812 | 6697812 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
50-065 | 50-065 | 50 | 231 - CMSM Niagara | 67156 | Niagara CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 3106 | 7042 | 7042-B01 | 6525 CARLTON AVE | NIAGARA FALLS | L2G5K4 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.0806 | -79.1075 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44026 | 2254668 | Construction Complete | Addition | Child Care | 2021-22 | 44501 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 1979668 | 0 | 0 | 0 | 1979668 | 2254668 | 2254668 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1979668
50-066 | 50-066 | 50 | 231 - CMSM Niagara | 67156 | Niagara CDSB | Monsignor Clancy | Monsignor Clancy Catholic Elementary School | ELE | 3447 | 7267 | 7267-B01 | 41 COLLIER RD S | THOROLD | L2V3S9 | 35-11-18-105 | Thorold | Thorold C | Niagara R | NIAGARA | Central | South | 43.1217 | -79.2159 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 104 | 3 | 49 | Y | - | Approved | 44039 | 5131382 | Under Construction | Addition | Consolidation | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3573495 | 0 | 1557887 | 0 | 0 | 0 | 5131382 | 5131382 | 5131382 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5131382
50-067 | 22-063+50-067 | 50 | N/A | 67156 | Niagara CDSB | St. Elizabeth | St. Elizabeth Catholic Elementray School | ELE | 25380 | 7620 | 7620-B02 | 31950 SUGARLOAF ST | WAINFLEET | L0S1V0 | 35-11-18-601 | Wainfleet | Wainfleet Tp | Niagara R | NIAGARA | Central | South | 42.9213 | -79.3743 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 118 | - | - | - | - | Approved | 44684 | 5435041 | Under Construction | New Construction | Condition | 2023-24 | 45174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5435041 | 0 | 0 | 0 | 0 | 0 | 5435041 | 5435041 | 5435041 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5435041
50-068 | 50-068 | 50 | N/A | 67156 | Niagara CDSB | Lincoln | Lincoln Catholic Elementary School | ELE | TBD | TBD | TBD | MOUNTAIN ST / CASSANDRA DR | BEAMSVILLE | TBD | 35-11-18-403 | Lincoln | Lincoln T | Niagara R | NIAGARA | Central | South | 43.1574 | -79.478 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 421 | 3 | 49 | N | - | Approved | 45022 | 12122607 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10108084 | 0 | 2014523 | 0 | 0 | 0 | 12122607 | 12122607 | 12122607 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12122607
51-001 | 51-001 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 16098 | 7933 | 7933-B02 | 322 FAIRVIEW DR | BRANTFORD | N3R2X6 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1699 | -80.2592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-002 | 51-002 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 16098 | 7933 | 7933-B02 | 322 FAIRVIEW DR | BRANTFORD | N3R2X6 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1699 | -80.2592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2965458 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3228586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3228586 | 3228586 | 2965458 | -263128 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-003 | 51-003 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Assumption College | Assumption College Catholic Secondary School | SEC | 3039 | 6996 | 6996-B01 | 257 SHELLARD LANE | BRANTFORD | N3T0M7 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1215 | -80.2974 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2075932 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2075932 | 2075932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2075932 | 2075932 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-004 | 51-004 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Assumption College | Assumption College Catholic Secondary School | SEC | 3039 | 6996 | 6996-B01 | 257 SHELLARD LANE | BRANTFORD | N3T0M7 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1215 | -80.2974 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3505487 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3505487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3505487 | 3505487 | 3505487 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-005 | 51-005 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | BHNCDSB Head Office | Administrative Office | OFF-ADM | 16098 | 7933 | 7933-B02 | 322 FAIRVIEW DR | BRANTFORD | N3R2X6 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1699 | -80.2592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1118652 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118652 | 1118652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118652 | 1118652 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-006 | 51-006 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Blessed Sacrement | Blessed Sacrement Catholic Elementary School | ELE | 3069 | 7012 | 7012-B01 | 185 KING ST W | BURFORD | N0E1A0 | 35-15-14-000 | Brant County | Brant County | Brant County | BRANT | Southwest | South | 43.1007 | -80.4375 | 41759 | 2013-14 | 2014-15 | - | - | - | 41759 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 39 | - | - | N | - | Not Required | - | 1379461 | Construction Complete | Addition | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408914 | 408914 | 0 | 0 | 538361 | 0 | 432186 | 0 | 0 | 0 | 0 | 0 | 970547 | 1379461 | 1379461 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 432186
51-007 | 51-007 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 10117 | 10402 | 10402-B01 | 128 EVERGREEN HILL RD | SIMCOE | N3Y4K1 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8244 | -80.3115 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21445047 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445047 | 445047 | 21000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000000 | 21445047 | 21445047 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-008 | 51-008 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 10117 | 10402 | 10402-B01 | 128 EVERGREEN HILL RD | SIMCOE | N3Y4K1 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8244 | -80.3115 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3106426 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3106426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3106426 | 3106426 | 3106426 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-009 | 51-009 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Jean Vanier | Jean Vanier Catholic Elementary School | ELE | 11312 | 7308 | 7308-B01 | 120 NINTH AVE | BRANTFORD | N3S1E7 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1212 | -80.2496 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8104922 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229887 | 429887 | 7675035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7675035 | 8104922 | 8104922 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-010 | 51-010 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 6104 | 8566 | 8566-B01 | 35 BRAEMAR AVE | CALEDONIA | N3W2M5 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0618 | -79.9638 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1314285 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1314285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1314285 | 1314285 | 1314285 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-012 | 51-012 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Our Lady of Fatima | Our Lady of Fatima Catholic Elementary School | ELE | 3522 | 7315 | 7315-L01 | 120 TALBOT RD | COURTLAND | N0J1E0 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8377 | -80.6339 | 41738 | 2013-14 | 2014-15 | 41738 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 75000 | Construction Complete | Land Acquisition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 75000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 75000
51-013 | 51-013 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Our Lady of Providence | Our Lady of Providence Catholic Elementary School | ELE | 10005 | 10360 | 10360-B01 | 55 KENT RD | BRANTFORD | N3R7X8 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1755 | -80.2852 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4330911 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330911 | 330911 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4330911 | 4330911 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-015 | 51-015 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 11052 | 12218 | 12218-B01 | 180 GRANDVILLE CIR | PARIS | N3L0A9 | 35-15-14-000 | Brant County | Brant County | Brant County | BRANT | Southwest | South | 43.1782 | -80.3941 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8376056 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409000 | 409000 | 7967056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7967056 | 8376056 | 8376056 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-016 | 23-006+51-016 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | St. Basil | St. Basil Catholic Elementary School | ELE | 14365 | 18009 | 18009-B01 | 365 BLACKBURN DR | BRANTFORD | N3T0G5 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1126 | -80.2969 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9050000 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050000 | 9050000 | 9050000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-017 | 51-017 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | St. Gabriel | St. Gabriel Catholic Elementary School | ELE | 10395 | 11095 | 11095-B01 | 14 FLANDERS DR | BRANTFORD | N3T6M2 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1242 | -80.2943 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5544358 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544358 | 5544358 | 5544358 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-019 | 51-019 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | St. John's College | St. John's College Catholic Secondary School | SEC | 3600 | 7376 | 7376-B01 | 80 PARIS RD | BRANTFORD | N3R1H9 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1604 | -80.2885 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7290123 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7290123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7290123 | 7290123 | 7290123 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-021 | 51-021 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | St. Josephs | St. Josephs Catholic Elementary School | ELE | 4118 | 7766 | 7766-B01 | 34 POTTS RD | SIMCOE | N3Y2S8 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8325 | -80.2952 | 42569 | 2015-16 | 2016-17 | 42569 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Cancelled | - | 250000 | Cancelled | Cancelled | Other | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-023 | 51-023 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | St. Peter | St. Peter Catholic Elementary School | ELE | 4411 | 7961 | 7961-B01 | 175 GLENWOOD DR | BRANTFORD | N3S3H1 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1433 | -80.2197 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 659369 | Construction Complete | Addition | Other | 2012-13 | 41153 | 138767 | 0 | 81864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220631 | 0 | 0 | 438738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438738 | 659369 | 659369 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-024 | 51-024 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | St. Pius X | St. Pius X Catholic Elementary School | ELE | 24239 | 7974 | 7974-B02 | 127 WOOD ST | BRANTFORD | N3R2L4 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1655 | -80.2721 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 300 | - | - | N | - | Not Required | - | 6921286 | Construction Complete | New Construction | Condition | 2013-14 | 41518 | 103026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59387 | 162413 | 0 | 0 | 479925 | 0 | 6278948 | 0 | 0 | 0 | 0 | 0 | 6758873 | 6921286 | 6921286 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6278948
51-025 | 51-025 | 51 | 228 - CMSM Norfolk | 67164 | Brant Haldimand Norfolk CDSB | Notre Dame | Notre Dame Catholic Elementary School | ELE | 6104 | 8566 | 8566-B01 | 35 BRAEMAR AVE | CALEDONIA | N3W2M5 | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0618 | -79.9638 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | N | 2 | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2016-17 | 42795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40735 | 0 | 0 | 40735 | 40735 | 40735 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 40735
51-026 | 51-026 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 16098 | 7933 | 7933-B02 | 322 FAIRVIEW DR | BRANTFORD | N3R2X6 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1699 | -80.2592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Other | Other | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441146 | 441146 | 441146 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
51-027 | 51-027 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | St. Frances Cabrini | St. Frances Cabrini Catholic Elementary School | ELE | 3927 | 7625 | 7625-B01 | 373 NORTHERN AVE | DELHI | N4B2R4 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8525 | -80.4887 | 42904 | 2016-17 | 2017-18 | - | - | - | 42904 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 49 | - | - | N | - | Approved | 43227 | 1333044 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 262169 | 0 | 920875 | 0 | 0 | 0 | 0 | 0 | 1183044 | 1333044 | 1333044 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 920875
51-028 | 51-028 | 51 | 200 - CMSM Brantford | 67164 | Brant Haldimand Norfolk CDSB | Our Lady of Providence | Our Lady of Providence Catholic Elementary School | ELE | 10005 | 10360 | 10360-B01 | 55 KENT RD | BRANTFORD | N3R7X8 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1755 | -80.2852 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43902 | 1706554 | Construction Complete | Addition | Child Care | 2021-22 | 44531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1706554 | 0 | 0 | 0 | 1706554 | 1706554 | 1706554 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1706554
51-029 | 51-029 | 51 | 228 - CMSM Norfolk | 67164 | Brant Haldimand Norfolk CDSB | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 10117 | 10402 | 10402-B01 | 128 EVERGREEN HILL RD | SIMCOE | N3Y4K1 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8244 | -80.3115 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44179 | 1731554 | Construction Complete | Addition | Child Care | 2021-22 | 44621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731554 | 0 | 0 | 0 | 1731554 | 1731554 | 1731554 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1731554
51-030 | 23-079+51-030 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Caledonia | Caledonia Catholic Elementary School | ELE | TBD | TBD | TBD | MACLACHLAN AVE / WHITHORN CRES | CALEDONIA | TBD | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0735 | -79.9313 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 305 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8142113 | 0 | 0 | 0 | 0 | 0 | 8142113 | 8142113 | 8142113 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8142113
51-031 | 51-031 | 51 | 200 - CMSM Brantford | 67164 | Brant Haldimand Norfolk CDSB | Brantford | Brantford Catholic Secondary School | SEC | TBD | TBD | TBD | TBD | BRANTFORD | N3T5L8 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 1119 | 8 | 128 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40301794 | 0 | 5424217 | 0 | 0 | 0 | 45726011 | 45726011 | 45726011 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 45726011
51-032 | 23-080+51-032 | 51 | N/A | 67164 | Brant Haldimand Norfolk CDSB | Caledonia | Caledonia Catholic Elementary School | ELE | TBD | TBD | TBD | MACLACHLAN AVE / WHITHORN CRES | CALEDONIA | TBD | 35-15-13-000 | Haldimand | Haldimand County | Haldimand County | HALDIMAND | Southwest | South | 43.0735 | -79.9313 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 305 | - | - | N | - | Planned | - | - | Planned | Land Acquisition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6381801 | 0 | 0 | 0 | 0 | 0 | 0 | 6381801 | 6381801 | 6381801 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6381801
52-001 | 52-001 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15776 | 18090 | 18090-B01 | 835 CAMPBELL ST | CORNWALL | K6H7B7 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0414 | -74.6938 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21030 | 0 | 0 | 0 | 0 | 0 | 21030 | 21030 | 0 | -21030 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 21030
52-002 | 52-002 | 52 | N/A | 67172 | CDSB of Eastern Ontario | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15776 | 18090 | 18090-B01 | 835 CAMPBELL ST | CORNWALL | K6H7B7 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0414 | -74.6938 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8104569 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8388823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8388823 | 8388823 | 8104569 | -284254 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-003 | 52-003 | 52 | N/A | 67172 | CDSB of Eastern Ontario | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 15776 | 18090 | 18090-B01 | 835 CAMPBELL ST | CORNWALL | K6H7B7 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0414 | -74.6938 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 869018 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869018 | 869018 | 869018 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-005 | 52-005 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Holy Cross | Holy Cross Catholic Elementary School | ELE | 3277 | 7153 | 7153-B01 | 521 CLOTHIER ST W | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0125 | -75.6543 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2196130 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2196130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2196130 | 2196130 | 2196130 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-007 | 52-007 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 10624 | 11263 | 11263-B01 | 18044 TYOTOWN RD | CORNWALL | K6H5R5 | 35-12-71-616 | South Glengarry | South Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0476 | -74.6726 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17793031 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17793031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17793031 | 17793031 | 17793031 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-010 | 52-010 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 3624 | 7398 | 7398-B01 | 1035 CONCESSION ST | RUSSELL | K4R1G7 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2637 | -75.3615 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1724855 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724855 | 1724855 | 1724855 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-011 | 52-011 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Notre Dame | Notre Dame Catholic Elementary and Secondary School | ELE/SEC | 3459 | 5088 | 5088-B01 | 157 MCKENZIE ST | CARLETON PLACE | K7C4P2 | 35-12-55-402 | Carleton Place | Carleton Place T | Lanark Co | LANARK | East | South | 45.143 | -76.1583 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 272 | - | - | N | - | Not Required | - | 6467017 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6613709 | 0 | 0 | 0 | 0 | 0 | 6613709 | 6613709 | 6509480 | -104229 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6613709
52-012 | 52-012 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Notre Dame | Notre Dame Catholic Elementary and Secondary School | ELE/SEC | 3459 | 5088 | 5088-B01 | 157 MCKENZIE ST | CARLETON PLACE | K7C4P2 | 35-12-55-402 | Carleton Place | Carleton Place T | Lanark Co | LANARK | East | South | 45.143 | -76.1583 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2835283 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2835283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2835283 | 2835283 | 2835283 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-013 | 52-013 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Our Lady of Good Counsel | Our Lady of Good Counsel Catholic Elementary School | ELE | 6085 | 8563 | 8563-B01 | 52 DICKINSON DR | INGLESIDE | K0C1M0 | 35-12-71-618 | South Stormont | South Stormont Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.001 | -74.9896 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1659368 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659368 | 1659368 | 1659368 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-015 | 52-015 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Our Lady of Good Counsel | Our Lady of Good Counsel Catholic Elementary School | ELE | 6085 | 8563 | 8563-B01 | 52 DICKINSON DR | INGLESIDE | K0C1M0 | 35-12-71-618 | South Stormont | South Stormont Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.001 | -74.9896 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 49 | - | - | N | - | Approved | 42451 | 1205503 | Construction Complete | Addition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292034 | 0 | 946004 | 0 | 0 | 0 | 0 | 0 | 1238038 | 1238038 | 1205503 | -32535 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 946004
52-018 | 52-018 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Andrew | St. Andrew Catholic Elementary School | ELE | 3716 | 7464 | 7464-B01 | 17283 COUNTY RD 18 | ST. ANDREW'S WEST | K0C2A0 | 35-12-71-618 | South Stormont | South Stormont Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0965 | -74.8003 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1380526 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380526 | 1380526 | 1380526 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-020 | 52-020 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Anne | St. Anne Catholic Elementary School | ELE | 3736 | 7480 | 7480-B01 | 607 SURGENOR ST | CORNWALL | K6J2H5 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0186 | -74.7685 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1666270 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666270 | 1666270 | 1666270 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-023 | 52-023 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Finnan's | St. Finnan's Catholic Elementary School | ELE | 3582 | 7362 | 7362-B01 | 220 MAIN ST N | ALEXANDRIA | K0C1A0 | 35-12-71-615 | North Glengarry | North Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.3051 | -74.632 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1290340 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1290340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1290340 | 1290340 | 1290340 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-024 | 52-024 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Francis Xavier | St. Francis Xavier Catholic Secondary School | SEC | 3596 | 5118 | 5118-B01 | 1235 RUSSELL RD | HAMMOND | K0A2A0 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.4214 | -75.21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3138671 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3138671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3138671 | 3138671 | 3138671 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-025 | 52-025 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Gregory | St. Gregory Catholic Elementary School | ELE | 10374 | 11085 | 11085-B01 | 176 TOWNLINE RD W | CARLETON PLACE | K7C3P7 | 35-12-55-402 | Carleton Place | Carleton Place T | Lanark Co | LANARK | East | South | 45.1395 | -76.1557 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5319980 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5319980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5319980 | 5319980 | 5319980 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-026 | 52-026 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Gregory | St. Gregory Catholic Elementary School | ELE | 10374 | 11085 | 11085-B01 | 176 TOWNLINE RD W | CARLETON PLACE | K7C3P7 | 35-12-55-402 | Carleton Place | Carleton Place T | Lanark Co | LANARK | East | South | 45.1395 | -76.1557 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 531759 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531759 | 531759 | 531759 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-028 | 52-028 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. James the Greater | St. James the Greater Catholic Elementary School | ELE | 10076 | 10385 | 10385-B01 | 5 CATHERINE ST | SMITHS FALLS | K7A3Z9 | 35-12-55-301 | Smiths Falls | Smiths Falls ST | Lanark Co | LANARK | East | South | 44.8929 | -76.0187 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2096237 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2096237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2096237 | 2096237 | 2096237 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-030 | 52-030 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. John | St. John Catholic Elementary School | ELE | 4053 | 3016 | 3016-B01 | 34 WILSON ST E | PERTH | K7H1L6 | 35-12-55-403 | Perth | Perth T | Lanark Co | LANARK | East | South | 44.8959 | -76.248 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1509689 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509689 | 1509689 | 1509689 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-031 | 52-031 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. John | St. John Catholic Secondary School | SEC | 4070 | 7737 | 7737-B01 | 2066 SCOTCH LINE RD RR 3 | PERTH | K7H3C5 | 35-12-55-403 | Perth | Perth T | Lanark Co | LANARK | East | South | 44.8861 | -76.2523 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1338766 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 1323766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1323766 | 1338766 | 1338766 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-032 | 52-032 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. John | St. John Catholic Secondary School | SEC | 4070 | 7737 | 7737-B01 | 2066 SCOTCH LINE RD RR 3 | PERTH | K7H3C5 | 35-12-55-403 | Perth | Perth T | Lanark Co | LANARK | East | South | 44.8861 | -76.2523 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2903621 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2903621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2903621 | 2903621 | 2903621 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-034 | 52-034 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Joseph | St. Joseph Catholic Elementary School | ELE | 3368 | 7211 | 7211-B01 | 80 COUNTY RD 1 | TOLEDO | K0E1Y0 | 35-12-56-622 | Elizabethtown-Kitley | Elizabethtown-Kitley Tp | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.7407 | -75.9986 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4909567 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 154500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154500 | 4418477 | 336590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4755067 | 4909567 | 4909567 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-035 | 52-035 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4134 | 7777 | 7777-B01 | 235 GEORGIANA ST | GANANOQUE | K7G1M9 | 35-12-56-301 | Gananoque | Gananoque ST | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.3342 | -76.1634 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3231318 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3231318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3231318 | 3231318 | 3231318 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-037 | 52-037 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Jude | St. Jude Catholic Elementary School | ELE | 3457 | 7272 | 7272-B01 | 5355 HIGHWAY 34 | VANKLEEK HILL | K0B1R0 | 35-12-67-613 | Champlain | Champlain Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5308 | -74.6455 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 451105 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451105 | 451105 | 451105 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-038 | 52-038 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Mark | St. Mark Catholic Elementary School | ELE | 11125 | 7779 | 7779-B01 | 420 MCAULEY RD RR 4 | PRESCOTT | K0E1T0 | 35-12-56-302 | Prescott | Prescott ST | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.723 | -75.5147 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8661014 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8661014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8661014 | 8661014 | 8661014 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-039 | 52-039 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Mary | St. Mary Catholic Secondary School | SEC | 4237 | 5201 | 5201-B01 | 40 CENTRAL AVE W | BROCKVILLE | K6V4N5 | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.5997 | -75.6959 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3560918 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49394 | 49394 | 3511524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3511524 | 3560918 | 3560918 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-040 | 52-040 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Mary-St. Cecilia | St. Mary-St. Cecilia Catholic Elementary School | ELE | 4278 | 7874 | 7874-B01 | 28 SHEA DR | MORRISBURG | K0C1X0 | 35-12-71-614 | South Dundas | South Dundas Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 44.8957 | -75.1876 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1697369 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697369 | 1697369 | 1697369 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-041 | 52-041 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Mary-St. Cecilia | St. Mary-St. Cecilia Catholic Elementary School | ELE | 4278 | 7874 | 7874-B01 | 28 SHEA DR | MORRISBURG | K0C1X0 | 35-12-71-614 | South Dundas | South Dundas Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 44.8957 | -75.1876 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 95 | - | - | N | - | Not Required | - | 1507265 | Construction Complete | Addition | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490407 | 0 | 1832613 | 0 | 0 | 0 | 0 | 0 | 2323020 | 2323020 | 1907265 | -415755 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1832613
52-042 | 52-042 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Michael | St. Michael Catholic Secondary School | SEC | 9822 | 5015 | 5015-B01 | 2755 HWY 43 | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0231 | -75.6508 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10690206 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10690206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10690206 | 10690206 | 10690206 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-043 | 52-043 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Michael | St. Michael Catholic Secondary School | SEC | 9822 | 5015 | 5015-B01 | 2755 HWY 43 | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0231 | -75.6508 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 214864 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214864 | 214864 | 214864 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-044 | 52-044 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Michael | St. Michael Catholic Secondary School | SEC | 9822 | 5015 | 5015-B01 | 2755 HWY 43 | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0231 | -75.6508 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8260902 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10613622 | 0 | 0 | 0 | 0 | 10613622 | 10613622 | 8260902 | -2352720 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-046 | 52-046 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 10455 | 11112 | 11112-B01 | 1211 RUSSELL RD S | RUSSELL | K4R1E5 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2514 | -75.3531 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12102888 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12102888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12102888 | 12102888 | 12102888 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-047 | 52-047 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Thomas Aquinas | St. Thomas Aquinas Catholic Secondary School | SEC | 10455 | 11112 | 11112-B01 | 1211 RUSSELL RD S | RUSSELL | K4R1E5 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2514 | -75.3531 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4276948 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5868439 | 0 | 0 | 0 | 0 | 5868439 | 5868439 | 4276948 | -1591491 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-048 | 52-048 | 52 | 219 - CMSM Lanark | 67172 | CDSB of Eastern Ontario | St. Francis de Sales | St. Francis de Sales Catholic Elementary School | ELE | 24588 | 7694 | 7694-B01 | 4 ROSS ST | SMITHS FALLS | K7A4L5 | 35-12-55-301 | Smiths Falls | Smiths Falls ST | Lanark Co | LANARK | East | South | 44.8856 | -76.0226 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 423 | 2 | 34 | Y | 5 | Approved | 43404 | 14467499 | Construction Complete | New Construction | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801630 | 0 | 9924928 | 0 | 1068840 | 2672101 | 0 | 0 | 14467499 | 14467499 | 14467499 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13665869
52-049 | 52-049 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Finnan's | St. Finnan's Catholic Elementary School | ELE | 3582 | 7362 | 7362-B01 | 220 MAIN ST N | ALEXANDRIA | K0C1A0 | 35-12-71-615 | North Glengarry | North Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.3051 | -74.632 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43941 | 262169 | Construction Complete | Addition | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 262169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262169 | 262169 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
52-050 | 52-050 | 52 | 235 - CMSM Leeds & Grenville | 67172 | CDSB of Eastern Ontario | St. Joseph | St. Joseph Catholic Elementary School | ELE | 4134 | 7777 | 7777-B01 | 235 GEORGIANA ST | GANANOQUE | K7G1M9 | 35-12-56-301 | Gananoque | Gananoque ST | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.3342 | -76.1634 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43941 | 2323773 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 122343 | 0 | 0 | 0 | 336000 | 0 | 0 | 0 | 0 | 458343 | 0 | 0 | 0 | 0 | 0 | 0 | 1865430 | 0 | 0 | 0 | 1865430 | 2323773 | 2323773 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1865430
52-051 | 52-051 | 52 | 219 - CMSM Lanark | 67172 | CDSB of Eastern Ontario | Holy Name of Mary | Holy Name of Mary Catholic Elementary School | ELE | 9677 | 10220 | 10220-B01 | 110 PATERSON ST | ALMONTE | K0A1A0 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.2309 | -76.1834 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 144 | 3 | 63 | Y | - | Approved | 43280 | 4858872 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3255609 | 0 | 1603263 | 0 | 0 | 0 | 4858872 | 4858872 | 4858872 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 4858872
52-052-01 | 52-052 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Joseph | St. Joseph Catholic Secondary School | SEC | 4086 | 5049 | 5049-B01 | 1500A CUMBERLAND ST | CORNWALL | K6J5V9 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0363 | -74.7506 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43433 | 4876094 | Construction Complete | Purchase | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4876094 | 0 | 0 | 0 | 0 | 0 | 4876094 | 4876094 | 5176094 | 300000 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4876094
52-052-02 | 52-052 | 52 | N/A | 67172 | CDSB of Eastern Ontario | St. Joseph | St. Joseph Catholic Secondary School | SEC | 4086 | 5049 | 5049-L01 | 1500A CUMBERLAND ST | CORNWALL | K6J5V9 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0363 | -74.7506 | 43213 | 2017-18 | 2018-19 | 43213 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43433 | 372206 | Construction Complete | Land Acquisition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372206 | 0 | 0 | 0 | 0 | 0 | 0 | 372206 | 372206 | 363000 | -9206 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 372206
52-053 | 52-053 | 52 | 236 - CMSM Prescott & Russell | 67172 | CDSB of Eastern Ontario | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 3624 | 7398 | 7398-B01 | 1035 CONCESSION ST | RUSSELL | K4R1G7 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2637 | -75.3615 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 1 | 24 | N | - | Approved | 44456 | 505794 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505794 | 0 | 0 | 0 | 505794 | 505794 | 505794 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 505794
52-054 | 52-054 | 52 | N/A | 67172 | CDSB of Eastern Ontario | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 3624 | 7398 | 7398-B01 | 1035 CONCESSION ST | RUSSELL | K4R1G7 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2637 | -75.3615 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3787976 | 0 | 0 | 0 | 0 | 0 | 3787976 | 3787976 | 3787976 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3787976
53-001 | 53-001 | 53 | N/A | 67180 | Ottawa CSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 10877 | 12036 | 12036-B01 | 570 WEST HUNT CLUB RD | NEPEAN | K2G3R4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3329 | -75.7282 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-002 | 53-002 | 53 | N/A | 67180 | Ottawa CSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 10877 | 12036 | 12036-B01 | 570 WEST HUNT CLUB RD | NEPEAN | K2G3R4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3329 | -75.7282 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11247664 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11081243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11081243 | 11081243 | 11238002 | 156759 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-003 | 53-003 | 53 | N/A | 67180 | Ottawa CSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 10877 | 12036 | 12036-B01 | 570 WEST HUNT CLUB RD | NEPEAN | K2G3R4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3329 | -75.7282 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 311910 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311910 | 311910 | 311910 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-004 | 53-004 | 53 | N/A | 67180 | Ottawa CSB | All Saints | All Saints Catholic Secondary School | SEC | 10129 | 10411 | 10411-B01 | 5115 KANATA AVE | KANATA | K2K3K5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3218 | -75.926 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 23467575 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59999 | 59999 | 23407576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23407576 | 23467575 | 23467575 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-005 | 53-005 | 53 | N/A | 67180 | Ottawa CSB | All Saints | All Saints Catholic Secondary School | SEC | 10129 | 10411 | 10411-B01 | 5115 KANATA AVE | KANATA | K2K3K5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3218 | -75.926 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6541871 | Construction Complete | Addition | Other | 2007-08 | 39326 | 26516 | 0 | 266193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292709 | 6249162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6249162 | 6541871 | 6541871 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-007 | 53-007 | 53 | N/A | 67180 | Ottawa CSB | Corpus Christi | Corpus Christi Catholic Elementary School | ELE | 3154 | 16804 | 16804-B01 | 798 LYON ST S | OTTAWA | K1S5H5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4015 | -75.6909 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 585694 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 60694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60694 | 0 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 585694 | 585694 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-009 | 53-009 | 53 | N/A | 67180 | Ottawa CSB | Guardian Angels | Guardian Angels Catholic Elementary School | ELE | 9784 | 10266 | 10266-B01 | 4 BAYWOOD DR | STITTSVILLE | K2S1K5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2501 | -75.9063 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4833982 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4833982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4833982 | 4833982 | 4833982 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-012 | 53-012 | 53 | N/A | 67180 | Ottawa CSB | Holy Family | Holy Family Catholic Elementary School | ELE | 3494 | 7293 | 7293-B01 | 245 OWL DR | OTTAWA | K1V9K3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3535 | -75.6637 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42482 | 663280 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254556 | 0 | 408724 | 0 | 0 | 0 | 0 | 0 | 663280 | 663280 | 663280 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 408724
53-014 | 53-014 | 53 | N/A | 67180 | Ottawa CSB | Holy Trinity | Holy Trinity Catholic Secondary School | SEC | 3366 | 5089 | 5089-B01 | 180 KATIMAVIK RD | KANATA | K2L4A7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3081 | -75.9023 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5271681 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 5170230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688 | 5170918 | 100763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100763 | 5271681 | 5271681 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-015 | 53-015 | 53 | N/A | 67180 | Ottawa CSB | St. Matthew | St. Matthew Catholic Secondary School | SEC | 3179 | 5093 | 5093-B01 | 6550 BILBERRY DR | ORLEANS | K1C2S9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4804 | -75.5324 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2750000 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 0 | 0 | 0 | 0 | 2750000 | 2750000 | 2750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-016 | 53-016 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | St. Isabel | St. Isabel Catholic Elementary School | ELE | 24529 | 19534 | 19534-B01 | 785 GOULBOURN FORCED RD | KANATA | K2T0N5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3382 | -75.9396 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 461 | 2 | 39 | N | - | Approved | 42887 | 10696618 | Construction Complete | New Construction | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272782 | 0 | 8405610 | 0 | 1018226 | 0 | 0 | 0 | 10696618 | 10696618 | 10696618 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9423836
53-017 | 53-017 | 53 | N/A | 67180 | Ottawa CSB | Monsignor Paul Baxter | Monsignor Paul Baxter Catholic Elementary School | ELE | 9782 | 10265 | 10265-B01 | 333 BEATRICE DR | NEPEAN | K2J4W1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2809 | -75.7287 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4766456 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4766456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4766456 | 4766456 | 4766456 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-019 | 53-019 | 53 | N/A | 67180 | Ottawa CSB | Mother Teresa | Mother Teresa Catholic Secondary School | SEC | 9543 | 5091 | 5091-B01 | 440 LONGFIELDS DR | NEPEAN | K2J4T1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2854 | -75.7391 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 18019834 | Construction Complete | New Construction | Other | 1998-99 | 36039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17992335 | 17992335 | 27499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27499 | 18019834 | 18019834 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-020 | 53-020 | 53 | N/A | 67180 | Ottawa CSB | Mother Teresa | Mother Teresa Catholic Secondary School | SEC | 9543 | 5091 | 5091-B01 | 440 LONGFIELDS DR | NEPEAN | K2J4T1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2854 | -75.7391 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5488180 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 5387770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5387770 | 100410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100410 | 5488180 | 5488180 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-021 | 53-021 | 53 | N/A | 67180 | Ottawa CSB | Notre Dame | Notre Dame Catholic Secondary School | SEC | 10285 | 7755 | 7755-B01 | 710 BROADVIEW AVE | OTTAWA | K2A2M2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3794 | -75.7558 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2089545 | Construction Complete | Addition | Other | 2002-03 | 37500 | 2089545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2089545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2089545 | 2089545 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-022 | 53-022 | 53 | N/A | 67180 | Ottawa CSB | OCSB Head Office | OCSB Head Office Facility Holding | HFA | 3178 | 7092 | 7092-B01 | 445 PLEASANT PARK RD | OTTAWA | K1H5M9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.394 | -75.6534 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 52041 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 0 | 52041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52041 | 52041 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-026 | 53-026 | 53 | N/A | 67180 | Ottawa CSB | Sacred Heart | Sacred Heart Catholic Secondary School | SEC | 9825 | 5063 | 5063-B01 | 5870 ABBOTT ST E | STITTSVILLE | K2S1X4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.264 | -75.9106 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 20714340 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2113000 | 2113000 | 18601340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18601340 | 20714340 | 20714340 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-027 | 53-027 | 53 | N/A | 67180 | Ottawa CSB | Sacred Heart | Sacred Heart Catholic Secondary School | SEC | 9825 | 5063 | 5063-B01 | 5870 ABBOTT ST E | STITTSVILLE | K2S1X4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.264 | -75.9106 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4072057 | Construction Complete | Addition | Other | 2003-04 | 37865 | 494580 | 0 | 1844093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61499 | 2400172 | 1671885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1671885 | 4072057 | 4072057 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-028 | 53-028 | 53 | N/A | 67180 | Ottawa CSB | St. Andrew | St. Andrew Catholic Elementary School | ELE | 10320 | 11015 | 11015-B01 | 201 CRESTWAY DR | NEPEAN | K2G6Z3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2851 | -75.7088 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5638086 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 10094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10094 | 5627992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5627992 | 5638086 | 5638086 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-029 | 53-029 | 53 | N/A | 67180 | Ottawa CSB | St. Anne | St. Anne Catholic Elementary School | ELE | 9781 | 10264 | 10264-B01 | 500 STONEHAVEN DR | KANATA | K2M2V6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.282 | -75.8447 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5021451 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5021451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5021451 | 5021451 | 5021451 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-030 | 53-030 | 53 | N/A | 67180 | Ottawa CSB | St. Benedict | St. Benedict Catholic Elementary School | ELE | 24425 | 19426 | 19426-B01 | 2525 RIVER MIST RD | NEPEAN | K2J5Z1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2423 | -75.7349 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 507 | - | - | N | - | Approved | 44651 | 9867655 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439776 | 0 | 8427879 | 0 | 0 | 0 | 0 | 0 | 9867655 | 9867655 | 9867655 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8427879
53-031 | 53-031 | 53 | N/A | 67180 | Ottawa CSB | St. Cecilia | St. Cecilia Catholic Elementary School | ELE | 18632 | 19086 | 19086-B01 | 3490 CAMBRIAN RD | NEPEAN | K2J0V1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2541 | -75.7324 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 9214000 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8254150 | 0 | 959850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9214000 | 9214000 | 9214000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-032 | 53-032 | 53 | N/A | 67180 | Ottawa CSB | St. Dominic | St. Dominic Catholic Elementary School | ELE | 24268 | 19260 | 19260-B01 | 2300 ESPRIT DR | ORLEANS | K4A0T5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4515 | -75.4704 | 41298 | 2012-13 | 2012-13 | - | - | - | 41298 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 507 | - | - | N | - | Not Required | - | 9908482 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4969388 | 0 | 959850 | 0 | 3979244 | 0 | 0 | 0 | 0 | 0 | 9908482 | 9908482 | 9908482 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3979244
53-035 | 53-035 | 53 | N/A | 67180 | Ottawa CSB | St. Emily | St. Emily Catholic Elementary School | ELE | 10893 | 12061 | 12061-B01 | 500 CHAPMAN MILLS DR | NEPEAN | K2J0J2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2722 | -75.7218 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7078785 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7078785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7078785 | 7078785 | 7078785 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-036 | 53-036 | 53 | N/A | 67180 | Ottawa CSB | St. Francis Xavier | St. Francis Xavier Catholic Secondary School | SEC | 11055 | 12185 | 12185-B01 | 3740 SPRATT RD | GLOUCESTER | K1V2M1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2898 | -75.6708 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 35957914 | Construction Complete | New Construction | Other | 2009-10 | 40057 | 2000000 | 0 | 1127544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 3927544 | 32030370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32030370 | 35957914 | 35957914 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-037 | 53-037 | 53 | N/A | 67180 | Ottawa CSB | St. Francis Xavier | St. Francis Xavier Catholic Secondary School | SEC | 11055 | 12185 | 12185-B01 | 3740 SPRATT RD | GLOUCESTER | K1V2M1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2898 | -75.6708 | 42317 | 2015-16 | 2015-16 | - | - | - | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 436 | - | - | N | - | Approved | 44651 | 7831599 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7831599 | 0 | 0 | 0 | 0 | 0 | 7831599 | 7831599 | 7831599 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7831599
53-038 | 53-038 | 53 | N/A | 67180 | Ottawa CSB | St. Gabriel | St. Gabriel Catholic Elementary School | ELE | 11326 | 12330 | 12330-B01 | 400 KEYROCK DR | KANATA | K2T0G6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3253 | -75.9297 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8668210 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7816961 | 0 | 851249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8668210 | 8668210 | 8668210 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-042 | 53-042 | 53 | N/A | 67180 | Ottawa CSB | St. Jerome | St. Jerome Catholic Elementary School | ELE | 10321 | 11067 | 11067-B01 | 4330 SPRATT RD | GLOUCESTER | K1V2A7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2767 | -75.6891 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6084401 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 5784401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5784401 | 6084401 | 6084401 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-045 | 53-045 | 53 | N/A | 67180 | Ottawa CSB | St. Joseph | St. Joseph Catholic Secondary School | SEC | 10127 | 10409 | 10409-B01 | 3333 GREENBANK RD | NEPEAN | K2J4J1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2625 | -75.7406 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24262296 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197013 | 197013 | 24065283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24065283 | 24262296 | 24262296 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-049 | 53-049 | 53 | N/A | 67180 | Ottawa CSB | St. Luke | St. Luke Catholic Elementary School | ELE | 4184 | 7813 | 7813-B01 | 2485 DWIGHT CRES | OTTAWA | K1G1C7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3948 | -75.6151 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 682111 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256000 | 0 | 0 | 426111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426111 | 682111 | 682111 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-050 | 53-050 | 53 | N/A | 67180 | Ottawa CSB | St. Mark | St. Mark Catholic Secondary School | SEC | 4573 | 5092 | 5092-B01 | 1040 DOZOIS RD | MANOTICK | K4M1B2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2444 | -75.6481 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2768081 | Construction Complete | Addition | Other | 2007-08 | 39326 | 2768081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2768081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2768081 | 2768081 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-051 | 53-051 | 53 | N/A | 67180 | Ottawa CSB | St. Martin de Porres | St. Martin de Porres Catholic Elementary School | ELE | 3238 | 7128 | 7128-B01 | 20 MCKITRICK DR | KANATA | K2L1T7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2929 | -75.8845 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 264446 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 264446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264446 | 264446 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-053 | 53-053 | 53 | N/A | 67180 | Ottawa CSB | LB Pearson | LB Pearson Catholic Secondary School | SEC | 3050 | 5090 | 5090-B01 | 2072 JASMINE CRES | GLOUCESTER | K1J8M5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4433 | -75.5958 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2750000 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750000 | 0 | 0 | 0 | 0 | 2750000 | 2750000 | 2750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-055 | 53-055 | 53 | N/A | 67180 | Ottawa CSB | St. Michael | St. Michael Catholic Elementary School | ELE | 3223 | 7118 | 7118-B01 | 159 KEDEY ST | FITZROY HARBOUR | K0A1X0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4715 | -76.216 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1692832 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351882 | 0 | 1340950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1692832 | 1692832 | 1692832 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-056 | 53-056 | 53 | N/A | 67180 | Ottawa CSB | St. Monica | St. Monica Catholic Elementary School | ELE | 4330 | 7912 | 7912-B01 | 2000 MERIVALE RD | NEPEAN | K2G1G6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.323 | -75.7178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 703763 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703763 | 703763 | 703763 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-057 | 53-057 | 53 | N/A | 67180 | Ottawa CSB | St. Monica | St. Monica Catholic Elementary School | ELE | 4330 | 7912 | 7912-B01 | 2000 MERIVALE RD | NEPEAN | K2G1G6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.323 | -75.7178 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 481282 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 19562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19562 | 0 | 0 | 461720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461720 | 481282 | 481282 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-058 | 53-058 | 53 | N/A | 67180 | Ottawa CSB | St. Patrick | St. Patrick Catholic Secondary School | SEC | 4153 | 7791 | 7791-B01 | 2525 ALTA VISTA DR | OTTAWA | K1V7T3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3779 | -75.66 | 42509 | 2015-16 | 2016-17 | - | - | - | 42509 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | 276 | - | - | N | - | Approved | 42874 | 7956731 | Construction Complete | Addition | Consolidation | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7956731 | 0 | 0 | 0 | 0 | 0 | 7956731 | 7956731 | 7956731 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7956731
53-059 | 53-059 | 53 | N/A | 67180 | Ottawa CSB | St. Paul | St. Paul Catholic Secondary School | SEC | 9994 | 5102 | 5102-B01 | 2675 DRAPER AVE | OTTAWA | K2H7A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3413 | -75.792 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5475664 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 5475664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5475664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5475664 | 5475664 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-060 | 53-060 | 53 | N/A | 67180 | Ottawa CSB | St. Peter | St. Peter Catholic Secondary School | SEC | 4398 | 5094 | 5094-B01 | 750 CHARLEMAGNE BLVD | ORLEANS | K4A3M4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4748 | -75.4774 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3793743 | Construction Complete | Addition | Other | 2003-04 | 37865 | 494839 | 0 | 1540664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74217 | 2109720 | 1684023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684023 | 3793743 | 3793743 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-061 | 53-061 | 53 | N/A | 67180 | Ottawa CSB | St. Philip | St. Philip Catholic Elementary School | ELE | 4418 | 7964 | 7964-B01 | 79 MAITLAND ST | RICHMOND | K0A2Z0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.1854 | -75.8363 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1413574 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 463574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463574 | 1413574 | 1413574 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-062 | 53-062 | 53 | N/A | 67180 | Ottawa CSB | St. Rita | St. Rita Catholic Elementary School | ELE | 5965 | 8507 | 8507-B01 | 1 INVERNESS AVE | NEPEAN | K2E6N6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3602 | -75.7111 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 308663 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 86000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000 | 0 | 0 | 222663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222663 | 308663 | 308663 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-063 | 53-063 | 53 | N/A | 67180 | Ottawa CSB | St. Stephen | St. Stephen Catholic Elementary School | ELE | 11053 | 12154 | 12154-B01 | 1145 STITTSVILLE MAIN ST | STITTSVILLE | K2S0M5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2753 | -75.9319 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7990184 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 754615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754615 | 7235569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7235569 | 7990184 | 7990184 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-064 | 53-064 | 53 | N/A | 67180 | Ottawa CSB | St. Theresa | St. Theresa Catholic Elementary School | ELE | 10125 | 10408 | 10408-B01 | 2000 PORTOBELLO BLVD | ORLEANS | K4A4M9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4636 | -75.4667 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5555097 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5555097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5555097 | 5555097 | 5555097 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
53-065 | 53-065 | 53 | N/A | 67180 | Ottawa CSB | Holy Redeemer | Holy Redeemer Catholic Elementary School | ELE | 3260 | 7140 | 7140-B01 | 75 MCCURDY DR | KANATA | K2L3W6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3034 | -75.9006 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 230 | - | - | N | - | Approved | 43207 | 5074349 | Construction Complete | Addition | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5074349 | 0 | 0 | 0 | 0 | 0 | 5074349 | 5074349 | 5074349 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5074349
53-066 | 53-066 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | Prince of Peace | Prince of Peace Catholic Elementary School | ELE | 3262 | 7141 | 7141-B01 | 1620 HEATHERINGTON RD | OTTAWA | K1V9P5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3738 | -75.6454 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259648 | 0 | 0 | 0 | 259648 | 259648 | 259648 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 259648
53-067 | 53-067 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | St. Luke | St. Luke Catholic Elementary School | ELE | 3379 | 7218 | 7218-B01 | 60 MOUNTSHANNON DR | NEPEAN | K2J4C2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2918 | -75.735 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519296 | 0 | 0 | 0 | 519296 | 519296 | 519296 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 519296
53-068 | 53-068 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | St. Elizabeth Ann Seton | St. Elizabeth Ann Seton Catholic Elementary School | ELE | 3045 | 6999 | 6999-B01 | 41 WEYBRIDGE DR | NEPEAN | K2J2Z8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2709 | -75.7687 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038592 | 0 | 0 | 0 | 1038592 | 1038592 | 0 | -1038592 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1038592
53-069 | 53-069 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | Chapel Hill | Chapel Hill Catholic Elementary School | ELE | 3122 | 7051 | 7051-B01 | 1534 FOREST VALLEY DR | ORLEANS | K1C6G9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4522 | -75.5407 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038592 | 0 | 0 | 0 | 1038592 | 1038592 | 0 | -1038592 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1038592
53-070 | 53-070 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 3226 | 7121 | 7121-B01 | 675 GARDENVALE RD | OTTAWA | K1K1C9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4345 | -75.6356 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778944 | 0 | 0 | 0 | 778944 | 778944 | 0 | -778944 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 778944
53-071 | 53-071 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | St. Dominic | St. Dominic Catholic Elementary School | ELE | 24268 | 19260 | 19260-B01 | 2300 ESPRIT DR | ORLEANS | K4A0T5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4515 | -75.4704 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038592 | 0 | 0 | 0 | 1038592 | 1038592 | 0 | -1038592 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1038592
53-072 | 53-072 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | St. Benedict | St. Benedict Catholic Elementary School | ELE | 24425 | 19426 | 19426-B01 | 2525 RIVER MIST RD | NEPEAN | K2J5Z1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2423 | -75.7349 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038592 | 0 | 0 | 0 | 1038592 | 1038592 | 0 | -1038592 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1038592
53-073 | 53-073 | 53 | N/A | 67180 | Ottawa CSB | St. Joseph | St. Joseph Catholic Secondary School | SEC | 10127 | 10409 | 10409-B01 | 3333 GREENBANK RD | NEPEAN | K2J4J1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2625 | -75.7406 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 650 | - | - | N | - | Approved | 44651 | 15770461 | Construction Complete | Addition | Accommodation Pressure | 2020-21 | 44305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14160837 | 0 | 0 | 0 | 0 | 0 | 14160837 | 14160837 | 14160837 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 14160837
53-074 | 53-074 | 53 | N/A | 67180 | Ottawa CSB | St. James | St. James Catholic Elementary School | ELE | 3088 | 7030 | 7030-B01 | 50 STONEHAVEN DR | KANATA | K2M2K6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2915 | -75.861 | 43921 | 2019-20 | 2019-20 | - | - | - | 43922 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | 138 | - | - | - | - | Approved | 44405 | 5303432 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44805 | 900000 | 910598 | 0 | 0 | 379100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2189698 | 0 | 0 | 0 | 0 | 2923358 | 0 | 0 | 0 | 0 | 0 | 2923358 | 5113056 | 5113056 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2923358
53-075 | 53-075 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | Fernbank | Fernbank Catholic Elementary School | ELE | 25048 | 20054 | 20054-B01 | 5505 FERNBANK RD | STITTSVILLE | K2S1B6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2834 | -75.912 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 507 | 2 | 39 | N | - | Approved | 45134 | 20253838 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 2637076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2637076 | 0 | 0 | 0 | 0 | 16288662 | 0 | 1328101 | 0 | 0 | 0 | 17616763 | 20253839 | 20253838 | -1 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 17616763
53-076 | 53-076 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | Barrhaven South | Barrhaven South Catholic Elementary School | ELE | 25550 | 20556 | 20556-B01 | 3387 BORRISOKANE RD | NEPEAN | K2J6K5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2587 | -75.7675 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 507 | 2 | 39 | N | - | Approved | 45134 | 20183615 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 2750806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750806 | 0 | 0 | 0 | 0 | 16105536 | 0 | 1327273 | 0 | 0 | 0 | 17432809 | 20183615 | 18148531 | -2035084 | - | No, Site to be acquired. Sign installation planned for October 1, 2021 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 17432809
53-077 | 53-077 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CSB | Findlay Creek | Findlay Creek Catholic Elementary School | ELE | TBD | TBD | TBD | KELLY FARM DR / FINDLAY CREEK DR | GLOUCESTER | TBD | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3178 | -75.6037 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 507 | 2 | 39 | N | - | Approved | 45134 | 22138668 | Approved | New Construction | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 2423900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2423900 | 0 | 0 | 0 | 0 | 18183653 | 0 | 1531115 | 0 | 0 | 0 | 19714768 | 22138668 | 23034346 | 895678 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19714768
53-078 | 53-078 | 53 | 207 - CMSM Ottawa | 67180 | Ottawa CDSB | Riverside South | Riverside South Catholic Elementary School | ELE | TBD | TBD | TBD | TBD | GLOUCESTER | K1V0Z6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 507 | 2 | 39 | N | - | Approved | 45134 | 21954714 | Planned | New Construction | Accommodation Pressure | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 2423900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2423900 | 0 | 0 | 0 | 0 | 17935598 | 0 | 1595216 | 0 | 0 | 0 | 19530814 | 21954714 | 21954714 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19530814
54-001 | 54-001 | 54 | N/A | 67199 | Renfrew County CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 18328 | 19069 | 19069-B01 | 499 PEMBROKE ST W | PEMBROKE | K8A5P1 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8244 | -77.1258 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-002 | 54-002 | 54 | N/A | 67199 | Renfrew County CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 18328 | 19069 | 19069-B01 | 499 PEMBROKE ST W | PEMBROKE | K8A5P1 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8244 | -77.1258 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 728793 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728793 | 728793 | 728793 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-003 | 54-003 | 54 | N/A | 67199 | Renfrew County CDSB | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18328 | 19069 | 19069-B01 | 499 PEMBROKE ST W | PEMBROKE | K8A5P1 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8244 | -77.1258 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 20720 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20720 | 20720 | 20720 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-004 | 54-004 | 54 | N/A | 67199 | Renfrew County CDSB | Bishop Smith | Bishop Smith Catholic Secondary School | SEC | 3065 | 5096 | 5096-B01 | 362 CARMODY ST | PEMBROKE | K8A4G2 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8187 | -77.1171 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1039182 | Construction Complete | Retrofit | Other | 2012-13 | 41153 | 0 | 0 | 0 | 1039182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1039182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1039182 | 1039182 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-005 | 54-005 | 54 | N/A | 67199 | Renfrew County CDSB | John XXIII | John XXIII Catholic Elementary School | ELE | 3356 | 7202 | 7202-B01 | 75 EDEY ST | ARNPRIOR | K7S1B9 | 35-12-69-401 | Arnprior | Arnprior T | Renfrew Co | RENFREW | East | South | 45.4295 | -76.3633 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1148285 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 372484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372484 | 0 | 0 | 775801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775801 | 1148285 | 1148285 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-006 | 54-006 | 54 | N/A | 67199 | Renfrew County CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 3543 | 7332 | 7332-B01 | 535 IRVING ST | PEMBROKE | K8A2V2 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.821 | -77.094 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1449937 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1449937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1449937 | 1449937 | 1449937 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-008 | 54-008 | 54 | N/A | 67199 | Renfrew County CDSB | Our Lady of Sorrows | Our Lady of Sorrows Catholic Elementary School | ELE | 10762 | 7343 | 7343-B01 | 19 MOHNS AVE | PETAWAWA | K8H2G7 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8978 | -77.2769 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5245082 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148598 | 1148598 | 4096484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4096484 | 5245082 | 5245082 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-009 | 54-009 | 54 | N/A | 67199 | Renfrew County CDSB | Our Lady of Sorrows | Our Lady of Sorrows Catholic Elementary School | ELE | 10762 | 7343 | 7343-B01 | 19 MOHNS AVE | PETAWAWA | K8H2G7 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8978 | -77.2769 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 831445 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 314244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314244 | 0 | 0 | 517201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517201 | 831445 | 831445 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-010 | 54-010 | 54 | N/A | 67199 | Renfrew County CDSB | St. Andrews | St. Andrews Catholic Elementary School | ELE | 3715 | 7463 | 7463-B01 | 35 CAMERON ST | KILLALOE | K0J2A0 | 35-12-69-633 | Killaloe, Hagarty and Richards | Killaloe, Hagarty and Richards Tp | Renfrew Co | RENFREW | East | South | 45.5571 | -77.4174 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 188 | - | - | N | - | Not Required | - | 582983 | Construction Complete | Retrofit | Consolidation | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582983 | 0 | 0 | 0 | 0 | 0 | 582983 | 582983 | 582983 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 582983
54-011 | 54-011 | 54 | N/A | 67199 | Renfrew County CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 3622 | 7396 | 7396-B01 | 18 REGALBUTO AVE | PETAWAWA | K8H1L3 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.9066 | -77.2702 | 41712 | 2013-14 | 2013-14 | - | - | - | 41712 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 259236 | Construction Complete | Demolition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 259236 | -40764 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 300000
54-012 | 54-012 | 54 | N/A | 67199 | Renfrew County CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 17382 | 19032 | 19032-B01 | 22 LEEDER LANE | PETAWAWA | K8H0B8 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8944 | -77.2567 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7323193 | Construction Complete | New Construction | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188447 | 1188447 | 6134746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6134746 | 7323193 | 7323193 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-013 | 54-013 | 54 | N/A | 67199 | Renfrew County CDSB | St. Francis of Assisi | St. Francis of Assisi Catholic Elementary School | ELE | 17382 | 19032 | 19032-B01 | 22 LEEDER LANE | PETAWAWA | K8H0B8 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8944 | -77.2567 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 98 | - | - | N | - | Not Required | - | 1477617 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517201 | 0 | 1871047 | 0 | 0 | 0 | 0 | 0 | 2388248 | 2388248 | 1477617 | -910631 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1871047
54-014 | 54-014 | 54 | N/A | 67199 | Renfrew County CDSB | St. Joseph's | St. Joseph's Catholic Secondary School | SEC | 4141 | 7782 | 7782-B01 | 835 FIRST ST | RENFREW | K7V4E1 | 35-12-69-404 | Renfrew | Renfrew T | Renfrew Co | RENFREW | East | South | 45.4649 | -76.671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3365793 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3358751 | 3358751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3358751 | 3358751 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-015 | 54-015 | 54 | N/A | 67199 | Renfrew County CDSB | St. Michael's | St. Michael's Catholic Elementary School | ELE | 4326 | 7910 | 7910-B01 | 5346 60 HWY | DOUGLAS | K0J1S0 | 35-12-69-631 | Admaston-Bromley | Admaston/Bromley Tp | Renfrew Co | RENFREW | East | South | 45.5147 | -76.9454 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 892095 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 374894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374894 | 0 | 0 | 517201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517201 | 892095 | 892095 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-016 | 54-016 | 54 | 223 - CMSM Renfrew | 67199 | Renfrew County CDSB | Our Lady of Lourdes | Our Lady of Lourdes Catholic Elementary School | ELE | 3543 | 7332 | 7332-B01 | 535 IRVING ST | PEMBROKE | K8A2V2 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.821 | -77.094 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Planned | - | 0 | Planned | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2117517 | 0 | 0 | 0 | 2117517 | 2117517 | 2117517 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 2117517
54-017 | 54-017 | 54 | 223 - CMSM Renfrew | 67199 | Renfrew County CDSB | St. John Bosco | St. John Bosco Catholic Elementary School | ELE | 4056 | 7725 | 7725-B01 | 99 PETER ST | BARRYS BAY | K0J1B0 | 35-12-69-634 | Madawaska Valley | Madawaska Valley Tp | Renfrew Co | RENFREW | East | South | 45.4911 | -77.6757 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43227 | 1606266 | Construction Complete | Retrofit | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606266 | 0 | 0 | 0 | 1606266 | 1606266 | 1606266 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1606266
54-018 | 54-018 | 54 | 223 - CMSM Renfrew | 67199 | Renfrew County CDSB | St. Joseph's | St. Joseph's Catholic Secondary School | SEC | 4141 | 7782 | 7782-B01 | 835 FIRST ST | RENFREW | K7V4E1 | 35-12-69-404 | Renfrew | Renfrew T | Renfrew Co | RENFREW | East | South | 45.4649 | -76.671 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 434 | 4 | 73 | Y | 1 | Approved | 44679 | 23490782 | Under Construction | Addition | Accommodation Pressure | 2023-24 | 45292 | 459875 | 0 | 0 | 3900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4359875 | 0 | 0 | 0 | 0 | 15217714 | 0 | 3378773 | 534421 | 0 | 0 | 19130908 | 23490783 | 23490782 | -1 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19130908
54-019 | 54-019 | 54 | N/A | 67199 | Renfrew County CDSB | St. Joseph's | St. Joseph's Catholic Elementary School | ELE | 11079 | 7782 | 7782-B01 | 835 FIRST ST | RENFREW | K7V4E1 | 35-12-69-404 | Renfrew | Renfrew T | Renfrew Co | RENFREW | East | South | 45.4649 | -76.671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7042 | 7042 | 7042 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
54-020 | 54-020 | 54 | N/A | 67199 | Renfrew County CDSB | Our Lady of Sorrows | Our Lady of Sorrows Catholic Elementary School | ELE | 10762 | 7343 | 7343-L01 | 19 MOHNS AVE | PETAWAWA | K8H2G7 | 35-12-69-405 | Petawawa | Petawawa T | Renfrew Co | RENFREW | East | South | 45.8978 | -77.2769 | 44679 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44679 | 130000 | Construction Complete | Land Acquisition | Other | 2021-22 | 44804 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | 130000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-001 | 55-001 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Unencumbered Capital Funding | Unencumbered Capital Funding | OFF-ADM | 15773 | 18087 | 18087-B01 | 151 DAIRY AVE | NAPANEE | K7R4B2 | 35-12-57-402 | Greater Napanee | Greater Napanee T | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.255 | -76.9491 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-002 | 55-002 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | FDK Projects | Full Day Kindergarten Projects | OFF-ADM | 15773 | 18087 | 18087-B01 | 151 DAIRY AVE | NAPANEE | K7R4B2 | 35-12-57-402 | Greater Napanee | Greater Napanee T | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.255 | -76.9491 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4131228 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4273466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4273466 | 4273466 | 4131228 | -142238 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-004 | 55-004 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Georges Vanier | Georges Vanier Catholic Elementary School | ELE | 9218 | 10051 | 10051-B01 | 100 TRACEY ST | BELLEVILLE | K8P2R8 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.184 | -77.4013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1058544 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058544 | 1058544 | 1058544 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-006 | 55-006 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Holy Rosary | Holy Rosary Catholic Elementary School | ELE | 9219 | 10052 | 10052-L01 | 10 PRINCE OF WALES DR | BELLEVILLE | K8P2T4 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1782 | -77.3845 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 138000 | Construction Complete | Land Acquisition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138000 | 138000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138000 | 138000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-009 | 55-009 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | John XXIII | John XXIII Catholic Elementary School | ELE | 3355 | 7201 | 7201-B01 | 736 HIGH GATE PARK DR | KINGSTON | K7M5Z9 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2465 | -76.6039 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1221100 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221100 | 1221100 | 1221100 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-011-01 | 55-011 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Francis Assisi | St. Francis Assisi Catholic Elementary School | ELE | 24448 | 7163 | 7163-B02 | 114 WILEY ST | KINGSTON | K7K5B5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2609 | -76.4907 | 41754 | 2013-14 | 2014-15 | - | - | - | 41754 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 363 | - | - | N | - | Approved | 42803 | 8576150 | Construction Complete | New Construction | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1373481 | 0 | 7202669 | 0 | 0 | 0 | 0 | 0 | 8576150 | 8576150 | 8576150 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7202669
55-011-03 | 55-011 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Holy Family | Holy Family Catholic Elementary School | ELE | 3293 | 7163 | 7163-B01 | 114 WILEY ST | KINGSTON | K7K5B5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.261 | -76.4898 | 42803 | 2016-17 | 2016-17 | - | - | - | 42803 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42803 | 405757 | Construction Complete | Demolition | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405757 | 0 | 0 | 0 | 0 | 0 | 405757 | 405757 | 405757 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 405757
55-012 | 55-012 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 3760 | 7497 | 7497-B01 | 1044 LANCASTER DR | KINGSTON | K7P2L6 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2559 | -76.5982 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 658082 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658082 | 658082 | 658082 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-013 | 55-013 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Mother Teresa | Mother Teresa Catholic Elementary School | ELE | 3760 | 7497 | 7497-B01 | 1044 LANCASTER DR | KINGSTON | K7P2L6 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2559 | -76.5982 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1151017 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 0 | 526017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526017 | 1151017 | 1151017 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-015 | 55-015 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 3206 | 7108 | 7108-B01 | 97 PARK CRES | AMHERSTVIEW | K7N1L7 | 35-12-57-612 | Loyalist | Loyalist Tp | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.2236 | -76.6406 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 69202 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69202 | 69202 | 69202 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-017 | 55-017 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Regiopolis-Notre Dame | Regiopolis-Notre Dame Catholic Secondary School | SEC | 3613 | 7387 | 7387-B01 | 130 RUSSELL ST | KINGSTON | K7K2E9 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2433 | -76.4939 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3400543 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400543 | 3400543 | 3400543 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-018 | 55-018 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | Sacred Heart | Sacred Heart Catholic Elementary School | ELE | 15291 | 10062 | 10062-B01 | 50 BURSTHALL ST | MARMORA | K0K2M0 | 35-12-51-626 | Marmora and Lake | Marmora and Lake M | Hastings Co | HASTINGS | East | South | 44.4812 | -77.6787 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4600019 | Construction Complete | New Construction | Condition | 2010-11 | 40422 | 280294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942305 | 1222599 | 3377420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3377420 | 4600019 | 4600019 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-019 | 55-019 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Gregory | St. Gregory Catholic Elementary School | ELE | 9227 | 10060 | 10060-B01 | 7 OWEN ST | PICTON | K0K2T0 | 35-12-68-000 | Prince Edward | Prince Edward Co | Prince Edward Co | PRINCE EDWARD | East | South | 44.0088 | -77.1326 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 335289 | Construction Complete | Addition | Other | 2012-13 | 41153 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 295289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295289 | 335289 | 335289 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-020 | 55-020 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 9221 | 10054 | 10054-B01 | 405 BRIDGE ST E | BELLEVILLE | K8N1P7 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.169 | -77.3584 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1297324 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1297324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1297324 | 1297324 | 1297324 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-022 | 55-022 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Marguerite Bourgeoys | St. Marguerite Bourgeoys Catholic Elementary School | ELE | 9437 | 10168 | 10168-B01 | 355 WATERLOO DR | KINGSTON | K7M8P5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2537 | -76.5534 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1176867 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176867 | 1176867 | 1176867 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-023 | 55-023 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Marguerite Bourgeoys | St. Marguerite Bourgeoys Catholic Elementary School | ELE | 9437 | 10168 | 10168-B01 | 355 WATERLOO DR | KINGSTON | K7M8P5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2537 | -76.5534 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 818474 | Construction Complete | Retrofit | Other | 2014-15 | 41883 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 518474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518474 | 818474 | 818474 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-024 | 55-024 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Martha | St. Martha Catholic Elementary School | ELE | 4224 | 7840 | 7840-B01 | 455 ST MARTHA ST | KINGSTON | K7K7C2 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2657 | -76.4467 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 124354 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124354 | 124354 | 124354 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-028 | 55-028 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Michael | St. Michael Catholic Elementary School | ELE | 9222 | 10055 | 10055-B02 | 273 CHURCH ST | BELLEVILLE | K8N3C7 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1677 | -77.3821 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10298706 | Construction Complete | New Construction | Other | 2011-12 | 40787 | 502703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467000 | 1969703 | 8329003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8329003 | 10298706 | 10298706 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-029 | 55-029 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 4381 | 7944 | 7944-B01 | 3889 WILTON RD | HARROWSMITH | K0H1V0 | 35-12-46-619 | South Frontenac | South Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 44.3998 | -76.67 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1479297 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1479297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1479297 | 1479297 | 1479297 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-030 | 55-030 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Patrick | St. Patrick Catholic Elementary School | ELE | 4381 | 7944 | 7944-B01 | 3889 WILTON RD | HARROWSMITH | K0H1V0 | 35-12-46-619 | South Frontenac | South Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 44.3998 | -76.67 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 69202 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69202 | 69202 | 69202 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-032 | 55-032 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Paul | St. Paul Catholic Secondary School | SEC | 9235 | 10068 | 10068-B01 | 15 TRIPP BLVD | TRENTON | K8V6M2 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.094 | -77.5981 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4437305 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2145582 | 1741113 | 550610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4437305 | 4437305 | 4437305 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-033 | 55-033 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Peter | St. Peter Facility Holding | HFA | 9224 | 10057 | 10057-B01 | 101 QUEEN ST | TRENTON | K8V4Y2 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.0999 | -77.5788 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6505746 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 210954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 252954 | 5793202 | 0 | 459590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6252792 | 6505746 | 6505746 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-034 | 55-034 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Theresa | St. Theresa Catholic Secondary School | SEC | 9236 | 10069 | 10069-B01 | 135 ADAM ST | BELLEVILLE | K8N5K3 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.1905 | -77.3819 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2519243 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2519243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2519243 | 2519243 | 2519243 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
55-036 | 55-036 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Martin of Tours | St. Martin of Tours Catholic Elementary School | ELE | 9233 | 10066 | 10066-B01 | 62 POST ST | WHITNEY | K0J2M0 | 35-13-85-601 | South Algonquin | South Algonquin Tp | Nipissing District | NIPISSING | Northeast | North | 45.4926 | -78.2335 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42828 | 1993036 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 446010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446010 | 0 | 0 | 0 | 0 | 1112355 | 0 | 0 | 0 | 0 | 0 | 1112355 | 1558365 | 1558365 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1112355
55-038 | 55-038 | 55 | 205 - CMSM Kingston | 67202 | Algonquin and Lakeshore CDSB | Kingston West | Kingston West Catholic Elementary School | ELE | 24851 | 19857 | 19857-B01 | 386 HOLDEN ST | KINGSTON | TBD | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2673 | -76.5897 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 481 | 4 | 73 | Y | 3 | Approved | 44516 | 20939736 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 2083438 | 0 | 2759268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4842706 | 0 | 0 | 1079932 | 0 | 10536599 | 0 | 2614496 | 1866003 | 0 | 0 | 16097030 | 20939736 | 20939736 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15017098
55-039-01 | 55-039 | 55 | 216 - CMSM Hastings | 67202 | Algonquin and Lakeshore CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 9221 | 10054 | 10054-B01 | 405 BRIDGE ST E | BELLEVILLE | K8N1P7 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.169 | -77.3584 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | 334 | 3 | 49 | Y | 2 | Approved | 44596 | 19766134 | Under Construction | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 4500000 | 0 | 1214248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5714248 | 0 | 0 | 0 | 0 | 10600448 | 0 | 2402763 | 1048675 | 0 | 0 | 14051886 | 19766134 | 19766134 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14051886
55-039-02 | 55-039 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Joseph | St. Joseph Catholic Elementary School | ELE | 9221 | 10054 | 10054-L01 | 405 BRIDGE ST E | BELLEVILLE | K8N1P7 | 35-12-51-103 | Belleville | Belleville C | Hastings Co | HASTINGS | East | South | 44.169 | -77.3584 | 43705 | 2018-19 | 2019-20 | 43705 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43705 | 875000 | Construction Complete | Land Acquisition | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875000 | 0 | 0 | 0 | 0 | 0 | 0 | 875000 | 875000 | 875000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 875000
55-040-01 | 55-040 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Gregory | St Gregory Catholic Elementary School | ELE | 25401 | 20407 | 20407-B01 | TBD | PICTON | TBD | 35-12-68-000 | Prince Edward | Prince Edward Co | Prince Edward Co | PRINCE EDWARD | East | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 354 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8736381 | 0 | 0 | 0 | 0 | 0 | 8736381 | 8736381 | 8736381 | 0 | - | No, Site to be acquired. Sign installation planned for August 1, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8736381
55-040-02 | 55-040 | 55 | N/A | 67202 | Algonquin and Lakeshore CDSB | St. Gregory | St Gregory Catholic Elementary School | ELE | 25401 | 20407 | 20407-B01 | TBD | PICTON | TBD | 35-12-68-000 | Prince Edward | Prince Edward Co | Prince Edward Co | PRINCE EDWARD | East | South | TBD | TBD | 44750 | 2021-22 | 2022-23 | 44750 | 2021-22 | 2022-23 | [17 empty] | Approved | 44750 | 4563400 | Planned | Land Acquisition | Accommodation Pressure | TBD | TBD | [16 empty] | 0 | 0 | 0 | 4563400 | 0 | 0 | 0 | 0 | 0 | 0 | 4563400 | 4563400 | 4563400 | 0 |  | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4563400
55-041 | 55-041 | 55 | 220 - CMSM Lennox & Addington | 67202 | Algonquin and Lakeshore CDSB | Our Lady of Mount Carmel | Our Lady of Mount Carmel Catholic Elementary School | ELE | 25526 | 7108 | 7108-B02 | 97 PARK CRES | AMHERSTVIEW | K7N1T1 | 35-12-57-612 | Loyalist | Loyalist Tp | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.2236 | -76.6406 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 449 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10427612 | 0 | 1684696 | 0 | 0 | 0 | 12112308 | 12112308 | 12112308 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12112308
55-042 | 55-042 | 55 | 220 - CMSM Lennox & Addington | 67202 | Algonquin and Lakeshore CDSB | JJ O'Neill | JJ O'Neill Catholic Elementary School | ELE | 3455 | 7271 | 7271-B01 | 240 MARILYN AVE | NAPANEE | K7R2L4 | 35-12-57-402 | Greater Napanee | Greater Napanee T | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.2473 | -76.9646 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 331 | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6966735 | 0 | 2933923 | 0 | 0 | 0 | 9900658 | 9900658 | 9900658 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9900658
56-001 | 56-001 | 56 | N/A | 28100 | CSP du Nord-Est | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 6375 | 8704 | 8704-B01 | 820 LAKESHORE DR | NORTH BAY | P1A2G8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.2658 | -79.4349 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-002 | 56-002 | 56 | N/A | 28100 | CSP du Nord-Est | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 6375 | 8704 | 8704-B01 | 820 LAKESHORE DR | NORTH BAY | P1A2G8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.2658 | -79.4349 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8762 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153077 | 153077 | 48560 | -104517 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-003 | 56-003 | 56 | N/A | 28100 | CSP du Nord-Est | Coeur du Nord | école élémentaire publique Coeur du Nord | ELE | 10692 | 8837 | 8837-B01 | 80 CEDAR ST | KAPUSKASING | P5N2B3 | 35-13-81-404 | Kapuskasing | Kapuskasing T | Cochrane District | COCHRANE | Northeast | North | 49.4205 | -82.4266 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6792409 | Construction Complete | New Construction | FL Capital Transitional | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3198573 | 3198573 | 3593836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3593836 | 6792409 | 6792409 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-004 | 56-004 | 56 | N/A | 28100 | CSP du Nord-Est | Coeur du Nord | école élémentaire publique Coeur du Nord | ELE | 10692 | 8837 | 8837-B01 | 80 CEDAR ST | KAPUSKASING | P5N2B3 | 35-13-81-404 | Kapuskasing | Kapuskasing T | Cochrane District | COCHRANE | Northeast | North | 49.4205 | -82.4266 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1081707 | Construction Complete | Addition | Accommodation Pressure | 2005-06 | 38596 | 138755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 498755 | 582952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582952 | 1081707 | 1081707 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-005 | 56-005 | 56 | N/A | 28100 | CSP du Nord-Est | Coeur du Nord | école élémentaire publique Coeur du Nord | ELE | 10692 | 8837 | 8837-B01 | 80 CEDAR ST | KAPUSKASING | P5N2B3 | 35-13-81-404 | Kapuskasing | Kapuskasing T | Cochrane District | COCHRANE | Northeast | North | 49.4205 | -82.4266 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 98 | - | - | N | - | Approved | 42205 | 4131248 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 81030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688168 | 0 | 0 | 769198 | 0 | 0 | 1376242 | 0 | 1865584 | 0 | 0 | 0 | 0 | 0 | 3241826 | 4011024 | 4011024 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1865584
56-006 | 56-006 | 56 | N/A | 28100 | CSP du Nord-Est | CSPNE Head Office | Administrative Office | OFF-ADM | 6375 | 8704 | 8704-B01 | 820 LAKESHORE DR | NORTH BAY | P1A2G8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.2658 | -79.4349 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2281831 | Construction Complete | Retrofit | Other | 2015-16 | 42248 | 0 | 0 | 0 | 505500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1776331 | 2281831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281831 | 2281831 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-007 | 56-007 | 56 | N/A | 28100 | CSP du Nord-Est | des Navigateurs | école élémentaire publique des Navigateurs | ELE | 10846 | 12018 | 12018-B01 | 39 HESSLE ST | NEW LISKEARD | P0J1P0 | 35-13-90-101 | Temiskaming Shores | Temiskaming Shores C | Timiskaming District | TIMISKAMING | Northeast | North | 47.5156 | -79.6735 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9122897 | Construction Complete | New Construction | FL Capital Transitional | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243616 | 243616 | 8879281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8879281 | 9122897 | 9122897 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-008 | 56-008 | 56 | N/A | 28100 | CSP du Nord-Est | Étoile du Nord | école élémentaire publique Étoile du Nord | ELE | 10080 | 6130 | 6130-B01 | 551 UNION ST | IROQUOIS FALLS | P0K1G0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7661 | -80.6937 | 40921 | 2011-12 | 2011-12 | - | - | - | 40921 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | 60 | - | - | N | - | Approved | 41487 | 4442403 | Construction Complete | Addition | Condition | 2015-16 | 42248 | 231724 | 0 | 0 | 0 | 0 | 183975 | 0 | 0 | 0 | 0 | 0 | 0 | 563620 | 0 | 0 | 979319 | 726137 | 1236947 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 3463084 | 4442403 | 4442403 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1500000
56-009 | 56-009 | 56 | N/A | 28100 | CSP du Nord-Est | Héritage | école élémentaire publique Héritage | ELE | 10847 | 12019 | 12019-B01 | 2345 CONNAUGHT AVE | NORTH BAY | P1B0A3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3284 | -79.4372 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10780515 | Construction Complete | New Construction | FL Capital Transitional | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3629327 | 3629327 | 7151188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7151188 | 10780515 | 10780515 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-010-01 | 56-010 | 56 | N/A | 28100 | CSP du Nord-Est | Jeunesse Active | école élémentaire publique Jeunesse Active | ELE | 6377 | 8706 | 8706-B01 | 130 LISGAR ST | STURGEON FALLS | P2B3H4 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.372 | -79.9409 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 61 | - | - | N | - | Approved | 41806 | 3504099 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 391900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391900 | 0 | 0 | 1111103 | 0 | 2001096 | 0 | 0 | 0 | 0 | 0 | 3112199 | 3504099 | 3504099 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2001096
56-010-02 | 56-010 | 56 | N/A | 28100 | CSP du Nord-Est | Jeunesse Active | école élémentaire publique Jeunesse Active | ELE | 6377 | 8706 | 8706-L01 | 130 LISGAR ST | STURGEON FALLS | P2B3H4 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.372 | -79.9409 | 41977 | 2014-15 | 2014-15 | 41977 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41977 | 55000 | Construction Complete | Land Acquisition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000 | 55000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 55000
56-011-01 | 56-011+60.1-014 | 56 | N/A | 28100 | CSP du Nord-Est | l'Alliance | école secondaire publique l'Alliance | SEC | 24454 | 12338 | 12338-B01 | 296 CAMBRIDGE AVE | IROQUOIS FALLS | P0K1E0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7624 | -80.6869 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 180 | - | - | N | - | Approved | 44189 | 9048830 | Construction Complete | New Construction | FL Capital Transitional | 2020-21 | 44075 | 0 | 0 | 657900 | 192983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1103992 | 0 | 0 | 1954875 | 0 | 0 | 0 | 0 | 7093955 | 0 | 0 | 0 | 0 | 0 | 7093955 | 9048830 | 9048830 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 7093955
56-011-02 | 56-011+60.1-014 | 56 | N/A | 28100 | CSP du Nord-Est | l'Alliance | école secondaire publique l'Alliance | SEC | 24454 | 12338 | 12338-L01 | 296 CAMBRIDGE AVE | IROQUOIS FALLS | P0K1E0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7624 | -80.6869 | 42292 | 2015-16 | 2015-16 | 42292 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42292 | 188355 | Construction Complete | Land Acquisition | FL Capital Transitional | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188355 | 0 | 0 | 0 | 0 | 0 | 0 | 188355 | 188355 | 188355 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 188355
56-012-01 | 56-012 | 56 | N/A | 28100 | CSP du Nord-Est | Lionel Gauthier | école élémentaire publique Lionel Gauthier | ELE | 24320 | 19312 | 19312-B01 | 145 ST. JEAN ST | TIMMINS | P4R0J7 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4775 | -81.3802 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 300 | - | - | N | - | Approved | 41785 | 10591048 | Construction Complete | New Construction | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 19179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735437 | 0 | 0 | 754616 | 0 | 0 | 1111103 | 0 | 8493179 | 0 | 0 | 0 | 0 | 0 | 9604282 | 10358898 | 10358898 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8493179
56-012-02 | 56-012 | 56 | N/A | 28100 | CSP du Nord-Est | Lionel Gauthier | école élémentaire publique Lionel Gauthier | ELE | 24320 | 19312 | 19312-L01 | 145 ST. JEAN ST | TIMMINS | P4R0J7 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4775 | -81.3802 | 40946 | 2011-12 | 2011-12 | 40946 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 40946 | 370000 | Construction Complete | Land Acquisition | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 370000 | 370000 | 370000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 370000
56-013 | 56-013 | 56 | N/A | 28100 | CSP du Nord-Est | l'Odyssée | école secondaire publique l'Odyssée | SEC | 10706 | 11266 | 11266-B01 | 480 NORMAN AVE | NORTH BAY | P1B0A8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3289 | -79.4352 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 14669338 | Construction Complete | New Construction | FL Capital Transitional | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 937574 | 937574 | 13731764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13731764 | 14669338 | 14669338 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-014 | 56-014 | 56 | N/A | 28100 | CSP du Nord-Est | Pavillon Héritage | école élémentaire publique Pavillon Héritage | ELE | 10449 | 8675 | 8675-B01 | 117 CHIPPEWA ST W | NORTH BAY | P1B6G3 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3151 | -79.4501 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1141609 | Construction Complete | Addition | Condition | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 753978 | 753978 | 0 | 387631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387631 | 1141609 | 1141609 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-015 | 56-015 | 56 | N/A | 28100 | CSP du Nord-Est | Renaissance | école secondaire publique Renaissance | SEC | 10142 | 10422 | 10422-B01 | 301 SHIRLEY ST N | TIMMINS | P4R1N5 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4776 | -81.3788 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 13398800 | Construction Complete | New Construction | FL Capital Transitional | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350060 | 1350060 | 12048740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12048740 | 13398800 | 13398800 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
56-016 | 56-016 | 56 | N/A | 28100 | CSP du Nord-Est | Lionel Gauthier | école élémentaire publique Lionel Gauthier | ELE | 24320 | 19312 | 19312-B01 | 145 ST. JEAN ST | TIMMINS | P4R0J7 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4775 | -81.3802 | 42971 | 2016-17 | 2017-18 | - | - | - | 42971 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 46 | - | - | N | - | Not Required | - | 949521 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 344990 | 1246531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1591521 | 0 | 0 | 0 | 0 | 232150 | 0 | 0 | 0 | 0 | 0 | 232150 | 1823671 | 1823671 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 232150
56-017 | 56-017 | 56 | N/A | 28100 | CSP du Nord-Est | Passeport Jeunesse | école élémentaire publique Passeport Jeunesse | ELE | 16239 | 17105 | 17105-B01 | 75 9TH ST | HEARST | P0L1N0 | 35-13-81-402 | Hearst | Hearst T | Cochrane District | COCHRANE | Northeast | North | 49.6839 | -83.6658 | 42887 | 2016-17 | 2017-18 | - | - | - | 42887 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42892 | 835689 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835689 | 0 | 0 | 0 | 0 | 0 | 835689 | 835689 | 835689 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 835689
56-018 | 56-018 | 56 | 302 - DSSAB Nipissing | 28100 | CSP du Nord-Est | l'Odyssée | école secondaire publique l'Odyssée | SEC | 10706 | 11266 | 11266-B01 | 480 NORMAN AVE | NORTH BAY | P1B0A8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3289 | -79.4352 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 34 | Y | - | Approved | 43342 | 1199926 | Construction Complete | Retrofit | Child Care | 2018-19 | 43494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199926 | 0 | 0 | 0 | 1199926 | 1199926 | 1199926 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1199926
56-019-01 | 56-019 | 56 | N/A | 28100 | CSP du Nord-Est | Passeport Jeunesse | école élémentaire publique Passeport Jeunesse | ELE | 16239 | 17105 | 17105-B01 | 75 9TH ST | HEARST | P0L1N0 | 35-13-81-402 | Hearst | Hearst T | Cochrane District | COCHRANE | Northeast | North | 49.6839 | -83.6658 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43677 | 1236879 | Construction Complete | Purchase | FL Capital Transitional | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236879 | 0 | 0 | 0 | 0 | 0 | 1236879 | 1236879 | 1236879 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1236879
56-019-02 | 56-019 | 56 | N/A | 28100 | CSP du Nord-Est | Passeport Jeunesse | école élémentaire publique Passeport Jeunesse | ELE | 16239 | 17105 | 17105-L01 | 75 9TH ST | HEARST | P0L1N0 | 35-13-81-402 | Hearst | Hearst T | Cochrane District | COCHRANE | Northeast | North | 49.6839 | -83.6658 | 43677 | 2018-19 | 2019-20 | 43677 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43677 | 635695 |  | Land Acquisition | FL Capital Transitional | 2019-20 | 43784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697695 | 0 | 0 | 0 | 0 | 0 | 0 | 697695 | 697695 | 697695 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 697695
56-020 | 56-019 | 56 | N/A | 28100 | CSP du Nord-Est | Passeport Jeunesse | école élémentaire publique Passeport Jeunesse | ELE | 16239 | 17105 | 17105-B01 | 75 9TH ST | HEARST | P0L1N0 | 35-13-81-402 | Hearst | Hearst T | Cochrane District | COCHRANE | Northeast | North | 49.6839 | -83.6658 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43727 | 3115553 | Construction Complete | Retrofit | FL Capital Transitional | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 1250000 | 0 | 0 | 0 | 0 | 1865553 | 0 | 0 | 0 | 0 | 0 | 1865553 | 3115553 | 3115553 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1865553
56-021 | 56-021 | 56 | N/A | 28100 | CSP du Nord-Est | Parry Sound | école secondaire publique Parry Sound | SEC | 25182 | 20171 | 20171-B01 | 70 JOSEPH ST | PARRY SOUND | P2A2G5 | 35-13-86-402 | Parry Sound | Parry Sound T | Parry Sound District | PARRY SOUND | Northeast | North | 45.3594 | -80.043 | 44335 | 2020-21 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | - | Other | Other | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-001 | 57-001 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 18295 | 5316 | 5316-B01 | 296 VAN HORNE ST | SUDBURY | P3B1H9 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4881 | -80.9867 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-002 | 57-002 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 18295 | 5316 | 5316-B01 | 296 VAN HORNE ST | SUDBURY | P3B1H9 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4881 | -80.9867 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 0 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98996 | 98996 | 98996 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-003 | 57-003 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Camille-Perron | école élémentaire publique Camille-Perron | ELE | 9946 | 5178 | 5178-B01 | 13 CHURCH ST | MARKSTAY | P0M2G0 | 35-13-88-412 | Markstay-Warren | Markstay-Warren M | Sudbury District | SUDBURY | Northeast | North | 46.4921 | -80.5445 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39882 | 4946096 | Construction Complete | Retrofit | Condition | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551072 | 0 | 390304 | 941376 | 4004720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4004720 | 4946096 | 4946096 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-004 | 57-004 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Cité-Supérieure | école secondaire publique Cité-Supérieure | SEC | 9559 | 5013 | 5013-B01 | 14 HEMLO DR | MARATHON | P0T2E0 | 35-14-89-403 | Marathon | Marathon T | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7171 | -86.3709 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2471471 | Construction Complete | Addition | FL Capital Transitional | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2471471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2471471 | 2471471 | 2471471 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-005 | 57-005 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | de la Découverte | école élémentaire publique de la Découverte | ELE | 10744 | 11961 | 11961-B01 | 1450 MAIN ST | VAL CARON | P3N1R8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6107 | -81.0012 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5226848 | Construction Complete | New Construction | FL Capital Transitional | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234531 | 1234531 | 3992317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3992317 | 5226848 | 5226848 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-006 | 57-006 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | de la Découverte | école élémentaire publique de la Découverte | ELE | 10744 | 11961 | 11961-B01 | 1450 MAIN ST | VAL CARON | P3N1R8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6107 | -81.0012 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1487805 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980000 | 0 | 0 | 507805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507805 | 1487805 | 1487805 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-007 | 57-007 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Écho-des-Rapides | école élémentaire publique Écho-des-Rapides | ELE | 11195 | 7837 | 7837-B01 | 145 HUGILL ST | SAULT STE. MARIE | P6A4E9 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5062 | -84.2906 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2158287 | Construction Complete | New Construction | FL Capital Transitional | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2158287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2158287 | 2158287 | 2158287 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-008 | 57-008 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Hélène-Gravel | école élémentaire publique Hélène-Gravel | ELE | 10279 | 5168 | 5168-B01 | 1412 STEPHEN ST | SUDBURY | P3E4L5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4608 | -81.0259 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 772286 | Construction Complete | New Construction | FL Capital Transitional | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 762286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762286 | 772286 | 772286 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-009 | 57-009 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Hélène-Gravel | école élémentaire publique Hélène-Gravel | ELE | 10279 | 5168 | 5168-B01 | 1412 STEPHEN ST | SUDBURY | P3E4L5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4608 | -81.0259 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1678284 | Construction Complete | Addition | Accommodation Pressure | 2007-08 | 39326 | 311501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311501 | 1366783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366783 | 1678284 | 1678284 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-010 | 57-010 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Hélène-Gravel | école élémentaire publique Hélène-Gravel | ELE | 10279 | 5168 | 5168-B01 | 1412 STEPHEN ST | SUDBURY | P3E4L5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4608 | -81.0259 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1717836 | Construction Complete | Addition | Child Care | 2012-13 | 41153 | 0 | 0 | 0 | 470130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509199 | 979329 | 0 | 0 | 738507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738507 | 1717836 | 1717836 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-011 | 57-011 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Jean-Éthier-Blais | école élémentaire publique Jean-Éthier-Blais | ELE | 10743 | 8459 | 8459-B01 | 2190 LASALLE BLVD | SUDBURY | P3A2A8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.523 | -80.9188 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4108735 | Construction Complete | New Construction | Condition | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3908735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3908735 | 4108735 | 4108735 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-012 | 57-012 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Jean-Éthier-Blais | école élémentaire publique Jean-Éthier-Blais | ELE | 10743 | 8459 | 8459-B01 | 2190 LASALLE BLVD | SUDBURY | P3A2A8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.523 | -80.9188 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1963632 | Construction Complete | Addition | Accommodation Pressure | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675428 | 675428 | 1288204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288204 | 1963632 | 1963632 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-013 | 57-013 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | l'Escalade | école élémentaire publique l'Escalade | ELE | 10745 | 11707 | 11707-B01 | 52 WINSTON RD | WAWA | P0S1K0 | 35-13-80-608 | Wawa | Wawa M | Algoma District | ALGOMA | Northeast | North | 47.9867 | -84.7744 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2080719 | Construction Complete | Purchase | FL Capital Transitional | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080719 | 2080719 | 2080719 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-014 | 57-014 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | l'Orée-des-Bois | école secondaire publique l'Orée-des-Bois | SEC | 10972 | 12117 | 12117-B01 | 159 DU PARC AVE | DUBREUIVILLE | P0S1B0 | 35-13-80-619 | Dubreuilville | Dubreuilville Tp | Algoma District | ALGOMA | Northeast | North | 48.3486 | -84.5477 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10861514 | Construction Complete | New Construction | FL Capital Transitional | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 9861514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9861514 | 10861514 | 10861514 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
57-015 | 57-015 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Cap sur l'Avenir | école secondaire publique Cap sur l'Avenir | SEC | 24587 | 19058 | 19058-B01 | 190 LARCH ST | SUDBURY | P3E1C5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4916 | -80.9901 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42884 | 1067838 | Construction Complete | Retrofit | Consolidation | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1067838 | 0 | 0 | 0 | 0 | 0 | 1067838 | 1067838 | 1067838 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1067838
57-016 | 02-028+57-016 | 57 | N/A | 28118 | CSP du Grand Nord de l'Ontario | Blind River | école élémentaire publique Blind River | ELE | 25138 | 19836 | 19836-B01 | 180 YOUNGFOX RD | BLIND RIVER | P0R1B0 | 35-13-80-401 | Blind River | Blind River T | Algoma District | ALGOMA | Northeast | North | 46.1833 | -82.9745 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 72 | - | - | - | - | Approved | 45203 | 5923948 | Planned | New Construction | FL Capital Transitional | 2024-25 | 45536 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 5423948 | 0 | 0 | 0 | 0 | 0 | 5423948 | 5923948 | 5923948 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5423948
57-017 | 57-017 | 57 | N/A | 28118 | CSP du Grand Nord de l’Ontario | Thunder Bay | école élémentaire publique Thunder Bay | ELE | TBD | TBD | TBD | TBD | THUNDER BAY | P7C1H2 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 257 | - | - | N | - | Planned | - | - | Planned | Purchase | FL Capital Transitional | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000 | 1100000 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1100000
58-001 | 58-001 | 58 | N/A | 66303 | CS Viamonde | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 9647 | 10186 | 10186-B01 | 116 CORNELIUS PKY | NORTH YORK | M6L2K5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7181 | -79.4755 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-002 | 58-002 | 58 | N/A | 66303 | CS Viamonde | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 9647 | 10186 | 10186-B01 | 116 CORNELIUS PKY | NORTH YORK | M6L2K5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7181 | -79.4755 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 5705906 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7068243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7068243 | 7068243 | 5539932 | -1528311 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-003 | 58-003 | 58 | N/A | 66303 | CS Viamonde | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 9647 | 10186 | 10186-B01 | 116 CORNELIUS PKY | NORTH YORK | M6L2K5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7181 | -79.4755 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2177962 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177962 | 2177962 | 2177962 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-004 | 58-004 | 58 | N/A | 66303 | CS Viamonde | Alexandre-Dumas | école élémentaire publique Alexandre-Dumas | ELE | 19493 | 9864 | 9864-B01 | 255 CORONATION DR | SCARBOROUGH | M1E2J3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7436 | -79.2387 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 350 | - | - | N | - | Approved | 42109 | 7868442 | Construction Complete | Purchase | FL Capital Transitional | 2013-14 | 41518 | 250000 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 950532 | 0 | 6317910 | 0 | 0 | 0 | 0 | 0 | 7268442 | 7868442 | 7868442 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6317910
58-005 | 58-005 | 58 | N/A | 66303 | CS Viamonde | de la Moraine | installation en banque de la Moraine | HFA | 9838 | 5101 | 5101-B01 | 13200 YONGE ST | RICHMOND HILL | L4E2T2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9495 | -79.4563 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 579761 | Construction Complete | FDK | FDK | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 53558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53558 | 0 | 0 | 472645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472645 | 526203 | 526203 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-006-01 | 58-006 | 58 | 234 - CMSM York | 66303 | CS Viamonde | de la Moraine | école élémentaire publique de la Moraine | ELE | 24569 | 5101 | 5101-B02 | 13200 YONGE ST | RICHMOND HILL | L4E2T2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9496 | -79.4564 | 42321 | 2015-16 | 2015-16 | - | - | - | 42321 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 259 | 3 | 49 | N | - | Approved | 43364 | 9968798 | Construction Complete | New Construction | Condition | 2019-20 | 43711 | 0 | 0 | 0 | 1544468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544468 | 0 | 0 | 504170 | 0 | 6437308 | 0 | 1482852 | 0 | 0 | 0 | 8424330 | 9968798 | 9968798 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7920160
58-006-03 | 58-006 | 58 | N/A | 66303 | CS Viamonde | de la Moraine | école élémentaire publique de la Moraine | HFA | 9838 | 5101 | 5101-B01 | 13200 YONGE ST | RICHMOND HILL | L4E2T2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.9495 | -79.4563 | 42815 | 2016-17 | 2016-17 | - | - | - | 42815 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42912 | 851051 | Construction Complete | Demolition | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851051 | 0 | 0 | 0 | 0 | 0 | 851051 | 851051 | 851051 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 851051
58-009 | 58-009 | 58 | N/A | 66303 | CS Viamonde | Bayview Nord-Centre Appian | école élémentaire publique Bayview Nord-Centre Appian | ELE | 24303 | 9905 | 9905-L01 | 44 APPIAN DR | NORTH YORK | M2J2P9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7858 | -79.3709 | 41606 | 2013-14 | 2013-14 | 41606 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41606 | 10754200 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10754200 | 0 | 0 | 0 | 0 | 0 | 0 | 10754200 | 10754200 | 10754200 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 10754200
58-010 | 58-010 | 58 | N/A | 66303 | CS Viamonde | Carrefour-des-jeunes | école élémentaire publique Carrefour-des-jeunes | ELE | 10710 | 11270 | 11270-B01 | 375 CENTRE ST N | BRAMPTON | L6V4N4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7071 | -79.7719 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5355000 | Construction Complete | New Construction | FL Capital Transitional | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355000 | 5355000 | 5355000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-012 | 58-012 | 58 | N/A | 66303 | CS Viamonde | Charles-Sauriol | école élémentaire publique Charles-Sauriol | ELE | 19832 | 7031 | 7031-B01 | 55 PELHAM AVE | TORONTO | M6N1A5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.668 | -79.4557 | 41074 | 2011-12 | 2012-13 | - | - | - | 41074 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41761 | 15726151 | Construction Complete | Purchase | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950532 | 0 | 14775619 | 0 | 0 | 0 | 0 | 0 | 15726151 | 15726151 | 15726151 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 14775619
58-013 | 58-013 | 58 | N/A | 66303 | CS Viamonde | Collège français | école secondaire publique Collège français | SEC | 9527 | 9387 | 9387-B02 | 90 CROATIA ST | TORONTO | M6H1K9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6581 | -79.438 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 727311 | Construction Complete | Retrofit | Condition | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 727311 | 0 | 0 | 0 | 0 | 0 | 727311 | 727311 | 727311 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 727311
58-014 | 58-014 | 58 | N/A | 66303 | CS Viamonde | CSV Head Office | Administrative Office | OFF-ADM | 9647 | 10186 | 10186-B01 | 116 CORNELIUS PKY | NORTH YORK | M6L2K5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7181 | -79.4755 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42520 | 3508626 | Construction Complete | Retrofit | Other | 2016-17 | 42614 | 0 | 0 | 0 | 3508626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3508626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3508626 | 3508626 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-015 | 58-015 | 58 | N/A | 66303 | CS Viamonde | des Quatre-Rivières | école élémentaire publique des Quatre-Rivières | ELE | 11114 | 12164 | 12164-B01 | 60 CENTURY DR | ORANGEVILLE | L9W3K4 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9021 | -80.1073 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3059883 | Construction Complete | New Construction | FL Capital Transitional | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3059883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3059883 | 3059883 | 3059883 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-016 | 58-016 | 58 | N/A | 66303 | CS Viamonde | du Chêne | école élémentaire publique du Chêne | ELE | 16622 | 6189 | 6189-B01 | 150 RIDGE DR | OAKVILLE | L6H1B8 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4606 | -79.6935 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 358 | - | - | N | - | Approved | 41631 | 7741159 | Construction Complete | Purchase | Accommodation Pressure | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259356 | 0 | 7258946 | 0 | 0 | 0 | 0 | 0 | 7518302 | 7518302 | 7518302 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7258946
58-017 | 58-017 | 58 | N/A | 66303 | CS Viamonde | Étienne-Brûlé | école secondaire publique Étienne-Brûlé | SEC | 8340 | 5120 | 5120-B01 | 300 BANBURY RD | NORTH YORK | M2L2V3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7524 | -79.3711 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 118397 | Construction Complete | Retrofit | Condition | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118397 | 118397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118397 | 118397 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-018 | 58-018 | 58 | N/A | 66303 | CS Viamonde | Micheline-Saint-Cyr | école élémentaire publique Micheline-Saint-Cyr | ELE | 18877 | 9582 | 9582-B01 | 85 FORTY FIRST ST | ETOBICOKE | M8W3P1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.59 | -79.544 | 40780 | 2010-11 | 2011-12 | - | - | - | 40780 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 200 | - | - | N | - | Not Required | - | 5762504 | Construction Complete | Purchase | FL Capital Transitional | 2017-18 | 42979 | 0 | 0 | 59689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475266 | 0 | 0 | 534955 | 0 | 0 | 475266 | 0 | 4752283 | 0 | 0 | 0 | 0 | 0 | 5227549 | 5762504 | 5762504 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4752283
58-019 | 58-019 | 58 | N/A | 66303 | CS Viamonde | Franco-Jeunesse | école secondaire publique Franco-Jeunesse | SEC | 9525 | 5019 | 5019-B01 | 940 MICHIGAN AVE | SARNIA | N7S2B1 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9991 | -82.3742 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 52034 | Construction Complete | Retrofit | Condition | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52034 | 52034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52034 | 52034 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-020 | 58-020+63-030 | 58 | N/A | 66303 | CS Viamonde | Franco-Jeunesse | école secondaire publique Franco-Jeunesse | SEC | 14361 | 5085 | 5085-B01 | 901 THE RAPIDS PKY | SARNIA | N7S6K2 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9947 | -82.3511 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40151 | 6191016 | Construction Complete | New Construction | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 106014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106014 | 6085002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6085002 | 6191016 | 6191016 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-021 | 58-021 | 58 | N/A | 66303 | CS Viamonde | Gabriel-Dumont | école secondaire publique Gabriel-Dumont | SEC | 14356 | 18002 | 18002-B01 | 2463 EVANS BLVD | LONDON | N6M0B1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9518 | -81.1716 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 293 | - | - | N | - | Approved | 39905 | 12962276 | Construction Complete | New Construction | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12593337 | 0 | 0 | 0 | 0 | 0 | 12593337 | 12593337 | 12593337 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 12593337
58-022 | 58-022 | 58 | N/A | 66303 | CS Viamonde | Gaétan-Gervais | école secondaire publique Gaétan-Gervais | SEC | 24370 | 19371 | 19371-B01 | 1075 MCCRANEY ST E | OAKVILLE | L6H1H9 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4648 | -79.7029 | 42321 | 2015-16 | 2015-16 | - | - | - | 42321 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 392 | - | - | N | - | Approved | 42321 | 18097892 | Construction Complete | New Construction | FL Capital Transitional | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5146310 | 0 | 0 | 0 | 12951582 | 0 | 0 | 0 | 0 | 0 | 18097892 | 18097892 | 18097892 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12951582
58-023 | 58-023 | 58 | N/A | 66303 | CS Viamonde | Hamilton | Hamilton | HLA | 24459 | 19462 | 19462-L0- | 125 RIFLE RANGE RD | HAMILTON | L8S3B7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2524 | -79.9281 | 42020 | 2014-15 | 2014-15 | 42020 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42140 | 6357555 | Construction Complete | Land Acquisition | Other | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6357555 | 0 | 0 | 0 | 0 | 0 | 0 | 6357555 | 6357555 | 6357555 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 6357555
58-026 | 58-026 | 58 | N/A | 66303 | CS Viamonde | Jeanne-Lajoie | école élémentaire publique Jeanne-Lajoie | ELE | 8338 | 5170 | 5170-B01 | 150 CARNFORTH RD | NORTH YORK | M4A2K7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7346 | -79.3213 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41712 | 1418561 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 581000 | 0 | 0 | 177355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758355 | 0 | 0 | 660206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660206 | 1418561 | 1418561 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-027 | 58-027 | 58 | N/A | 66303 | CS Viamonde | Jeunes sans frontières | école secondaire publique Jeunes sans frontières | SEC | 10773 | 11981 | 11981-B01 | 7585 FINANCIAL DR | BRAMPTON | L6Y5P4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.624 | -79.7588 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 24209168 | Construction Complete | New Construction | FL Capital Transitional | 2007-08 | 39326 | 0 | 0 | 1569629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3284460 | 4854089 | 19355079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19355079 | 24209168 | 24209168 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-028 | 58-028 | 58 | N/A | 66303 | CS Viamonde | Kitchener Sud | Kitchener Sud | HLA | 24185 | 19177 | 19177-L0- | QUINTE CRESCENT / MORRISON RD | KITCHENER | N2A3J2 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4314 | -80.4146 | 40995 | 2011-12 | 2011-12 | 40995 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40995 | 4500000 | Construction Complete | Land Acquisition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 4500000 | 4500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4500000
58-029 | 58-029 | 58 | N/A | 66303 | CS Viamonde | la Fontaine | école élémentaire publique la Fontaine | ELE | 9494 | 10179 | 10179-B01 | 10110 ISLINGTON AVE | KLEINBURG | L0J1C0 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8346 | -79.6211 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 526203 | Construction Complete | FDK | FDK | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 53558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53558 | 0 | 0 | 472645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472645 | 526203 | 526203 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-030 | 58-030 | 58 | N/A | 66303 | CS Viamonde | la Mosaïque | école élémentaire publique la Mosaïque | ELE | 11116 | 12165 | 12165-B01 | 80 QUEENSDALE AVE | EAST YORK | M4J1Y3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6871 | -79.3303 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11229614 | Construction Complete | New Construction | FL Capital Transitional | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11229614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11229614 | 11229614 | 11229614 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-032-01 | 58-032 | 58 | N/A | 66303 | CS Viamonde | la Pommeraie | école élémentaire publique la Pommeraie | ELE | 24285 | 19277 | 19277-B01 | 3500 SETTLEMENT TRAIL | LONDON | N6P0C3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9321 | -81.3054 | 42184 | 2014-15 | 2015-16 | - | - | - | 42184 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | 343 | - | - | N | - | Approved | 42184 | 8259613 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 878132 | 0 | 0 | 878132 | 0 | 0 | 988568 | 0 | 6392913 | 0 | 0 | 0 | 0 | 0 | 7381481 | 8259613 | 8259613 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6392913
58-032-02 | 58-032 | 58 | N/A | 66303 | CS Viamonde | la Pommeraie | école élémentaire publique la Pommeraie | ELE | 24285 | 19277 | 19277-L01 | 3500 SETTLEMENT TRAIL | LONDON | N6P0C3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9321 | -81.3054 | 41509 | 2012-13 | 2013-14 | 41509 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41509 | 2779954 | Construction Complete | Land Acquisition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2779954 | 0 | 0 | 0 | 0 | 0 | 0 | 2779954 | 2779954 | 2779954 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2779954
58-033 | 58-033 | 58 | N/A | 66303 | CS Viamonde | Laure-Rièse | école élémentaire publique Laure-Rièse | ELE | 14354 | 18001 | 18001-B01 | 339 ALTON TOWERS CIR | SCARBOROUGH | M1V4L3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8226 | -79.2771 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41038 | 14040855 | Construction Complete | New Construction | FL Capital Transitional | 2014-15 | 41883 | 0 | 0 | 1715318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540388 | 0 | 30641 | 2286347 | 11754508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11754508 | 14040855 | 14040855 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-034 | 58-034 | 58 | N/A | 66303 | CS Viamonde | l'Envolée | école élémentaire publique l'Envolée | ELE | 9496 | 5133 | 5133-B01 | 1799 OTTAWA ST | WINDSOR | N8Y1R4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3112 | -83.0075 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 214833 | Construction Complete | FDK | FDK | 2011-12 | 40787 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 164833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164833 | 214833 | 214833 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-038 | 58-038 | 58 | N/A | 66303 | CS Viamonde | Louise-Charron | école élémentaire publique Louise-Charron | ELE | 24286 | 6389 | 6389-B01 | 2520 CABANA RD W | WINDSOR | N9G1E5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2537 | -83.0332 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 117 | - | - | N | - | Approved | 41806 | 4572656 | Construction Complete | Purchase | FL Capital Transitional | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244622 | 0 | 0 | 244622 | 0 | 0 | 0 | 0 | 4328034 | 0 | 0 | 0 | 0 | 0 | 4328034 | 4572656 | 4572656 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4328034
58-039 | 58-039 | 58 | N/A | 66303 | CS Viamonde | Marie-Curie | école élémentaire publique Marie-Curie | ELE | 7862 | 8943 | 8943-B01 | 40 HUNT CLUB DR | LONDON | N6H3Y3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9748 | -81.3282 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2150775 | Construction Complete | Addition | Accommodation Pressure | 2012-13 | 41153 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 1750775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750775 | 2150775 | 2150775 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-040 | 58-040 | 58 | N/A | 66303 | CS Viamonde | Markham Est | Markham Est | HLA | 24553 | 19558 | 19558-L0- | 228 COUNTRY GLEN RD | MARKHAM | L6B1B5 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.8922 | -79.2359 | 42453 | 2015-16 | 2015-16 | 42453 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42453 | 12277000 | Construction Complete | Land Acquisition | Other | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12277000 | 0 | 0 | 0 | 0 | 0 | 0 | 12277000 | 12277000 | 12277000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 12277000
58-041 | 58-041 | 58 | N/A | 66303 | CS Viamonde | Mathieu-da-Costa | école élémentaire publique Mathieu-da-Costa | ELE | 9529 | 10186 | 10186-B01 | 116 CORNELIUS PKY | NORTH YORK | M6L2K5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7181 | -79.4755 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3005614 | Construction Complete | Retrofit | Condition | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 2600614 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755614 | 3005614 | 3005614 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-042 | 58-042 | 58 | N/A | 66303 | CS Viamonde | Lamothe-Cadillac | école secondaire publique Lamothe-Cadillac | SEC | 10772 | 11980 | 11980-B01 | 1775 TOTTEN ST | WINDSOR | N9B1X4 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2892 | -83.0469 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 16633700 | Construction Complete | New Construction | FL Capital Transitional | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4458117 | 4458117 | 12175583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12175583 | 16633700 | 16633700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-043-01 | 58-043 | 58 | 230 - CMSM Halton | 66303 | CS Viamonde | Dyane-Adam | école élémentaire publique Dyane-Adam | ELE | 24460 | 19463 | 19463-B01 | 500 CEDAR HEDGE RD | MILTON | L9T6J4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5266 | -79.8434 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 354 | 3 | 49 | Y | 1 | Approved | 43404 | 10134298 | Construction Complete | New Construction | FL Capital Transitional | 2019-20 | 43711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771378 | 0 | 7305905 | 0 | 1542761 | 514254 | 0 | 0 | 10134298 | 10134298 | 10134298 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9362920
58-043-02 | 58-043 | 58 | N/A | 66303 | CS Viamonde | Dyane-Adam | école élémentaire publique Dyane-Adam | ELE | 24460 | 19463 | 19463-L01 | 500 CEDAR HEDGE RD | MILTON | L9T6J4 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5266 | -79.8434 | 42062 | 2014-15 | 2014-15 | 42062 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42062 | 6768000 | Construction Complete | Land Acquisition | FL Capital Transitional | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6768000 | 0 | 0 | 0 | 0 | 0 | 0 | 6768000 | 6768000 | 6768000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 6768000
58-044-01 | 58-044 | 58 | 232 - CMSM Peel | 66303 | CS Viamonde | le Flambeau | école élémentaire publique le Flambeau | ELE | 24284 | 19276 | 19276-B01 | 600 NOVO STAR DR | MISSISSAUGA | L5W1G4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6322 | -79.7153 | 42279 | 2015-16 | 2015-16 | - | - | - | 42279 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 366 | 3 | 49 | N | - | Approved | 42633 | 10555754 | Construction Complete | New Construction | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 558489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659199 | 0 | 0 | 1217688 | 0 | 0 | 988568 | 0 | 7554920 | 0 | 794578 | 0 | 0 | 0 | 9338066 | 10555754 | 10555754 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 8349498
58-044-02 | 58-044 | 58 | N/A | 66303 | CS Viamonde | le Flambeau | école élémentaire publique le Flambeau | ELE | 24284 | 19276 | 19276-L01 | 600 NOVO STAR DR | MISSISSAUGA | L5W1G4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6322 | -79.7153 | 41379 | 2012-13 | 2013-14 | 41379 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41379 | 7266475 | Construction Complete | Land Acquisition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7266475 | 0 | 0 | 0 | 0 | 0 | 0 | 7266475 | 7266475 | 7266475 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 7266475
58-045 | 58-045 | 58 | N/A | 66303 | CS Viamonde | Norval-Morrisseau | école secondaire publique Norval-Morrisseau | SEC | 10845 | 5146 | 5146-B01 | 51 WRIGHT ST | RICHMOND HILL | L4C4A2 | 35-11-27-404 | Richmond Hill | Richmond Hill T | York R | YORK | GTA | South | 43.8776 | -79.4415 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 432 | - | - | N | - | Not Required | - | 16253726 | Construction Complete | New Construction | FL Capital Transitional | 2012-13 | 41156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12253726 | 4000000 | 0 | 0 | 0 | 0 | 16253726 | 16253726 | 16253726 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 12253726
58-049 | 58-049 | 58 | N/A | 66303 | CS Viamonde | Pierre-Elliott-Trudeau | école élémentaire publique Pierre-Elliott-Trudeau | ELE | 9913 | 5057 | 5057-B01 | 65 GRACE ST | TORONTO | M6J2S4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6521 | -79.4143 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4429251 | Construction Complete | New Construction | FL Capital Transitional | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26251 | 26251 | 4403000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4403000 | 4429251 | 4429251 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-051 | 58-051 | 58 | N/A | 66303 | CS Viamonde | Renaissance | école élémentaire publique Renaissance | ELE | 9488 | 5127 | 5127-B01 | 1226 LOCKHART RD | BURLINGTON | L7S1H1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3208 | -79.8075 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 495 | - | - | N | - | Approved | 41712 | 552224 | Construction Complete | Addition | FL Capital Transitional | 2014-15 | 41883 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 0 | 0 | 377224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377224 | 552224 | 552224 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-052 | 58-052 | 58 | N/A | 66303 | CS Viamonde | Roméo Dallaire | école secondaire publique Roméo Dallaire | SEC | 10774 | 11982 | 11982-B01 | 736 ESSA RD | BARRIE | L4N9E9 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3261 | -79.7158 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39605 | 17329491 | Construction Complete | New Construction | FL Capital Transitional | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3557806 | 3557806 | 13771685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13771685 | 17329491 | 17329491 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
58-053 | 58-053 | 58 | N/A | 66303 | CS Viamonde | Ronald-Marion | école élémentaire et secondaire publique Ronald-Marion | ELE/SEC | 14359-14357-24221 | 18004 | 18004-B01 | 2235 BROCK RD | PICKERING | L1V2P8 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8606 | -79.0789 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 569 | - | - | N | - | Approved | 39905 | 23136031 | Construction Complete | New Construction | FL Capital Transitional | 2013-14 | 41520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637263 | 0 | 0 | 637263 | 0 | 0 | 0 | 0 | 22498768 | 0 | 0 | 0 | 0 | 0 | 22498768 | 23136031 | 23136031 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 22498768
58-055 | 58-055+64-061 | 58 | N/A | 66303 | CS Viamonde | Toronto Ouest | école secondaire publique Toronto Ouest | SEC | 18880 | 9511 | 9511-B01 | 330 LANSDOWNE AVE | TORONTO | M6H3Y1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6533 | -79.441 | 40774 | 2010-11 | 2011-12 | - | - | - | 40774 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 495 | - | - | N | - | Approved | 41806 | 23510640 | Construction Complete | Purchase | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23510640 | 0 | 0 | 0 | 0 | 0 | 23510640 | 23510640 | 23510640 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 23510640
58-056-01 | 58-056 | 58 | N/A | 66303 | CS Viamonde | David-Saint-Jacques | école secondaire publique David-Saint-Jacques | SEC | 24458 | 6979 | 6979-B02 | 80 BURLINGTON DR | KITCHENER | N2B1T5 | 35-15-25-103 | Kitchener | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4314 | -80.4146 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 323 | - | - | N | - | Approved | 43454 |  | Construction Complete | New Construction | FL Capital Transitional | 2019-20 | 43709 | 0 | 0 | 0 | 2856897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856897 | 0 | 0 | 0 | 0 | 10481931 | 0 | 0 | 0 | 0 | 0 | 10481931 | 13338828 | 13338828 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 10481931
58-056-02 | 58-056 | 58 | N/A | 66303 | CS Viamonde | David-Saint-Jacques | école secondaire publique David-Saint-Jacques | SEC | 24458 | 6979 | 6979-L02 | 80 BURLINGTON DR | KITCHENER | N2B1T5 | 35-15-25-103 | Kitchener | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4314 | -80.4146 | 43145 | 2017-18 | 2017-18 | 43145 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43454 |  | Construction Complete | Land Acquisition | FL Capital Transitional | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6263500 | 0 | 0 | 0 | 0 | 0 | 0 | 6263500 | 6263500 | 6263500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 6263500
58-057-01 | 58-057 | 58 | 231 - CMSM Niagara | 66303 | CS Viamonde | Franco-Niagara | école élémentaire et secondaire publique Franco-Niagara | ELE/SEC | 24462 | 5099 | 5099-B02 | 670 TANGUAY AVE | WELLAND | L3B4G2 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.9892 | -79.2245 | 42279 | 2015-16 | 2015-16 | - | - | - | 42279 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | 43214 | 2017-18 | 2018-19 | 375 | 3 | 49 | N | - | Approved | 43214 | 15728410 | Construction Complete | New Construction | Consolidation | 2019-20 | 43913 | 0 | 0 | 0 | 873023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678975 | 0 | 0 | 1551998 | 0 | 0 | 494285 | 0 | 11870550 | 0 | 818415 | 0 | 993162 | 0 | 14176412 | 15728410 | 15728410 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13682127
58-057-03 | 58-057 | 58 | N/A | 66303 | CS Viamonde | Confédération | école secondaire publique Confédération | SEC | 5343 | 5099 | 5099-B01 | 670 TANGUAY AVE | WELLAND | L3B4G2 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.9892 | -79.2245 | 43214 | 2017-18 | 2018-19 | - | - | - | 43214 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43214 | 2745130 | Construction Complete | Demolition | Consolidation | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2745130 | 0 | 0 | 0 | 0 | 0 | 2745130 | 2745130 | 2745130 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2745130
58-058 | 58-058 | 58 | 229 - CMSM Durham | 66303 | CS Viamonde | Viola-Léger | école élémentaire publique Viola-Léger | ELE | 24574 | 6396 | 6396-B01 | 116 ONTARIO ST | BOWMANVILLE | L1C2T4 | 35-11-10-402 | Clarington | Clarington M | Durham R | DURHAM | GTA | South | 43.9065 | -78.6809 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 210 | 3 | 49 | Y | 1 | Approved | 43222 | 5675204 | Construction Complete | Purchase | FL Capital Transitional | 2018-19 | 43344 | 194996 | 1000000 | 1730378 | 0 | 0 | 0 | 0 | 155004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080378 | 0 | 0 | 400000 | 0 | 1156235 | 0 | 778943 | 259648 | 0 | 0 | 2594826 | 5675204 | 5675204 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 2194826
58-059-01 | 58-059+64-078 | 58 | N/A | 66303 | CS Viamonde | Georges-P-Vanier | école secondaire publique Georges-P-Vanier | SEC | 24602-24603 | 19535 | 19535-B01 | 36 BROUGHTON AVE | HAMILTON | L8W3S5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1901 | -79.8518 | 42933 | 2016-17 | 2017-18 | - | - | - | 42933 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 400 | - | - | N | - | Planned | - | 0 | Planned | New Construction | Consolidation | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13257763 | 0 | 0 | 0 | 0 | 0 | 13257763 | 13257763 | 13257763 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13257763
58-059-02 | 58-059+64-078 | 58 | N/A | 66303 | CS Viamonde | Georges-P-Vanier | école secondaire publique Georges-P-Vanier | SEC | 24602-24603 | 19535 | 19535-L01 | 36 BROUGHTON AVE | HAMILTON | L8W3S5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1901 | -79.8518 | 42723 | 2016-17 | 2016-17 | 42723 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42723 | 2987172 | Construction Complete | Land Acquisition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2987172 | 0 | 0 | 0 | 0 | 0 | 0 | 2987172 | 2987172 | 2987172 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2987172
58-060 | 58-060 | 58 | 211 - CMSM Toronto | 66303 | CS Viamonde | Alexandre-Dumas | école élémentaire publique Alexandre-Dumas | ELE | 19493 | 9864 | 9864-B01 | 255 CORONATION DR | SCARBOROUGH | M1E2J3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7436 | -79.2387 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257127 | 0 | 0 | 0 | 257127 | 257127 | 0 | -257127 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 257127
58-061 | 58-061 | 58 | 211 - CMSM Toronto | 66303 | CS Viamonde | Charles-Sauriol | école élémentaire publique Charles-Sauriol | ELE | 19832 | 7031 | 7031-B01 | 55 PELHAM AVE | TORONTO | M6N1A5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.668 | -79.4557 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Approved | 42887 | 529378 | Construction Complete | Addition | Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529378 | 0 | 0 | 0 | 529378 | 529378 | 529378 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 529378
58-062 | 58-062 | 58 | 234 - CMSM York | 66303 | CS Viamonde | la Fontaine | école élémentaire publique la Fontaine | ELE | 9494 | 10179 | 10179-B01 | 10110 ISLINGTON AVE | KLEINBURG | L0J1C0 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8346 | -79.6211 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 3 | 49 | Y | 1 | Approved | 43980 | 3521962 | Construction Complete | Addition | Child Care | 2021-22 | 44470 | 475600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533852 | 0 | 0 | 2009452 | 0 | 0 | 0 | 0 | 0 | 0 | 1512510 | 0 | 0 | 0 | 1512510 | 3521962 | 3521962 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1512510
58-063 | 58-063 | 58 | 230 - CMSM Halton | 66303 | CS Viamonde | Patricia-Picknell | école élémentaire publique Patricia-Picknell | ELE | 9491 | 5165 | 5165-B01 | 1257 SEDGEWICK CRES | OAKVILLE | L6L1X5 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4159 | -79.6968 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2021-22 | 44470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257127 | 0 | 0 | 0 | 257127 | 257127 | 257127 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 257127
58-064 | 58-064 | 58 | 231 - CMSM Niagara | 66303 | CS Viamonde | LaMarsh | école élémentaire publique LaMarsh | ELE | 697 | 5759 | 5759-B01 | 4751 DRUMMOND RD | NIAGARA FALLS | L2E6C8 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.106 | -79.0992 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 42912 | 259648 | Construction Complete | Addition | Child Care | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259648 | 0 | 0 | 0 | 259648 | 259648 | 259648 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 259648
58-066 | 58-066 | 58 | 211 - CMSM Toronto | 66303 | CS Viamonde | Félix-Leclerc | école élémentaire publique Félix-Leclerc | ELE | 8337 | 9372 | 9372-B01 | 50 CELESTINE DR | ETOBICOKE | M9R3N3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6899 | -79.5615 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44918 | 3762273 | Under Construction | Addition | Child Care | 2022-23 | 44929 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932260 | 0 | 0 | 1432260 | 0 | 0 | 0 | 0 | 0 | 0 | 2330013 | 0 | 0 | 0 | 2330013 | 3762273 | 3762273 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2330013
58-067 | 58-067 | 58 | 231 - CMSM Niagara | 66303 | CS Viamonde | l'Héritage | école élémentaire publique l'Héritage | ELE | 9497 | 10180 | 10180-B01 | 35 PRINCE CHARLES DR | ST CATHARINES | L2N3Y8 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1959 | -79.2492 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43902 | 1956213 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 413451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413451 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 1956213 | 1956213 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
58-068 | 58-068 | 58 | 211 - CMSM Toronto | 66303 | CS Viamonde | Mathieu-da-Costa | école élémentaire publique Mathieu-da-Costa | ELE | 9529 | 10186 | 10186-B01 | 116 CORNELIUS PKY | NORTH YORK | M6L2K5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7181 | -79.4755 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44344 | 3008102 | Construction Complete | Addition | Child Care | 2021-22 | 44564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465340 | 0 | 0 | 1465340 | 0 | 0 | 0 | 0 | 0 | 0 | 1542762 | 0 | 0 | 0 | 1542762 | 3008102 | 3008102 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1542762
58-069 | 58-069 | 58 | 224 - CMSM Simcoe | 66303 | CS Viamonde | la Source | école élémentaire publique la Source | ELE | 9571 | 10198 | 10198-B01 | 70 MADELAINE DR | BARRIE | L4N9T2 | 35-11-70-101 | Barrie | Barrie C | Simcoe Co | SIMCOE | Central | South | 44.3518 | -79.6435 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | 1 | Approved | 44293 | 2843578 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415070 | 0 | 0 | 1415070 | 0 | 0 | 0 | 0 | 0 | 0 | 1428508 | 0 | 0 | 0 | 1428508 | 2843578 | 2843578 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1428508
58-070 | 58-070 | 58 | 211 - CMSM Toronto | 66303 | CS Viamonde | Pierre-Elliott-Trudeau | école élémentaire publique Pierre-Elliott-Trudeau | ELE | 9913 | 5057 | 5057-B01 | 65 GRACE ST | TORONTO | M6J2S4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6521 | -79.4143 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | 1 | Planned | - | 0 | Planned | Addition | Child Care | 2022-23 | 44929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529380 | 0 | 0 | 529380 | 0 | 0 | 0 | 0 | 0 | 0 | 1588138 | 0 | 0 | 0 | 1588138 | 2117518 | 2117518 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1588138
58-071 | 58-071 | 58 | 232 - CMSM Peel | 66303 | CS Viamonde | Carrefour-des-jeunes | école élémentaire publique Carrefour-des-jeunes | ELE | 10710 | 11270 | 11270-B01 | 375 CENTRE ST N | BRAMPTON | L6V4N4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7071 | -79.7719 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | 1 | Approved | 44278 | 3264680 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1632169 | 0 | 0 | 1632169 | 0 | 0 | 0 | 0 | 0 | 0 | 1632511 | 0 | 0 | 0 | 1632511 | 3264680 | 3264680 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1632511
58-072 | 58-072 | 58 | 214 - CMSM Dufferin | 66303 | CS Viamonde | des Quatre-Rivières | école élémentaire publique des Quatre-Rivières | ELE | 11114 | 12164 | 12164-B01 | 60 CENTURY DR | ORANGEVILLE | L9W3K4 | 35-11-43-401 | Orangeville | Orangeville T | Dufferin Co | DUFFERIN | Central | South | 43.9021 | -80.1073 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | 2 | Approved | 43727 | 1817536 | Construction Complete | Retrofit | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519296 | 0 | 0 | 519296 | 0 | 0 | 0 | 0 | 0 | 0 | 1298240 | 0 | 0 | 0 | 1298240 | 1817536 | 1817536 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1298240
58-073 | 58-073 | 58 | 211 - CMSM Toronto | 66303 | CS Viamonde | Laure-Rièse | école élémentaire publique Laure-Rièse | ELE | 14354 | 18001 | 18001-B01 | 339 ALTON TOWERS CIR | SCARBOROUGH | M1V4L3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.8226 | -79.2771 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | - | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 257127 | 0 | 0 | 0 | 257127 | 852127 | 0 | -852127 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 257127
58-074 | 58-074 | 58 | 229 - CMSM Durham | 66303 | CS Viamonde | Ronald-Marion | école élémentaire et secondaire publique Ronald-Marion | ELE/SEC | 14359-14357-24221 | 18004 | 18004-B01 | 2235 BROCK RD | PICKERING | L1V2P8 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8606 | -79.0787 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44916 | 4970959 | Under Construction | Addition | Child Care | 2022-23 | 44929 | 116815 | 0 | 105132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2485479 | 0 | 0 | 2707426 | 0 | 0 | 0 | 0 | 0 | 0 | 2263533 | 0 | 0 | 0 | 2263533 | 4970959 | 4970959 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2263533
58-075-01 | 58-075 | 58 | N/A | 66303 | CS Viamonde | Toronto Est | école secondaire publique Toronto Est | SEC | 24792-24791 | 9448 | 9448-B01 | 24 MOUNTJOY AVE | TORONTO | M4J1J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6808 | -79.3305 | 43857 | 2019-20 | 2019-20 | - | - | - | 43857 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43857 | 4585000 | Construction Complete | Purchase | Accommodation Pressure | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4585000 | 0 | 0 | 0 | 0 | 0 | 4585000 | 4585000 | 4585000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4585000
58-075-02 | 58-075 | 58 | N/A | 66303 | CS Viamonde | Toronto Est | école secondaire publique Toronto Est | SEC | 24792-24791 | 9448 | 9448-L01 | 24 MOUNTJOY AVE | TORONTO | M4J1J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6808 | -79.3305 | 43857 | 2019-20 | 2019-20 | 43857 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43857 | 5656098 | Construction Complete | Land Acquisition | Accommodation Pressure | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5656098 | 0 | 0 | 0 | 0 | 0 | 0 | 5656098 | 5656098 | 5656098 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 5656098
58-075-03 | 58-075 | 58 | N/A | 66303 | CS Viamonde | Toronto Est | école secondaire publique Toronto Est | SEC | 24792-24791 | 9448 | 9448-B01 | 24 MOUNTJOY AVE | TORONTO | M4J1J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6808 | -79.3305 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 501 | - | - | N | - | Approved | 44519 | 26777908 | Under Construction | Retrofit | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 3595217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615514 | 4210731 | 0 | 0 | 0 | 0 | 22567177 | 0 | 0 | 0 | 0 | 0 | 22567177 | 26777908 | 26777908 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 22567177
58-076 | 58-076 | 58 | N/A | 66303 | CS Viamonde | Gabriel-Dumont | école secondaire publique Gabriel-Dumont | ELE/SEC | 14355 | 18002 | 18002-B01 | 2463 EVANS BLVD | LONDON | N6M0B1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9516 | -81.1717 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 216 | - | - | - | - | Approved | 44665 | 6760982 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6760982 | 0 | 0 | 0 | 0 | 0 | 6760982 | 6760982 | 6760982 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6760982
58-077 | 58-077 | 58 | N/A | 66303 | CS Viamonde | Jeunes sans frontières | école secondaire publique Jeunes sans frontières | ELE/SEC | 10059 | 11981 | 11981-B01 | 7585 FINANCIAL DR | BRAMPTON | L6Y5P4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.6245 | -79.7581 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 216 | - | - | - | - | Approved | 44385 | 6186324 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6186324 | 0 | 0 | 0 | 0 | 0 | 6186324 | 6186324 | 6186324 | 0 | - | Yes | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6186324
58-078 | 58-078 | 58 | 211 - CMSM Toronto | 66303 | CS Viamonde | Paul-Demers | école élémentaire publique Paul-Demers | ELE | 25464 | 9905 | 9905-B02 | 44 APPIAN DR | NORTH YORK | M2J2P9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7858 | -79.3709 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 412 | 4 | 73 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9357322 | 0 | 2182082 | 0 | 0 | 0 | 11539404 | 11539404 | 11539404 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11539404
58-079 | 58-079 | 58 | 233 - CMSM Waterloo | 66303 | CS Viamonde | l'Harmonie | école élémentaire publique l'Harmonie | ELE | 10272 | 5966 | 5966-B01 | 158 BRIDGEPORT RD E | WATERLOO | N2J2K4 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4717 | -80.5079 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 4 | 73 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139296 | 0 | 0 | 0 | 2139296 | 2139296 | 2139296 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 2139296
58-080 | 58-080 | 58 | 206 - CMSM London | 66303 | CS Viamonde | Marie-Curie | école élémentaire publique Marie-Curie | ELE | 7862 | 8943 | 8943-B01 | 40 HUNT CLUB DR | LONDON | N6H3Y3 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9748 | -81.3282 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | 39 | N | - | Planned | - | - | Planned | Retrofit | Child Care | 2022-23 | 44810 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418682 | 0 | 0 | 618682 | 0 | 0 | 0 | 0 | 0 | 0 | 267412 | 0 | 0 | 0 | 267412 | 886094 | 886094 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 267412
58-081 | 58-081 | 58 | 203 - CMSM Hamilton | 66303 | CS Viamonde | Pavillon de la jeunesse | école élémentaire publique Pavillon de la jeunesse | ELE | 10662 | 9144 | 9144-B01 | 105 HIGH ST | HAMILTON | L8T3Z4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2266 | -79.8241 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636562 | 0 | 0 | 0 | 1636562 | 1636562 | 1636562 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1636562
58-082 | 58-082 | 58 | 230 - CMSM Halton | 66303 | CS Viamonde | Renaissance | école élémentaire publique Renaissance | ELE | 9488 | 5127 | 5127-B01 | 1226 LOCKHART RD | BURLINGTON | L7S1H1 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3208 | -79.8075 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 3 | 49 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636562 | 0 | 0 | 0 | 1636562 | 1636562 | 1636562 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 1636562
58-083 | 58-083 | 58 | 229 - CMSM Durham | 66303 | CS Viamonde | Whitby-Ajax | école élémentaire publique Whitby-Ajax | ELE | TBD | TBD | TBD | TURNERBURY AVE / AINLEY ST | AJAX | TBD | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.878 | -79.0047 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 317 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8173224 | 0 | 1700737 | 0 | 0 | 0 | 9873961 | 9873961 | 9873961 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9873961
58-087 | 58-087 | 58 | N/A | 66303 | CS Viamonde | Ronald-Marion | école élémentaire et secondaire publique Ronald-Marion | ELE/SEC | 14359-14357-24221 | 18004 | 18004-B01 | 2235 BROCK RD | PICKERING | L1V2P8 | 35-11-10-102 | Pickering | Pickering C | Durham R | DURHAM | GTA | South | 43.8602 | -79.0789 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 69 | - | - | N | - | Planned | - | - | Planned | Retrofit | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367837 | 0 | 0 | 0 | 0 | 0 | 367837 | 367837 | 367837 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 367837
58-088 | 58-083 | 58 | N/A | 66303 | CS Viamonde | Whitby-Ajax | école élémentaire publique Whitby-Ajax | ELE | TBD | TBD | TBD | TURNERBURY AVE / AINLEY ST | AJAX | TBD | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.878 | -79.0047 | 44553 | 2021-22 | 2021-22 | 44553 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44553 | 15190353 | Under Construction | Land Acquisition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17559843 | 0 | 0 | 0 | 0 | 0 | 0 | 17559843 | 17559843 | 17559843 | 0 | - | No, TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 17559843
58-089 | 58-089 | 58 | 203 - CMSM Hamilton | 66303 | CS Viamonde | Hamilton Ouest | école élémentaire publique Hamilton Ouest | ELE | TBD | TBD | TBD | TBD | HAMILTON | L8S3B7 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 271 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | FL Capital Transitional | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303175 | 0 | 1994965 | 0 | 0 | 0 | 10298140 | 10298140 | 10298140 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10298140
58-090 | 58-090 | 58 | N/A | 66303 | CS Viamonde | Brampton | école élémentaire publique Brampton | HLA | TBD | TBD | TBD | TBD | BRAMPTON | TBD | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | TBD | TBD | TBD | TBD | TBD | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Planned | - | - | Planned | Land Acquisition | Accommodation Pressure | 2022-23 | 45169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10226859 | 0 | 0 | 0 | 0 | 0 | 0 | 10226859 | 10226859 | 10226859 | 0 | - | No | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 10226859
59-001 | 59-001 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 10576 | 11125 | 11125-B01 | 2445 ST. LAURENT BLVD | OTTAWA | K1G6C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3813 | -75.6264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -514056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -514056 | -514056 | 0 | 514056 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-002 | 59-002 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 10576 | 11125 | 11125-B01 | 2445 ST. LAURENT BLVD | OTTAWA | K1G6C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3813 | -75.6264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1582328 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2066912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2066912 | 2066912 | 1582328 | -484584 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-003 | 59-003 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 10576 | 11125 | 11125-B01 | 2445 ST. LAURENT BLVD | OTTAWA | K1G6C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3813 | -75.6264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 479110 | Construction Complete | Other | Other | 2012-13 | 41153 | 0 | 0 | 0 | 479110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479110 | 479110 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-004 | 59-004 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Carrefour Jeunesse | école élémentaire publique Carrefour Jeunesse | ELE | 2014 | 6599 | 6599-B01 | 927 ST JEAN ST | ROCKLAND | K4K1P4 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5439 | -75.2882 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42025 | 412097 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 412097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412097 | 412097 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-005 | 59-005 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Carrefour Jeunesse | école élémentaire publique Carrefour Jeunesse | ELE | 2014 | 6599 | 6599-B01 | 927 ST JEAN ST | ROCKLAND | K4K1P4 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5439 | -75.2882 | 42321 | 2015-16 | 2015-16 | - | - | - | 42321 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 184 | - | - | N | - | Approved | 43342 | 4324942 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 43174 | 0 | 0 | 0 | 0 | 503238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503238 | 0 | 0 | 0 | 0 | 3821704 | 0 | 0 | 0 | 0 | 0 | 3821704 | 4324942 | 4324942 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3821704
59-006 | 59-006 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Charlotte-Lemieux | école élémentaire publique Charlotte-Lemieux | ELE | 1684 | 6384 | 6384-B01 | 2093 BEL-AIR DR | OTTAWA | K2C0X2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3629 | -75.7631 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4492079 | Construction Complete | Addition | Other | 2001-02 | 37135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4492079 | 4492079 | 4492079 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-007 | 59-007 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Cité-Jeunesse | école élémentaire publique Cité-Jeunesse | ELE | 3 | 5303 | 5303-B01 | 30 FULLERTON AVE | TRENTON | K8V1E4 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.1139 | -77.5549 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7577317 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7577317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7577317 | 7577317 | 7577317 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-008 | 59-008 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Cité-Jeunesse | école élémentaire publique Cité-Jeunesse | ELE | 3 | 5303 | 5303-B01 | 30 FULLERTON AVE | TRENTON | K8V1E4 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.1139 | -77.5549 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41829 | 5680480 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 800000 | 0 | 0 | 4437000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443480 | 5680480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5680480 | 5680480 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-009 | 59-009 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | de Kanata | école élémentaire publique de Kanata | ELE | 9976 | 10352 | 10352-B01 | 1385 HALTON TERR | KANATA | K2K2P9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3485 | -75.9367 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4610109 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4610109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4610109 | 4610109 | 4610109 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-010 | 59-010 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | de Kanata | école élémentaire publique de Kanata | ELE | 9976 | 10352 | 10352-B01 | 1385 HALTON TERR | KANATA | K2K2P9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3485 | -75.9367 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 856809 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119757 | 119757 | 737052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 737052 | 856809 | 856809 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-011 | 59-011 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | de Kanata | école élémentaire publique de Kanata | ELE | 9976 | 10352 | 10352-B01 | 1385 HALTON TERR | KANATA | K2K2P9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3485 | -75.9367 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 374 | - | - | N | - | Approved | 41815 | 8106933 | Construction Complete | Addition | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719888 | 0 | 0 | 719888 | 0 | 0 | 503976 | 0 | 6883069 | 0 | 0 | 0 | 0 | 0 | 7387045 | 8106933 | 8106933 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6883069
59-012 | 59-012 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | de la Rivière-Castor | école élémentaire publique de la Rivière-Castor | ELE | 9868 | 10304 | 10304-B01 | 100 MAHEU ST | EMBRUN | K0A1W0 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2761 | -75.2882 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 151970 | Construction Complete | Retrofit | Child Care | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151970 | 0 | 0 | 151970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151970 | 151970 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-013 | 59-013 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | de la Rivière-Castor | école élémentaire publique de la Rivière-Castor | ELE | 9868 | 10304 | 10304-B01 | 100 MAHEU ST | EMBRUN | K0A1W0 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2761 | -75.2882 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4009397 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4009397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4009397 | 4009397 | 4009397 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-014 | 59-014 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | de la Salle | école secondaire publique de la Salle | SEC | 5336 | 8198 | 8198-B01 | 501 OLD ST. PATRICK ST | OTTAWA | K1N8R3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.435 | -75.6849 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9049109 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43044 | 43044 | 9006065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9006065 | 9049109 | 9049109 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-016 | 59-016 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | des Sentiers | école élémentaire publique des Sentiers | ELE | 9869 | 10305 | 10305-B01 | 2159 NANTES ST | ORLEANS | K4A4C4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4595 | -75.4612 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7428708 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084221 | 2084221 | 5344487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5344487 | 7428708 | 7428708 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-017 | 59-017 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Gabrielle-Roy | école élémentaire publique Gabrielle-Roy | ELE | 9981 | 10355 | 10355-B01 | 3395 D'AOUST AVE | GLOUCESTER | K1T4A8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3487 | -75.6347 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6355397 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861608 | 861608 | 5493789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5493789 | 6355397 | 6355397 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-018 | 59-018 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Gisèle-Lalonde | école secondaire publique Gisèle-Lalonde | SEC | 9980 | 10354 | 10354-B01 | 500 MILLENNIUM BLVD | ORLEANS | K4A4X3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4687 | -75.4453 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 21763342 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3124330 | 3124330 | 18639012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18639012 | 21763342 | 21763342 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-020 | 59-020 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Kemptville | école élémentaire et secondaire publique Kemptville | HLA | 24829 | 19835 | 19835-L0- | 234 COUNTY ROAD 44 | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0323 | -75.6636 | 42258 | 2015-16 | 2015-16 | 42258 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1500000 | Construction Complete | Land Acquisition | FL Capital Transitional | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 1500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1500000
59-021 | 59-021 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | l'Académie de la Seigneurie | école élémentaire publique l'Académie de la Seigneurie | ELE | 10600 | 11280 | 11280-B01 | 731 RUE DES POMMIERS | CASSELMAN | K0A1M0 | 35-12-67-614 | The Nation | The Nation M | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3045 | -75.09 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9089330 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9089330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9089330 | 9089330 | 9089330 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-022 | 59-022 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | l'Académie de la Seigneurie | école secondaire publique l'Académie de la Seigneurie | SEC | 10602 | 11280 | 11280-B01 | 731 RUE DES POMMIERS | CASSELMAN | K0A1M0 | 35-12-67-502 | Casselman | Casselman V | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3045 | -75.0903 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8390150 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30858 | 30858 | 8359292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8359292 | 8390150 | 8390150 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-023 | 59-023 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | l'Alternative | école secondaire publique l'Alternative | SEC | 24242 | 11125 | 11125-B01 | 2445 ST. LAURENT BLVD | OTTAWA | K1G6C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3812 | -75.6263 | 41435 | 2012-13 | 2013-14 | - | - | - | 41435 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41701 | 320013 | Construction Complete | Retrofit | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 127692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127692 | 0 | 0 | 0 | 0 | 192321 | 0 | 0 | 0 | 0 | 0 | 192321 | 320013 | 320013 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 192321
59-024 | 59-024 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | le Carrefour / CÉPEO Siège Social | école secondaire publique le Carrefour / CÉPEO Siège Social | SEC | 10482 | 11125 | 11125-B01 | 2445 ST. LAURENT BLVD | OTTAWA | K1G6C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3813 | -75.6264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 14356933 | Construction Complete | New Construction | Consolidation | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7487930 | 7487930 | 6869003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6869003 | 14356933 | 14356933 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-025 | 59-025 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | le Prélude | école élémentaire publique le Prélude | ELE | 9978 | 10353 | 10353-B01 | 6025 LONGLEAF DR | ORLEANS | K1W1J2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4375 | -75.5301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5202703 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5202703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5202703 | 5202703 | 5202703 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-026 | 59-026 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | le Sommet | école secondaire publique le Sommet | SEC | 10394 | 11094 | 11094-B01 | 894 CECILE BLVD | HAWKESBURY | K6A3R5 | 35-12-67-401 | Hawkesbury | Hawkesbury T | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6033 | -74.5987 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9953896 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9953896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9953896 | 9953896 | 9953896 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-027 | 59-027 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | le Sommet | école secondaire publique le Sommet | SEC | 10394 | 11094 | 11094-B01 | 894 CECILE BLVD | HAWKESBURY | K6A3R5 | 35-12-67-401 | Hawkesbury | Hawkesbury T | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6033 | -74.5987 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 119678 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119678 | 119678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119678 | 119678 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-028 | 59-028 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Mauril-Bélanger | école élémentaire publique Mauril-Bélanger | ELE | 6006 | 8527 | 8527-B01 | 307 MONTGOMERY ST | VANIER | K1L7W8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4327 | -75.6673 | 41435 | 2012-13 | 2013-14 | - | - | - | 41435 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41701 | 3748623 | Construction Complete | Retrofit | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 2540776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2540776 | 0 | 0 | 0 | 0 | 1207847 | 0 | 0 | 0 | 0 | 0 | 1207847 | 3748623 | 3748623 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1207847
59-029 | 59-029 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | l'Équinoxe | école élémentaire et secondaire publique l'Équinoxe | ELE/SEC | 11081 | 6156 | 6156-B01 | 399 ISABELLA ST | PEMBROKE | K8A5T4 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8246 | -77.1217 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 835000 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835000 | 835000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835000 | 835000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-030 | 59-030 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | l'Héritage | école élémentaire et secondaire publique l'Héritage | ELE/SEC | 5339 | 8199 | 8199-B01 | 1111 MONTREAL RD | CORNWALL | K6H1E1 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0187 | -74.7002 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7021896 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996970 | 1996970 | 5024926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5024926 | 7021896 | 7021896 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-031 | 59-031 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | l'Odyssée | école élémentaire publique l'Odyssée | ELE | 658 | 5733 | 5733-B01 | 1770 GREY NUNS DR | ORLEANS | K1C1C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4684 | -75.536 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1100105 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100105 | 1100105 | 1100105 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-032 | 59-032 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Louis-Riel | école secondaire publique Louis-Riel | SEC | 5313 | 8183 | 8183-B01 | 1655 BEARBROOK RD | GLOUCESTER | K1B4N3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4411 | -75.5716 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3034766 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3034766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3034766 | 3034766 | 3034766 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-033 | 59-033 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Louis-Riel | école secondaire publique Louis-Riel | SEC | 5313 | 8183 | 8183-B01 | 1655 BEARBROOK RD | GLOUCESTER | K1B4N3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4411 | -75.5716 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7570964 | Construction Complete | Retrofit | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7570964 | 7570964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7570964 | 7570964 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-034 | 59-034 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Louis-Riel | école secondaire publique Louis-Riel | SEC | 5313 | 8183 | 8183-B01 | 1655 BEARBROOK RD | GLOUCESTER | K1B4N3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4411 | -75.5716 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42025 | 94797 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 94797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94797 | 94797 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-035 | 59-035 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Louis-Riel | école secondaire publique Louis-Riel | SEC | 5313 | 8183 | 8183-B01 | 1655 BEARBROOK RD | GLOUCESTER | K1B4N3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4411 | -75.5716 | 42321 | 2015-16 | 2015-16 | - | - | - | 42321 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 252 | - | - | N | - | Approved | 43062 | 8001336 | Construction Complete | Addition | Condition | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 725810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 725810 | 0 | 0 | 0 | 0 | 7275526 | 0 | 0 | 0 | 0 | 0 | 7275526 | 8001336 | 8001336 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7275526
59-036 | 59-036 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Madeleine-de-Roybon-Mille-Îles | école élémentaire et secondaire publique Madeleine-de-Roybon-Mille-Îles | ELE/SEC | 21043 | 5720 | 5720-B01 | 72 GILMOUR AVE | KINGSTON | K7M9G6 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2424 | -76.5259 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15341795 | Construction Complete | New Construction | Condition | 2011-12 | 40787 | 0 | 0 | 0 | 8008570 | 0 | 540658 | 0 | 0 | 0 | 0 | 0 | 0 | 661699 | 0 | 1200001 | 10410928 | 4930867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4930867 | 15341795 | 15341795 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-038 | 59-038 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Marie-Curie | école élémentaire publique Marie-Curie | ELE | 694 | 5756 | 5756-B01 | 837 QUINLAN RD | OTTAWA | K1G1R8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3987 | -75.6304 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42025 | 5480701 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 487595 | 0 | 0 | 4993106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -432806 | 5047895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5047895 | 5047895 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-039 | 59-039 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Maurice-Lapointe | école élémentaire et secondaire publique Maurice-Lapointe | ELE/SEC | 18111 | 12241 | 12241-B01 | 17 BRIDGESTONE DR | KANATA | K2M0E9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2788 | -75.8587 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 314 | - | - | N | - | Not Required | - | 12987381 | Construction Complete | New Construction | Accommodation Pressure | 2011-12 | 40787 | 0 | 0 | 0 | 3084745 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3439896 | 8024641 | 4962740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4962740 | 12987381 | 12987381 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-041 | 59-041 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Maurice-Lapointe | école élémentaire et secondaire publique Maurice-Lapointe | ELE/SEC | 18111 | 12241 | 12241-B01 | 17 BRIDGESTONE DR | KANATA | K2M0E9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2788 | -75.8587 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 480 | - | - | N | - | Approved | 41306 | 14626693 | Construction Complete | Addition | FL Capital Transitional | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 1358334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1358334 | 0 | 0 | 0 | 0 | 13298027 | 0 | 0 | 0 | 0 | 0 | 13298027 | 14656361 | 14656361 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13298027
59-042 | 59-042 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Michaëlle-Jean | école élémentaire publique Michaëlle-Jean | ELE | 10603 | 11271 | 11271-B01 | 11 CLARIDGE DR | NEPEAN | K2J5A3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2882 | -75.7263 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7692606 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238293 | 1238293 | 6454313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6454313 | 7692606 | 7692606 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-043 | 59-043 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Michaëlle-Jean | école élémentaire publique Michaëlle-Jean | ELE | 10603 | 11271 | 11271-B01 | 11 CLARIDGE DR | NEPEAN | K2J5A3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2882 | -75.7263 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 328 | - | - | N | - | Not Required | - | 3813856 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969169 | 0 | 2922344 | 0 | 0 | 0 | 0 | 0 | 3891513 | 3891513 | 3891513 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2922344
59-044 | 59-044 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Nouvel-Horizon | école élémentaire publique Nouvel-Horizon | ELE | 9449 | 10173 | 10173-B01 | 433 CARTIER BLVD | HAWKESBURY | K6A1V9 | 35-12-67-401 | Hawkesbury | Hawkesbury T | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6063 | -74.6012 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 685291 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685291 | 685291 | 685291 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-045 | 59-045 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Omer-Deslauriers | école secondaire publique Omer-Deslauriers | SEC | 10769 | 8257 | 8257-B01 | 159 CHESTERTON DR | NEPEAN | K2E7E6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3501 | -75.7166 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11456022 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 1884332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273000 | 2157332 | 9298690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9298690 | 11456022 | 11456022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-046 | 59-046 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Omer-Deslauriers | école secondaire publique Omer-Deslauriers | SEC | 10769 | 8257 | 8257-B01 | 159 CHESTERTON DR | NEPEAN | K2E7E6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3501 | -75.7166 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 990712 | Construction Complete | Retrofit | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990712 | 990712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990712 | 990712 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-047 | 59-047 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Pavillon Francojeunesse | école élémentaire publique Pavillon Francojeunesse | ELE | 14035 | 12335 | 12335-B01 | 339 WILBROD ST | OTTAWA | K1N6M4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.428 | -75.6796 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2300000 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 2300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-048 | 59-048 | 59 | 207 - CMSM Ottawa | 66311 | CÉP de l'Est de l'Ontario | Michel-Dupuis | école élémentaire publique Michel-Dupuis | ELE | 24444 | 19447 | 19447-B01 | 715 BRIAN GOOD AVE | MANOTICK | K4M0H3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2672 | -75.6932 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 366 | 2 | 39 | N | - | Approved | 43055 | 11550580 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 1647134 | 1106987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439465 | 0 | 0 | 3193586 | 0 | 0 | 484585 | 0 | 7214392 | 0 | 558795 | 0 | 0 | 0 | 8257772 | 11451358 | 11451358 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7773187
59-049 | 59-049 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Rockland | Rockland | HLA | 24445 | 19448 | 19448-L0- | 8720 COUNTY ROAD 17 | CLARENCE-ROCKLAND | TBD | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5577 | -75.2695 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41819 | 1220000 | Construction Complete | Land Acquisition | Other | 2015-16 | 42248 | 0 | 0 | 0 | 274000 | 946000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220000 | 1220000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-050 | 59-050 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Rose des Vents | école élémentaire publique Rose des Vents | ELE | 1611 | 6339 | 6339-B01 | 1650 SECOND ST E | CORNWALL | K6H2C3 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0316 | -74.6936 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1308167 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308167 | 1308167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308167 | 1308167 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-051 | 59-051 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Rose des Vents | école élémentaire publique Rose des Vents | ELE | 1611 | 6339 | 6339-B01 | 1650 SECOND ST E | CORNWALL | K6H2C3 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0316 | -74.6936 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3313641 | Construction Complete | Addition | Consolidation | 2010-11 | 40422 | 252687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760954 | 0 | 0 | 1013641 | 0 | 0 | 0 | 0 | 0 | 2300000 | 0 | 0 | 0 | 0 | 2300000 | 3313641 | 3313641 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-052 | 59-052 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Séraphin-Marion | école élémentaire publique Séraphin-Marion | ELE | 10411 | 6144 | 6144-B01 | 2147 LOYOLA AVE | GLOUCESTER | K1J7W3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4527 | -75.5922 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4759377 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59377 | 59377 | 4700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700000 | 4759377 | 4759377 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-053 | 59-053 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Terre des Jeunes | école élémentaire publique Terre des Jeunes | ELE | 4081 | 7740 | 7740-B01 | 33 LOCHIEL ST E | ALEXANDRIA | K0C1A0 | 35-12-71-615 | North Glengarry | North Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.306 | -74.6314 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7261352 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7261352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7261352 | 7261352 | 7261352 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-054 | 59-054 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Trille-des-Bois | école élémentaire publique Trille-des-Bois | ELE | 10390 | 8524 | 8524-B01 | 140 GENEST ST | VANIER | K1L7Y9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4406 | -75.6698 | 41435 | 2012-13 | 2013-14 | - | - | - | 41435 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41701 | 582587 | Construction Complete | Retrofit | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1319 | 0 | 0 | 242292 | 0 | 338976 | 0 | 0 | 0 | 0 | 0 | 581268 | 582587 | 582587 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 338976
59-055 | 59-055 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Trille-des-Bois (Annexe) | école élémentaire publique Trille-des-Bois (Annexe) | ELE | 5995 | 8524 | 8524-B02 | 135 ALICE ST | VANIER | K1L7X5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4397 | -75.6706 | 41435 | 2012-13 | 2013-14 | - | - | - | 41435 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41701 | 1279051 | Construction Complete | Retrofit | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 726944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726944 | 0 | 0 | 0 | 0 | 552107 | 0 | 0 | 0 | 0 | 0 | 552107 | 1279051 | 1279051 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 552107
59-056 | 59-056 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | de la Salle | école secondaire publique de la Salle | SEC | 5336 | 8198 | 8198-B01 | 501 OLD ST. PATRICK ST | OTTAWA | K1N8R3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.435 | -75.6849 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 210 | - | - | N | - | Approved | 44127 | 13317727 | Construction Complete | Addition | Accommodation Pressure | 2021-22 | 44440 | 0 | 150000 | 0 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5858460 | 0 | 0 | 6483460 | 0 | 0 | 0 | 0 | 6834267 | 0 | 0 | 0 | 0 | 0 | 6834267 | 13317727 | 13317727 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6834267
59-057 | 59-057 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Pierre-de-Bois | école secondaire publique Pierre-des-Bois | SEC | 24582-24611 | 19588 | 19588-B01 | 1310 CHAPMAN MILLS WALK | NEPEAN | K2J6L9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.263 | -75.7589 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 681 | - | - | N | - | Approved | 43857 | 23347054 | Construction Complete | New Construction | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 19847053 | 0 | 0 | 0 | 0 | 0 | 19847053 | 23347053 | 23347053 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 19847053
59-058 | 59-058 | 59 | 236 - CMSM Prescott & Russell | 66311 | CÉP de l'Est de l'Ontario | de la Rivière-Castor | école élémentaire publique de la Rivière-Castor | ELE | 9868 | 10304 | 10304-B01 | 100 MAHEU ST | EMBRUN | K0A1W0 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2761 | -75.2882 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44281 | 1900000 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851325 | 0 | 0 | 851325 | 0 | 0 | 0 | 0 | 0 | 0 | 1048675 | 0 | 0 | 0 | 1048675 | 1900000 | 1900000 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1048675
59-059 | 59-059 | 59 | 207 - CMSM Ottawa | 66311 | CÉP de l'Est de l'Ontario | des Sentiers | école élémentaire publique des Sentiers | ELE | 9869 | 10305 | 10305-B01 | 2159 NANTES ST | ORLEANS | K4A4C4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4595 | -75.4612 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519296 | 0 | 0 | 0 | 519296 | 519296 | 0 | -519296 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 519296
59-060 | 59-060 | 59 | 207 - CMSM Ottawa | 66311 | CÉP de l'Est de l'Ontario | Gabrielle-Roy | école élémentaire publique Gabrielle-Roy | ELE | 9981 | 10355 | 10355-B01 | 3395 D'AOUST AVE | GLOUCESTER | K1T4A8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3487 | -75.6347 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557887 | 0 | 0 | 0 | 1557887 | 1557887 | 0 | -1557887 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1557887
59-061 | 59-061 | 59 | 223 - CMSM Renfrew | 66311 | CÉP de l'Est de l'Ontario | l'Équinoxe | école élémentaire publique l'Équinoxe | ELE | 10987 | 6156 | 6156-B01 | 399 ISABELLA ST | PEMBROKE | K8A5T4 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8238 | -77.1216 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44281 | 1850000 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791243 | 0 | 0 | 791243 | 0 | 0 | 0 | 0 | 0 | 0 | 1058757 | 0 | 0 | 0 | 1058757 | 1850000 | 1850000 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1058757
59-062-01 | 59-062+66-111 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Mille Îles | école secondaire publique Mille Îles | SEC | 24818-24817 | 19823 | 19823-B01 | 1381 DEMERS AVE | KINGSTON | TBD | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2499 | -76.5607 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43173 | 2017-18 | 2017-18 | 300 | - | - | N | - | Approved | 44176 | 14895022 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 1918550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918550 | 0 | 0 | 0 |  | 11855472 | 0 | 0 | 0 | 1700000 | 0 | 13555472 | 15474022 | 14895022 | -579000 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13555472
59-062-02 | 59-062+66-111 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Mille Îles | école secondaire publique Mille Îles | SEC | 24818-24817 | 19823 | 19823-L01 | 1381 DEMERS AVE | KINGSTON | TBD | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2499 | -76.5607 | 43227 | 2017-18 | 2018-19 | 43227 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43885 | 3509625 | Construction Complete | Land Acquisition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3686500 | 0 | 0 | 0 | 0 | 0 | 0 | 3686500 | 3686500 | 3509625 | -176875 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3686500
59-063 | 59-063 | 59 | 236 - CMSM Prescott & Russell | 66311 | CÉP de l'Est de l'Ontario | Nouvel-Horizon | école élémentaire publique Nouvel-Horizon | ELE | 9449 | 10173 | 10173-B01 | 433 CARTIER BLVD | HAWKESBURY | K6A1V9 | 35-12-67-401 | Hawkesbury | Hawkesbury T | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6063 | -74.6012 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 92 | 1 | 15 | Y | - | Approved | 44180 | 4573819 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 300000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 2249482 | 0 | 524337 | 0 | 0 | 0 | 2773819 | 4573819 | 4573819 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 2773819
59-064-01 | 59-064 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Rivière Rideau | école élémentaire et secondaire publique Rivière Rideau | ELE/SEC | 24696 | 19502 | 19502-B02 | 51 ACADEMIC CRES | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0087 | -75.639 | 43157 | 2017-18 | 2017-18 | - | - | - | 43157 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43157 | 2678100 | Construction Complete | Purchase | FL Capital Transitional | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2678100 | 0 | 0 | 0 | 0 | 0 | 2678100 | 2678100 | 2678100 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2678100
59-064-02 | 59-064 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Rivière Rideau | école élémentaire et secondaire publique Rivière Rideau | ELE/SEC | 24696 | 19502 | 19502-L02 | 51 ACADEMIC CRES | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0087 | -75.639 | 43157 | 2017-18 | 2017-18 | 43157 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43157 | 1500000 | Construction Complete | Land Acquisition | FL Capital Transitional | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 1500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1500000
59-065 | 59-064 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Rivière Rideau | école élémentaire et secondaire publique Rivière Rideau | ELE/SEC | 24696 | 19502 | 19502-B02 | 51 ACADEMIC CRES | KEMPTVILLE | K0G1J0 | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 45.0087 | -75.639 | 42321 | 2015-16 | 2015-16 | - | - | - | 42321 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | 489 | - | - | N | - | Approved | 43950 | 13769627 | Construction Complete | Retrofit | FL Capital Transitional | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028112 | 0 | 9077471 | 0 | 0 | 0 | 0 | 0 | 10105583 | 10105583 | 9591527 | -514056 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 9077471
59-066 | 59-066 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Marie-Curie | école élémentaire publique Marie-Curie | ELE | 694 | 5756 | 5756-B01 | 837 QUINLAN RD | OTTAWA | K1G1R8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3987 | -75.6304 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
59-067 | 59-067 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Maurice-Lapointe | école élémentaire et secondaire publique Maurice-Lapointe | ELE/SEC | 18111 | 12241 | 12241-B01 | 17 BRIDGESTONE DR | KANATA | K2M0E9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2788 | -75.8587 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44385 | 743165 | Construction Complete | Addition | Other | 2020-21 | 44075 | 0 | 0 | 0 | 743165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743165 | 743165 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-069 | 59-069 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | le Prélude | école élémentaire publique le Prélude | ELE | 9978 | 10353 | 10353-B01 | 6025 LONGLEAF DR | ORLEANS | K1W1J2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4375 | -75.5301 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44385 | 1117934 | Construction Complete | Addition | Other | 2020-21 | 44075 | 0 | 0 | 0 | 1117934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117934 | 1117934 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-070 | 59-070 | 59 | 207 - CMSM Ottawa | 66311 | CÉP de l'Est de l'Ontario | Kanata Sud | école élémentaire publique Kanata Sud | ELE | 24971 | 19977 | 19977-B01 | 5609 FERNBANK RD | STITTSVILLE | K2S1B6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2733 | -75.8712 | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | 475 | 3 | 49 | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10810940 | 0 | 1652606 | 0 | 0 | 0 | 12463546 | 12463546 | 12463546 | 0 | - | No, Ministry is following up with the school board | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 12463546
59-071 | 59-071 | 59 | 207 - CMSM Ottawa | 66311 | CÉP de l'Est de l'Ontario | Barrhaven Sud | école élémentaire publique Barrhaven Sud | ELE | 25547 | 20553 | 20553-B01 | KILBIRNIE DR / ALEX POLOWIN AVE | OTTAWA | TBD | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2397 | -75.7363 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 475 | 3 | 49 | N | - | Approved | 44769 | 17337356 | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 750000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458810 | 0 | 0 | 1758810 | 0 | 0 | 0 | 0 | 13925940 | 0 | 1652606 | 0 | 0 | 0 | 15578546 | 17337356 | 17337356 | 0 | - | No, Ministry is following up with the school board | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15578546
59-072 | 59-072 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Mamawi | école élémentaire publique Mamawi | ELE | 24972 | 6162 | 6162-B01 | 20 HARRISON ST | NEPEAN | K2H7H5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3368 | -75.7881 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | 256 | - | - | N | - | Not Required | - | - | Construction Complete | Purchase | Accommodation Pressure | 2020-21 | 44344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1455353 | 0 | 0 | 0 | 0 | 0 | 1455353 | 1455353 | 1455353 | 0 | - | No, Ministry is following up with the school board | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1455353
59-074 | 59-074 | 59 | 207 - CMSM Ottawa | 66311 | CÉP de l'Est de l'Ontario | Orléans Sud | école élémentaire publique Orléans Sud | ELE | TBD | TBD | TBD | MER BLEUE RD / JÉRÔME JODOIN DR | ORLÉANS | TBD | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | TBD | TBD | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 354 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | FL Capital Transitional | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8950223 | 0 | 1751759 | 0 | 0 | 0 | 10701982 | 10701982 | 10701982 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10701982
59-075 | 59-075 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Temporary Accommodation | Temporary Accommodation | OFF-ADM | 10576 | 11125 | 11125-B01 | 2445 ST. LAURENT BLVD | OTTAWA | K1G6C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3813 | -75.6264 | 44476 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44476 | 2712000 | Under Construction | Other | Other | 2022-23 | 44805 | 0 | 0 | 160000 | 2192080 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 2712080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2712080 | 2712080 | 0 | - | No, TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
59-076 | 59-076 | 59 | N/A | 66311 | CÉP de l'Est de l'Ontario | Kingston | école élémentaire publique Kingston | ELE | TBD | TBD | TBD | HOLDEN ST | KINGSTON | TBD | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | TBD | TBD | 44622 | 2021-22 | 2021-22 | 44622 | 2021-22 | 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44622 | 5486870 | Construction Complete | Land Acquisition | Accommodation Pressure | 2021-22 | 44804 | 0 | 0 | 0 | 0 | 3840809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3840809 | 0 | 0 | 0 | 1646061 | 0 | 0 | 0 | 0 | 0 | 0 | 1646061 | 5486870 | 5486870 | 0 | - | No, TBD | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1646061
59-077 | 59-077 | 59 | 207 - CMSM Ottawa | 66311 | CÉP de l’Est de l’Ontario | Louise-Arbour | école élémentaire publique Louise-Arbour | ELE | TBD | TBD | TBD | TBD | OTTAWA | K1R6R9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 449 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12469140 | 0 | 2014523 | 0 | 0 | 0 | 14483663 | 14483663 | 14483663 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14483663
60.1-001 | 60.1-001 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 24190 | 12023 | 12023-B02 | 896 RIVERSIDE DR | TIMMINS | P4N3W2 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4769 | -81.3619 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-002 | 60.1-002 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 24190 | 12023 | 12023-B02 | 896 RIVERSIDE DR | TIMMINS | P4N3W2 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4769 | -81.3619 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2997474 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997473 | 2997473 | 2997473 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-004 | 60.1-004 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Anicet-Morin | école élémentaire catholique Anicet-Morin | ELE | 7718 | 8855 | 8855-B01 | 1070 POWER AVE | TIMMINS | P4R1B4 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4768 | -81.3693 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8797688 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8797688 | 8797688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8797688 | 8797688 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-007 | 60.1-007 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Point de service de Hearst | Point de service de Hearst | OFF-ADM | 24190 | 12023 | 12023-B02 | 896 RIVERSIDE DR | TIMMINS | P4N3W2 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4769 | -81.3619 | 42018 | 2014-15 | 2014-15 | - | - | - | 42018 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | 21 | - | - | N | - | Not Required | - | 82000 | Construction Complete | Demolition | Consolidation | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 | 0 | 0 | 0 | 0 | 0 | 82000 | 82000 | 82000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 82000
60.1-008 | 60.1-008 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Don Bosco | école élémentaire catholique Don Bosco | ELE | 7720 | 8857 | 8857-B01 | 400 LONERGAN BLVD | TIMMINS | P4P1C7 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4992 | -81.3472 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2008204 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008204 | 2008204 | 2008204 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-012 | 60.1-012 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Jean-Vanier | école secondaire catholique Jean-Vanier | SEC | 10861 | 8868 | 8868-B02 | 52 DUNCAN AVE S | KIRKLAND LAKE | P2N1Y1 | 35-13-90-405 | Kirkland Lake | Kirkland Lake T | Timiskaming District | TIMISKAMING | Northeast | North | 48.1488 | -80.0307 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12939986 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7204846 | 7204846 | 5735140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5735140 | 12939986 | 12939986 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-013 | 60.1-013 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Jean-Vanier | école secondaire catholique Jean-Vanier | SEC | 10861 | 8868 | 8868-B02 | 52 DUNCAN AVE S | KIRKLAND LAKE | P2N1Y1 | 35-13-90-405 | Kirkland Lake | Kirkland Lake T | Timiskaming District | TIMISKAMING | Northeast | North | 48.1488 | -80.0307 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1698000 | Construction Complete | Demolition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1698000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1698000 | 1698000 | 1698000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-014-01 | 56-011+60.1-014 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | l'Alliance | école secondaire catholique l'Alliance | SEC | 11191 | 12338 | 12338-B01 | 296 CAMBRIDGE AVE | IROQUOIS FALLS | P0K1E0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7624 | -80.6869 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 180 | - | - | N | - | Approved | 44189 | 9048830 | Construction Complete | New Construction | FL Capital Transitional | 2020-21 | 44141 | 0 | 0 | 0 | 850883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1103992 | 0 | 0 | 1954875 | 0 | 0 | 0 | 0 | 7093955 | 0 | 0 | 0 | 0 | 0 | 7093955 | 9048830 | 9048830 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 7093955
60.1-014-02 | 56-011+60.1-014 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | l'Alliance | école secondaire catholique l'Alliance | SEC | 11191 | 12338 | 12338-L01 | 296 CAMBRIDGE AVE | IROQUOIS FALLS | P0K1E0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7624 | -80.6869 | 42292 | 2015-16 | 2015-16 | 42292 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42292 | 188355 | Construction Complete | Land Acquisition | FL Capital Transitional | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188355 | 0 | 0 | 0 | 0 | 0 | 0 | 188355 | 188355 | 188355 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 188355
60.1-015 | 60.1-015 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Nouveau-Regard (Pavillon Jeunesse-Nord) | école secondaire catholique Nouveau-Regard (Pavillon Jeunesse-Nord) | SEC | 10857 | 12025 | 12025-B01 | 399 8TH ST | COCHRANE | P0L1C0 | 35-13-81-407 | Cochrane | Cochrane T | Cochrane District | COCHRANE | Northeast | North | 49.071 | -81.0134 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 15266354 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15266354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15266354 | 15266354 | 15266354 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-018 | 60.1-018 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Sacré-Cœur | école élémentaire catholique Sacré-Cœur | ELE | 7705 | 8842 | 8842-B01 | 560 DIEPPE ST | TIMMINS | P4N7N4 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4874 | -81.3418 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6949772 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5529276 | 5529276 | 0 | 1420496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420496 | 6949772 | 6949772 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-019 | 60.1-019 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Saint-Dominique | école élémentaire catholique Saint-Dominique | ELE | 7709 | 8846 | 8846-B01 | 855 PARK AVE | TIMMINS | P4N8G2 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.479 | -81.3621 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 880930 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880930 | 880930 | 880930 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-023 | 60.1-023 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Saint-Jude | école élémentaire catholique Saint-Jude | ELE | 7714 | 8851 | 8851-B01 | 225 DIXON ST | PORCUPINE | P0N1C0 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4925 | -81.168 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41379 | 618925 | Construction Complete | Retrofit | Child Care | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590501 | 0 | 0 | 590501 | 0 | 0 | 28424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28424 | 618925 | 618925 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-024 | 60.1-024 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Saint-Michel | école élémentaire catholique Saint-Michel | ELE | 7738 | 8871 | 8871-B01 | 998075 HIGHWAY 11 N | NEW LISKEARD | P0J1P0 | 35-13-90-101 | Temiskaming Shores | Temiskaming Shores C | Timiskaming District | TIMISKAMING | Northeast | North | 47.5434 | -79.6736 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 78 | - | - | N | - | Approved | 42436 | 7022432 | Construction Complete | Addition | Consolidation | 2017-18 | 42979 | 0 | 350608 | 235407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1747659 | 0 | 0 | 2333674 | 0 | 0 | 2674301 | 0 | 1914457 | 0 | 0 | 0 | 0 | 0 | 4588758 | 6922432 | 6922432 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1914457
60.1-025 | 60.1-025 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Saints-Martyrs-Canadiens | école élémentaire catholique Saints-Martyrs-Canadiens | ELE | 4568 | 8081 | 8081-B01 | 425 TEEFY ST | IROQUOIS FALLS | P0K1G0 | 35-13-81-403 | Iroquois Falls | Iroquois Falls T | Cochrane District | COCHRANE | Northeast | North | 48.7552 | -80.6899 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41379 | 694495 | Construction Complete | Retrofit | Child Care | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595808 | 0 | 0 | 595808 | 0 | 0 | 98687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98687 | 694495 | 694495 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-026 | 60.1-026 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Thériault | école secondaire catholique Thériault | SEC | 7717 | 8854 | 8854-B01 | 341 THERIAULT BLVD | TIMMINS | P4N7K3 | 35-13-81-101 | Timmins | Timmins C | Cochrane District | COCHRANE | Northeast | North | 48.4826 | -81.3489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 980454 | Construction Complete | Retrofit | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743842 | 743842 | 0 | 236612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236612 | 980454 | 980454 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.1-027 | 60.1-027 | 60.1 | 301 - DSSAB Cochrane | 29106 | CSCD des Grandes Rivières | Jacques-Cartier | école élémentaire catholique Jacques-Cartier | ELE | 3346 | 7194 | 7194-B01 | 8 BRUNELLE RD S | KAPUSKASING | P5N2T2 | 35-13-81-404 | Kapuskasing | Kapuskasing T | Cochrane District | COCHRANE | Northeast | North | 49.4079 | -82.4025 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403337 | 0 | 0 | 0 | 403337 | 403337 | 403337 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 403337
60.1-028 | 60.1-028 | 60.1 | N/A | 29106 | CSCD des Grandes Rivières | Sainte-Marie | école secondaire catholique Sainte-Marie | SEC | 7742 | 8875 | 8875-B01 | 340 HESSLE AVE | NEW LISKEARD | P0J1P0 | 35-13-90-101 | Temiskaming Shores | Temiskaming Shores C | Timiskaming District | TIMISKAMING | Northeast | North | 47.5164 | -79.6603 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44684 | 5660000 | Under Construction | Addition | Other | 2023-24 | 45170 | 0 | 0 | 0 | 3357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2303000 | 0 | 0 | 5660000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5660000 | 5660000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-001 | 60.2-001 | 60.2 | N/A | 29114 | CSC Franco-Nord | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 18310 | 7064 | 7064-B01 | 681C CHIPPEWA ST W | NORTH BAY | P1B6G8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3261 | -79.4518 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-002 | 60.2-002 | 60.2 | N/A | 29114 | CSC Franco-Nord | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 18310 | 7064 | 7064-B01 | 681C CHIPPEWA ST W | NORTH BAY | P1B6G8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3261 | -79.4518 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1030458 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150312 | 1150312 | 1150312 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-003 | 60.2-003 | 60.2 | N/A | 29114 | CSC Franco-Nord | Algonquin | école secondaire catholique Algonquin | SEC | 17273 | 6985 | 6985-B01 | 555 ALGONQUIN AVE | NORTH BAY | P1B4W8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3181 | -79.4662 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7660338 | Construction Complete | Addition | Condition | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4660338 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 7660338 | 7660338 | 7660338 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-004 | 60.2-004 | 60.2 | N/A | 29114 | CSC Franco-Nord | Franco-Cité | école secondaire catholique Franco-Cité | SEC | 3252 | 5103 | 5103-B01 | 90 MAIN ST | STURGEON FALLS | P2B2Z7 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3725 | -79.9282 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6402486 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 3547886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362000 | 3909886 | 0 | 2492600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2492600 | 6402486 | 6402486 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-005 | 60.2-005 | 60.2 | N/A | 29114 | CSC Franco-Nord | Algonquin | école secondaire catholique Algonquin | SEC | 11034 | 6985 | 6985-B01 | 555 ALGONQUIN AVE | NORTH BAY | P1B4W8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3182 | -79.4664 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 16700909 | Construction Complete | Retrofit | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16700909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16700909 | 16700909 | 16700909 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-006 | 60.2-006 | 60.2 | N/A | 29114 | CSC Franco-Nord | la Résurrection | école élémentaire catholique la Résurrection | ELE | 3615 | 7389 | 7389-B01 | 136 THIRD ST | STURGEON FALLS | P2B3C6 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3603 | -79.9236 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1555042 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515229 | 515229 | 1039813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1039813 | 1555042 | 1555042 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-007 | 60.2-007 | 60.2 | N/A | 29114 | CSC Franco-Nord | la Résurrection | école élémentaire catholique la Résurrection | ELE | 3615 | 7389 | 7389-B01 | 136 THIRD ST | STURGEON FALLS | P2B3C6 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3603 | -79.9236 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41695 | 1633122 | Construction Complete | Retrofit | Child Care | 2015-16 | 42248 | 323784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650444 | 0 | 658894 | 1633122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633122 | 1633122 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-008 | 60.2-008 | 60.2 | N/A | 29114 | CSC Franco-Nord | Lorrain | école élémentaire catholique Lorrain | ELE | 3389 | 7227 | 7227-B01 | 245 YONGE ST RR 1 | BONFIELD | P0H1E0 | 35-13-85-602 | Bonfield | Bonfield Tp | Nipissing District | NIPISSING | Northeast | North | 46.2363 | -79.1459 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 164 | - | - | N | - | Approved | 42205 | 2201427 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576665 | 0 | 0 | 576665 | 0 | 0 | 626119 | 0 | 998643 | 0 | 0 | 0 | 0 | 0 | 1624762 | 2201427 | 2201427 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 998643
60.2-009 | 60.2-009 | 60.2 | N/A | 29114 | CSC Franco-Nord | Mariale | école élémentaire catholique Mariale | ELE | 3404 | 7237 | 7237-B01 | 1000 BIRCH ST | THORNE | P0H2J0 | 35-13-85-000 | Nipissing District | Nipissing District | Nipissing District | NIPISSING | Northeast | North | 46.7004 | -79.1039 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 72 | - | - | N | - | Approved | 42135 | 1998000 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1998000 | 0 | 0 | 0 | 0 | 0 | 1998000 | 1998000 | 1998000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1998000
60.2-010 | 60.2-010 | 60.2 | N/A | 29114 | CSC Franco-Nord | Sainte-Anne-Élisabeth-Bruyère | école élémentaire et secondaire catholique Sainte-Anne-Élisabeth-Bruyère | ELE/SEC | 19994 | 8063 | 8063-B01 | 359 BRYDGES ST | MATTAWA | P0H1V0 | 35-13-85-403 | Mattawa | Mattawa T | Nipissing District | NIPISSING | Northeast | North | 46.3186 | -78.7119 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41072 | 17185027 | Construction Complete | New Construction | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 1729287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528606 | 0 | 0 | 2257893 | 14927134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14927134 | 17185027 | 17185027 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-012 | 60.2-012 | 60.2 | N/A | 29114 | CSC Franco-Nord | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 3663 | 7427 | 7427-B01 | 150 LEVESQUE ST | STURGEON FALLS | P0H2G0 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3699 | -79.9266 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40946 | 1173440 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 473440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473440 | 1173440 | 1173440 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-013 | 60.2-013 | 60.2 | N/A | 29114 | CSC Franco-Nord | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 3663 | 7427 | 7427-B01 | 150 LEVESQUE ST | STURGEON FALLS | P0H2G0 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3699 | -79.9266 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40946 | 523297 | Construction Complete | Demolition | Consolidation | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523297 | 0 | 0 | 523297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 523297 | 523297 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-014 | 60.2-014 | 60.2 | N/A | 29114 | CSC Franco-Nord | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 12725 | 7402 | 7402-B01 | 93 MICHAUD ST | STURGEON FALLS | P2B1B9 | 35-13-85-406 | West Nipissing | West Nipissing M | Nipissing District | NIPISSING | Northeast | North | 46.3735 | -79.9213 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 8940768 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8940768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8940768 | 8940768 | 8940768 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-016 | 60.2-016 | 60.2 | N/A | 29114 | CSC Franco-Nord | Saints-Anges | école élémentaire catholique Saints-Anges | ELE | 19969 | 7064 | 7064-B01 | 681B CHIPPEWA ST W | NORTH BAY | P1B6G8 | 35-13-85-101 | North Bay | North Bay C | Nipissing District | NIPISSING | Northeast | North | 46.3261 | -79.4518 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41072 | 12704169 | Construction Complete | Addition | Condition | 2012-13 | 41153 | 0 | 0 | 862275 | 639380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515230 | 0 | 0 | 2016885 | 10687284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10687284 | 12704169 | 12704169 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
60.2-017-01 | 60.2-017 | 60.2 | N/A | 29114 | CSC Franco-Nord | Saint-Thomas-d'Aquin | école élémentaire catholique Saint-Thomas-d'Aquin | ELE | 24391 | 19392 | 19392-B01 | 1245 VILLAGE RD RR 1 | ASTORVILLE | P0H1B0 | 35-13-85-606 | East Ferris | East Ferris M | Nipissing District | NIPISSING | Northeast | North | 46.187 | -79.2866 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 245 | - | - | N | - | Approved | 41850 | 8126396 | Construction Complete | New Construction | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845693 | 0 | 7280703 | 0 | 0 | 0 | 0 | 0 | 8126396 | 8126396 | 8126396 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7280703
60.2-017-02 | 60.2-017 | 60.2 | N/A | 29114 | CSC Franco-Nord | Saint-Thomas-d'Aquin | école élémentaire catholique Saint-Thomas-d'Aquin | ELE | 24391 | 19392 | 19392-L01 | 1245 VILLAGE RD RR 1 | ASTORVILLE | P0H1B0 | 35-13-85-606 | East Ferris | East Ferris M | Nipissing District | NIPISSING | Northeast | North | 46.187 | -79.2866 | 41725 | 2013-14 | 2013-14 | 41725 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41725 | 2112022 | Construction Complete | Land Acquisition | Condition | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112022 | 0 | 0 | 0 | 0 | 0 | 0 | 2112022 | 2112022 | 2112022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2112022
61-001 | 61-001 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 24243 | 19235 | 19235-B01 | 201 JOGUES ST | SUDBURY | P3C5L7 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4977 | -80.9904 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-002 | 61-002 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Projects MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 24243 | 19235 | 19235-B01 | 201 JOGUES ST | SUDBURY | P3C5L7 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4977 | -80.9904 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4185621 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3598529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3598529 | 3598529 | 4185622 | 587093 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-003 | 61-003 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Alliance-Saint-Joseph | école élémentaire catholique Alliance-Saint-Joseph | ELE | 4095 | 7750 | 7750-B01 | 3634 ERRINGTON AVE | CHELMSFORD | P0M1L0 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.585 | -81.1981 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7430193 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 247256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145233 | 392489 | 7037704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7037704 | 7430193 | 7430193 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-004 | 61-004 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Collège Notre-Dame | école secondaire catholique Collège Notre-Dame | SEC | 3147 | 7069 | 7069-B01 | 100 LEVIS ST | SUDBURY | P3C2H1 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4988 | -80.993 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4500000 | Construction Complete | Retrofit | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 4500000 | 4500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-005 | 61-005 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | du Sacré-Cœur | école secondaire catholique du Sacré-Cœur | SEC | 10562 | 8649 | 8649-B01 | 261 NOTRE DAME AVE | SUDBURY | P3C5K4 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4998 | -80.9889 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6730431 | Construction Complete | Retrofit | Other | 2003-04 | 37865 | 1233578 | 0 | 574638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88395 | 1896611 | 4833820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4833820 | 6730431 | 6730431 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-007 | 61-007 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Jean-Paul II | école élémentaire catholique Jean-Paul II | ELE | 3478 | 7285 | 7285-B01 | 1795 MAIN ST | VAL CARON | P3N1R8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6097 | -81.0144 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8726902 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 1068826 | 0 | 196083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102395 | 1367304 | 7359598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7359598 | 8726902 | 8726902 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-008 | 61-008 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Jean-Paul II | école élémentaire catholique Jean-Paul II | ELE | 3478 | 7285 | 7285-L01 | 1795 MAIN ST | VAL CARON | P3N1R8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.6097 | -81.0144 | 41058 | 2011-12 | 2012-13 | 41058 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 550000 | Construction Complete | Land Acquisition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 550000 | 550000 | 550000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 550000
61-009 | 61-009 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Jeunesse-Nord | école secondaire catholique Jeunesse-Nord | SEC | 10618 | 11283 | 11283-B01 | 117 YOUNGFOX RD | BLIND RIVER | P0R1B0 | 35-13-80-401 | Blind River | Blind River T | Algoma District | ALGOMA | Northeast | North | 46.1849 | -82.9654 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6995564 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158929 | 158929 | 6836635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6836635 | 6995564 | 6995564 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-011 | 61-011 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Notre-Dame-du-Sault | école élémentaire et secondaire catholique Notre-Dame-du-Sault | ELE/SEC | 11188 | 7287 | 7287-B01 | 600 NORTH ST | SAULT STE. MARIE | P6B2B9 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5327 | -84.3358 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40605 | 13667492 | Construction Complete | Addition | FL Capital Transitional | 2012-13 | 41153 | 263228 | 0 | 274820 | 1473687 | 0 | 874936 | 0 | 0 | 0 | 0 | 0 | 0 | 541218 | 0 | 0 | 3427889 | 10239603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10239603 | 13667492 | 13667492 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-015 | 61-015 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Saint-Denis | école élémentaire catholique Saint-Denis | ELE | 11189 | 12342 | 12342-B01 | 1200 RAMSEY VIEW CRT | SUDBURY | P3E0E5 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4785 | -81.0069 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 319 | - | - | N | - | Not Required | - | 11927575 | Construction Complete | New Construction | Condition | 2012-13 | 41153 | 0 | 0 | 822738 | 0 | 0 | 690744 | 0 | 0 | 0 | 0 | 0 | 0 | 533151 | 0 | 0 | 2046633 | 9614367 | 0 | 266575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9880942 | 11927575 | 11927575 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-018 | 61-018 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Sainte-Marie | école élémentaire catholique Sainte-Marie | ELE | 2857 | 6966 | 6966-B01 | 25 MARIER ST | AZILDA | P0M1B0 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.5525 | -81.1153 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3891780 | Construction Complete | Addition | Other | 2007-08 | 39326 | 2380370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 2397370 | 1494410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1494410 | 3891780 | 3891780 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-022 | 61-022 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 6011 | 8529 | 8529-L01 | 44 LAWTON ST | BLIND RIVER | P0R1B0 | 35-13-80-401 | Blind River | Blind River T | Algoma District | ALGOMA | Northeast | North | 46.1861 | -82.9519 | 41815 | 2013-14 | 2014-15 | 41815 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41815 | 324900 | Construction Complete | Land Acquisition | Other | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324900 | 0 | 0 | 0 | 0 | 0 | 0 | 324900 | 324900 | 324900 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 324900
61-024 | 61-024 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Saint-Joseph | école élémentaire et secondaire catholique Saint-Joseph | ELE/SEC | 10637 | 8831 | 8831-B02 | 101 CHURCHILL AVE | WAWA | P0S1K0 | 35-13-80-608 | Wawa | Wawa M | Algoma District | ALGOMA | Northeast | North | 47.9913 | -84.7774 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7956024 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 196091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34837 | 230928 | 7725096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7725096 | 7956024 | 7956024 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-026-01 | 31-007+61-026 | 61 | 307 - DSSAB Manitoulin-Sudbury | 29122 | CSC du Nouvel-Ontario | Renaissance | école élémentaire et secondaire catholique Renaissance | ELE/SEC | 11184-24607 | 7405 | 7405-B02 | 273 MEAD BLVD | ESPANOLA | P5E1B3 | 35-13-88-405 | Espanola | Espanola T | Sudbury District | SUDBURY | Northeast | North | 46.2603 | -81.7729 | 41758 | 2013-14 | 2014-15 | - | - | - | 41758 | 2013-14 | 2014-15 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 310 | 3 | 49 | N | - | Approved | 43161 | 14324815 | Construction Complete | New Construction | FL Capital Transitional | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317977 | 317977 | 0 | 0 | 0 | 0 | 12594386 | 0 | 1412452 | 0 | 0 | 0 | 14006838 | 14324815 | 14324815 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14006838
61-026-02 | 31-007+61-026 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Renaissance | école élémentaire et secondaire catholique Renaissance | ELE/SEC | 11184-24607 | 7405 | 7405-L02 | 273 MEAD BLVD | ESPANOLA | P5E1B3 | 35-13-88-405 | Espanola | Espanola T | Sudbury District | SUDBURY | Northeast | North | 46.2603 | -81.7729 | 42178 | 2014-15 | 2015-16 | 42178 | 2014-15 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42178 | 555553 | Construction Complete | Land Acquisition | FL Capital Transitional | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555553 | 0 | 0 | 0 | 0 | 0 | 0 | 555553 | 555553 | 555553 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 555553
61-028 | 61-028 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Saint-Pierre | école élémentaire catholique Saint-Pierre | ELE | 4427 | 7972 | 7972-B01 | 2115 RITA ST | SUDBURY | P3B1L9 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4889 | -80.9314 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 973929 | Construction Complete | Addition | Child Care | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533151 | 0 | 0 | 533151 | 440778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440778 | 973929 | 973929 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-029 | 61-029 | 61 | N/A | 29122 | CSC du Nouvel-Ontario | Trillium | école élémentaire et secondaire catholique Trillium | ELE/SEC | 10813 | 12049 | 12049-B01 | 9 BROOMHEAD RD | CHAPLEAU | P0M1K0 | 35-13-88-606 | Chapleau | Chapleau Tp | Sudbury District | SUDBURY | Northeast | North | 47.8411 | -83.41 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9368971 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 27177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 87177 | 9281794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281794 | 9368971 | 9368971 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
61-030 | 61-030 | 61 | 202 - CMSM Greater Sudbury | 29122 | CSC du Nouvel-Ontario | Hanmer-Val Thérèse | école élémentaire catholique Hanmer-Val Thérèse | ELE | 24608 | 19614 | 19614-B01 | TBD | SUDBURY | TBD | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | TBD | TBD | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | 567 | 4 | 73 | Y | 1 | Approved | 44972 | 24528646 | Planned | New Construction | Consolidation | 2023-24 | 45170 | 0 | 0 | 546095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546095 | 0 | 0 | 2061789 |  | 15557764 | 0 | 3511669 | 589879 | 0 | 0 | 21721101 | 22267196 | 24528646 | 2261450 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 19659312
61-031 | 61-031 | 61 | 307 - DSSAB Manitoulin-Sudbury | 29122 | CSC du Nouvel-Ontario | Saint-Charles-Borromée | école élémentaire catholique Saint-Charles-Borromée | ELE | 3029 | 6990 | 6990-B01 | 22 STE ANNE ST | ST CHARLES | P0M2W0 | 35-13-88-413 | St. Charles | St.-Charles M | Sudbury District | SUDBURY | Northeast | North | 46.364 | -80.4192 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2017-18 | 43160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299982 | 0 | 0 | 0 | 299982 | 299982 | 299982 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 299982
61-032 | 61-030 | 61 | 202 - CMSM Greater Sudbury | 29122 | CSC du Nouvel-Ontario | Hanmer-Val Thérèse | école élémentaire catholique Hanmer-Val Thérèse | ELE | 24608 | 19614 | 19614-L01 | TBD | SUDBURY | TBD | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | TBD | TBD | 44138 | 2020-21 | 2020-21 | 44138 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44706 | 2182221 | Construction Complete | Land Acquisition | Consolidation | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191688 | 0 | 0 | 0 | 0 | 0 | 0 | 3191688 | 3191688 | 930238 | -2261450 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3191688
62-001 | 62-001 | 62 | N/A | 29130 | CSDC des Aurores boréales | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 24187 | 11284 | 11284-B01 | 175 HIGH ST N | THUNDER BAY | p7a8c7 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4444 | -89.2294 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-002 | 62-002 | 62 | N/A | 29130 | CSDC des Aurores boréales | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 24187 | 11284 | 11284-B01 | 175 HIGH ST N | THUNDER BAY | p7a8c7 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4444 | -89.2294 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 687124 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760162 | 760162 | 687124 | -73038 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-003 | 62-003 | 62 | N/A | 29130 | CSDC des Aurores boréales | de la Vérendrye | école secondaire catholique de la Vérendrye | SEC | 10740 | 11284 | 11284-B01 | 175 HIGH ST N | THUNDER BAY | p7a8c7 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4444 | -89.2294 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12001419 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12001419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12001419 | 12001419 | 12001419 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-004 | 62-004 | 62 | N/A | 29130 | CSDC des Aurores boréales | de la Vérendrye | école secondaire catholique de la Vérendrye | SEC | 10740 | 11284 | 11284-B01 | 175 HIGH ST N | THUNDER BAY | p7a8c7 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4444 | -89.2294 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1200000 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-005 | 62-005 | 62 | N/A | 29130 | CSDC des Aurores boréales | de l'Enfant-Jésus | école élémentaire catholique de l'Enfant-Jésus | ELE | 11039 | 5377 | 5377-B01 | 161 AIRPORT RD | DRYDEN | P8N2Y4 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7935 | -92.7552 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1556402 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1556402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1556402 | 1556402 | 1556402 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-008 | 62-008 | 62 | N/A | 29130 | CSDC des Aurores boréales | Franco-Supérieur | école élémentaire catholique Franco-Supérieur | ELE | 6515 | 5187 | 5187-B01 | 220 ELGIN ST | THUNDER BAY | P7A0A4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4407 | -89.2147 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 600534 | Construction Complete | Addition | Child Care | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600534 | 0 | 0 | 600534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600534 | 600534 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-009 | 62-009 | 62 | N/A | 29130 | CSDC des Aurores boréales | Franco-Supérieur | école élémentaire catholique Franco-Supérieur | ELE | 6515 | 5187 | 5187-B01 | 220 ELGIN ST | THUNDER BAY | P7A0A4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4407 | -89.2147 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1474987 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1474987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1474987 | 1474987 | 1474987 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-011 | 34.2-005-62-011 | 62 | N/A | 29130 | CSDC des Aurores boréales | Franco-Terrace | école élémentaire catholique Franco-Terrace | ELE | 11069 | 12063 | 12063-B01 | 17 CARTIER RD | TERRACE BAY | P0T2W0 | 35-14-89-613 | Terrace Bay | Terrace Bay Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 48.7812 | -87.1046 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2214613 | Construction Complete | New Construction | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214613 | 2214613 | 2214613 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-012 | 62-012 | 62 | N/A | 29130 | CSDC des Aurores boréales | Immaculée-Conception | école élémentaire catholique Immaculée-Conception | ELE | 10768 | 11470 | 11470-B01 | 119 LILY PAD RD | IGNACE | P0T1T0 | 35-14-89-602 | Dorion | Dorion Tp | Thunder Bay District | THUNDER BAY | Northwest | North | 49.4055 | -91.6592 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3000000 | Construction Complete | Retrofit | Condition | 2016-17 | 42614 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-013 | 62-013 | 62 | N/A | 29130 | CSDC des Aurores boréales | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 4099 | 5005 | 5005-B01 | 308 4TH ST N | GERALDTON | P0T1M0 | 35-14-89-404 | Greenstone | Greenstone M | Thunder Bay District | THUNDER BAY | Northwest | North | 49.7284 | -86.9453 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 202994 | Construction Complete | Retrofit | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202994 | 202994 | 202994 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
62-014 | 62-014 | 62 | N/A | 29130 | CSDC des Aurores boréales | Franco-Supérieur | école élémentaire catholique Franco-Supérieur | ELE | 6515 | 5187 | 5187-L01 | 220 ELGIN ST | THUNDER BAY | P7A0A4 | 35-14-89-101 | Thunder Bay | Thunder Bay C | Thunder Bay District | THUNDER BAY | Northwest | North | 48.4407 | -89.2147 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44280 | 335488 | Construction Complete | Land Acquisition | Other | 2021-22 | 44440 | 0 | 0 | 0 | 335488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335488 | 335488 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-001 | 63-001 | 63 | N/A | 67300 | CSC Providence | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 24188 | 19180 | 19180-B01 | 7515 FOREST GLADE DR | WINDSOR | N8T3P5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.297 | -82.9264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-002 | 63-002 | 63 | N/A | 67300 | CSC Providence | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 24188 | 19180 | 19180-B01 | 7515 FOREST GLADE DR | WINDSOR | N8T3P5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.297 | -82.9264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 654615 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590943 | 590943 | 590943 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-003 | 63-003 | 63 | N/A | 67300 | CSC Providence | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24188 | 19180 | 19180-B01 | 7515 FOREST GLADE DR | WINDSOR | N8T3P5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.297 | -82.9264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4182 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4182 | 4182 | 4182 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-004 | 63-004 | 63 | N/A | 67300 | CSC Providence | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24188 | 19180 | 19180-B01 | 7515 FOREST GLADE DR | WINDSOR | N8T3P5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.297 | -82.9264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 31287 | Construction Complete | Other | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31287 | 31287 | 31287 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-005 | 63-005 | 63 | N/A | 67300 | CSC Providence | de Pain Court | école secondaire catholique de Pain Court | SEC | 3216 | 7112 | 7112-B01 | 14 NOTRE DAME ST | PAIN COURT | N0P1Z0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.3918 | -82.2941 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2230070 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230070 | 2230070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230070 | 2230070 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-006 | 63-006 | 63 | N/A | 67300 | CSC Providence | EJ Lajeunesse | école secondaire catholique EJ Lajeunesse | SEC | 7839 | 8924 | 8924-B01 | 600 E C ROW AVE W | WINDSOR | N9E1A5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2769 | -83.0198 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2230467 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230467 | 2230467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230467 | 2230467 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-007 | 63-007 | 63 | N/A | 67300 | CSC Providence | Frère-André | école élémentaire catholique Frère-André | ELE | 5970 | 8510 | 8510-B01 | 400 BASE LINE RD W | LONDON | N6J1W1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9633 | -81.2784 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2060320 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060320 | 2060320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060320 | 2060320 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-008 | 63-008 | 63 | N/A | 67300 | CSC Providence | Georges-P-Vanier | école élémentaire catholique Georges-P-Vanier | ELE | 7811 | 8897 | 8897-B01 | 6200 EDGAR ST | WINDSOR | N8S2A6 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3245 | -82.9593 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41806 | 771589 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 6854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6854 | 0 | 0 | 726877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726877 | 733731 | 733731 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-009 | 63-009 | 63 | N/A | 67300 | CSC Providence | l'Essor | école secondaire catholique l'Essor | SEC | 9288 | 10110 | 10110-B01 | 13605 ST. GREGORY'S RD | WINDSOR | N8N3E4 | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.3137 | -82.864 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 4819297 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4819297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4819297 | 4819297 | 4819297 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-010 | 63-010 | 63 | N/A | 67300 | CSC Providence | Monseigneur-Jean-Noël | école élémentaire catholique Monseigneur-Jean-Noël | ELE | 7818 | 8903 | 8903-B01 | 3225 CALIFORNIA AVE | WINDSOR | N9E3K5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2589 | -83.0345 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 73310 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23903 | 23903 | 49407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49407 | 73310 | 73310 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-011 | 63-011 | 63 | N/A | 67300 | CSC Providence | Monseigneur-Jean-Noël | école élémentaire catholique Monseigneur-Jean-Noël | ELE | 7818 | 8903 | 8903-B01 | 3225 CALIFORNIA AVE | WINDSOR | N9E3K5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2589 | -83.0345 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1659935 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150861 | 150861 | 1343213 | 165861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509074 | 1659935 | 1659935 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-012 | 63-012 | 63 | N/A | 67300 | CSC Providence | Pavillon des Jeunes | école élémentaire catholique Pavillon des Jeunes | ELE | 3193 | 7101 | 7101-B01 | 326 ROURKE LINE RR 3 | BELLE RIVER | N0R1A0 | 35-15-45-412 | Lakeshore | Lakeshore T | Essex Co | ESSEX | Southwest | South | 42.2879 | -82.7329 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40798 | 2188231 | Construction Complete | Addition | Child Care | 2014-15 | 41883 | 0 | 434000 | 0 | 279652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442653 | 0 | 134146 | 1290451 | 0 | 0 | 1032842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032842 | 2323293 | 2323293 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-013 | 63-013 | 63 | N/A | 67300 | CSC Providence | Pavillon des Jeunes | école élémentaire catholique Pavillon des Jeunes | ELE | 3193 | 7101 | 7101-B01 | 326 ROURKE LINE RR 3 | BELLE RIVER | N0R1A0 | 35-15-45-412 | Lakeshore | Lakeshore T | Essex Co | ESSEX | Southwest | South | 42.2879 | -82.7329 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2027581 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 2027581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027581 | 2027581 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-014 | 63-014 | 63 | N/A | 67300 | CSC Providence | Saint-Antoine | école élémentaire catholique Saint-Antoine | ELE | 3771 | 7507 | 7507-B01 | 1317 LESPERANCE RD | WINDSOR | N8N1X6 | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.3099 | -82.8866 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 661795 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 75582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75582 | 0 | 0 | 484584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484584 | 560166 | 560166 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-015 | 63-015 | 63 | N/A | 67300 | CSC Providence | Saint-Antoine | école élémentaire catholique Saint-Antoine | ELE | 3771 | 7507 | 7507-B01 | 1317 LESPERANCE RD | WINDSOR | N8N1X6 | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.3099 | -82.8866 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Cancelled | - | 0 | Cancelled | Cancelled | Other | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-016 | 63-016 | 63 | N/A | 67300 | CSC Providence | Saint-Dominique-Savio | école élémentaire et secondaire catholique Saint-Dominique-Savio | ELE/SEC | 10542 | 11159 | 11159-B01 | 800 23RD ST E | OWEN SOUND | N4K6Z5 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5871 | -80.9233 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Not Required | - | 3778053 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 459490 | 0 | 0 | 420916 | 0 | 0 | 179853 | 0 | 0 | 447960 | 0 | 0 | 1508219 | 0 | 0 | 484585 | 0 | 1785249 | 0 | 0 | 0 | 0 | 0 | 2269834 | 3778053 | 3778053 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1785249
63-017 | 63-017 | 63 | N/A | 67300 | CSC Providence | Saint-Dominique-Savio | école élémentaire et secondaire catholique Saint-Dominique-Savio | ELE/SEC | 10542 | 11159 | 11159-B01 | 800 23RD ST E | OWEN SOUND | N4K6Z5 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5871 | -80.9233 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6612335 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6612335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6612335 | 6612335 | 6612335 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-018 | 63-018 | 63 | N/A | 67300 | CSC Providence | Saint-Edmond | école élémentaire catholique Saint-Edmond | ELE | 10392 | 8923 | 8923-B01 | 1880 TOTTEN ST | WINDSOR | N9B1X3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2893 | -83.0473 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1544118 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544118 | 1544118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544118 | 1544118 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-019 | 63-019 | 63 | N/A | 67300 | CSC Providence | Sainte-Jeanne-d'Arc | école élémentaire catholique Sainte-Jeanne-d'Arc | ELE | 5873 | 5044 | 5044-B01 | 35 FALLONS LANE | LONDON | N5V5C1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0252 | -81.2024 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2291319 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2291319 | 2291319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2291319 | 2291319 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-020 | 63-020 | 63 | N/A | 67300 | CSC Providence | Sainte-Jeanne-d'Arc | école élémentaire catholique Sainte-Jeanne-d'Arc | ELE | 5873 | 5044 | 5044-B01 | 35 FALLONS LANE | LONDON | N5V5C1 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 43.0252 | -81.2024 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 940057 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679395 | 679395 | 260662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260662 | 940057 | 940057 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-021 | 63-021 | 63 | N/A | 67300 | CSC Providence | Sainte-Marguerite-Bourgeoys-Notre-Dame | école élémentaire et secondaire catholique Sainte-Marguerite-Bourgeoys-Notre-Dame | ELE/SEC | 16797 | 19018 | 19018-B01 | 700 BRISTOL ST | WOODSTOCK | N4T0E4 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1493 | -80.7151 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 350 | - | - | N | - | Not Required | - | 15380193 | Construction Complete | New Construction | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434585 | 0 | 0 | 434585 | 14491484 | 0 | 434585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14926069 | 15360654 | 15360654 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-022 | 63-022 | 63 | N/A | 67300 | CSC Providence | Sainte-Marguerite-d'Youville | école élémentaire catholique Sainte-Marguerite-d'Youville | ELE | 9289 | 10111 | 10111-B01 | 13025 ST. THOMAS ST | WINDSOR | N8N3P3 | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.321 | -82.8742 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Not Required | - | 1033126 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484585 | 0 | 548541 | 0 | 0 | 0 | 0 | 0 | 1033126 | 1033126 | 1033126 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 548541
63-023 | 63-023 | 63 | N/A | 67300 | CSC Providence | Sainte-Marie | école secondaire catholique Sainte-Marie | SEC | 3199 | 5032 | 5032-B01 | 431 JULIANA DR | WOODSTOCK | N4V1E8 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1133 | -80.7496 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 234556 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234556 | 234556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234556 | 234556 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-024 | 63-024 | 63 | N/A | 67300 | CSC Providence | Sainte-Marie | Administrative Office | OFF-ADM | 4205 | 7827 | 7827-B01 | 105 GLENWOOD DR | CHATHAM | N7L3X5 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4216 | -82.2045 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 17022 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17022 | 17022 | 17022 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-025 | 63-025 | 63 | N/A | 67300 | CSC Providence | Sainte-Marie | école élémentaire catholique Sainte-Marie | ELE | 11064 | 12167 | 12167-B01 | 90 DALE DR | CHATHAM | N7L0B2 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4004 | -82.2282 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7813905 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21996 | 21996 | 7791909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7791909 | 7813905 | 7813905 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-026 | 63-026 | 63 | N/A | 67300 | CSC Providence | Sainte-Marie | école élémentaire catholique Sainte-Marie | ELE | 11064 | 12167 | 12167-B01 | 90 DALE DR | CHATHAM | N7L0B2 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4004 | -82.2282 | 41877 | 2013-14 | 2014-15 | - | - | - | 41877 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Approved | 42102 | 2948748 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 348226 | 0 | 0 | 0 | 0 | 0 | 577774 | 0 | 0 | 926000 | 0 | 0 | 0 | 0 | 2022748 | 0 | 0 | 0 | 0 | 0 | 2022748 | 2948748 | 2948748 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2022748
63-027 | 63-027 | 63 | N/A | 67300 | CSC Providence | Sainte-Thérèse | école élémentaire catholique Sainte-Thérèse | ELE | 7824 | 8909 | 8909-B01 | 5305 TECUMSEH RD E | WINDSOR | N8T1C5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3081 | -82.96 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2293279 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2293279 | 2293279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2293279 | 2293279 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-028 | 63-028 | 63 | N/A | 67300 | CSC Providence | Sainte-Thérèse | école élémentaire catholique Sainte-Thérèse | ELE | 7824 | 8909 | 8909-B01 | 5305 TECUMSEH RD E | WINDSOR | N8T1C5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3081 | -82.96 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Not Required | - | 4338356 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422925 | 0 | 1915431 | 0 | 0 | 0 | 0 | 0 | 4338356 | 4338356 | 4338356 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1915431
63-029 | 63-029 | 63 | N/A | 67300 | CSC Providence | Saint-Francis | école élémentaire catholique Saint-Francis | ELE | 3942 | 7637 | 7637-B01 | 11 ST. CLAIR ST | TILBURY | N0P2L0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.2592 | -82.4351 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 263138 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263138 | 263138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263138 | 263138 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-030 | 58-020+63-030 | 63 | N/A | 67300 | CSC Providence | Saint-François-Xavier | école secondaire catholique Saint-François-Xavier | SEC | 3944 | 5085 | 5085-B01 | 901 THE RAPIDS PKY | SARNIA | N7S6K2 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9934 | -82.3537 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3807436 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 225943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 2025943 | 1781493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781493 | 3807436 | 3807436 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-031 | 63-031 | 63 | N/A | 67300 | CSC Providence | Saint-Jean-Baptiste | école élémentaire catholique Saint-Jean-Baptiste | ELE | 11266 | 12345 | 12345-B01 | 365 FRYER ST | AMHERSTBURG | N9V0C3 | 35-15-45-409 | Amherstburg | Amherstburg T | Essex Co | ESSEX | Southwest | South | 42.0978 | -83.0985 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8784107 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459801 | 509801 | 8274306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8274306 | 8784107 | 8784107 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-032 | 63-032 | 63 | N/A | 67300 | CSC Providence | Saint-Jean-Baptiste | école élémentaire catholique Saint-Jean-Baptiste | ELE | 11266 | 12345 | 12345-L01 | 365 FRYER ST | AMHERSTBURG | N9V0C3 | 35-15-45-409 | Amherstburg | Amherstburg T | Essex Co | ESSEX | Southwest | South | 42.0978 | -83.0985 | 41941 | 2014-15 | 2014-15 | 41941 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 179092 | Construction Complete | Land Acquisition | Other | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179092 | 0 | 0 | 0 | 0 | 0 | 0 | 179092 | 179092 | 179092 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 179092
63-033 | 63-033 | 63 | N/A | 67300 | CSC Providence | Saint-Jean-de-Brébeuf | école élémentaire catholique Saint-Jean-de-Brébeuf | ELE | 11063 | 12166 | 12166-B01 | 270 CHELTON RD | LONDON | N6M0B9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9582 | -81.1761 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7834112 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 844885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049625 | 1894510 | 5939602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5939602 | 7834112 | 7834112 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-034 | 63-034 | 63 | N/A | 67300 | CSC Providence | Saint-Jean-de-Brébeuf | école élémentaire catholique Saint-Jean-de-Brébeuf | ELE | 11063 | 12166 | 12166-B01 | 270 CHELTON RD | LONDON | N6M0B9 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | 42.9582 | -81.1761 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 92 | - | - | N | - | Not Required | - | 891119 | Construction Complete | Addition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891119 | 0 | 0 | 0 | 0 | 0 | 891119 | 891119 | 891119 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 891119
63-035 | 63-035 | 63 | N/A | 67300 | CSC Providence | Saint-Michel | école élémentaire catholique Saint-Michel | ELE | 4299 | 7890 | 7890-B01 | 33 SHERMAN ST | LEAMINGTON | N8H5H6 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0428 | -82.5942 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 44808 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25673 | 25673 | 19135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19135 | 44808 | 44808 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-036 | 63-036 | 63 | N/A | 67300 | CSC Providence | Saint-Michel | école élémentaire catholique Saint-Michel | ELE | 4299 | 7890 | 7890-B01 | 33 SHERMAN ST | LEAMINGTON | N8H5H6 | 35-15-45-413 | Leamington | Leamington M | Essex Co | ESSEX | Southwest | South | 42.0428 | -82.5942 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1858676 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503846 | 503846 | 1354830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354830 | 1858676 | 1858676 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-037 | 63-037 | 63 | N/A | 67300 | CSC Providence | Saint-Philippe | école élémentaire catholique Saint-Philippe | ELE | 4419 | 7965 | 7965-B01 | 7195 ST PHILIPPES LINE RR 1 | GRANDE POINTE | N0P1S0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4426 | -82.3527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 25060 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25060 | 25060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25060 | 25060 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-038 | 63-038 | 63 | N/A | 67300 | CSC Providence | Saint-Philippe | école élémentaire catholique Saint-Philippe | ELE | 4419 | 7965 | 7965-B01 | 7195 ST PHILIPPES LINE RR 1 | GRANDE POINTE | N0P1S0 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4426 | -82.3527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 745053 | Construction Complete | Addition | Other | 2014-15 | 41883 | 0 | 0 | 0 | 268752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268752 | 0 | 0 | 484584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484584 | 753336 | 753336 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-039 | 63-039 | 63 | N/A | 67300 | CSC Providence | Saint-Thomas-d'Aquin | école élémentaire catholique Saint-Thomas-d'Aquin | ELE | 4504 | 8030 | 8030-B01 | 931 CHAMPLAIN RD | SARNIA | N7V2E9 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9996 | -82.3767 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1456771 | Construction Complete | Addition | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456771 | 1456771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1456771 | 1456771 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-040 | 63-040 | 63 | N/A | 67300 | CSC Providence | Saint-Thomas-d'Aquin | école élémentaire catholique Saint-Thomas-d'Aquin | ELE | 4504 | 8030 | 8030-B01 | 931 CHAMPLAIN RD | SARNIA | N7V2E9 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9996 | -82.3767 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 31287 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31287 | 31287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31287 | 31287 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-041 | 63-041 | 63 | N/A | 67300 | CSC Providence | Siège Social du CSCP | Administrative Office | OFF-ADM | 24188 | 19180 | 19180-B01 | 7515 FOREST GLADE DR | WINDSOR | N8T3P5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.297 | -82.9264 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 633522 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633522 | 633522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633522 | 633522 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-042 | 63-042 | 63 | N/A | 67300 | CSC Providence | Sainte-Marguerite-Bourgeoys-Notre-Dame | école élémentaire et secondaire catholique Sainte-Marguerite-Bourgeoys-Notre-Dame | ELE/SEC | 16797 | 19018 | 19018-B01 | 700 BRISTOL ST | WOODSTOCK | N4T0E4 | 35-15-37-101 | Woodstock | Woodstock C | Oxford Co | OXFORD | Southwest | South | 43.1493 | -80.7151 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | 184 | - | - | N | - | Approved | 42970 | 3770280 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3770280 | 0 | 0 | 0 | 0 | 0 | 3770280 | 3770280 | 3770280 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3770280
63-043 | 63-043 | 63 | N/A | 67300 | CSC Providence | EJ Lajeunesse | école secondaire catholique EJ Lajeunesse | SEC | 7839 | 8924 | 8924-B01 | 600 E C ROW AVE W | WINDSOR | N9E1A5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2769 | -83.0198 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 538445 | Construction Complete | Addition | Other | 2016-17 | 42614 | 0 | 0 | 0 | 538445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538445 | 538445 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
63-044 | 63-044 | 63 | 212 - CMSM Windsor | 67300 | CSC Providence | Sainte-Thérèse | école élémentaire catholique Sainte-Thérèse | ELE | 7824 | 8909 | 8909-B01 | 5305 TECUMSEH RD E | WINDSOR | N8T1C5 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.3081 | -82.96 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 45168 | 1742850 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 871425 | 0 | 0 | 871425 | 0 | 0 | 0 | 0 | 0 | 0 | 871426 | 0 | 0 | 0 | 871426 | 1742851 | 1742850 | -1 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 871426
63-045 | 63-045 | 63 | 212 - CMSM Windsor | 67300 | CSC Providence | Sainte-Marguerite-d'Youville | école élémentaire catholique Sainte-Marguerite-d'Youville | ELE | 9289 | 10111 | 10111-B01 | 13025 ST. THOMAS ST | WINDSOR | N8N3P3 | 35-15-45-414 | Tecumseh | Tecumseh T | Essex Co | ESSEX | Southwest | South | 42.321 | -82.8742 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44657 | 1770904 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270257 | 0 | 0 | 1270257 | 0 | 0 | 0 | 0 | 0 | 0 | 2086042 | 0 | 0 | 0 | 2086042 | 3356299 | 3356299 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 2086042
63-046 | 63-046 | 63 | 212 - CMSM Windsor | 67300 | CSC Providence | Saint-Edmond | école élémentaire catholique Saint-Edmond | ELE | 10392 | 8923 | 8923-B01 | 1880 TOTTEN ST | WINDSOR | N9B1X3 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2893 | -83.0473 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 44665 | 617894 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620418 | 0 | 0 | 620418 | 0 | 0 | 0 | 0 | 0 | 0 | 620419 | 0 | 0 | 0 | 620419 | 1240837 | 617894 | -622943 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 620419
63-047 | 63-047 | 63 | 215 - CMSM Grey | 67300 | CSC Providence | Saint-Dominique-Savio | école élémentaire catholique Saint-Dominique-Savio | ELE | 10541 | 11159 | 11159-B01 | 800 23RD ST E | OWEN SOUND | N4K6Z5 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5871 | -80.9233 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 44665 | 620079 | Under Construction | Addition | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100783 | 0 | 0 | 100783 | 0 | 0 | 0 | 0 | 0 | 0 | 519296 | 0 | 0 | 0 | 519296 | 620079 | 620079 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 519296
63-048 | 63-048 | 63 | N/A | 67300 | CSC Providence | Monseigneur-Bruyère | école secondaire catholique Monseigneur-Bruyère | SEC | TBD | TBD | TBD | HAMILTON RD / HIGHBURY AVE N | LONDON | TBD | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | TBD | TBD | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 587 | - | - | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2024-25 | 45536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18929013 | 0 | 0 | 0 | 0 | 0 | 18929013 | 18929013 | 18929013 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 18929013
64-001 | 64-001 | 64 | N/A | 67318 | CSC MonAvenir | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 24600 | 5152 | 5152-B01 | 110 DREWRY AVE | NORTH YORK | M2M1C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7863 | -79.4234 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -605000 | 0 | 924004 | 0 | 0 | 0 | 0 | 0 | 319004 | 319004 | 0 | -319004 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 924004
64-002 | 64-002 | 64 | N/A | 67318 | CSC MonAvenir | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 24600 | 5152 | 5152-B01 | 110 DREWRY AVE | NORTH YORK | M2M1C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7863 | -79.4234 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 15565295 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14965547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14965547 | 14965547 | 14965547 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-003 | 64-003 | 64 | N/A | 67318 | CSC MonAvenir | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24600 | 5152 | 5152-B01 | 110 DREWRY AVE | NORTH YORK | M2M1C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7863 | -79.4234 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 670294 | Construction Complete | Other | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670294 | 670294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670294 | 670294 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-004 | 64-004 | 64 | N/A | 67318 | CSC MonAvenir | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24600 | 5152 | 5152-B01 | 110 DREWRY AVE | NORTH YORK | M2M1C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7863 | -79.4234 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1022206 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1022206 | 1022206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1022206 | 1022206 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-005 | 64-005 | 64 | N/A | 67318 | CSC MonAvenir | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24600 | 5152 | 5152-B01 | 110 DREWRY AVE | NORTH YORK | M2M1C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7863 | -79.4234 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 869636 | Construction Complete | Other | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869636 | 869636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869636 | 869636 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-006 | 64-006 | 64 | N/A | 67318 | CSC MonAvenir | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 24600 | 5152 | 5152-B01 | 110 DREWRY AVE | NORTH YORK | M2M1C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7863 | -79.4234 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 185783 | Construction Complete | Other | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185783 | 185783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185783 | 185783 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-007 | 64-007 | 64 | N/A | 67318 | CSC MonAvenir | Ange-Gabriel | école élémentaire catholique Ange-Gabriel | ELE | 10398 | 7627 | 7627-B02 | 1830 MEADOWVALE BLVD | MISSISSAUGA | L5N7L2 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6144 | -79.7498 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6107670 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33474 | 33474 | 6074196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6074196 | 6107670 | 6107670 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-009-01 | 64-009 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Jean-Bosco | école élémentaire catholique Saint-Jean-Bosco | ELE | 11222 | 12348 | 12348-B01 | 55 ABBOTSIDE WAY | CALEDON | L7C4C3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7509 | -79.8176 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 277 | - | - | N | - | Approved | 42158 | 6531574 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698922 | 0 | 0 | 698922 | 0 | 0 | 475266 | 0 | 5357386 | 0 | 0 | 0 | 0 | 0 | 5832652 | 6531574 | 6531574 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5357386
64-009-02 | 64-009 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Jean-Bosco | école élémentaire catholique Saint-Jean-Bosco | ELE | 11222 | 12348 | 12348-L01 | 55 ABBOTSIDE WAY | CALEDON | L7C4C3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7509 | -79.8176 | 41228 | 2012-13 | 2012-13 | 41228 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41228 | 5793593 | Construction Complete | Land Acquisition | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5793593 | 0 | 0 | 0 | 0 | 0 | 0 | 5793593 | 5793593 | 5793593 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 5793593
64-011 | 64-011 | 64 | N/A | 67318 | CSC MonAvenir | du Bon Berger | école élémentaire catholique du Bon Berger | ELE | 18117 | 8059 | 8059-B01 | 343 JONES AVE | TORONTO | M4J3G4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6726 | -79.3368 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42079 | 4909626 | Construction Complete | Purchase | Accommodation Pressure | 2014-15 | 41883 | 609626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609626 | 0 | 0 | 1270014 | 0 | 3024736 | 0 | 0 | 0 | 0 | 0 | 4294750 | 4904376 | 4904376 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3024736
64-012 | 64-012 | 64 | N/A | 67318 | CSC MonAvenir | du Sacré-Cœur | école élémentaire catholique du Sacré-Cœur | ELE | 11193 | 12346 | 12346-B01 | 98 ESSEX ST | TORONTO | M6G1T3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6674 | -79.4248 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41019 | 9650687 | Construction Complete | Retrofit | Condition | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587537 | 0 | 0 | 587537 | 0 | 0 | 0 | 0 | 9063150 | 0 | 0 | 0 | 0 | 0 | 9063150 | 9650687 | 9650687 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 9063150
64-015 | 64-015 | 64 | N/A | 67318 | CSC MonAvenir | Immaculée-Conception | école élémentaire catholique Immaculée-Conception | ELE | 7968 | 5131 | 5131-B02 | 153 CHURCH ST | ST CATHARINES | L2R3E2 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.164 | -79.2412 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 388073 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388073 | 0 | 0 | 0 | 0 | 388073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388073 | 388073 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-016 | 64-016 | 64 | N/A | 67318 | CSC MonAvenir | Jean-Béliveau | école élémentaire catholique Jean-Béliveau | ELE | 11126 | 12351 | 12351-B01 | 19300 2ND CONCESSION RD | EAST GWILLIMBURY | L9N0H3 | 35-11-27-407 | East Gwillimbury | East Gwillimbury T | York R | YORK | GTA | South | 44.1028 | -79.468 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 10417044 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 9474990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698921 | 0 | 0 | 10173911 | 243133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243133 | 10417044 | 10417044 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-017 | 64-017 | 64 | N/A | 67318 | CSC MonAvenir | Jean-Paul II | école élémentaire catholique Jean-Paul II | ELE | 10746 | 6550 | 6550-B01 | 1001 HUTCHISON AVE | WHITBY | L1N2A3 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8776 | -78.9252 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3504441 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3219219 | 0 | 0 | 0 | 0 | 3219219 | 285222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285222 | 3504441 | 3504441 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-019 | 64-019 | 64 | N/A | 67318 | CSC MonAvenir | Jean-Vanier | école secondaire catholique Jean-Vanier | SEC | 10833 | 19615 | 19615-B01 | 620 RIVER | WELLAND | L3B5N6 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 43.0106 | -79.2335 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 16286626 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4994230 | 4994230 | 11292396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11292396 | 16286626 | 16286626 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-021 | 64-021 | 64 | N/A | 67318 | CSC MonAvenir | Marguerite-Bourgeois | école élémentaire catholique Marguerite-Bourgeois | ELE | 8279 | 9322 | 9322-B01 | 117 WATERLOO RD | BORDEN | L0M1C0 | 35-11-70-000 | Simcoe County | Simcoe Co | Simcoe Co | SIMCOE | Central | South | 44.2857 | -79.8836 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 537842 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537842 | 0 | 0 | 0 | 0 | 537842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537842 | 537842 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-023 | 64-023 | 64 | N/A | 67318 | CSC MonAvenir | Mère-Élisabeth-Bruyère | école élémentaire catholique Mère-Élisabeth-Bruyère | ELE | 10043 | 5194 | 5194-B01 | 280 GLENRIDGE DR | WATERLOO | N2J3W4 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4832 | -80.5104 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1905299 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605299 | 0 | 0 | 0 | 0 | 605299 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 1905299 | 1905299 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-024-01 | 64-024 | 64 | 230 - CMSM Halton | 67318 | CSC MonAvenir | Sainte-Anne | école élémentaire catholique Sainte-Anne | ELE | 24463 | 19466 | 19466-B01 | 1150 FERGUSON DR | MILTON | L9T0M7 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5193 | -79.8434 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 308 | 2 | 39 | Y | - | Approved | 43020 | 8407900 | Construction Complete | New Construction | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028507 | 0 | 0 | 1028507 | 0 | 0 | 771380 | 0 | 6921850 | 0 | 0 | 0 | 0 | 0 | 7693230 | 8721737 | 8721737 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6921850
64-024-02 | 64-024 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Anne | école élémentaire catholique Sainte-Anne | ELE | 24463 | 19466 | 19466-L01 | 1150 FERGUSON DR | MILTON | L9T0M7 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5193 | -79.8434 | 42062 | 2014-15 | 2014-15 | 42062 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42062 | 4987510 | Construction Complete | Land Acquisition | Accommodation Pressure | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4987510 | 0 | 0 | 0 | 0 | 0 | 0 | 4987510 | 4987510 | 4987510 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4987510
64-025-01 | 64-025 | 64 | 232 - CMSM Peel | 67318 | CSC MonAvenir | Mississauga | école élémentaire catholique Mississauga | ELE | 24464 | 19467 | 19467-B01 | TBD | MISSISSAUGA | TBD | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | TBD | TBD | 42647 | 2016-17 | 2016-17 | - | - | - | 42647 | 2016-17 | 2016-17 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 294 | 2 | 39 | N | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756255 | 0 | 5691509 | 0 | 2292467 | 0 | 0 | 0 | 8740231 | 8740231 | 8740231 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 7983976
64-025-02 | 64-025 | 64 | N/A | 67318 | CSC MonAvenir | Mississauga | école élémentaire catholique Mississauga | ELE | 24464 | 19467 | 19467-B01 | TBD | MISSISSAUGA | TBD | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | TBD | TBD | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Cancelled | - | 0 | Cancelled | Cancelled | Accommodation Pressure | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-027 | 64-027 | 64 | N/A | 67318 | CSC MonAvenir | Monseigneur-Jamot | école élémentaire catholique Monseigneur-Jamot | ELE | 9614 | 5182 | 5182-B01 | 186 ROMAINE ST | PETERBOROUGH | K9J2C4 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2918 | -78.3207 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 247711 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247711 | 0 | 0 | 0 | 0 | 247711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247711 | 247711 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-028-01 | 64-028 | 64 | 208 - CMSM Peterborough | 67318 | CSC MonAvenir | Monseigneur-Jamot | école élémentaire et secondaire catholique Monseigneur-Jamot | ELE/SEC | 24430 | 19430 | 19430-B01 | 2350 WOODGLADE BLVD | PETERBOROUGH | K9K2L1 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2923 | -78.3661 | 42279 | 2015-16 | 2015-16 | - | - | - | 42279 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 432 | 2 | 39 | N | - | Approved | 42299 | 11406371 | Construction Complete | New Construction | FL Capital Transitional | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452650 | 0 | 0 | 452650 | 0 | 0 | 988568 | 0 | 9419543 | 0 | 545610 | 0 | 0 | 0 | 10953721 | 11406371 | 11406371 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9965153
64-028-02 | 64-028 | 64 | N/A | 67318 | CSC MonAvenir | Monseigneur-Jamot | école élémentaire et secondaire catholique Monseigneur-Jamot | ELE/SEC | 24430 | 19430 | 19430-L01 | 2350 WOODGLADE BLVD | PETERBOROUGH | K9K2L1 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.2923 | -78.3661 | 41831 | 2013-14 | 2014-15 | 41831 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41831 | 7126250 | Construction Complete | Land Acquisition | FL Capital Transitional | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7126250 | 0 | 0 | 0 | 0 | 0 | 0 | 7126250 | 7126250 | 7126250 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 7126250
64-029 | 64-029 | 64 | N/A | 67318 | CSC MonAvenir | Notre-Dame | école élémentaire catholique Notre-Dame | ELE | 3462 | 7275 | 7275-B01 | 400 CUMBERLAND AVE | HAMILTON | L8M2A2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2419 | -79.8361 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1714548 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714548 | 0 | 0 | 0 | 0 | 1714548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714548 | 1714548 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-030-01 | 64-030 | 64 | N/A | 67318 | CSC MonAvenir | Notre-Dame-de-Grâce | école élémentaire catholique Notre-Dame-de-Grâce | ELE | 24495 | 9586 | 9586-B02 | 59 CLEMENT RD | ETOBICOKE | M9R1Y5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6794 | -79.5592 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 349 | - | - | N | - | Approved | 42496 | 13549598 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822576 | 0 | 0 | 822576 | 0 | 0 | 1418606 | 0 | 6004836 | 0 | 0 | 0 | 0 | 0 | 7423442 | 8246018 | 8246018 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6004836
64-030-02 | 64-030 | 64 | N/A | 67318 | CSC MonAvenir | Etobicoke | école élémentaire catholique Etobicoke | ELE | 18118 | 9586 | 9586-B01 | 59 CLEMENT RD | ETOBICOKE | M9R1Y5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6794 | -79.5592 | 40793 | 2011-12 | 2011-12 | - | - | - | 40793 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40793 | 4800000 | Construction Complete | Purchase | Accommodation Pressure | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800000 | 0 | 0 | 0 | 0 | 0 | 4800000 | 4800000 | 4800000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 4800000
64-030-03 | 64-030 | 64 | N/A | 67318 | CSC MonAvenir | Etobicoke | école élémentaire catholique Etobicoke | ELE | 18118 | 9586 | 9586-B01 | 59 CLEMENT RD | ETOBICOKE | M9R1Y5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6794 | -79.5592 | 40793 | 2011-12 | 2011-12 | - | - | - | 40793 | 2011-12 | 2011-12 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40793 | 4800000 | Construction Complete | Demolition | Accommodation Pressure | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503580 | 0 | 0 | 0 | 0 | 0 | 503580 | 503580 | 503580 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 503580
64-031-01 | 64-031 | 64 | 224 - CMSM Simcoe | 67318 | CSC MonAvenir | Notre-Dame-de-la-Huronie | école élémentaire catholique Notre-Dame-de-la-Huronie | ELE | 24429 | 19431 | 19431-B01 | 55 FINDLAY DR | COLLINGWOOD | L9Y0G6 | 35-11-70-403 | Collingwood | Collingwood T | Simcoe Co | SIMCOE | Central | South | 44.4828 | -80.2164 | 42279 | 2015-16 | 2015-16 | - | - | - | 42279 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 200 | 2 | 39 | N | - | Approved | 42292 | 6488294 | Construction Complete | New Construction | FL Capital Transitional | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452650 | 0 | 0 | 452650 | 0 | 0 | 494284 | 0 | 4995750 | 0 | 545610 | 0 | 0 | 0 | 6035644 | 6488294 | 6488294 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5541360
64-031-02 | 64-031 | 64 | N/A | 67318 | CSC MonAvenir | Notre-Dame-de-la-Huronie | école élémentaire catholique Notre-Dame-de-la-Huronie | ELE | 24429 | 19431 | 19431-L01 | 55 FINDLAY DR | COLLINGWOOD | L9Y0G6 | 35-11-70-403 | Collingwood | Collingwood T | Simcoe Co | SIMCOE | Central | South | 44.4828 | -80.2164 | 41509 | 2012-13 | 2013-14 | 41509 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41509 | 1376106 | Construction Complete | Land Acquisition | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376106 | 0 | 0 | 0 | 0 | 0 | 0 | 1376106 | 1376106 | 1376106 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1376106
64-032 | 64-032 | 64 | N/A | 67318 | CSC MonAvenir | Notre-Dame-de-la-Jeunesse | école élémentaire catholique Notre-Dame-de-la-Jeunesse | ELE | 8771 | 9667 | 9667-B01 | 71 RITCHIE AVE | AJAX | L1S6S5 | 35-11-10-401 | Ajax | Ajax T | Durham R | DURHAM | GTA | South | 43.8549 | -79.0359 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 396643 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396643 | 0 | 0 | 0 | 0 | 396643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396643 | 396643 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-034 | 64-034 | 64 | N/A | 67318 | CSC MonAvenir | Oakville | Oakville | HLA | 24531 | 19536 | 19536-L0- | TBD | OAKVILLE | TBD | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | TBD | TBD | 42486 | 2015-16 | 2016-17 | 42486 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42486 | 13265769 | Construction Complete | Land Acquisition | Other | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13265769 | 0 | 0 | 0 | 0 | 0 | 0 | 13265769 | 13265769 | 13265769 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 13265769
64-035-01 | 64-035 | 64 | N/A | 67318 | CSC MonAvenir | Pape-François | école élémentaire et secondaire catholique Pape-François | ELE/SEC | 24195 | 19167 | 19167-B01 | 276 SUNSET BLVD | STOUFFVILLE | L4A3R1 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9678 | -79.2545 | 40786 | 2010-11 | 2011-12 | - | - | - | 40786 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 420 | - | - | N | - | Approved | 41866 | 13214114 | Construction Complete | New Construction | FL Capital Transitional | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698922 | 0 | 0 | 698922 | 0 | 0 | 475266 | 0 | 12039926 | 0 | 0 | 0 | 0 | 0 | 12515192 | 13214114 | 13214114 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12039926
64-035-02 | 64-035 | 64 | N/A | 67318 | CSC MonAvenir | Pape-François | école élémentaire et secondaire catholique Pape-François | ELE/SEC | 24195 | 19167 | 19167-L01 | 276 SUNSET BLVD | STOUFFVILLE | L4A3R1 | 35-11-27-406 | Whitchurch-Stouffville | Whitchurch - Stouffville T | York R | YORK | GTA | South | 43.9678 | -79.2545 | 41122 | 2011-12 | 2012-13 | 41122 | 2011-12 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41122 | 4470000 | Construction Complete | Land Acquisition | FL Capital Transitional | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4470000 | 0 | 0 | 0 | 0 | 0 | 0 | 4470000 | 4470000 | 4470000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 4470000
64-036 | 64-036 | 64 | N/A | 67318 | CSC MonAvenir | Père-René-de-Galinée | école secondaire catholique Père-René-de-Galinée | SEC | 10146 | 5144 | 5144-B01 | 450 MAPLE GROVE RD RR 32 | CAMBRIDGE | N3H4R7 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4243 | -80.3817 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9564344 | Construction Complete | New Construction | Other | 2001-02 | 37135 | 0 | 0 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334191 | 391191 | 9173153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9173153 | 9564344 | 9564344 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-037 | 64-037 | 64 | N/A | 67318 | CSC MonAvenir | Port Hope | école élémentaire catholique Port Hope | ELE | 24253 | 10096 | 10096-B01 | 10 PINE ST S | PORT HOPE | L1A3E7 | 35-12-61-409 | Port Hope | Port Hope M | Northumberland Co | NORTHUMBERLAND | East | South | 43.9525 | -78.2982 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Cancelled | - | 0 | Cancelled | Cancelled | FL Capital Transitional | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547470 | 0 | 0 | 0 | 0 | 0 | 547470 | 547470 | 547470 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 547470
64-038 | 64-038 | 64 | N/A | 67318 | CSC MonAvenir | Renaissance | école secondaire catholique Renaissance | SEC | 10400 | 11096 | 11096-B01 | 700 BLOOMINGTON RD | AURORA | L4G0E1 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9583 | -79.4838 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 19182364 | Construction Complete | New Construction | Other | 2008-09 | 39692 | 0 | 0 | 3096757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158250 | 3255007 | 15927357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15927357 | 19182364 | 19182364 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-039 | 64-039 | 64 | N/A | 67318 | CSC MonAvenir | René-Lamoureux | école élémentaire catholique René-Lamoureux | ELE | 3192 | 7100 | 7100-B01 | 385 MEADOWS BLVD | MISSISSAUGA | L4Z1G5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6062 | -79.6297 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 277529 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277529 | 0 | 0 | 0 | 0 | 277529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277529 | 277529 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-041 | 64-041 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Antoine | école élémentaire catholique Saint-Antoine | ELE | 3770 | 7506 | 7506-B01 | 4572 PORTAGE RD | NIAGARA FALLS | L2E6A8 | 35-11-18-101 | Niagara Falls | Niagara Falls C | Niagara R | NIAGARA | Central | South | 43.1076 | -79.0939 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 362784 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362784 | 0 | 0 | 0 | 0 | 362784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362784 | 362784 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-042 | 64-042 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Charles-Garnier | école secondaire catholique Saint-Charles-Garnier | SEC | 8757 | 5123 | 5123-B01 | 4101 BALDWIN ST S | WHITBY | L1R2W6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9179 | -78.9573 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 104 | - | - | N | - | Cancelled | - | 0 | Cancelled | Cancelled | Accommodation Pressure | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-043 | 64-043 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Charles-Garnier | école secondaire catholique Saint-Charles-Garnier | SEC | 8774 | 5123 | 5123-B01 | 4101 BALDWIN ST S | WHITBY | L1R2W6 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.9178 | -78.9573 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 195 | - | - | N | - | Approved | 39691 | 1935843 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850000 | 1850000 | 85843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85843 | 1935843 | 1935843 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-044 | 64-044 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Croix | école élémentaire catholique Sainte-Croix | ELE | 8284 | 9325 | 9325-B01 | 1-351 RUE LAFONTAINE RD W | TINY | L9M0H1 | 35-11-70-614 | Tiny | Tiny Tp | Simcoe Co | SIMCOE | Central | South | 44.7573 | -80.0536 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1007316 | Construction Complete | Retrofit | Condition | 2011-12 | 40787 | 7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7316 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 1007316 | 1007316 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-045 | 64-045 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Famille | école secondaire catholique Sainte-Famille | SEC | 3929 | 7627 | 7627-B01 | 1780 MEADOWVALE BLVD | MISSISSAUGA | L5N7K8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.6147 | -79.7478 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3225339 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384369 | 384369 | 2840970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2840970 | 3225339 | 3225339 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-046 | 64-046 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Jeanne-d'Arc | école élémentaire catholique Sainte-Jeanne-d'Arc | ELE | 3081 | 7024 | 7024-B01 | 25 LAURELCREST ST | BRAMPTON | L6S4C4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7106 | -79.7365 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1448603 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1448603 | 1448603 | 1448603 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-049 | 64-049 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Marguerite-Bourgeoys | école élémentaire catholique Sainte-Marguerite-Bourgeoys | ELE | 3401 | 7234 | 7234-B01 | 60 CLENCH AVE | BRANTFORD | N3T1B8 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1249 | -80.2694 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1021003 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021003 | 0 | 0 | 0 | 0 | 1021003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021003 | 1021003 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-050 | 64-050 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Marguerite-Bourgeoys | école élémentaire catholique Sainte-Marguerite-Bourgeoys | ELE | 3401 | 7234 | 7234-B01 | 60 CLENCH AVE | BRANTFORD | N3T1B8 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1249 | -80.2694 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 63 | - | - | N | - | Not Required | - | 2777197 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 2627197 | 0 | 0 | 0 | 0 | 0 | 2777197 | 2777197 | 2777197 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2627197
64-051 | 64-051 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Marguerite-Bourgeoys | école élémentaire catholique Sainte-Marguerite-Bourgeoys | ELE | 4210 | 7831 | 7831-B01 | 111 JOHN BUTTON BLVD | MARKHAM | L3R9C1 | 35-11-27-402 | Markham | Markham T | York R | YORK | GTA | South | 43.864 | -79.3583 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 493656 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493656 | 0 | 0 | 0 | 0 | 493656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493656 | 493656 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-055 | 64-055 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Marie | école élémentaire catholique Sainte-Marie | ELE | 3377 | 7216 | 7216-B01 | 165 QUEEN ST N | SIMCOE | N3Y3Y7 | 35-15-12-103 | Norfolk | Norfolk County | Norfolk County | NORFOLK | Southwest | South | 42.8399 | -80.3122 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 189813 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189813 | 0 | 0 | 0 | 0 | 189813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189813 | 189813 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-058 | 64-058 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Trinité | école secondaire catholique Sainte-Trinité | SEC | 11224 | 12349 | 12349-B01 | 2600 GRAND OAK TRAIL | OAKVILLE | L6M0R4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4372 | -79.7736 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41782 | 25441923 | Construction Complete | New Construction | Other | 2013-14 | 41518 | 0 | 0 | 3023882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023882 | 11003239 | 0 | 0 | 0 | 349302 | 0 | 0 | 0 | 0 | 11065500 | 22418041 | 25441923 | 25441923 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 349302
64-059 | 64-059 | 64 | N/A | 67318 | CSC MonAvenir | Saint-François-d'Assise | école élémentaire catholique Saint-François-d'Assise | ELE | 10399 | 7787 | 7787-B01 | 58 EMPRESS AVE | WELLAND | L3B1K9 | 35-11-18-104 | Welland | Welland C | Niagara R | NIAGARA | Central | South | 42.9808 | -79.2313 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5422780 | Construction Complete | New Construction | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5422780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5422780 | 5422780 | 5422780 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-061 | 58-055+64-061 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Frère-André | école secondaire catholique Saint-Frère-André | SEC | 11128 | 9511 | 9511-B01 | 330 LANSDOWNE AVE | TORONTO | M6H3Y1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6525 | -79.4406 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41806 | 22923638 | Construction Complete | Purchase | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22923638 | 0 | 0 | 0 | 0 | 0 | 22923638 | 22923638 | 22923638 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 22923638
64-063 | 64-063 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Jean-Baptiste | école élémentaire catholique Saint-Jean-Baptiste | ELE | 4032 | 7704 | 7704-B01 | 1910 BROAD HOLLOW GATE | MISSISSAUGA | L5L3T4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5428 | -79.6671 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 892924 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892924 | 0 | 0 | 0 | 0 | 892924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892924 | 892924 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-068 | 64-068 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Louis | école élémentaire catholique Saint-Louis | ELE | 8283 | 9324 | 9324-L01 | 54 DUFFERIN ST | PENETANGUISHENE | L9M1H4 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7819 | -79.9198 | 41379 | 2012-13 | 2013-14 | 41379 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40604 | 64520 | Construction Complete | Land Acquisition | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64520 | 0 | 0 | 0 | 0 | 0 | 0 | 64520 | 64520 | 64520 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 64520
64-069 | 64-069 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Michel | école élémentaire catholique Saint-Michel | ELE | 11129 | 12354 | 12354-B01 | 29 MEADOWVALE RD | SCARBOROUGH | M1C1R7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7779 | -79.156 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 213 | - | - | N | - | Not Required | - | 11571999 | Construction Complete | New Construction | FL Capital Transitional | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452440 | 0 | 0 | 452440 | 0 | 0 | 0 | 0 | 7185059 | 0 | 0 | 0 | 0 | 3934500 | 11119559 | 11571999 | 11571999 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 7185059
64-070 | 64-070 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Nicolas | école élémentaire catholique Saint-Nicolas | ELE | 11339 | 17151 | 17151-B01 | 720 WOODWARD AVE | MILTON | L9T4A3 | 35-11-14-402 | Milton | Milton T | Halton R | HALTON | GTA | South | 43.5287 | -79.8776 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 7734292 | Construction Complete | New Construction | FL Capital Transitional | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7734292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7734292 | 7734292 | 7734292 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-072 | 64-072 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Noël-Chabanel | école élémentaire catholique Saint-Noël-Chabanel | ELE | 6257 | 8638 | 8638-B01 | 640 TRICO DR | CAMBRIDGE | N3H5P2 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4042 | -80.3401 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 304718 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304718 | 0 | 0 | 0 | 0 | 304718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304718 | 304718 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-074 | 64-074 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Noël-Chabanel | école élémentaire catholique Saint-Noël-Chabanel | ELE | 11194 | 12347 | 12347-B01 | 30 THISTLE DOWN BLVD | ETOBICOKE | M9V1H8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7363 | -79.5606 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41038 | 12316027 | Construction Complete | New Construction | Condition | 2013-14 | 41518 | 0 | 0 | 2345776 | 137756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405291 | 0 | 0 | 2888823 | 9427204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9427204 | 12316027 | 12316027 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-076 | 64-076 | 64 | N/A | 67318 | CSC MonAvenir | Saint-René-Goupil | école élémentaire catholique Saint-René-Goupil | ELE | 4445 | 7986 | 7986-B01 | 221 SCOTTSDALE DR | GUELPH | N1G3A1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5222 | -80.2435 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 74410 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74410 | 0 | 0 | 0 | 0 | 74410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74410 | 74410 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-077-01 | 64-077 | 64 | N/A | 67318 | CSC MonAvenir | Père-Philippe-Lamarche | école secondaire catholique Père-Philippe-Lamarche | SEC | 11127 | 12352 | 12352-B01 | 2850 EGLINTON AVE E | SCARBOROUGH | M1J2C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7393 | -79.2408 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | 500 | - | - | N | - | Approved | 44386 | 14339514 | Construction Complete | New Construction | FL Capital Transitional | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14339514 | 0 | 0 | 0 | 0 | 0 | 14339514 | 14339514 | 14339514 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 14339514
64-077-02 | 64-077 | 64 | N/A | 67318 | CSC MonAvenir | Père-Philippe-Lamarche | école secondaire catholique Père-Philippe-Lamarche | SEC | 11127 | 12352 | 12352-L01 | 2850 EGLINTON AVE E | SCARBOROUGH | M1J2C8 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7393 | -79.2408 | 41487 | 2012-13 | 2013-14 | 41487 | 2012-13 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 41487 | 8578500 | Construction Complete | Land Acquisition | FL Capital Transitional | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8578500 | 0 | 0 | 0 | 0 | 0 | 0 | 8578500 | 8578500 | 8578500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 8578500
64-078-01 | 58-059+64-078 | 64 | N/A | 67318 | CSC MonAvenir | Mère-Teresa | école secondaire catholique Mère-Teresa | SEC | 24530-24306 | 19535 | 19535-B01 | 36 BROUGHTON AVE | HAMILTON | L8W3S5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1901 | -79.8518 | 42933 | 2016-17 | 2017-18 | - | - | - | 42933 | 2016-17 | 2017-18 | - | - | - | - | - | - | - | - | - | 400 | - | - | N | - | Planned | - | 0 | Planned | New Construction | Consolidation | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13257763 | 0 | 0 | 0 | 0 | 0 | 13257763 | 13257763 | 13257763 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13257763
64-078-02 | 58-059+64-078 | 64 | N/A | 67318 | CSC MonAvenir | Mère-Teresa | école secondaire catholique Mère-Teresa | SEC | 24530-24306 | 19535 | 19535-L01 | 36 BROUGHTON AVE | HAMILTON | L8W3S5 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.1901 | -79.8518 | 42723 | 2016-17 | 2016-17 | 42723 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 42723 | 2916014 | Construction Complete | Land Acquisition | Consolidation | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916014 | 0 | 0 | 0 | 0 | 0 | 0 | 2916014 | 2916014 | 2916014 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2916014
64-079 | 64-079 | 64 | 203 - CMSM Hamilton | 67318 | CSC MonAvenir | Notre-Dame | école élémentaire catholique Notre-Dame | ELE | 3462 | 7275 | 7275-B01 | 400 CUMBERLAND AVE | HAMILTON | L8M2A2 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2419 | -79.8361 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132267 | 0 | 0 | 132267 | 0 | 0 | 0 | 0 | 0 | 0 | 124860 | 0 | 0 | 0 | 124860 | 257127 | 257127 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 124860
64-080 | 64-080 | 64 | 232 - CMSM Peel | 67318 | CSC MonAvenir | Saint-Jean-Baptiste | école élémentaire catholique Saint-Jean-Baptiste | ELE | 4032 | 7704 | 7704-B01 | 1910 BROAD HOLLOW GATE | MISSISSAUGA | L5L3T4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5428 | -79.6671 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44987 | 2080120 | Construction Complete | Addition | Child Care | 2022-23 | 44927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040060 | 0 | 0 | 1040060 | 0 | 0 | 0 | 0 | 0 | 0 | 1040060 | 0 | 0 | 0 | 1040060 | 2080120 | 2080120 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1040060
64-081 | 64-081 | 64 | 224 - CMSM Simcoe | 67318 | CSC MonAvenir | Saint-Louis | école élémentaire catholique Saint-Louis | ELE | 8283 | 9324 | 9324-B01 | 54 DUFFERIN ST | PENETANGUISHENE | L9M1H4 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7819 | -79.9198 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 44005 | 324690 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 264690 | 0 | 0 | 0 | 264690 | 324690 | 324690 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 264690
64-082 | 64-082 | 64 | 224 - CMSM Simcoe | 67318 | CSC MonAvenir | Sainte-Croix | école élémentaire catholique Sainte-Croix | ELE | 8284 | 9325 | 9325-B01 | 1-351 RUE LAFONTAINE RD W | TINY | L9M0H1 | 35-11-70-614 | Tiny | Tiny Tp | Simcoe Co | SIMCOE | Central | South | 44.7573 | -80.0536 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44127 | 529379 | Construction Complete | Retrofit | Child Care | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529379 | 0 | 0 | 0 | 529379 | 529379 | 529379 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 529379
64-083 | 64-083 | 64 | 234 - CMSM York | 67318 | CSC MonAvenir | Le-Petit-Prince | école élémentaire catholique Le-Petit-Prince | ELE | 9480 | 10174 | 10174-B01 | 79 AVRO RD | MAPLE | L6A1Y3 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.85 | -79.5246 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43950 | 711111 | Construction Complete | Addition | Child Care | 2020-21 | 44197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206941 | 0 | 0 | 206941 | 0 | 0 | 0 | 0 | 0 | 0 | 504171 | 0 | 0 | 0 | 504171 | 711112 | 711112 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 504171
64-084 | 64-084 | 64 | 233 - CMSM Waterloo | 67318 | CSC MonAvenir | Mère-Élisabeth-Bruyère | école élémentaire catholique Mère-Élisabeth-Bruyère | ELE | 10043 | 5194 | 5194-B01 | 280 GLENRIDGE DR | WATERLOO | N2J3W4 | 35-15-25-103 | Waterloo | Waterloo C | Waterloo R | WATERLOO | Southwest | South | 43.4832 | -80.5104 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 44344 | 1124239 | Construction Complete | Addition | Child Care | 2021-22 | 44562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160568 | 0 | 0 | 160568 | 0 | 0 | 0 | 0 | 0 | 0 | 963671 | 0 | 0 | 0 | 963671 | 1124239 | 1124239 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 963671
64-085 | 64-085 | 64 | 229 - CMSM Durham | 67318 | CSC MonAvenir | Jean-Paul II | école élémentaire catholique Jean-Paul II | ELE | 10746 | 6550 | 6550-B01 | 1001 HUTCHISON AVE | WHITBY | L1N2A3 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | 43.8776 | -78.9252 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 43950 | 504171 | Construction Complete | Addition | Child Care | 2020-21 | 44197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504171 | 0 | 0 | 0 | 504171 | 504171 | 504171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 504171
64-086 | 64-086 | 64 | 211 - CMSM Toronto | 67318 | CSC MonAvenir | Saint-Michel | école élémentaire catholique Saint-Michel | ELE | 11129 | 12354 | 12354-B01 | 29 MEADOWVALE RD | SCARBOROUGH | M1C1R7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7779 | -79.156 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 34 | Y | - | Approved | 44344 | 1170340 | Construction Complete | Addition | Child Care | 2021-22 | 44621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398959 | 0 | 0 | 398959 | 0 | 0 | 0 | 0 | 0 | 0 | 771381 | 0 | 0 | 0 | 771381 | 1170340 | 1170340 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 771381
64-087-01 | 64-087 | 64 | 234 - CMSM York | 67318 | CSC MonAvenir | Vaughan | école secondaire catholique Vaughan | SEC | 24799 | 7122 | 7122-B02 | 200 ABERDEEN AVE | WOODBRIDGE | L4L1C4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8006 | -79.5706 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 407 | 3 | 49 | Y | - | Approved | 44678 | 16470796 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 2078551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433296 | 0 | 50000 | 2561847 | 0 | 0 | 0 | 0 | 19425730 | 0 | 1512511 | 0 | 0 | 0 | 20938241 | 23500088 | 23500088 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 20938241
64-087-02 | 64-087 | 64 | N/A | 67318 | CSC MonAvenir | Vaughan | école secondaire catholique Vaughan | SEC | 24799 | 7122 | 7122-L02 | 200 ABERDEEN AVE | WOODBRIDGE | L4L1C4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8006 | -79.5706 | 43561 | 2018-19 | 2019-20 | 43561 | 2018-19 | 2019-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43561 | 22601317 | Construction Complete | Land Acquisition | Accommodation Pressure | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22601317 | 0 | 0 | 0 | 0 | 0 | 0 | 22601317 | 22601317 | 22601317 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 22601317
64-088 | 64-088 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Trinité | école secondaire catholique Sainte-Trinité | SEC | 11224 | 12349 | 12349-B01 | 2600 GRAND OAK TRAIL | OAKVILLE | L6M0R4 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4372 | -79.7736 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 180 | - | - | N | - | Approved | 44880 | 6590481 | Under Construction | Addition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 223624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223624 | 0 | 0 | 0 | 0 | 6568836 | 0 | 0 | 0 | 0 | 0 | 6568836 | 6792460 | 6792460 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6568836
64-089 | 64-089 | 64 | N/A | 67318 | CSC MonAvenir | Père-René-de-Galinée | école secondaire catholique Père-René-de-Galinée | SEC | 10146 | 5144 | 5144-B01 | 450 MAPLE GROVE RD RR 32 | CAMBRIDGE | N3H4R7 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4243 | -80.3817 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | 178 | - | - | N | - | Approved | 43929 | 5977013 | Construction Complete | Addition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 224125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224125 | 0 | 0 | 0 | 0 | 5752888 | 0 | 0 | 0 | 0 | 0 | 5752888 | 5977013 | 5977013 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5752888
64-090 | 64-090 | 64 | N/A | 67318 | CSC MonAvenir | Cobourg | école élémentaire catholique Cobourg | HLA | 24801 | 19808 | 19808-L0- | 950 NEW AMHERST BLVD | COBOURG | K9A0B2 | 35-12-61-403 | Cobourg | Cobourg T | Northumberland Co | NORTHUMBERLAND | East | South | 43.9678 | -78.2122 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43173 | 5155020 | Construction Complete | Land Acquisition | FL Capital Transitional | 2018-19 | 43344 | 0 | 0 | 5155020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5155020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5155020 | 5155020 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-092 | 64-092 | 64 | N/A | 67318 | CSC MonAvenir | Brampton | école secondaire catholique Brampton | ELE/SEC | 25403 | 20409 | 20409-B01 | TBD | BRAMPTON | TBD | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | TBD | TBD | 43922 | 2019-20 | 2020-21 | - | - | - | 43921 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - | 410 | - | - | - | - | Planned | - | 0 | Planned | New Construction | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13630094 | 0 | 0 | 0 | 0 | 0 | 13630094 | 13630094 | 13630094 | 0 | - | No, Site to be acquired. Sign installation planned for August 1, 2022 | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 13630094
64-093 | 64-089 | 64 | N/A | 67318 | CSC MonAvenir | Père-René-de-Galinée | école secondaire catholique Père-René-de-Galinée | SEC | 10146 | 5144 | 5144-L01 | 450 MAPLE GROVE RD RR 32 | CAMBRIDGE | N3H4R7 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.4243 | -80.3817 | 43929 | 2019-20 | 2020-21 | 43929 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43929 | 889203 | Construction Complete | Land Acquisition | Accommodation Pressure | 2021-22 | 44440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 889203 | 0 | 0 | 0 | 0 | 0 | 0 | 889203 | 889203 | 889203 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 889203
64-094 | 64-094 | 64 | N/A | 67318 | CSC MonAvenir | Sainte-Marguerite-d'Youville | école élémentaire catholique Sainte-Marguerite-d'Youville | ELE | 3753 | 7492 | 7492-B01 | 755 ROYAL YORK RD | ETOBICOKE | M8Y2T3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6359 | -79.5059 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 44005 | 1210000 | Construction Complete | FDK | FDK | 2021-22 | 44562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605000 | 0 | 0 | 605000 | 0 | 0 | 1210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210000 | 1815000 | 1815000 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
64-095 | 64-095 | 64 | 211 - CMSM Toronto | 67318 | CSC MonAvenir | du Sacré-Cœur | école élémentaire catholique du Sacré-Cœur | ELE | 11193 | 12346 | 12346-B01 | 98 ESSEX ST | TORONTO | M6G1T3 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6674 | -79.4248 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 1 | 24 | N | - | Planned | - | - | Planned | Retrofit | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196180 | 0 | 0 | 196180 | 0 | 0 | 0 | 0 | 0 | 0 | 280783 | 0 | 0 | 0 | 280783 | 476963 | 280783 | -196180 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 280783
64-096 | 64-096 | 64 | 200 - CMSM Brantford | 67318 | CSC MonAvenir | Sainte-Marguerite-Bourgeoys | école élémentaire catholique Sainte-Marguerite-Bourgeoys | ELE | 3401 | 7234 | 7234-B01 | 60 CLENCH AVE | BRANTFORD | N3T1B8 | 35-15-15-000 | Brantford | Brantford City | Brantford City | BRANT | Southwest | South | 43.1249 | -80.2694 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 1 | 24 | N | - | Planned | - | - | Planned | Addition | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486908 | 0 | 0 | 486908 | 0 | 0 | 0 | 0 | 0 | 0 | 545521 | 0 | 0 | 0 | 545521 | 1032429 | 1032429 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 545521
64-097 | 64-097 | 64 | 211 - CMSM Toronto | 67318 | CSC MonAvenir | Sainte-Madeleine | école élémentaire catholique Sainte-Madeleine | ELE | 4559 | 7685 | 7685-B01 | 1 NESS DR | NORTH YORK | M3A2W1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7626 | -79.3227 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | 39 | N | - | Planned | - | - | Planned | Retrofit | Child Care | 2022-23 | 44810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335966 | 0 | 0 | 335966 | 0 | 0 | 0 | 0 | 0 | 0 | 545521 | 0 | 0 | 0 | 545521 | 881487 | 881487 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 545521
64-098 | 64-098 | 64 | N/A | 67318 | CSC MonAvenir | Saint-Michel | école élémentaire catholique Saint-Michel | ELE | 11129 | 12354 | 12354-B01 | 29 MEADOWVALE RD | SCARBOROUGH | M1C1R7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.778 | -79.1561 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 92 | - | - | N | - | Approval | 45167 | 2879698 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879699 | 0 | 0 | 0 | 0 | 0 | 2879699 | 2879699 | 2879699 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2879699
64-099 | 64-099 | 64 | N/A | 67318 | CSC MonAvenir | Saint-René-Goupil | école élémentaire catholique Saint-René-Goupil | ELE | 4445 | 7986 | 7986-B01 | 221 SCOTTSDALE DR | GUELPH | N1G3A1 | 35-15-75-101 | Guelph | Guelph C | Wellington Co | WELLINGTON | Southwest | South | 43.5222 | -80.2435 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 138 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272670 | 0 | 0 | 0 | 0 | 0 | 3272670 | 3272670 | 3272670 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3272670
64-100 | 64-100 | 64 | 229 - CMSM Durham | 67318 | CSC MonAvenir | Brooklyn | école élémentaire catholique Brooklyn | ELE | TBD | TBD | TBD | TBD | WHITBY | L1M2C8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 354 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | FL Capital Transitional | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9992969 | 0 | 1955848 | 0 | 0 | 0 | 11948817 | 11948817 | 11948817 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 11948817
64-101 | 64-090 | 64 |  | 67318 | CSC MonAvenir | Cobourg | école élémentaire catholique Cobourg | ELE | 24801 | 19808 | 19808-B01 | 950 NEW AMHERST BLVD | COBOURG | K9A0B2 | 35-12-61-403 | Cobourg | Cobourg T | Northumberland Co | NORTHUMBERLAND | East | South | 43.9678 | -78.2122 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 259 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | FL Capital Transitional | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8068475 | 0 | 2014523 | 0 | 0 | 0 | 10082998 | 10082998 | 10082998 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10082998
64-102 | 64-025 | 64 | N/A | 67318 | CSC MonAvenir | Mississauga | école élémentaire catholique Mississauga | ELE | 24464 | 19467 | 19467-L01 | TBD | MISSISSAUGA | TBD | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | TBD | TBD | 44684 | 2021-22 | 2022-23 | 44684 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44684 | 21016886 | Construction Complete | Land Acquisition | Accommodation Pressure | 2021-22 | 44804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21016886 | 0 | 0 | 0 | 0 | 0 | 0 | 21016886 | 21016886 | 21016886 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 21016886
64-103 | 64-092 | 64 | N/A | 67318 | CSC MonAvenir | Brampton | école secondaire catholique Brampton | HLA | 25403 | 20409 | 20409-L01 | TBD | BRAMPTON | TBD | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | TBD | TBD | TBD | TBD | TBD | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Planned | - | - | Planned | Land Acquisition | Accommodation Pressure | 2022-23 | 45169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18946206 | 0 | 0 | 0 | 0 | 0 | 0 | 18946206 | 18946206 | 18946206 | 0 | - | No | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 18946206
64-104 | 64-100 | 64 | 229 - CMSM Durham | 67318 | CSC MonAvenir | Brooklyn | école élémentaire catholique Brooklyn | ELE | TBD | TBD | TBD | TBD | WHITBY | L1M2C8 | 35-11-10-404 | Whitby | Whitby T | Durham R | DURHAM | GTA | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 354 | 3 | 49 | N | - | Planned | - | - | Planned | New Construction | FL Capital Transitional | 2027-28 | 46637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13093813 | 0 | 0 | 0 | 0 | 0 | 0 | 13093813 | 13093813 | 13093813 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 13093813
65-001 | 65-001 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 24439 | 19442 | 19442-B01 | 875 COUNTY ROAD 17 | L'ORIGNAL | K0B1K0 | 35-12-67-613 | Champlain | Champlain Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6111 | -74.6819 | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | Pre 2010-11 | Pre 2010-11 | Pre 2010-11 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950736 | 0 | 0 | 0 | 0 | 0 | 950736 | 950736 | 0 | -950736 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | NO as GPL-C reallocation | Not Applicable | Not Applicable | 950736
65-002 | 65-002 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 24439 | 19442 | 19442-B01 | 875 COUNTY ROAD 17 | L'ORIGNAL | K0B1K0 | 35-12-67-613 | Champlain | Champlain Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6111 | -74.6819 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4540491 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4737794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4737794 | 4737794 | 4540491 | -197303 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-003 | 65-003 | 65 | 236 - CMSM Prescott & Russell | 67326 | CSDC de l'Est ontarien | Saint-Grégoire | école élémentaire catholique Saint-Grégoire | ELE | 6204 | 8612 | 8612-B01 | 50 HOME ST | VANKLEEK HILL | K0B1R0 | 35-12-67-613 | Champlain | Champlain Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5215 | -74.6489 | 43090 | 2016-17 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242292 | 0 | 0 | 242292 | 0 | 0 | 0 | 0 | 0 | 0 | 262169 | 0 | 0 | 0 | 262169 | 504461 | 504461 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 262169
65-004 | 65-004 | 65 | N/A | 67326 | CSDC de l'Est ontarien | de Casselman | école secondaire catholique de Casselman | SEC | 3115 | 7044 | 7044-B01 | 778 BREBEUF ST | CASSELMAN | K0A1M0 | 35-12-67-502 | Casselman | Casselman V | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.316 | -75.0879 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 11805495 | Construction Complete | Addition | Other | 2006-07 | 38961 | 8454759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 10854759 | 950736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950736 | 11805495 | 11805495 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-005 | 65-005 | 65 | N/A | 67326 | CSDC de l'Est ontarien | de Casselman Pavillon Saint-Paul | école élémentaire catholique de Casselman Pavillon Saint-Paul | ELE | 4370 | 7044 | 7044-B02 | 133 RUE LAURIER | CASSELMAN | K0A1M0 | 35-12-67-502 | Casselman | Casselman V | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3158 | -75.085 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1149175 | Construction Complete | Addition | Other | 2005-06 | 38596 | 1149175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149175 | 1149175 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-006 | 65-006 | 65 | N/A | 67326 | CSDC de l'Est ontarien | de l'Ange-Gardien | école élémentaire catholique de l'Ange-Gardien | ELE | 10724 | 7217 | 7217-B01 | 4831 2ND LINE RD | NORTH LANCASTER | K0C1Z0 | 35-12-71-616 | South Glengarry | South Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.2477 | -74.5013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5401183 | Construction Complete | Retrofit | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5401183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5401183 | 5401183 | 5401183 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-007 | 65-007 | 65 | N/A | 67326 | CSDC de l'Est ontarien | de l'Ange-Gardien | école élémentaire catholique de l'Ange-Gardien | ELE | 10724 | 7217 | 7217-B01 | 4831 2ND LINE RD | NORTH LANCASTER | K0C1Z0 | 35-12-71-616 | South Glengarry | South Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.2477 | -74.5013 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 73209 | Construction Complete | Addition | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73209 | 73209 | 73209 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-008 | 65-008 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Pavillon Plantagenet | école secondaire catholique Pavillon Plantagenet | SEC | 11074 | 7382 | 7382-B01 | 6150 COUNTY ROAD 17 | PLANTAGENET | K0B1L0 | 35-12-67-612 | Alfred and Plantagenet | Alfred and Plantagenet Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5473 | -74.9992 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 445000 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445000 | 445000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445000 | 445000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-009 | 65-009 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Pavillon Embrun | école secondaire catholique Pavillon Embrun | SEC | 11265 | 7093 | 7093-B01 | 1276 SAINT JACQUES ST | EMBRUN | K0A1W0 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2712 | -75.2752 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6532050 | Construction Complete | Retrofit | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6532050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6532050 | 6532050 | 6532050 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-010 | 65-010 | 65 | N/A | 67326 | CSDC de l'Est ontarien | d'Embrun Pavillon Saint-Jean | école élémentaire catholique d'Embrun Pavillon Saint-Jean | ELE | 3627 | 3017 | 3017-B01 | 1045 NOTRE DAME ST | EMBRUN | K0A1W0 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.275 | -75.2739 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 346 | - | - | N | - | Not Required | - | 2052000 | Construction Complete | Retrofit | Condition | 2011-12 | 40787 | 33128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465881 | 0 | 0 | 499009 | 1552991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552991 | 2052000 | 2052000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-012 | 65-012 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Pavillon la Citadelle | école secondaire catholique Pavillon la Citadelle | SEC | 11071 | 7215 | 7215-B01 | 510 MCCONNELL AVE | CORNWALL | K6H4M1 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0232 | -74.7132 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 537000 | Construction Complete | Retrofit | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537000 | 537000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537000 | 537000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-014 | 65-014 | 65 | N/A | 67326 | CSDC de l'Est ontarien | le Relais | école secondaire catholique le Relais | SEC | 10725 | 11286 | 11286-B01 | 100 MCNABB ST | ALEXANDRIA | K0C1A0 | 35-12-71-615 | North Glengarry | North Glengarry Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.3161 | -74.6348 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12492467 | Construction Complete | Retrofit | Other | 2004-05 | 38231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1297712 | 1297712 | 11194755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11194755 | 12492467 | 12492467 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-015 | 65-015 | 65 | N/A | 67326 | CSDC de l'Est ontarien | l'Escale | école secondaire catholique l'Escale | SEC | 3390 | 7228 | 7228-B01 | 1535 DU PARC AVE | ROCKLAND | K4K1C3 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5498 | -75.2865 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4704321 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711632 | 711632 | 3992689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3992689 | 4704321 | 4704321 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-016 | 65-016 | 65 | N/A | 67326 | CSDC de l'Est ontarien | l'Escale | école secondaire catholique l'Escale | SEC | 3390 | 7228 | 7228-B01 | 1535 DU PARC AVE | ROCKLAND | K4K1C3 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5498 | -75.2865 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4100000 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000 | 4100000 | 4100000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-017 | 65-017 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Pavillon Rockland | école secondaire catholique Pavillon Rockland | SEC | 10958 | 7228 | 7228-B01 | 1535 DU PARC AVE | ROCKLAND | K4K1C3 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.549 | -75.2863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3903125 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3903125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3903125 | 3903125 | 3903125 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-018 | 65-018 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Marie-Tanguay | école élémentaire catholique Marie-Tanguay | ELE | 4550 | 8069 | 8069-B01 | 1500 HOLY CROSS BLVD | CORNWALL | K6H2X1 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0362 | -74.6966 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1493751 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493751 | 1493751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1493751 | 1493751 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-023 | 65-023 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Sainte-Félicité | école élémentaire catholique Sainte-Félicité | ELE | 6207 | 8614 | 8614-B01 | 1647 LANDRY ST | CLARENCE CREEK | K0A1N0 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5092 | -75.2186 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 231335 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231335 | 231335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231335 | 231335 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-024 | 65-024 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Sainte-Lucie | école élémentaire catholique Sainte-Lucie | ELE | 3150 | 7072 | 7072-B01 | 17337 DOW ST | LONG SAULT | K0C1P0 | 35-12-71-618 | South Stormont | South Stormont Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0766 | -74.7795 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 197242 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197242 | 197242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197242 | 197242 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-025 | 65-025 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Sainte-Lucie | école élémentaire catholique Sainte-Lucie | ELE | 3150 | 7072 | 7072-B01 | 17337 DOW ST | LONG SAULT | K0C1P0 | 35-12-71-618 | South Stormont | South Stormont Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0766 | -74.7795 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 669050 | Construction Complete | Addition | Other | 2013-14 | 41518 | 0 | 0 | 211159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211159 | 0 | 0 | 457891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457891 | 669050 | 669050 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-027 | 65-027 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Sainte-Trinité | école élémentaire catholique Sainte-Trinité | ELE | 4565 | 8078 | 8078-B01 | 879 SAINT-JOSEPH ST | ROCKLAND | K4K1C2 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5478 | -75.287 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1500000 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 1500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-028 | 65-028 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Grégoire | école élémentaire catholique Saint-Grégoire | ELE | 6204 | 8612 | 8612-B01 | 50 HOME ST | VANKLEEK HILL | K0B1R0 | 35-12-67-613 | Champlain | Champlain Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5215 | -74.6489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3828891 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3828891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3828891 | 3828891 | 3828891 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-029 | 65-029 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Jean-Baptiste | école élémentaire catholique Saint-Jean-Baptiste | ELE | 4025 | 7697 | 7697-B01 | 35 LONGUEUIL ST | L'ORIGNAL | K0B1K0 | 35-12-67-613 | Champlain | Champlain Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6174 | -74.692 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1214240 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 0 | 199683 | 794557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994240 | 1214240 | 1214240 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-031 | 65-031 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 4131 | 7775 | 7775-B01 | 3250 RUE PRINCIPALE | WENDOVER | K0A3K0 | 35-12-67-612 | Alfred and Plantagenet | Alfred and Plantagenet Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5721 | -75.1303 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41470 | 1025901 | Construction Complete | Addition | Other | 2013-14 | 41518 | 86051 | 0 | 373000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459051 | 0 | 0 | 566850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566850 | 1025901 | 1025901 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-032 | 65-032 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Luc | école élémentaire catholique Saint-Luc | ELE | 4176 | 7807 | 7807-B01 | 1023 ELIZABETH ST | CURRAN | K0B1C0 | 35-12-67-612 | Alfred and Plantagenet | Alfred and Plantagenet Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.4938 | -74.9981 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 562752 | Construction Complete | Demolition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562752 | 562752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562752 | 562752 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-033 | 65-033 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Mathieu | école élémentaire catholique Saint-Mathieu | ELE | 3141 | 7065 | 7065-B01 | 3155 GENDRON RD | HAMMOND | K0A2A0 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.4401 | -75.2387 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 2042171 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042171 | 1042171 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2042171 | 2042171 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-035 | 65-035 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Paul | école élémentaire catholique Saint-Paul | ELE | 4378 | 7941 | 7941-B01 | 260 MAIN ST | PLANTAGENET | K0B1L0 | 35-12-67-612 | Alfred and Plantagenet | Alfred and Plantagenet Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5339 | -74.9966 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1264616 | Construction Complete | Addition | Child Care | 2012-13 | 41153 | 329260 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 465881 | 0 | 0 | 915141 | 0 | 0 | 349475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349475 | 1264616 | 1264616 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-036 | 65-036 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Viateur | école élémentaire catholique Saint-Viateur | ELE | 4521 | 8046 | 8046-B01 | 205 LIMOGES RD | LIMOGES | K0A2M0 | 35-12-67-614 | The Nation | The Nation M | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3502 | -75.2632 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1756931 | Construction Complete | Addition | Consolidation | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556931 | 0 | 0 | 556931 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 1756931 | 1756931 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
65-038 | 65-038 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 4131 | 7775 | 7775-B01 | 3250 RUE PRINCIPALE | WENDOVER | K0A3K0 | 35-12-67-612 | Alfred and Plantagenet | Alfred and Plantagenet Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5721 | -75.1303 | 42695 | 2016-17 | 2016-17 | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1200000 | Construction Complete | Retrofit | Accommodation Pressure | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 1200000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1200000
65-039 | 65-039 | 65 | 236 - CMSM Prescott & Russell | 67326 | CSDC de l'Est ontarien | Sacré-Cœur | école élémentaire catholique Sacré-Cœur | ELE | 3143 | 7066 | 7066-B01 | 2233 DOLLARD ST | BOURGET | K0A1E0 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.437 | -75.1578 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 44385 | 375315 | Under Construction | Retrofit | Child Care | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113146 | 0 | 0 | 113146 | 0 | 0 | 0 | 0 | 0 | 0 | 262169 | 0 | 0 | 0 | 262169 | 375315 | 375315 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 262169
65-040 | 65-040 | 65 | 201 - CMSM Cornwall | 67326 | CSDC de l'Est ontarien | Sainte-Lucie | école élémentaire catholique Sainte-Lucie | ELE | 3150 | 7072 | 7072-B01 | 17337 DOW ST | LONG SAULT | K0C1P0 | 35-12-71-618 | South Stormont | South Stormont Tp | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0766 | -74.7795 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 43949 | 524337 | Construction Complete | Addition | Child Care | 2021-22 | 44593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524337 | 0 | 0 | 0 | 524337 | 524337 | 524337 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 524337
65-041 | 65-041 | 65 | 236 - CMSM Prescott & Russell | 67326 | CSDC de l'Est ontarien | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 3626 | 7400 | 7400-B01 | 1008 RUSSELL RD N | RUSSELL | K4R1G7 | 35-12-67-611 | Russell | Russell Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.2655 | -75.3636 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 44306 | 1068459 | Construction Complete | Retrofit | Child Care | 2021-22 | 44682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281953 | 0 | 0 | 281953 | 0 | 0 | 0 | 0 | 0 | 0 | 786506 | 0 | 0 | 0 | 786506 | 1068459 | 1068459 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 786506
65-043 | 65-043 | 65 | 236 - CMSM Prescott & Russell | 67326 | CSDC de l'Est ontarien | Saint-Viateur | école élémentaire catholique Saint-Viateur | ELE | 4521 | 8046 | 8046-B01 | 205 LIMOGES RD | LIMOGES | K0A2M0 | 35-12-67-614 | The Nation | The Nation M | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3502 | -75.2632 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44406 | 1092548 | Under Construction | Addition | Child Care | 2022-23 | 44835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43873 | 0 | 0 | 43873 | 0 | 0 | 0 | 0 | 0 | 0 | 1048675 | 0 | 0 | 0 | 1048675 | 1092548 | 1092548 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 1048675
65-044 | 65-044 | 65 | 201 - CMSM Cornwall | 67326 | CSDC de l'Est ontarien | Marie-Tanguay | école élémentaire catholique Marie-Tanguay | ELE | 4550 | 8069 | 8069-B01 | 1500 HOLY CROSS BLVD | CORNWALL | K6H2X1 | 35-12-71-101 | Cornwall | Cornwall C | Stormont, Dundas and Glengarry UCo | STORMONT, DUNDAS AND GLENGARRY | East | South | 45.0362 | -74.6966 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 44259 | 608536 | Construction Complete | Addition | Child Care | 2021-22 | 44593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608536 | 0 | 0 | 0 | 608536 | 608536 | 608536 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 608536
65-045 | 65-045 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Isidore | école élémentaire catholique Saint-Isidore | ELE | 4009 | 7686 | 7686-B01 | 20 DE L'ÉCOLE ST | ST ISIDORE | K0C2B0 | 35-12-67-614 | The Nation | The Nation M | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3843 | -74.906 | 43190 | 2017-18 | 2017-18 | - | - | - | 43190 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Not Required | - | 40000 | Construction Complete | ASD Pilot | ASD Pilot | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 40000 | 0 | - | N/A, Not a project reported on OB | NO not to be counted as CP project | YES must be counted | Not Applicable | Not Applicable | 40000
65-046 | 65-046 | 65 | 236 - CMSM Prescott & Russell | 67326 | CSDC de l'Est ontarien | Saint-Joseph | école élémentaire catholique Saint-Joseph | ELE | 4131 | 7775 | 7775-B01 | 3250 RUE PRINCIPALE | WENDOVER | K0A3K0 | 35-12-67-612 | Alfred and Plantagenet | Alfred and Plantagenet Tp | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5721 | -75.1303 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 44385 | 660861 | Under Construction | Addition | Child Care | 2022-23 | 44835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432595 | 0 | 0 | 432595 | 0 | 0 | 0 | 0 | 0 | 0 | 524337 | 0 | 0 | 0 | 524337 | 956932 | 956932 | 0 | - | N/A, Project was approved prior to June 2018 | Not Applicable | Not Applicable | YES as part of CC only | YES | 524337
65-047 | 65-047 | 65 | N/A | 67326 | CSDC de l'Est ontarien | Saint-Viateur | école élémentaire catholique Saint-Viateur | ELE | 4521 | 8046 | 8046-B01 | 205 LIMOGES RD | LIMOGES | K0A2M0 | 35-12-67-614 | The Nation | The Nation M | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3502 | -75.2632 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 115 | - | - | N | - | Approved | 45184 | 5788181 | Planned | Addition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5788181 | 0 | 0 | 0 | 0 | 0 | 5788181 | 5788181 | 2804053 | -2984128 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5788181
66-001 | 66-001 | 66 | N/A | 67334 | CÉC du Centre-Est | Financement des immobilisations non-grevées | Financement des immobilisations non-grevées | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | - | Board Wide Input Line | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337 | 0 | 0 | 0 | 2337 | 2337 | 0 | -2337 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | NO | YES | 2337
66-002 | 66-002 | 66 | N/A | 67334 | CÉC du Centre-Est | Projets MJTP | Projets maternelle/jardin à temps plein | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 6711817 | Construction Complete | FDK | FDK | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5849930 | 5849930 | 5849930 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-003 | 66-003 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 629646 | Construction Complete | Other | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629646 | 629646 | 629646 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-004 | 66-004 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 590471 | Construction Complete | Other | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590471 | 590471 | 590471 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-005 | 66-005 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 859529 | Construction Complete | Other | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859529 | 859529 | 859529 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-006 | 66-006 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1796046 | Construction Complete | Other | Other | 2011-12 | 40787 | 0 | 0 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000 | 96046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96046 | 1796046 | 1796046 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-007 | 66-007 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1515000 | Construction Complete | Other | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515000 | 1515000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515000 | 1515000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-008 | 66-008 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 700000 | Construction Complete | Other | Other | 2013-14 | 41518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-009 | 66-009 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 840000 | Construction Complete | Other | Other | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840000 | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840000 | 840000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-010 | 66-010 | 66 | N/A | 67334 | CÉC du Centre-Est | BWE (TA) | Board Wide Expense (Temporary Asset) | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 231885 | Construction Complete | Other | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231885 | 231885 | 231885 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-011 | 66-011 | 66 | N/A | 67334 | CÉC du Centre-Est | Alain-Fortin | école élémentaire catholique Alain-Fortin | ELE | 11164 | 12223 | 12223-B01 | 676 LAKERIDGE DR | ORLEANS | K4A0J8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4474 | -75.4743 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 461 | - | - | N | - | Not Required | - | 13942840 | Construction Complete | New Construction | Accommodation Pressure | 2010-11 | 40422 | 0 | 0 | 0 | 1202980 | 3447286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397020 | 0 | 0 | 5047286 | 8895554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8895554 | 13942840 | 13942840 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-012 | 66-012 | 66 | N/A | 67334 | CÉC du Centre-Est | Alain-Fortin | école élémentaire catholique Alain-Fortin | ELE | 11164 | 12223 | 12223-B01 | 676 LAKERIDGE DR | ORLEANS | K4A0J8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4474 | -75.4743 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41785 | 1819523 | Construction Complete | Addition | Accommodation Pressure | 2013-14 | 41518 | 0 | 0 | 0 | 695950 | 555000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568573 | 1819523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819523 | 1819523 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-013 | 66-013 | 66 | N/A | 67334 | CÉC du Centre-Est | Ange-Gabriel | école élémentaire et secondaire catholique Ange-Gabriel | ELE/SEC | 10786 | 11991 | 11991-B01 | 1515 KENSINGTON PKY | BROCKVILLE | K6V6H9 | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.6117 | -75.7182 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8216661 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32652 | 32652 | 8184009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8184009 | 8216661 | 8216661 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-015 | 66-015 | 66 | N/A | 67334 | CÉC du Centre-Est | Ange-Gabriel | école élémentaire et secondaire catholique Ange-Gabriel | ELE/SEC | 10786 | 11991 | 11991-B01 | 1515 KENSINGTON PKY | BROCKVILLE | K6V6H9 | 35-12-56-101 | Brockville | Brockville C | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.6117 | -75.7182 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 84 | - | - | N | - | Approved | 41072 | 2458519 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2458519 | 0 | 0 | 0 | 0 | 0 | 2458519 | 2458519 | 2458519 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 2458519
66-016 | 66-016 | 66 | N/A | 67334 | CÉC du Centre-Est | Arc-en-Ciel | école élémentaire catholique Arc-en-Ciel | ELE | 9413 | 10163 | 10163-B01 | 1830 PORTOBELLO BLVD | ORLEANS | K4A3T6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4721 | -75.4704 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 440952 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 114564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326388 | 440952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440952 | 440952 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-017 | 66-017 | 66 | N/A | 67334 | CÉC du Centre-Est | Arc-en-Ciel | école élémentaire catholique Arc-en-Ciel | ELE | 9413 | 10163 | 10163-B01 | 1830 PORTOBELLO BLVD | ORLEANS | K4A3T6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4721 | -75.4704 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 757674 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 757674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757674 | 757674 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-019-01 | 66-019 | 66 | 223 - CMSM Renfrew | 67334 | CÉC du Centre-Est | Arnprior | école élémentaire catholique Arnprior | ELE | 24449 | 19452 | 19452-B01 | 225 BASKIN DR W | ARNPRIOR | K7S0E3 | 35-12-69-401 | Arnprior | Arnprior T | Renfrew Co | RENFREW | East | South | 45.4294 | -76.3748 | 42321 | 2015-16 | 2015-16 | - | - | - | 42321 | 2015-16 | 2015-16 | 42317 | 2015-16 | 2015-16 | - | - | - | - | - | - | 248 | 3 | 49 | N | - | Approved | 44477 | 12887349 | Under Construction | New Construction | FL Capital Transitional | 2023-24 | 45170 | 0 | 0 | 0 | 2745562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2745562 | 0 | 0 | 509113 | 0 | 7431027 | 0 | 2201647 | 0 | 0 | 0 | 10141787 | 12887349 | 12887349 | 0 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9632674
66-019-02 | 66-019 | 66 | N/A | 67334 | CÉC du Centre-Est | Arnprior | école élémentaire catholique Arnprior | ELE | 24449 | 19452 | 19452-L01 | 225 BASKIN DR W | ARNPRIOR | K7S0E3 | 35-12-69-401 | Arnprior | Arnprior T | Renfrew Co | RENFREW | East | South | 45.4294 | -76.3748 | 42037 | 2014-15 | 2014-15 | 42037 | 2014-15 | 2014-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 44477 | 1622127 | Construction Complete | Land Acquisition | FL Capital Transitional | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879252 | 0 | 0 | 0 | 0 | 0 | 0 | 1879252 | 1879252 | 1879252 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1879252
66-020 | 66-020 | 66 | N/A | 67334 | CÉC du Centre-Est | Béatrice-Desloges | école secondaire catholique Béatrice-Desloges | SEC | 6193 | 5027 | 5027-B01 | 1999 PROVENCE AVE | ORLEANS | K4A3Y6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4687 | -75.4595 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6160110 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 116935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5839130 | 5956065 | 204045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204045 | 6160110 | 6160110 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-021 | 66-021 | 66 | N/A | 67334 | CÉC du Centre-Est | Béatrice-Desloges | école secondaire catholique Béatrice-Desloges | SEC | 6193 | 5027 | 5027-B01 | 1999 PROVENCE AVE | ORLEANS | K4A3Y6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4687 | -75.4595 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 531742 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 14973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516769 | 531742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531742 | 531742 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-022 | 66-022 | 66 | N/A | 67334 | CÉC du Centre-Est | Béatrice-Desloges | école secondaire catholique Béatrice-Desloges | SEC | 6193 | 5027 | 5027-B01 | 1999 PROVENCE AVE | ORLEANS | K4A3Y6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4687 | -75.4595 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12302276 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3565870 | 3565870 | 8736406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8736406 | 12302276 | 12302276 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-023 | 66-023 | 66 | N/A | 67334 | CÉC du Centre-Est | Bernard-Grandmaître | école élémentaire catholique Bernard-Grandmaître | ELE | 10803 | 12043 | 12043-B01 | 4170 SPRATT RD | GLOUCESTER | K1V0Z5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2849 | -75.6821 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9712968 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 1622768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 717756 | 2340524 | 7372444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7372444 | 9712968 | 9712968 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-024 | 66-024 | 66 | N/A | 67334 | CÉC du Centre-Est | Bernard-Grandmaître | école élémentaire catholique Bernard-Grandmaître | ELE | 10803 | 12043 | 12043-B01 | 4170 SPRATT RD | GLOUCESTER | K1V0Z5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2849 | -75.6821 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41785 | 2259050 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 0 | 0 | 0 | 1704050 | 555000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2259050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2259050 | 2259050 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-026 | 66-026 | 66 | N/A | 67334 | CÉC du Centre-Est | de la Découverte | école élémentaire catholique de la Découverte | ELE | 10144 | 10423 | 10423-B01 | 866 SCALA AVE | ORLEANS | K4A4T6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4636 | -75.4672 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 7588115 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2388083 | 2388083 | 5200032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200032 | 7588115 | 7588115 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-027 | 66-027 | 66 | N/A | 67334 | CÉC du Centre-Est | de la Découverte | école élémentaire catholique de la Découverte | ELE | 10144 | 10423 | 10423-B01 | 866 SCALA AVE | ORLEANS | K4A4T6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4636 | -75.4672 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 571030 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571030 | 571030 | 571030 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-029 | 66-029 | 66 | N/A | 67334 | CÉC du Centre-Est | des Pins | école élémentaire catholique des Pins | ELE | 3679 | 7440 | 7440-B01 | 1487 RIDGEBROOK DR | GLOUCESTER | K1B4K6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6053 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41782 | 1269116 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 564993 | 0 | 0 | 0 | 0 | 0 | 494711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059704 | 0 | 0 | 209412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209412 | 1269116 | 1269116 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-030 | 66-030 | 66 | N/A | 67334 | CÉC du Centre-Est | des Pionniers | école élémentaire catholique des Pionniers | ELE | 3170 | 7089 | 7089-B01 | 720 MERKLEY DR | ORLEANS | K4A1L8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4739 | -75.4813 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1096401 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 1096401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096401 | 1096401 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-032 | 66-032 | 66 | N/A | 67334 | CÉC du Centre-Est | des Voyageurs | école élémentaire catholique des Voyageurs | ELE | 3496 | 7294 | 7294-B01 | 6030 VOYAGEUR DR | ORLEANS | K1C2T1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4737 | -75.5522 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 486737 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 486737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486737 | 486737 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-034 | 66-034 | 66 | N/A | 67334 | CÉC du Centre-Est | Édouard-Bond | école élémentaire catholique Édouard-Bond | ELE | 10011 | 10362 | 10362-B01 | 920 PARKHAVEN AVE | OTTAWA | K2B5K3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3633 | -75.7767 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1238766 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104421 | 104421 | 1134345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1134345 | 1238766 | 1238766 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-035 | 66-035 | 66 | N/A | 67334 | CÉC du Centre-Est | Édouard-Bond | école élémentaire catholique Édouard-Bond | ELE | 10011 | 10362 | 10362-B01 | 920 PARKHAVEN AVE | OTTAWA | K2B5K3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3633 | -75.7767 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41782 | 907090 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 312361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63958 | 376319 | 0 | 0 | 530771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530771 | 907090 | 907090 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-036 | 66-036 | 66 | N/A | 67334 | CÉC du Centre-Est | Élisabeth-Bruyère | école élémentaire catholique Élisabeth-Bruyère | ELE | 9412 | 10162 | 10162-B01 | 100 STONEHAVEN DR | KANATA | K2M2H4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2865 | -75.8467 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 604188 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 155573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15561 | 171134 | 433054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433054 | 604188 | 604188 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-038 | 66-038 | 66 | N/A | 67334 | CÉC du Centre-Est | Franco-Cité | école secondaire catholique Franco-Cité | SEC | 3187 | 5016 | 5016-B01 | 623 SMYTH RD | OTTAWA | K1G1N7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4004 | -75.6416 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41435 | 9480820 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 600000 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2580820 | 7180820 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 9480820 | 9480820 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-039 | 66-039 | 66 | N/A | 67334 | CÉC du Centre-Est | Franco-Ouest | école secondaire catholique Franco-Ouest | SEC | 9719 | 5142 | 5142-B01 | 411 SEYTON DR | NEPEAN | K2H8X1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3155 | -75.8327 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9733926 | Construction Complete | Addition | Other | 2006-07 | 38961 | 0 | 0 | 78600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 943357 | 1021957 | 8711969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8711969 | 9733926 | 9733926 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-040 | 66-040 | 66 | N/A | 67334 | CÉC du Centre-Est | Garneau | école secondaire catholique Garneau | SEC | 10521 | 7138 | 7138-B01 | 6588 CARRIÈRE ST | ORLÉANS | K1C1J4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4654 | -75.525 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3348786 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 312077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86900 | 398977 | 2949809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2949809 | 3348786 | 3348786 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-041 | 66-041 | 66 | N/A | 67334 | CÉC du Centre-Est | Georges-Étienne-Cartier | école élémentaire catholique Georges-Étienne-Cartier | ELE | 4582 | 8090 | 8090-B01 | 880 THORNDALE DR | OTTAWA | K1V6Y3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3635 | -75.6721 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42192 | 3281912 | Construction Complete | Addition | Child Care | 2016-17 | 42614 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848852 | 0 | 1633060 | 3281912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3281912 | 3281912 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-042 | 66-042 | 66 | N/A | 67334 | CÉC du Centre-Est | Centre de formation | Administrative Office | OFF-ADM | 9824 | 6993 | 6993-B01 | 235 MCARTHUR AVE | VANIER | K1L6P3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4325 | -75.6601 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1098000 | Construction Complete | Retrofit | Other | 2010-11 | 40422 | 0 | 0 | 0 | 1098000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098000 | 1098000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-043 | 66-043 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Horizon-Jeunesse | école élémentaire catholique Horizon-Jeunesse | ELE | 24450 | 6993 | 6993-B01 | 349 OLMSTEAD ST | VANIER | K1L1B1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4323 | -75.6605 | 42086 | 2014-15 | 2014-15 | - | - | - | 42086 | 2014-15 | 2014-15 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 350 | 3 | 49 | N | - | Approved | 43215 | 15463703 | Construction Complete | Addition | Consolidation | 2019-20 | 43836 | 1142911 | 0 | 249000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 918227 | 0 | 0 | 2310138 | 0 | 0 | 999051 | 0 | 14110986 | 0 | 713835 | 0 | 0 | 0 | 15823872 | 18134010 | 18134010 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14824821
66-044 | 66-044 | 66 | N/A | 67334 | CÉC du Centre-Est | Jeanne-Lajoie | école élémentaire et secondaire catholique Jeanne-Lajoie | ELE/SEC | 10658 | 11160 | 11160-B01 | 1257 PEMBROKE ST W | PEMBROKE | K8A5R3 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8354 | -77.1504 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 18398890 | Construction Complete | New Construction | Other | 2005-06 | 38596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285000 | 285000 | 18113890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18113890 | 18398890 | 18398890 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-045 | 66-045 | 66 | N/A | 67334 | CÉC du Centre-Est | Jeanne-Lajoie | école élémentaire et secondaire catholique Jeanne-Lajoie | ELE/SEC | 10658 | 11160 | 11160-B01 | 1257 PEMBROKE ST W | PEMBROKE | K8A5R3 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8354 | -77.1504 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1694800 | Construction Complete | Addition | Other | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1694800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1694800 | 1694800 | 1694800 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-046 | 66-046 | 66 | N/A | 67334 | CÉC du Centre-Est | Jeanne-Lajoie | école élémentaire et secondaire catholique Jeanne-Lajoie | ELE/SEC | 10658 | 11160 | 11160-B01 | 1257 PEMBROKE ST W | PEMBROKE | K8A5R3 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8354 | -77.1504 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 2350000 | Construction Complete | Addition | Other | 2011-12 | 40787 | 0 | 0 | 800000 | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350000 | 2350000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-048 | 66-048 | 66 | N/A | 67334 | CÉC du Centre-Est | Saint-Jean-Paul II | école élémentaire catholique Saint-Jean-Paul II | ELE | 10649 | 11288 | 11288-B01 | 5473 ABBOTT ST E | STITTSVILLE | K2S0A8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2693 | -75.9045 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8158570 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065513 | 2065513 | 6093057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6093057 | 8158570 | 8158570 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-050 | 66-050 | 66 | N/A | 67334 | CÉC du Centre-Est | Jean-Robert-Gauthier | école élémentaire catholique Jean-Robert-Gauthier | ELE | 11173 | 12243 | 12243-B01 | 651 CHAPMAN MILLS DR | NEPEAN | K2J0W7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2701 | -75.7323 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 10426884 | Construction Complete | New Construction | Other | 2006-07 | 38961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992351 | 1992351 | 8434533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8434533 | 10426884 | 10426884 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-051 | 66-051 | 66 | N/A | 67334 | CÉC du Centre-Est | Jean-Robert-Gauthier | école élémentaire catholique Jean-Robert-Gauthier | ELE | 11173 | 12243 | 12243-B01 | 651 CHAPMAN MILLS DR | NEPEAN | K2J0W7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2701 | -75.7323 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 12686443 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 1600000 | 2294363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3894363 | 8792080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8792080 | 12686443 | 12686443 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-053 | 66-053 | 66 | N/A | 67334 | CÉC du Centre-Est | JL-Couroux | école élémentaire catholique JL-Couroux | ELE | 10195 | 10458 | 10458-B01 | 10 FINDLAY AVE | CARLETON PLACE | K7C3Z6 | 35-12-55-402 | Carleton Place | Carleton Place T | Lanark Co | LANARK | East | South | 45.1294 | -76.1288 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3191693 | Construction Complete | New Construction | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191693 | 3191693 | 3191693 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-054 | 66-054 | 66 | N/A | 67334 | CÉC du Centre-Est | la Source | école élémentaire catholique la Source | ELE | 11295 | 12360 | 12360-B01 | 1445 DUFORD DR | ORLEANS | K1E1E8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4723 | -75.5089 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4560000 | Construction Complete | Purchase | Accommodation Pressure | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4560000 | 0 | 0 | 0 | 0 | 4560000 | 4560000 | 4560000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-056 | 66-056 | 66 | N/A | 67334 | CÉC du Centre-Est | la Vérendrye | école élémentaire catholique la Vérendrye | ELE | 3370 | 7212 | 7212-B01 | 614 EASTVALE DR | GLOUCESTER | K1J6Z6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4604 | -75.5976 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1281069 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 1281069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281069 | 1281069 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-058 | 66-058 | 66 | N/A | 67334 | CÉC du Centre-Est | Lamoureux | école élémentaire catholique Lamoureux | ELE | 3374 | 7213 | 7213-B01 | 2540 KALADAR AVE | OTTAWA | K1V8C5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3727 | -75.6713 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 986936 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 986936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986936 | 986936 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-059 | 66-059 | 66 | N/A | 67334 | CÉC du Centre-Est | Lamoureux | école élémentaire catholique Lamoureux | ELE | 3374 | 7213 | 7213-B01 | 2540 KALADAR AVE | OTTAWA | K1V8C5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3727 | -75.6713 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41379 | 1150828 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 900828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900828 | 1150828 | 1150828 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-060 | 66-060 | 66 | N/A | 67334 | CÉC du Centre-Est | Laurier-Carrière | école élémentaire catholique Laurier-Carrière | ELE | 3450 | 7269 | 7269-B01 | 14 FOUR SEASONS DR | NEPEAN | K2E7P8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3524 | -75.7125 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 679065 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 679065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679065 | 679065 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-061 | 66-061 | 66 | N/A | 67334 | CÉC du Centre-Est | Laurier-Carrière | école élémentaire catholique Laurier-Carrière | ELE | 3450 | 7269 | 7269-B01 | 14 FOUR SEASONS DR | NEPEAN | K2E7P8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3524 | -75.7125 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 138 | - | - | N | - | Approved | 40941 | 2500575 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103000 | 0 | 0 | 0 | 0 | 0 | 0 | 103000 | 0 | 0 | 1153498 | 0 | 1244077 | 0 | 0 | 0 | 0 | 0 | 2397575 | 2500575 | 2500575 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1244077
66-062 | 66-062 | 66 | N/A | 67334 | CÉC du Centre-Est | l'Envol | école élémentaire catholique l'Envol | ELE | 9849 | 10298 | 10298-B01 | 45 JOHNSON DR | TRENTON | K8V6V7 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.1108 | -77.5554 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3529560 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69462 | 69462 | 3460098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460098 | 3529560 | 3529560 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-063 | 66-063 | 66 | N/A | 67334 | CÉC du Centre-Est | l'Envol | école élémentaire catholique l'Envol | ELE | 9849 | 10298 | 10298-B01 | 45 JOHNSON DR | TRENTON | K8V6V7 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.1108 | -77.5554 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1099122 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 377512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377512 | 0 | 0 | 721610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721610 | 1099122 | 1099122 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-064 | 66-064 | 66 | N/A | 67334 | CÉC du Centre-Est | Le-Petit-Prince | école élémentaire catholique Le-Petit-Prince | ELE | 9824 | 6993 | 6993-B01 | 235 MCARTHUR AVE | VANIER | K1L6P3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4324 | -75.659 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 3533829 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21500 | 21500 | 3512329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3512329 | 3533829 | 3533829 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-065 | 66-065 | 66 | N/A | 67334 | CÉC du Centre-Est | l'Étoile-de-l'Est | école élémentaire catholique l'Étoile-de-l'Est | ELE | 9805 | 10278 | 10278-B01 | 6220 BEAUSEJOUR DR | ORLEANS | K1C8E4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4575 | -75.5319 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5705829 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 574923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417626 | 992549 | 4713280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4713280 | 5705829 | 5705829 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-066 | 66-066 | 66 | N/A | 67334 | CÉC du Centre-Est | Marie-Rivier | école secondaire catholique Marie-Rivier | SEC | 3580 | 5104 | 5104-B01 | 711 DALTON AVE | KINGSTON | K7M8N6 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.27 | -76.5232 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 491001 | Construction Complete | Addition | Other | 2010-11 | 40422 | 0 | 0 | 0 | 168033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322968 | 491001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491001 | 491001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-067 | 66-067 | 66 | N/A | 67334 | CÉC du Centre-Est | Marius-Barbeau | école élémentaire catholique Marius-Barbeau | ELE | 3618 | 7392 | 7392-B01 | 1345 NOTTING HILL AVE | OTTAWA | K1V6T3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3717 | -75.6565 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4211501 | Construction Complete | Addition | Other | 2009-10 | 40057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2461501 | 2461501 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 4211501 | 4211501 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-068 | 66-068 | 66 | N/A | 67334 | CÉC du Centre-Est | Mer Bleue | école secondaire catholique Mer Bleue | SEC | 24277 | 19269 | 19269-B01 | 6401 RENAUD RD | ORLEANS | K1W0H8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4359 | -75.5028 | 41299 | 2012-13 | 2012-13 | - | - | - | 41299 | 2012-13 | 2012-13 | - | - | - | - | - | - | - | - | - | 881 | - | - | N | - | Approved | 42054 | 32462104 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 1650080 | 9721150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11371230 | 500000 | 0 | 0 | 0 | 20590874 | 0 | 0 | 0 | 0 | 0 | 21090874 | 32462104 | 32462104 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 20590874
66-069 | 66-069 | 66 | N/A | 67334 | CÉC du Centre-Est | Minto | école secondaire catholique Minto | SEC | 10526 | 11147 | 11147-B01 | 801 AVIATION PKY | OTTAWA | K1K4R3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4399 | -75.6271 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 9187096 | Construction Complete | New Construction | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1677050 | 1677050 | 7510046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7510046 | 9187096 | 9187096 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-070 | 66-070 | 66 | N/A | 67334 | CÉC du Centre-Est | Monseigneur-Rémi-Gaulin | école élémentaire catholique Monseigneur-Rémi-Gaulin | ELE | 3198 | 7105 | 7105-B01 | 51 VIRGINIA ST | KINGSTON | K7K5Y3 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2696 | -76.4863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 864855 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864855 | 864855 | 864855 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-071 | 66-071 | 66 | N/A | 67334 | CÉC du Centre-Est | Monseigneur-Rémi-Gaulin | école élémentaire catholique Monseigneur-Rémi-Gaulin | ELE | 3198 | 7105 | 7105-B01 | 51 VIRGINIA ST | KINGSTON | K7K5Y3 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2696 | -76.4863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 491001 | Construction Complete | Retrofit | Child Care | 2010-11 | 40422 | 0 | 0 | 0 | 168033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322968 | 0 | 0 | 491001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491001 | 491001 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-072 | 66-072 | 66 | N/A | 67334 | CÉC du Centre-Est | Monseigneur-Rémi-Gaulin | école élémentaire catholique Monseigneur-Rémi-Gaulin | ELE | 3198 | 7105 | 7105-B01 | 51 VIRGINIA ST | KINGSTON | K7K5Y3 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2696 | -76.4863 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41379 | 350672 | Construction Complete | Retrofit | Other | 2013-14 | 41518 | 111989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111989 | 0 | 0 | 238683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238683 | 350672 | 350672 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-073 | 66-073 | 66 | N/A | 67334 | CÉC du Centre-Est | Montfort | école élémentaire catholique Montfort | ELE | 3430 | 7254 | 7254-B01 | 641 SLADEN AVE | OTTAWA | K1K2S8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4403 | -75.6431 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 314751 | Construction Complete | Addition | Other | 2000-01 | 36770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314751 | 314751 | 314751 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-074 | 66-074 | 66 | N/A | 67334 | CÉC du Centre-Est | Montfort | école élémentaire catholique Montfort | ELE | 11134 | 7050 | 7050-B02 | 350 DEN HAAG DR | OTTAWA | K1K0W9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4416 | -75.6336 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 12972267 | Construction Complete | New Construction | Condition | 2008-09 | 39692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397020 | 0 | 502980 | 900000 | 12072267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12072267 | 12972267 | 12972267 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-075 | 66-075 | 66 | N/A | 67334 | CÉC du Centre-Est | Montfort | école élémentaire catholique Montfort | ELE | 11134 | 7050 | 7050-B02 | 350 DEN HAAG DR | OTTAWA | K1K0W9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4416 | -75.6336 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41097 | 660959 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 449919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449919 | 0 | 0 | 211040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211040 | 660959 | 660959 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-076 | 66-076 | 66 | N/A | 67334 | CÉC du Centre-Est | Notre-Dame-des-Champs | école élémentaire catholique Notre-Dame-des-Champs | ELE | 14501 | 18018 | 18018-B01 | 6280 RENAUD RD | NAVAN | K4B1H9 | 35-12-46-618 | North Frontenac | North Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 45.4327 | -75.5091 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 13006574 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 230628 | 3463650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443480 | 0 | 4907 | 4142665 | 8003700 | 0 | 860209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8863909 | 13006574 | 13006574 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-077 | 66-077 | 66 | N/A | 67334 | CÉC du Centre-Est | Notre-Place | école élémentaire catholique Notre-Place | ELE | 24375 | 19376 | 19376-B01 | 665 DES AUBEPINES DR | ORLEANS | K4A0Z3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4474 | -75.4844 | 41877 | 2013-14 | 2014-15 | - | - | - | 41877 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 412 | - | - | N | - | Approved | 42269 | 14699654 | Construction Complete | New Construction | Accommodation Pressure | 2016-17 | 42614 | 0 | 0 | 0 | 0 | 4639791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998260 | 0 | 0 | 5638051 | 0 | 0 | 998260 | 0 | 8063343 | 0 | 0 | 0 | 0 | 0 | 9061603 | 14699654 | 14699654 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 8063343
66-078 | 66-078 | 66 | N/A | 67334 | CÉC du Centre-Est | Paul-Desmarais | école secondaire catholique Paul-Desmarais | SEC | 18115 | 19374 | 19374-B01 | 5315 ABBOTT ST E | STITTSVILLE | K2S0X3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2747 | -75.8969 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 739 | - | - | N | - | Approved | 42478 | 33748910 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 1539100 | 11357500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12896600 | 1200000 | 0 | 0 | 0 | 19652310 | 0 | 0 | 0 | 0 | 0 | 20852310 | 33748910 | 33748910 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 19652310
66-079 | 66-079 | 66 | N/A | 67334 | CÉC du Centre-Est | Pierre-Elliott-Trudeau | école élémentaire catholique Pierre-Elliott-Trudeau | ELE | 9847 | 10297 | 10297-B01 | 601 LONGFIELDS DR | NEPEAN | K2J4X1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2853 | -75.7445 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 6206021 | Construction Complete | New Construction | Other | 2002-03 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417889 | 1417889 | 4788132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788132 | 6206021 | 6206021 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-081 | 66-081 | 66 | N/A | 67334 | CÉC du Centre-Est | Pierre-Savard | école secondaire catholique Pierre-Savard | SEC | 11166 | 11287 | 11287-B01 | 1110 LONGFIELDS DR | NEPEAN | K2J0H9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2731 | -75.7375 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 16456301 | Construction Complete | New Construction | Other | 2010-11 | 40422 | 0 | 0 | 0 | 0 | 2360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360000 | 14096301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096301 | 16456301 | 16456301 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-082 | 66-082 | 66 | N/A | 67334 | CÉC du Centre-Est | Pierre-Savard | école secondaire catholique Pierre-Savard | SEC | 11166 | 11287 | 11287-B01 | 1110 LONGFIELDS DR | NEPEAN | K2J0H9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2731 | -75.7375 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 3398790 | Construction Complete | Addition | Other | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 998790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998790 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 3398790 | 3398790 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-083 | 66-083 | 66 | N/A | 67334 | CÉC du Centre-Est | Pierre-Savard | école secondaire catholique Pierre-Savard | SEC | 11166 | 11287 | 11287-B01 | 1110 LONGFIELDS DR | NEPEAN | K2J0H9 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2731 | -75.7375 | 41765 | 2013-14 | 2014-15 | - | - | - | 41765 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 254 | - | - | N | - | Approved | 42018 | 4390871 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6887871 | 0 | 0 | 0 | 0 | 0 | 6887871 | 6887871 | 4593599 | -2294272 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 6887871
66-084 | 66-084 | 66 | N/A | 67334 | CÉC du Centre-Est | Reine-des-Bois | école élémentaire catholique Reine-des-Bois | ELE | 3194 | 7102 | 7102-B01 | 1450 DUFORD DR | ORLEANS | K1E1E6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.472 | -75.5096 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41379 | 522454 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188698 | 188698 | 0 | 0 | 333756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333756 | 522454 | 522454 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-085 | 66-085 | 66 | N/A | 67334 | CÉC du Centre-Est | Roger-Saint-Denis | école élémentaire catholique Roger-Saint-Denis | ELE | 3619 | 7393 | 7393-B01 | 186 BARROW CRES | KANATA | K2L2C7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3113 | -75.8823 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 190453 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188039 | 188039 | 0 | 0 | 2414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2414 | 190453 | 190453 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-086 | 66-086 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Anne | école élémentaire catholique Sainte-Anne | ELE | 4545 | 8064 | 8064-B01 | 235 BEAUSOLEIL DR | OTTAWA | K1N0C1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4326 | -75.682 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41396 | 7330882 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 963409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148609 | 1112018 | 5300000 | 0 | 918864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6218864 | 7330882 | 7330882 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-087 | 66-087 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Bernadette | école élémentaire catholique Sainte-Bernadette | ELE | 3245 | 7134 | 7134-B01 | 3781 SIXTH ST | GLOUCESTER | K1T1K5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3519 | -75.6232 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1200083 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 105791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094292 | 1200083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200083 | 1200083 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-088 | 66-088 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Bernadette | école élémentaire catholique Sainte-Bernadette | ELE | 3245 | 7134 | 7134-B01 | 3781 SIXTH ST | GLOUCESTER | K1T1K5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3519 | -75.6232 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 490031 | Construction Complete | Addition | Other | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370265 | 0 | 0 | 0 | 0 | 0 | 0 | 370265 | 0 | 0 | 119766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119766 | 490031 | 490031 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-089 | 66-089 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Geneviève | école élémentaire catholique Sainte-Geneviève | ELE | 4555 | 8071 | 8071-B01 | 2198 ARCH ST | OTTAWA | K1G2H7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3898 | -75.6313 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 826481 | Construction Complete | Addition | Other | 2002-03 | 37500 | 0 | 0 | 26481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 826481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826481 | 826481 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-090 | 66-090 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Geneviève | école élémentaire catholique Sainte-Geneviève | ELE | 4555 | 8071 | 8071-B01 | 2198 ARCH ST | OTTAWA | K1G2H7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3898 | -75.6313 | 41765 | 2013-14 | 2014-15 | - | - | - | 41765 | 2013-14 | 2014-15 | - | - | - | - | - | - | - | - | - | 308 | - | - | N | - | Approved | 44684 | 9557239 | Construction Complete | Addition | Accommodation Pressure | 2016-17 | 42614 | 820000 | 0 | 0 | 1000000 | 0 | 0 | 598854 | 0 | 30648 | 0 | 0 | 0 | 0 | 0 | 0 | 2449502 | 0 | 0 | 1750127 | 0 | 5357610 | 0 | 0 | 0 | 0 | 0 | 7107737 | 9557239 | 9557239 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 5357610
66-091 | 66-091 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Kateri | école élémentaire catholique Sainte-Kateri | ELE | 18114 | 19046 | 19046-B01 | 2450 RIVER MIST RD | NEPEAN | K2J5W5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2454 | -75.7362 | 40731 | 2010-11 | 2011-12 | - | - | - | 40731 | 2010-11 | 2011-12 | - | - | - | - | - | - | - | - | - | 400 | - | - | N | - | Approved | 40889 | 10716916 | Construction Complete | New Construction | Accommodation Pressure | 2015-16 | 42248 | 0 | 0 | 0 | 231042 | 2416960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2648002 | 0 | 0 | 891726 | 0 | 7177188 | 0 | 0 | 0 | 0 | 0 | 8068914 | 10716916 | 10716916 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 7177188
66-092 | 66-092 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Marguerite-Bourgeoys | école élémentaire catholique Sainte-Marguerite-Bourgeoys | ELE | 3411 | 7242 | 7242-B01 | 306 READ ST | MERRICKVILLE | K0G1N0 | 35-12-56-506 | Merrickville-Wolford | Merrickville-Wolford V | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.914 | -75.8414 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 841062 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 841062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 841062 | 841062 | 841062 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-093 | 66-093 | 66 | N/A | 67334 | CÉC du Centre-Est | Sainte-Marguerite-Bourgeoys | école élémentaire catholique Sainte-Marguerite-Bourgeoys | ELE | 3411 | 7242 | 7242-B01 | 306 READ ST | MERRICKVILLE | K0G1N0 | 35-12-56-506 | Merrickville-Wolford | Merrickville-Wolford V | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | 44.914 | -75.8414 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 554360 | Construction Complete | Addition | Other | 2007-08 | 39326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554360 | 554360 | 554360 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-094 | 66-094 | 66 | N/A | 67334 | CÉC du Centre-Est | Saint-François-d'Assise | école élémentaire catholique Saint-François-d'Assise | ELE | 3959 | 7649 | 7649-B01 | 35 MELROSE AVE | OTTAWA | K1Y1T8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4024 | -75.7237 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 4491700 | Construction Complete | Retrofit | Condition | 2009-10 | 40057 | 0 | 0 | 0 | 418405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231595 | 0 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 3841700 | 0 | 0 | 0 | 0 | 3841700 | 4491700 | 4491700 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-096 | 66-096 | 66 | N/A | 67334 | CÉC du Centre-Est | Saint-Guillaume | école élémentaire catholique Saint-Guillaume | ELE | 3164 | 7084 | 7084-B01 | 5750 BUCKLAND RD SS 901 | VARS | K0A3H0 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3557 | -75.3537 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 41379 | 844794 | Construction Complete | Addition | Accommodation Pressure | 2015-16 | 42248 | 8886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293334 | 302220 | 0 | 0 | 542574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542574 | 844794 | 844794 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-097 | 66-097 | 66 | N/A | 67334 | CÉC du Centre-Est | Saint-Joseph-d'Orléans | école élémentaire catholique Saint-Joseph-d'Orléans | ELE | 3488 | 7138 | 7138-B02 | 6664 CARRIÈRE ST | ORLÉANS | K1C1J4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4657 | -75.5214 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 891755 | Construction Complete | Retrofit | Other | 2000-01 | 36770 | 0 | 0 | 470484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421271 | 891755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891755 | 891755 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-098 | 66-098 | 66 | N/A | 67334 | CÉC du Centre-Est | Saint-Joseph-d'Orléans | école élémentaire catholique Saint-Joseph-d'Orléans | ELE | 3488 | 7138 | 7138-B02 | 6664 CARRIÈRE ST | ORLÉANS | K1C1J4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4657 | -75.5214 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 40889 | 354277 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 114284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114284 | 0 | 0 | 239993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239993 | 354277 | 354277 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-099 | 66-099 | 66 | N/A | 67334 | CÉC du Centre-Est | Saint-Rémi | école élémentaire catholique Saint-Rémi | ELE | 14498 | 18017 | 18017-B01 | 100 WALDEN DR | KANATA | K2K0G8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3278 | -75.9235 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 11319576 | Construction Complete | New Construction | Accommodation Pressure | 2012-13 | 41153 | 0 | 0 | 0 | 0 | 3347168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312199 | 0 | 0 | 3659367 | 6800000 | 0 | 860209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7660209 | 11319576 | 11319576 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-100 | 66-100 | 66 | N/A | 67334 | CÉC du Centre-Est | Samuel-Genest | école secondaire catholique Samuel-Genest | SEC | 3121 | 7050 | 7050-B01 | 704 CARSON'S RD | OTTAWA | K1K2H3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4429 | -75.6293 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 1256956 | Construction Complete | Addition | Other | 1999-00 | 36404 | 0 | 0 | 466418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664140 | 1130558 | 126398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126398 | 1256956 | 1256956 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-101 | 66-101 | 66 | N/A | 67334 | CÉC du Centre-Est | Samuel-Genest | école secondaire catholique Samuel-Genest | SEC | 10653 | 7050 | 7050-B01 | 704 CARSON'S RD | OTTAWA | K1K2H3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4429 | -75.6293 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 8374070 | Construction Complete | Addition | Other | 2003-04 | 37865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4321000 | 4321000 | 4053070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4053070 | 8374070 | 8374070 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-102 | 66-102 | 66 | N/A | 67334 | CÉC du Centre-Est | CÉCCE Head Office | Administrative Office | OFF-ADM | 18349 | 19076 | 19076-B01 | 4000 LABELLE ST | GLOUCESTER | K1J1A1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4219 | -75.6333 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1705671 | Construction Complete | Retrofit | Other | 2016-17 | 42614 | 0 | 0 | 0 | 1705671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1705671 | 1705671 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-103 | 66-103 | 66 | N/A | 67334 | CÉC du Centre-Est | Terre-des-Jeunes | école élémentaire catholique Terre-des-Jeunes | ELE | 10875 | 5128 | 5128-B01 | 1303 FELLOWS RD | OTTAWA | K2C2V8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3522 | -75.7681 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 39691 | 5229270 | Construction Complete | New Construction | Other | 2000-01 | 36770 | 0 | 0 | 3529270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 3769270 | 1460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460000 | 5229270 | 5229270 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
66-105 | 66-105 | 66 | 223 - CMSM Renfrew | 67334 | CÉC du Centre-Est | Jeanne-Lajoie | école élémentaire et secondaire catholique Jeanne-Lajoie | ELE/SEC | 10658 | 11160 | 11160-B01 | 1257 PEMBROKE ST W | PEMBROKE | K8A5R3 | 35-12-69-101 | Pembroke | Pembroke C | Renfrew Co | RENFREW | East | South | 45.8354 | -77.1504 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42758 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 34 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2018-19 | 43470 | 0 | 0 | 0 | 204934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204235 | 0 | 40971 | 450140 | 0 | 0 | 0 | 0 | 0 | 0 | 1058757 | 0 | 0 | 0 | 1058757 | 1508897 | 1508897 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1058757
66-106 | 66-106 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Sainte-Anne | école élémentaire catholique Sainte-Anne | ELE | 4545 | 8064 | 8064-B01 | 235 BEAUSOLEIL DR | OTTAWA | K1N0C1 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4326 | -75.682 | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | 42695 | 2016-17 | 2016-17 | - | - | - | - | - | - | - | 2 | 18 | Y | - | Not Required | - | 0 | Construction Complete | Addition | Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038591 | 0 | 0 | 0 | 1038591 | 1038591 | 1038591 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1038591
66-107 | 66-107 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Lamoureux | école élémentaire catholique Lamoureux | ELE | 3374 | 7213 | 7213-B01 | 2540 KALADAR AVE | OTTAWA | K1V8C5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3727 | -75.6713 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 44385 | 2271612 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 450593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596539 | 0 | 0 | 1047132 | 0 | 0 | 0 | 0 | 0 | 0 | 1224480 | 0 | 0 | 0 | 1224480 | 2271612 | 2271612 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1224480
66-108 | 66-108 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Roger-Saint-Denis | école élémentaire catholique Roger-Saint-Denis | ELE | 3619 | 7393 | 7393-B01 | 186 BARROW CRES | KANATA | K2L2C7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3113 | -75.8823 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 2 | 34 | Y | 1 | Approved | 44627 | 2336835 | Construction Complete | Addition | Child Care | 2021-22 | 44440 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168417 | 0 | 0 | 1227417 | 0 | 0 | 0 | 0 | 0 | 0 | 1109418 | 0 | 0 | 0 | 1109418 | 2336835 | 2336835 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 1109418
66-109 | 66-109 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Arc-en-Ciel | école élémentaire catholique Arc-en-Ciel | ELE | 9413 | 10163 | 10163-B01 | 1830 PORTOBELLO BLVD | ORLEANS | K4A3T6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4721 | -75.4704 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Not Required | - | 0 | Construction Complete | Retrofit | Child Care | 2018-19 | 43378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292902 | 0 | 0 | 0 | 292902 | 292902 | 292902 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 292902
66-110 | 66-110 | 66 | 216 - CMSM Hastings | 67334 | CÉC du Centre-Est | l'Envol | école élémentaire catholique l'Envol | ELE | 9849 | 10298 | 10298-B01 | 45 JOHNSON DR | TRENTON | K8V6V7 | 35-12-51-104 | Quinte West | Quinte West C | Hastings Co | HASTINGS | East | South | 44.1108 | -77.5554 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43949 | 748395 | Construction Complete | Addition | Child Care | 2020-21 | 44204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748395 | 0 | 0 | 0 | 748395 | 748395 | 748395 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 748395
66-111-01 | 59-062+66-111 | 66 | 205 - CMSM Kingston | 67334 | CÉC du Centre-Est | Marie-Rivier | école secondaire catholique Marie-Rivier | SEC | 24809-25411 | 19823 | 19823-B01 | 1381 DEMERS AVE | KINGSTON | TBD | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2499 | -76.5607 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | 43223 | 2017-18 | 2018-19 | 43173 | 2017-18 | 2017-18 | 300 | 3 | 49 | Y | 1 | Approved | 44176 | 17124000 | Under Construction | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 1918550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918550 | 0 | 0 | 0 | 0 | 11855472 | 0 | 1699599 | 529379 | 1700000 | 0 | 15784450 | 17703000 | 17124000 | -579000 | - | N/A, Project was approved prior to June 2018 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 15784450
66-111-02 | 59-062+66-111 | 66 | N/A | 67334 | CÉC du Centre-Est | Marie-Rivier | école secondaire catholique Marie-Rivier | SEC | 24809-25411 | 19823 | 19823-L01 | 1381 DEMERS AVE | KINGSTON | TBD | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2499 | -76.5607 | 43227 | 2017-18 | 2018-19 | 43227 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Approved | 43885 | 3509625 | Construction Complete | Land Acquisition | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3686500 | 0 | 0 | 0 | 0 | 0 | 0 | 3686500 | 3686500 | 3509625 | -176875 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3686500
66-112 | 66-112 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Jonathan-Pitre | école élémentaire catholique Jonathan-Pitre | ELE | 24808 | 19815 | 19815-B01 | 925 RALPH HENNESSY AVE | GLOUCESTER | K1X0C3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2716 | -75.6799 | 43131 | 2017-18 | 2017-18 | - | - | - | 43131 | 2017-18 | 2017-18 | 43172 | 2017-18 | 2017-18 | - | - | - | - | - | - | 412 | 3 | 49 | Y | - | Approved | 43560 | 14213534 | Construction Complete | New Construction | Accommodation Pressure | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 3570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570000 | 0 | 0 | 1059362 | 0 | 8026285 | 0 | 1557887 | 0 | 0 | 0 | 10643534 | 14213534 | 14213534 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 9584172
66-113 | 66-113 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Au Cœur d'Ottawa | école élémentaire catholique Au Cœur d'Ottawa | ELE | 25529 | 25535 | 25535-B01 | 205 SCHOLASTIC DR | OTTAWA | K1S5H3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4095 | -75.6739 | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 351 | 2 | 39 | N | - | Not Required | - | - | Under Construction | Purchase | FL Capital Transitional | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 0 | 550869 | 0 | 0 | 0 | 5750869 | 5750869 | 5750869 | 0 | - | Yes | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 5750869
66-114 | 66-114 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Avalon III | école élémentaire catholique Avalon III | ELE | 25514 | 20520 | 20520-B01 | WALL RD | OTTAWA | TBD | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | TBD | TBD | 44124 | 2020-21 | 2020-21 | - | - | - | 44124 | 2020-21 | 2020-21 | 44124 | 2020-21 | 2020-21 | - | - | - | - | - | - | 412 | 2 | 39 | N | - | Planned | - | - | Planned | New Construction | Accommodation Pressure | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9449061 | 0 | 1101738 | 0 | 0 | 0 | 10550799 | 10550799 | 10550799 | 0 | - | No, Site to be acquired. Sign installation planned for November 1, 2021 | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 10550799
66-115 | 66-115 | 66 | 207 - CMSM Ottawa | 67334 | CÉC du Centre-Est | Sainte-Marie | école élémentaire catholique Sainte-Marie | ELE | 3246 | 7135 | 7135-B01 | 2599 INNES RD | GLOUCESTER | K1B3J8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.432 | -75.5663 | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | 44280 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | 2 | 39 | N | - | Approved | 44679 | 848623 | Under Construction | Retrofit | Child Care | 2022-23 | 44805 | 196135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101619 | 0 | 0 | 297754 | 0 | 0 | 0 | 0 | 0 | 0 | 550869 | 0 | 0 | 0 | 550869 | 848623 | 848623 | 0 | - | No, TBD | Not Applicable | Not Applicable | YES as part of CC only | YES | 550869
66-116 | 66-116 | 66 | N/A | 67334 | CÉC du Centre-Est | Paul-Desmarais | école secondaire catholique Paul-Desmarais | SEC | 18115-24373 | 19374 | 19374-B01 | 5315 ABBOTT ST E | STITTSVILLE | K2S0X3 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2747 | -75.8969 | 44523 | 2021-22 | 2021-22 | - | - | - | 44523 | 2021-22 | 2021-22 | 44523 | 2021-22 | 2021-22 | - | - | - | - | - | - | 389 | - | - | N | - | Approved | 45015 | 12975913 | Planned | Addition | Accommodation Pressure | 2022-23 | 44805 | 0 | 0 | 0 | 0 | 998731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998731 | 0 | 0 | 0 | 0 | 11977182 | 0 | 0 | 0 | 0 | 0 | 11977182 | 12975913 | 12975913 | 0 | - | No, TBD | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 11977182
66-117 | 66-117 | 66 | N/A | 67334 | CÉC du Centre-Est | Mer Bleue | école secondaire catholique Mer Bleue | SEC | 24277-24376 | 19269 | 19269-B01 | 6401 RENAUD RD | ORLEANS | K1W0H8 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4359 | -75.5028 | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | - | - | - | 343 | - | - | N | - | Planned | - | - | Planned | Addition | Accommodation Pressure | 2025-26 | 45901 | 0 | 0 | 0 | 0 | 786570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786570 | 0 | 0 | 0 | 0 | 12144986 | 0 | 0 | 0 | 0 | 0 | 12144986 | 12931556 | 12931556 | 0 | - | No | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 12144986
66-118 | 66-118 | 66 | 235 - CMSM Leeds & Grenville | 67334 | CÉC du Centre-Est | Notre-Dame | école élémentaire et secondaire catholique Notre-Dame | ELE/SEC | TBD | TBD | TBD | TBD | KEMPTVILLE | K0G1JO | 35-12-56-617 | North Grenville | North Grenville M | Leeds and Grenville UCo | LEEDS AND GRENVILLE | East | South | TBD | TBD | 44672 | 2021-22 | 2022-23 | - | - | - | 44672 | 2021-22 | 2022-23 | 44672 | 2021-22 | 2022-23 | - | - | - | - | - | - | 417 | 2 | 39 | N | - | Planned | - | - | Planned | New Construction | FL Capital Transitional | 2026-27 | 46266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13533242 | 0 | 1382133 | 0 | 0 | 0 | 14915375 | 14915375 | 14915375 | 0 | - | No | YES counts as a CP project | YES must be counted | YES as part of CP (CP+CC) | YES | 14915375
66-119 | 66-119 | 66 |  | 67334 | CÉC du Centre-Est | ESC Franco-Cite | [48 empty] | 0 | 0 | 428845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428845 | 428845 | 0
100-001 | 100-001 | 100 | N/A | 15148 | James Bay Lowlands SSB | Northern Lights | Northern Lights Secondary School | SEC | 24770 | 19777 | 19777-B01 | 2 KEEWATIN DR | MOOSONEE | P0L1Y0 | 35-13-81-408 | Moosonee | Moosonee T | Cochrane District | COCHRANE | Northeast | North | 51.285 | -80.6256 | 41725 | 2013-14 | 2013-14 | - | - | - | 41725 | 2013-14 | 2013-14 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 1176000 | Construction Complete | Retrofit | Condition | 2015-16 | 42248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 1176000 | 1176000 | 1176000 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 1176000
103-001 | 103-001 | 103 | N/A | 79910 | Penetanguishene PSSB | Burkevale | Burkevale Protestant Elementary School | ELE | 24759 | 19766 | 19766-B01 | 39 BURKE ST | PENETANGUISHENE | L9M1C4 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7758 | -79.9336 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Not Required | - | 160836 | Construction Complete | Retrofit | Condition | 2014-15 | 41883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160836 | 160836 | 160836 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
103-002 | 103-002 | 103 | N/A | 79910 | Penetanguishene PSSB | Burkevale | Burkevale Protestant Elementary School | ELE | 24759 | 19766 | 19766-B01 | 39 BURKE ST | PENETANGUISHENE | L9M1C4 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7758 | -79.9336 | 42486 | 2015-16 | 2016-17 | - | - | - | 42486 | 2015-16 | 2016-17 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42745 | 3531219 | Construction Complete | Retrofit | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3531219 | 0 | 0 | 0 | 0 | 0 | 3531219 | 3531219 | 3531219 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 3531219
103-003 | 103-003 | 103 | N/A | 79910 | Penetanguishene PSSB | Burkevale | Burkevale Protestant Elementary School | ELE | 24759 | 19766 | 19766-B01 | 39 BURKE ST | PENETANGUISHENE | L9M1C4 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7758 | -79.9336 | 42989 | 2017-18 | 2017-18 | - | - | - | 42989 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 42989 | 649900 | Construction Complete | Retrofit | Condition | 2017-18 | 42979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649900 | 0 | 0 | 0 | 0 | 0 | 649900 | 649900 | 649900 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 649900
103-004 | 103-004 | 103 | N/A | 79910 | Penetanguishene PSSB | Burkevale | Burkevale Protestant Elementary School | ELE | 24759 | 19766 | 19766-B01 | 39 BURKE ST | PENETANGUISHENE | L9M1C4 | 35-11-70-406 | Penetanguishene | Penetanguishene T | Simcoe Co | SIMCOE | Central | South | 44.7758 | -79.9336 | 43129 | 2017-18 | 2017-18 | - | - | - | 43129 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | - | - | - | - | - | N | - | Approved | 43129 | 143520 | Construction Complete | Addition | Accommodation Pressure | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143520 | 0 | 0 | 0 | 0 | 0 | 143520 | 143520 | 143520 | 0 | - | N/A, Not a project reported on OB | YES counts as a CP project | YES must be counted | Not Applicable | Not Applicable | 143520
202-001 | 202-001 | 202 | 202 - CMSM Greater Sudbury | - | CMSM Greater Sudbury | Garderie Place des Arts | Garderie Place des Arts | (CB) | - | - | - | 27 LARCH ST | SUDBURY | P3E1B8 | 35-13-23-000 | Greater Sudbury | Greater Sudbury C | Greater Sudbury C | SUDBURY | Northeast | North | 46.4903 | -80.9955 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 750000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585000 | 0 | 0 | 0 | 585000 | 585000 | 750000 | 165000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 585000
203-001 | 203-001 | 203 | 203 - CMSM Hamilton | - | CMSM Hamilton | Biindigen Community HUB | Biindigen Community HUB | (CB) | - | - | - | 785 BRITANNIA AVE | HAMILTON | L8H2B6 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2395 | -79.7814 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 3 | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
203-002 | 203-002 | 203 | 203 - CMSM Hamilton | - | CMSM Hamilton | King George | King George | (CB) | - | - | - | 77 GAGE AVE N | HAMILTON | L8L6Z8 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2513 | -79.8276 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | Y | 3 | Approved | 43195 | 2040000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530000 | 510000 | 0 | 0 | 2040000 | 2040000 | 2040000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2040000
203-003 | 203-003 | 203 | 203 - CMSM Hamilton | - | CMSM Hamilton | Riverdale Community HUB | Riverdale Community HUB | (CB) | - | - | - | 150 VIOLET DR | HAMILTON | L8E6B4 | 35-11-16-000 | Hamilton | Hamilton C | Hamilton C | HAMILTON | Central | South | 43.2328 | -79.7575 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 3 | 49 | Y | 3 | Approved | 43195 | 2040000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530000 | 510000 | 0 | 0 | 2040000 | 2040000 | 2040000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2040000
204-001 | 204-001 | 204 | 204 - CMSM Kawartha Lakes | - | CMSM Kawartha Lakes | Bobcaygeon | Bobcaygeon | (CB) | - | - | - | 3 DUKE ST | BOBCAYGEON | K0M1A0 | 35-12-72-000 | Kawartha Lakes | Kawartha Lakes C | Kawartha Lakes C | KAWARTHA LAKES | East | South | 44.5447 | -78.5437 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Approved | 43195 | 750000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000 | 750000 | 750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 750000
204-002 | 204-002 | 204 | 204 - CMSM Kawartha Lakes | - | CMSM Kawartha Lakes | Minden | Minden | (CB) | - | - | - | 16 PRENTICE ST | MINDEN | K0M2K0 | 35-12-49-611 | Minden Hills | Minden Hills Tp | Haliburton Co | HALIBURTON | East | South | 44.9318 | -78.7276 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 750000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 0 | 750000 | 750000 | 750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 750000
205-001 | 205-001 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | EarlyON East Kingston | EarlyON East Kingston | (CB) | - | - | - | 695 INNOVATION DR | KINGSTON | K7K7E6 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.3034 | -76.4176 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 525000 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 525000 | 525000 | 525000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 525000
205-002 | 205-002 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | EarlyON Central Kingston | EarlyON Central Kingston | (CB) | - | - | - | 299 CONCESSION ST | KINGSTON | K7K2B9 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2322 | -76.4821 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 262500 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262500 | 0 | 0 | 262500 | 262500 | 262500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 262500
205-003 | 205-003 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | Helen Tuft's Nursery School | Helen Tuft's Nursery School | (CB) | - | - | - | 559 BAGOT ST | KINGSTON | K7K3E6 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2395 | -76.4847 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 43195 | 30000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 30000
205-004 | 205-004 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | Outreach in Central Kingston | Outreach in Central Kingston | (CB) | - | - | - | 263 WELLER AVE | KINGSTON | K7K2V4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2653 | -76.4818 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 50000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 50000 | 50000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 50000
205-005 | 205-005 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | Outreach in North Frontenac | Outreach in North Frontenac | (CB) | - | - | - | 1004 ART DUFFY RD | ARDEN | K0H2P0 | 35-12-46-616 | Central Frontenac | Central Frontenac Tp | Frontenac Co | FRONTENAC | East | South | 44.7205 | -76.9239 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 50000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 50000 | 50000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 50000
205-006 | 205-006 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | Outreach in South Frontenac | Outreach in South Frontenac | (CB) | - | - | - | 4365 MILL ST | ELGINBURG | K0H2T0 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.3188 | -76.5408 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 50000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 50000 | 50000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 50000
205-007 | 205-007 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | Outreach in West Kingston | Outreach in West Kingston | (CB) | - | - | - | 1350 GARDINERS RD | KINGSTON | K7P0E5 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.2753 | -76.569 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 50000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 50000 | 50000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 50000
205-008 | 205-008 | 205 | 205 - CMSM Kingston | - | CMSM Kingston | Outreach in West Kingston | Outreach in West Kingston | (CB) | - | - | - | 1300 BATH RD | KINGSTON | K7M4X4 | 35-12-45-000 | Kingston | Kingston C | Kingston C | FRONTENAC | East | South | 44.219 | -76.5681 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 50000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 50000 | 50000 | 50000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 50000
206-001 | 206-001 | 206 | 206 - CMSM London | - | CMSM London | Ilderton EarlyON & Library | Ilderton EarlyON & Library | (CB) | - | - | - | 40 HERITAGE DR | ILDERTON | N0M2A0 | 35-15-59-616 | Middlesex Centre | Middlesex Centre M | Middlesex Co | MIDDLESEX | Southwest | South | 43.0781 | -81.3754 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 530000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530000 | 0 | 0 | 530000 | 530000 | 530000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 530000
206-002 | 206-002 | 206 | 206 - CMSM London | - | CMSM London | Nshwaasnangong - Indigenous-led Child Care | Indigenous-led Child Care | (CB) | - | - | - | 449 HILL ST | LONDON | N6B1E5 | 35-15-59-101 | London | London C | London C | MIDDLESEX | Southwest | South | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 43195 | 2500000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 2500000 | 2500000 | 2500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2500000
206-003 | 206-003 | 206 | 206 - CMSM London | - | CMSM London | Nshwaasnangong - Indigenous-led Child Care | Strathroy EarlyON & Library | (CB) | - | - | - | 34 FRANK ST | STRATHROY | N7G2R4 | 35-15-59-621 | Strathroy-Caradoc | Strathroy-Caradoc Tp | Middlesex Co | MIDDLESEX | Southwest | South | 42.956 | -81.6245 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 525000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 525000 | 525000 | 525000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 525000
207-001 | 207-001 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Nshwaasnangong - Indigenous-led Child Care | EarlyON Mobile Unit | (CB) | - | - | - | 815 ST LAURENT BLVD | OTTAWA | K1K3A7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.2987 | -75.8905 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 515000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 0 | 0 | 515000 | 515000 | 515000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 515000
207-002 | 207-002 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Nshwaasnangong - Indigenous-led Child Care | Francophone Child Care Programs | (CB) | - | - | - | 998 FRANCES ST | OTTAWA | K1K3L5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4273 | -75.6484 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 515000 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 0 | 0 | 0 | 515000 | 515000 | 515000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 515000
207-003 | 207-003 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Nshwaasnangong - Indigenous-led Child Care | High Needs Area Ward 10 - Project A | (CB) | - | - | - | 2826 SPRINGLAND DR | OTTAWA | K1V9S7 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3816 | -75.6347 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 43195 | 1545000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2317500 | 0 | 0 | 0 | 2317500 | 2317500 | 1545000 | -772500 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2317500
207-004 | 207-004 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Nshwaasnangong - Indigenous-led Child Care | High Needs Area Ward 10 - Project B | (CB) | - | - | - | - | OTTAWA | - | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3816 | -75.6347 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772500 | 772500 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
207-005 | 207-005 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Nshwaasnangong - Indigenous-led Child Care | High Needs Area Ward 7 - Project A | (CB) | - | - | - | 411 CORKSTOWN RD | OTTAWA | K2K0J5 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3666 | -75.7925 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 1545000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545000 | 0 | 0 | 0 | 1545000 | 1545000 | 1545000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1545000
207-006 | 207-006 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Nshwaasnangong - Indigenous-led Child Care | High Needs Area Ward 7 - Project B | (CB) | - | - | - | 2345 ALTA VISTA DR | OTTAWA | K1H7M6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.3666 | -75.7925 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 772500 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772500 | 0 | 0 | 0 | 772500 | 772500 | 772500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 772500
207-007 | 207-007 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Indigenous Child Care Program | Indigenous Child Care Program | (CB) | - | - | - | 1099 LONGFIELDS DR | OTTAWA | K2J5L2 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4312 | -75.6601 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 2 | 30 | Y | - | Approved | 43195 | 1030000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030000 | 0 | 0 | 0 | 1030000 | 1030000 | 1030000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1030000
207-008 | 207-008 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Young Mothers | Young Mothers | (CB) | - | - | - | 150 MANN AVE | OTTAWA | K1N8P4 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.422 | -75.6694 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 515000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 0 | 0 | 0 | 515000 | 515000 | 515000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 515000
207-009 | 207-009 | 207 | 207 - CMSM Ottawa | - | CMSM Ottawa | Young Mothers (Francophone) | Young Mothers | (CB) | - | - | - | 1125 COLONEL BY DR | OTTAWA | K1S5B6 | 35-12-20-000 | Ottawa | Ottawa C | Ottawa C | OTTAWA | East | South | 45.4343 | -75.6647 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 772500 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 0 | 0 | 0 | 515000 | 515000 | 772500 | 257500 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 515000
208-001 | 208-001 | 208 | 208 - CMSM Peterborough | - | CMSM Peterborough | Compass Early Learning and Care | Compass Early Learning and Care | (CB) | - | - | - | 553 BONACCORD ST | PETERBOROUGH | K9H3A8 | 35-12-66-101 | Peterborough | Peterborough C | Peterborough Co | PETERBOROUGH | East | South | 44.3084 | -78.3362 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 1150000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 0 | 0 | 1150000 | 1150000 | 1150000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1150000
208-002 | 208-002 | 208 | 208 - CMSM Peterborough | - | CMSM Peterborough | Trent Child Care Bridgenorth | Trent Child Care Bridgenorth | (CB) | - | - | - | 832 CHARLES ST | BRIDGENORTH | K0L1H0 | 35-12-66-623 | Selwyn | Selwyn Tp | Peterborough Co | PETERBOROUGH | East | South | 44.379 | -78.3831 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 200000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 200000
209-001 | 209-001 | 209 | 209 - CMSM St. Thomas | - | CMSM St. Thomas | St. Thomas Elgin Social Services Hub | St. Thomas Elgin Social Services Hub | (CB) | - | - | - | 25 ST. CATHARINE ST | ST. THOMAS | N5P2V6 | 35-15-44-101 | St. Thomas | St. Thomas C | Elgin Co | ELGIN | Southwest | South | 42.7788 | -81.2024 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 5 | 88 | Y | - | Approved | 43195 | 2600000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 0 | 0 | 0 | 2600000 | 2600000 | 2600000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2600000
210-001 | 210-001 | 210 | 210 - CMSM Stratford | - | CMSM Stratford | Elma Logan Recreation Complex | Elma Logan Recreation Complex | (CB) | - | - | - | 200 NELSON ST | MONKTON | N0K1P0 | 35-15-65-403 | North Perth | North Perth M | Perth Co | PERTH | Southwest | South | 43.59 | -81.085 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 1 | 15 | Y | 2 | Approved | 43195 | 1590000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530000 | 1060000 | 0 | 0 | 1590000 | 1590000 | 1590000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1590000
211-001 | 211-001 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Ancaster Early Learning & Child Care | Ancaster Early Learning & Child Care | (CB) | - | - | - | 45 ANCASTER RD | NORTH YORK | M3K1S7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.733 | -79.4661 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43195 | 1020000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020000 | 0 | 0 | 0 | 1020000 | 1020000 | 1020000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1020000
211-002 | 211-002 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Bessarion Child Care | Bessarion Child Care | (CB) | - | - | - | 100 WOODSY PARK LN | TORONTO | M2K1C2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7689 | -79.3747 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43195 | 2040000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040000 | 0 | 0 | 0 | 2040000 | 2040000 | 2040000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2040000
211-003 | 211-003 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | East Toronto Village Children's | East Toronto Village Children's | (CB) | - | - | - | 43 KIMBERLEY AVE | TORONTO | M4E2Z4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6828 | -79.298 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 525000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 0 | 525000 | 525000 | 525000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 525000
211-004 | 211-004 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | East York East Toronto Family Resources Cosburn | East York East Toronto Family Resources Cosburn | (CB) | - | - | - | 1108 GREENWOOD AVE | EAST YORK | M4J4E6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6923 | -79.3382 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 255000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
211-005 | 211-005 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | East York East Toronto Family Resources Danforth | East York East Toronto Family Resources Danforth | (CB) | - | - | - | 3079 DANFORTH AVE | SCARBOROUGH | M1L1A9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6912 | -79.2873 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 255000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 0 | 0 | 255000 | 255000 | 255000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 255000
211-006 | 211-006 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Eastside Club | Eastside Club | (CB) | - | - | - | 100 GALLOWAY RD | SCARBOROUGH | M1E1W7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7573 | -79.1934 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Approved | 43195 | 1020000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020000 | 0 | 0 | 0 | 1020000 | 1020000 | 1020000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1020000
211-007 | 211-007 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Jane & Finch Community and Family | Jane & Finch Community and Family | (CB) | - | - | - | 1911 FINCH AVE W, SUITE 50A | NORTH YORK | M3N2V2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7568 | -79.5151 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 3 | Approved | 43195 | 765000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765000 | 0 | 0 | 765000 | 765000 | 765000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 765000
211-008 | 211-008 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Massey Centre ELC | Massey Centre ELC | (CB) | - | - | - | 1102 BROADVIEW AVE | EAST YORK | M4K2S5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6866 | -79.3566 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
211-009 | 211-009 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Network Glendower Child Care relocation | Network Glendower Child Care relocation | (CB) | - | - | - | 1020 MCNICOLL AVE | SCARBOROUGH | M1W2J6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7975 | -79.3048 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
211-010 | 211-010 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Network Jubilee Child Care | Network Jubilee Child Care | (CB) | - | - | - | 55 EMMETT AVE | YORK | M6M2E4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6886 | -79.5034 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
211-011 | 211-011 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Network Just Kids | Network Just Kids | (CB) | - | - | - | 1695 KEELE ST | YORK | M6M3W7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6851 | -79.4727 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
211-012 | 211-012 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Network Child Care Services Ossington Avenue North | Network Child Care Services Ossington Avenue North | (CB) | - | - | - | 756 OSSINGTON AVE | TORONTO | M6G3T9 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6626 | -79.4263 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43195 | 525000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 0 | 525000 | 525000 | 525000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 525000
211-013 | 211-013 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | North York Junior YMCA | North York Junior YMCA | (CB) | - | - | - | 567 SHEPPARD AVE E | NORTH YORK | M2K1B2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7656 | -79.3868 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 510000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
211-014 | 211-014 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Prosserman JCC Daycare & Preschool | Prosserman JCC Daycare & Preschool | (CB) | - | - | - | 4588 BATHURST ST | NORTH YORK | M2R1W6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7632 | -79.4421 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
211-015 | 211-015 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Scadding Court Community | Scadding Court Community | (CB) | - | - | - | 707 DUNDAS ST W | TORONTO | M5T2W6 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6516 | -79.4047 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 262500 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262500 | 0 | 0 | 262500 | 262500 | 262500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 262500
211-016 | 211-016 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Scarborough Centre for Healthy Communities | Scarborough Centre for Healthy Communities | (CB) | - | - | - | 4110 LAWRENCE AVE E | SCARBOROUGH | M1E2S1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7672 | -79.1948 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 255000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 0 | 0 | 255000 | 255000 | 255000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 255000
211-017 | 211-017 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | SickKids Center for Community Mental Health | SickKids Center for Community Mental Health | (CB) | - | - | - | 1645 SHEPPARD AVE W | NORTH YORK | M3M2N4 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7424 | -79.4962 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 510000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
211-018 | 211-018 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | St. Stephen's Waterfront Child Care | St. Stephen's Waterfront Child Care | (CB) | - | - | - | 635 QUEENS QUAY W | TORONTO | M5V2N2 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6358 | -79.3972 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 24 | Y | - | Approved | 43195 | 525000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 0 | 0 | 0 | 525000 | 525000 | 525000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 525000
211-019 | 211-019 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | Terry Tan Bloordale | Terry Tan Bloordale | (CB) | - | - | - | 4258 BLOOR ST W | ETOBICOKE | M9C1Z7 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6345 | -79.5688 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
211-020 | 211-020 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | West End YMCA | West End YMCA | (CB) | - | - | - | 931 COLLEGE ST | TORONTO | M6H1A1 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.6534 | -79.4259 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 262500 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262500 | 0 | 0 | 0 | 262500 | 262500 | 262500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 262500
211-021 | 211-021 | 211 | 211 - CMSM Toronto | - | CMSM Toronto | York University Cooperative Daycare | York Universtiy Co-operative Daycare | (CB) | - | - | - | 90 ATKINSON RD | NORTH YORK | M3J2S5 | 35-11-11-060 | Toronto | Toronto C | Toronto C | TORONTO | GTA | South | 43.7713 | -79.5007 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
212-001 | 212-001 | 212 | 212 - CMSM Windsor | - | CMSM Windsor | Ska:Na Family Learning Centre Northway | Ska:Na Family Learning Centre Northway | (CB) | - | - | - | 1699 NORTHWAY AVE | WINDSOR | N9B3L8 | 35-15-45-101 | Windsor | Windsor C | Essex Co | ESSEX | Southwest | South | 42.2871 | -83.0559 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43195 | 2100000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 0 | 0 | 0 | 2100000 | 2100000 | 2100000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2100000
215-001 | 215-001 | 215 | 215 - CMSM Grey | - | CMSM Grey | Dundalk Community Arena | Dundalk Community Arena | (CB) | - | - | - | 550 MAIN ST E | DUNDALK | N0C1B0 | 35-15-47-621 | Southgate | Southgate Tp | Grey Co | GREY | Southwest | South | 44.1764 | -80.3839 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 3 | Approved | 43195 | 302500 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302500 | 0 | 0 | 302500 | 302500 | 302500 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 302500
215-002 | 215-002 | 215 | 215 - CMSM Grey | - | CMSM Grey | Sydenham | Sydenham | (CB) | - | - | - | 1130 8TH ST E | OWEN SOUND | N4K1M7 | 35-15-47-101 | Owen Sound | Owen Sound C | Grey Co | GREY | Southwest | South | 44.5671 | -80.9208 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257500 | 257500 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
218-001 | 218-001 | 218 | 218 - CMSM Lambton | - | CMSM Lambton | London Bridge Child Care | London Bridge Child Care | (CB) | - | - | - | 1014 OAK AVE | SARNIA | N7S3T7 | 35-15-54-102 | Sarnia | Sarnia C | Lambton Co | LAMBTON | Southwest | South | 42.9709 | -82.3711 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 1490000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1490000 | 0 | 0 | 0 | 1490000 | 1490000 | 1490000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1490000
219-001 | 219-001 | 219 | 219 - CMSM Lanark | - | CMSM Lanark | Carleton Place Child Care | Carleton Place Child Care | (CB) | - | - | - | 3 FRANCIS ST | CARLETON PLACE | K7C0C1 | 35-12-55-402 | Carleton Place | Carleton Place T | Lanark Co | LANARK | East | South | 45.1437 | -76.1351 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 6 | 91 | Y | - | Approved | 43195 | 2915000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2915000 | 0 | 0 | 0 | 2915000 | 2915000 | 2915000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2915000
220-001 | 220-001 | 220 | 220 - CMSM Lennox & Addington | - | CMSM Lennox & Addington | LARC Amherstview Daycare | LARC Amherstview Daycare | (CB) | - | - | - | 73 KILDARE AVE | AMHERSTVIEW | K7N1J1 | 35-12-57-612 | Loyalist | Loyalist Tp | Lennox and Addington Co | LENNOX AND ADDINGTON | East | South | 44.2223 | -76.6569 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 1575000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575000 | 0 | 0 | 0 | 1575000 | 1575000 | 1575000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1575000
221-001 | 221-001 | 221 | 221 - CMSM Northumberland | - | CMSM Northumberland | Grafton Licensed Child Care Family Grouping | Grafton Licensed Child Care Family Grouping | (CB) | - | - | - | 718 STATION ST | GRAFTON | K0K2G0 | 35-12-61-616 | Alnwick-Haldimand | Alnwick-Haldimand Tp | Northumberland Co | NORTHUMBERLAND | East | South | 43.9901 | -78.023 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 1 | 15 | Y | 1 | Approved | 43195 | 515000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257500 | 257500 | 0 | 0 | 515000 | 515000 | 515000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 515000
225-001 | 225-001 | 225 | 225 - CMSM Wellington | - | CMSM Wellington | Wellington Place Early Learning & Child Care | Wellington Place Early Learning & Child Care | (CB) | - | - | - | 536 WELLINGTON RD 18 | FERGUS | N1M2W3 | 35-15-75-614 | Centre Wellington | Centre Wellington Tp | Wellington Co | WELLINGTON | Southwest | South | 43.6934 | -80.3995 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 64 | Y | - | Approved | 43195 | 2080000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080000 | 0 | 0 | 0 | 2080000 | 2080000 | 2080000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2080000
226-001 | 226-001 | 226 | 226 - CMSM Muskoka | - | CMSM Muskoka | Gravenhurst Integrated Child Care & EarlyON | Gravenhurst Integrated Child Care & EarlyON | (CB) | - | - | - | 180 BROCK ST | GRAVENHURST | P1P1X2 | 35-11-33-402 | Gravenhurst | Gravenhurst T | Muskoka D | MUSKOKA | Central | South | 44.9203 | -79.3729 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 1 | 15 | Y | 1 | Approved | 43195 | 519770 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269770 | 250000 | 0 | 0 | 519770 | 519770 | 519770 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 519770
226-002 | 226-002 | 226 | 226 - CMSM Muskoka | - | CMSM Muskoka | Macaulay Tree House | Macaulay Tree House | (CB) | - | - | - | 50 THE GRANITE BLUFF | BRACEBRIDGE | P1L1L4 | 35-11-33-401 | Bracebridge | Bracebridge T | Muskoka D | MUSKOKA | Central | South | 45.0532 | -79.2965 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43195 | 1926570 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1926570 | 0 | 0 | 0 | 1926570 | 1926570 | 1926570 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1926570
227-001 | 227-001 | 227 | 227 - CMSM Chatham-Kent | - | CMSM Chatham-Kent | Ska:na Family Learning Centre Chatham | Indigenous Child Care Chatham | (CB) | - | - | - | 25 EIGHTH ST | CHATHAM | N7M4J4 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4158 | -82.1992 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 1560000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560000 | 0 | 0 | 0 | 1560000 | 1560000 | 1560000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1560000
227-002 | 227-002 | 227 | 227 - CMSM Chatham-Kent | - | CMSM Chatham-Kent | Ska:na Family Learning Centre Wallaceburg | Indigenous Child Care Wallaceburg | (CB) | - | - | - | 1541 DUFFERIN AVE | WALLACEBURG | N8A2W8 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.58 | -82.3833 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 1560000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560000 | 0 | 0 | 0 | 1560000 | 1560000 | 1560000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1560000
227-003 | 227-003 | 227 | 227 - CMSM Chatham-Kent | - | CMSM Chatham-Kent | May Court Child Care | May Court Child Care | (CB) | - | - | - | 275 MCNAUGHTON AVE WEST | CHATHAM | N7L1R8 | 35-15-53-000 | Chatham-Kent | Chatham-Kent M | Chatham-Kent M | CHATHAM-KENT | Southwest | South | 42.4085 | -82.2096 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43195 | 1300000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 1300000 | 1300000 | 1300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1300000
230-001 | 230-001 | 230 | 230 - CMSM Halton | - | CMSM Halton | East Plains Co-operative | East Plains Co-operative | (CB) | - | - | - | 375 PLAINS RD E | BURLINGTON | L7T2C7 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3161 | -79.8411 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000 | 460000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
230-002 | 230-002 | 230 | 230 - CMSM Halton | - | CMSM Halton | Halton Hills Child Care | Halton Hills Child Care | (CB) | - | - | - | 60 PARK AVE | GEORGETOWN | L7G5X3 | 35-11-14-401 | Halton Hills | Halton Hills T | Halton R | HALTON | GTA | South | 43.6497 | -79.924 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 510000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
230-003 | 230-003 | 230 | 230 - CMSM Halton | - | CMSM Halton | ROCK | ROCK | (CB) | - | - | - | 710 CUMBERLAND AVE | BURLINGTON | L7N3M9 | 35-11-14-101 | Burlington | Burlington C | Halton R | HALTON | GTA | South | 43.3521 | -79.7871 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 510000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510000 | 0 | 0 | 510000 | 510000 | 510000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 510000
230-004 | 230-004 | 230 | 230 - CMSM Halton | - | CMSM Halton | Seedlings Children's | Seedlings Children's | (CB) | - | - | - | 320 BRONTE RD | OAKVILLE | L6H1M3 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.3972 | -79.7225 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550000 | 2550000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
230-005 | 230-005 | 230 | 230 - CMSM Halton | - | CMSM Halton | Halton Centre for Child Care | Halton Centre for Child Care | (CB) | - | - | - | 1151 BRONTE RD | OAKVILLE | L6M3L1 | 35-11-14-403 | Oakville | Oakville T | Halton R | HALTON | GTA | South | 43.4151 | -79.7419 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 6 | 98 | Y | - | Approved | 43195 | 3060000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060000 | 0 | 0 | 0 | 3060000 | 3060000 | 3060000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3060000
231-001 | 231-001 | 231 | 231 - CMSM Niagara | - | CMSM Niagara | A Child's World Family Care Lookout Ridge | A Child's World Family Care Lookout Ridge | (CB) | - | - | - | 1505 LOOKOUT ST | RIDGEVILLE | L0S1E5 | 35-11-18-405 | Pelham | Pelham T | Niagara R | NIAGARA | Central | South | 43.0438 | -79.3004 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Approved | 43195 | 515000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 0 | 0 | 0 | 515000 | 515000 | 515000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 515000
231-002 | 231-002 | 231 | 231 - CMSM Niagara | - | CMSM Niagara | Child and Family | Child and Family | (CB) | - | - | - | 796 BUFFALO RD | FORT ERIE | L2A5H2 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.8961 | -78.9698 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 1020000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020000 | 0 | 0 | 1020000 | 1020000 | 1020000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1020000
231-003 | 231-003 | 231 | 231 - CMSM Niagara | - | CMSM Niagara | Kidzdome | Kidzdome | (CB) | - | - | - | 162 MAIN ST E | GRIMSBY | L3M1P4 | 35-11-18-402 | Grimsby | Grimsby T | Niagara R | NIAGARA | Central | South | 43.1894 | -79.5498 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 78 | Y | - | Approved | 43195 | 1802500 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545000 | 0 | 0 | 0 | 1545000 | 1545000 | 1802500 | 257500 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1545000
231-004 | 231-004 | 231 | 231 - CMSM Niagara | - | CMSM Niagara | Niagara Nursery School | Niagara Nursery School | (CB) | - | - | - | 14 ANDERSON LANE | NIAGARA-ON-THE-LAKE | L0S1J0 | 35-11-18-404 | Niagara-on-the-Lake | Niagara-on-the-Lake T | Niagara R | NIAGARA | Central | South | 43.2473 | -79.0869 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 515000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515000 | 0 | 0 | 0 | 515000 | 515000 | 515000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 515000
231-005 | 231-005 | 231 | 231 - CMSM Niagara | - | CMSM Niagara | St. Catharines Regional Child Care | St. Catharines Regional Child Care | (CB) | - | - | - | 179 CARLTON ST | ST. CATHARINES | L2R1S1 | 35-11-18-103 | St. Catharines | St. Catharines C | Niagara R | NIAGARA | Central | South | 43.1731 | -79.2489 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 40 | Y | - | Approved | 43195 | 1275000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275000 | 0 | 0 | 0 | 1275000 | 1275000 | 1275000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1275000
231-006 | 231-006 | 231 | 231 - CMSM Niagara | - | CMSM Niagara | Under the Rainbow Child Care Services | Under the Rainbow Child Care Services | (CB) | - | - | - | 748 BUFFALO RD | FORT ERIE | L2A5H2 | 35-11-18-401 | Fort Erie | Fort Erie T | Niagara R | NIAGARA | Central | South | 42.8961 | -78.9698 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 72 | Y | - | Approved | 43195 | 1535000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1535000 | 0 | 0 | 0 | 1535000 | 1535000 | 1535000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1535000
232-001 | 232-001 | 232 | 232 - CMSM Peel | - | CMSM Peel | Brampton Southwest Library | Brampton Southwest Library | (CB) | - | - | - | 8405 FINANCIAL DR | BRAMPTON | L6Y0C1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.636 | -79.7796 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 250000 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000 | 250000 | 250000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 250000
232-002 | 232-002 | 232 | 232 - CMSM Peel | - | CMSM Peel | Brampton Northeast Supercentre | Brampton Northeast Supercentre | (CB) | - | - | - | 11825 BRAMALEA RD | BRAMPTON | L6R3S9 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7717 | -79.7805 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 3 | Approved | 43195 | 750000 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 750000 | 750000 | 750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 750000
232-003 | 232-003 | 232 | 232 - CMSM Peel | - | CMSM Peel | Caledon East | Caledon East | (CB) | - | - | - | 6215 OLD CHURCH RD | CALEDON | L7C1J7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.8738 | -79.8607 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 500000 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 500000 | 500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 500000
232-004 | 232-004 | 232 | 232 - CMSM Peel | - | CMSM Peel | Cooksville Caring for Kids | Cooksville Caring for Kids | (CB) | - | - | - | 130 DUNDAS ST E | MISSISSAUGA | L5A3V8 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5829 | -79.6124 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 5 | 80 | Y | 3 | Approved | 43195 | 2250000 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1166667 | 750000 | 0 | 0 | 1916667 | 1916667 | 2250000 | 333333 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1916667
232-005 | 232-005 | 232 | 232 - CMSM Peel | - | CMSM Peel | Earlsbridge Plaza | Eastbridge Plaza | (CB) | - | - | - | 10 EARLSBRIDGE BLVD | BRAMPTON | L7A3P1 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7026 | -79.829 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 500000 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 500000 | 500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 500000
232-006 | 232-006 | 232 | 232 - CMSM Peel | - | CMSM Peel | Fletcher's Meadow Plaza | Fletcher's Meadow Plaza | (CB) | - | - | - | 31 WORTHINGTON AVE | BRAMPTON | L7A2Y7 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.683 | -79.8166 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 750000 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 0 | 0 | 750000 | 750000 | 750000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 750000
232-007 | 232-007 | 232 | 232 - CMSM Peel | - | CMSM Peel | Gore Meadows | Gore Meadows | (CB) | - | - | - | 10100 THE GORE RD | BRAMPTON | L6P0A6 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7929 | -79.6929 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 5 | Approved | 43195 | 1250000 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 1250000 | 1250000 | 1250000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1250000
232-008 | 232-008 | 232 | 232 - CMSM Peel | - | CMSM Peel | Inglewood Community | Inglewood Community | (CB) | - | - | - | 15825 MCLAUGHLIN RD | CALEDON | L7C1H4 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7997 | -79.9372 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 2 | 39 | Y | 1 | Approved | 43195 | 1500000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 500000 | 0 | 0 | 1500000 | 1500000 | 1500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1500000
232-009 | 232-009 | 232 | 232 - CMSM Peel | - | CMSM Peel | Little Angels 1 | Little Angels 1 | (CB) | - | - | - | 1245 EGLINTON AVE W | MISSISSAUGA | L5N2M4 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5804 | -79.6837 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 250000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 250000 | 250000 | 250000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 250000
232-010 | 232-010 | 232 | 232 - CMSM Peel | - | CMSM Peel | Little Angels 2 | Little Angels 2 | (CB) | - | - | - | 6341 MISSISSAUGA RD | MISSISSAUGA | L5N1A5 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5953 | -79.7304 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 2 | 25 | Y | - | Approved | 43195 | 500000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 500000
232-011 | 232-011 | 232 | 232 - CMSM Peel | - | CMSM Peel | Salvation Army Erin Mills Day Care | Salvation Army Erin Mills Day Care | (CB) | - | - | - | 2460 THE COLLEGEWAY | MISSISSAUGA | L5L1V3 | 35-11-21-102 | Mississauga | Mississauga C | Peel R | PEEL | GTA | South | 43.5359 | -79.686 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
232-012 | 232-012 | 232 | 232 - CMSM Peel | - | CMSM Peel | Springdale | Springdale | (CB) | - | - | - | 51 MOUNTAINASH RD | BRAMPTON | L6R1W0 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.7604 | -79.7275 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 500000 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | 500000 | 500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 500000
232-013 | 232-013 | 232 | 232 - CMSM Peel | - | CMSM Peel | YMCA Kennedy | YMCA Kennedy | (CB) | - | - | - | 9996 KENNEDY RD N | BRAMPTON | L6V4G3 | 35-11-21-101 | Brampton | Brampton C | Peel R | PEEL | GTA | South | 43.715 | -79.7765 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | Y | - | Cancelled | - | 0 | Cancelled | Cancelled | Community Based Child Care | CANCELLED | CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 0
233-001 | 233-001 | 233 | 233 - CMSM Waterloo | - | CMSM Waterloo | Cambridge Family Early Years & EarlyON | Cambridge Family Early Years & EarlyON | (CB) | - | - | - | 73 WATER ST N | CAMBRIDGE | N1R3C5 | 35-15-25-101 | Cambridge | Cambridge C | Waterloo R | WATERLOO | Southwest | South | 43.3614 | -80.3145 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 3 | Approved | 43195 | 250000 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 250000 | 250000 | 250000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 250000
233-002 | 233-002 | 233 | 233 - CMSM Waterloo | - | CMSM Waterloo | Journey Together funded Child & Family Program | Journey Together funded Child & Family Program | (CB) | - | - | - | 236 WOODHAVEN RD | KITCHENER | N2C1V5 | 35-15-25-102 | Kitchener | Kitchener C | Waterloo R | WATERLOO | Southwest | South | 43.4527 | -80.4848 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 3 | Approved | 43195 | 450000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 450000 | 450000 | 450000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 450000
234-001 | 234-001 | 234 | 234 - CMSM York | - | CMSM York | Aurora Children's | Aurora Children's | (CB) | - | - | - | 18335 LESLIE ST | AURORA | L9N0M3 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9622 | -79.4671 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 7 | 127 | Y | - | Approved | 43195 | 3000000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 3000000 | 3000000 | 3000000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 3000000
234-002 | 234-002 | 234 | 234 - CMSM York | - | CMSM York | Denison Child Care | Denison Child Care | (CB) | - | - | - | 605 FERNBANK RD | NEWMARKET | L3X3E4 | 35-11-27-403 | Newmarket | Newmarket T | York R | YORK | GTA | South | 44.0691 | -79.4767 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 73 | Y | - | Approved | 43195 | 2000000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000 | 2000000 | 2000000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2000000
234-003 | 234-003 | 234 | 234 - CMSM York | - | CMSM York | Netivot Ha Torah | Netivot Ha Torah | (CB) | - | - | - | 18 ATKINSON AVE | THORNHILL | L4J8C8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8092 | -79.4433 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 4 | 87 | Y | - | Approved | 43195 | 500000 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 500000
234-004 | 234-004 | 234 | 234 - CMSM York | - | CMSM York | Social Enterprise for Canada Aurora EarlyON | Social Enterprise for Canada Aurora EarlyON | (CB) | - | - | - | 140 ENGELHARD DRIVE | AURORA | L4G6X6 | 35-11-27-401 | Aurora | Aurora T | York R | YORK | GTA | South | 43.9904 | -79.4553 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 300000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 300000 | 300000 | 300000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 300000
234-005 | 234-005 | 234 | 234 - CMSM York | - | CMSM York | Social Enterprise for Canada Woodbridge EarlyON | Social Enterprise for Canada Woodbridge EarlyON | (CB) | - | - | - | 140 WOODBRIDGE AVE | WOODBRIDGE | L4L4K9 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.7856 | -79.5934 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 225000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 225000 | 225000 | 225000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 225000
234-006 | 234-006 | 234 | 234 - CMSM York | - | CMSM York | The Congregation of the Passionist Sisters of San Paola | The Congregation of the Passionist Sisters of San Paola | (CB) | - | - | - | 1431 CLARENCE ST | WOODBRIDGE | L4H3C4 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.8207 | -79.6069 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 7 | 141 | Y | - | Approved | 43195 | 386000 | Construction Complete | Retrofit | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386000 | 0 | 0 | 0 | 386000 | 386000 | 386000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 386000
234-007 | 234-007 | 234 | 234 - CMSM York | - | CMSM York | Vaughan Metropolitan Centre YMCA | Vaughan Metropolitan Centre YMCA | (CB) | - | - | - | 200 APPLEMILL RD | CONCORD | L4K0J8 | 35-11-27-101 | Vaughan | Vaughan C | York R | YORK | GTA | South | 43.796 | -79.5287 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 5 | 75 | Y | - | Approved | 43195 | 2500000 | Construction Complete | Addition | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 2500000 | 2500000 | 2500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2500000
236-001 | 236-001 | 236 | 236 - CMSM Prescott & Russell | - | CMSM Prescott & Russell | Centre pour l'enfant et la famille ON y va | Centre pour l'enfant et la famille ON y va | (CB) | - | - | - | 2303 RUE LAURIER | ROCKLAND | K4K1L7 | 35-12-67-101 | Clarence-Rockland | Clarence-Rockland C | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.5379 | -75.2965 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 520000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 0 | 0 | 520000 | 520000 | 520000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 520000
236-002 | 236-002 | 236 | 236 - CMSM Prescott & Russell | - | CMSM Prescott & Russell | Centre pour l'enfant et la famille ON y va | Centre pour l'enfant et la famille ON y va | (CB) | - | - | - | 874, 876, 878 RUE JAMES | HAWKESBURY | K6A2W8 | 35-12-67-401 | Hawkesbury | Hawkesbury T | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.6016 | -74.6178 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 520000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 0 | 0 | 520000 | 520000 | 520000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 520000
236-003 | 236-003 | 236 | 236 - CMSM Prescott & Russell | - | CMSM Prescott & Russell | Centre pour l'enfant et la famille ON y va | Centre pour l'enfant et la famille ON y va | (CB) | - | - | - | 676 PRINCIPALE | CASSELMAN | K0A1M0 | 35-12-67-502 | Casselman | Casselman V | Prescott and Russell UCo | PRESCOTT AND RUSSELL | East | South | 45.3098 | -75.0838 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 1 | Approved | 43195 | 260000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000 | 0 | 0 | 260000 | 260000 | 260000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 260000
301-001 | 301-001 | 301 | 301 - DSSAB Cochrane | - | DSSAB Cochrane | Cochrane Child Care Centre | Town of Cochrane Child Care | (CB) | - | - | - | 435 TENTH AVE | COCHRANE | P0L1C0 | 35-13-81-407 | Cochrane | Cochrane T | Cochrane District | COCHRANE | Northeast | North | 49.0698 | -81.0198 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 10 | Y | - | Approved | 43195 | 800000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 800000 | 800000 | 800000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 800000
302-001 | 302-001 | 302 | 302 - DSSAB Nipissing | - | DSSAB Nipissing | EarlyON South Algonquin/Kidz Kastel Children's South Algonquin | EarlyON South Algonquin/Kidz Kastel Children's South Algonquin | (CB) | - | - | - | 6 GALEAIRY LAKE RD | WHITNEY | K0J2M0 | 35-13-85-601 | South Algonquin | South Algonquin Tp | Nipissing District | NIPISSING | Northeast | North | 45.4887 | -78.2447 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 1 | 15 | Y | 1 | Approved | 43195 | 525000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212500 | 312500 | 0 | 0 | 525000 | 525000 | 525000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 525000
303-001 | 303-001 | 303 | 303 - DSSAB Parry Sound | - | DSSAB Parry Sound | Highlands Early Learning and Child Care | Highlands Early Learning and Child Care | (CB) | - | - | - | 2500 HWY 592 N | EMSDALE | P0A1J0 | 35-13-86-616 | Perry | Perry Tp | Parry Sound District | PARRY SOUND | Northeast | North | 45.5432 | -79.3249 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 2 | 39 | Y | - | Approved | 43195 | 595000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595000 | 0 | 0 | 0 | 595000 | 595000 | 595000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 595000
303-002 | 303-002 | 303 | 303 - DSSAB Parry Sound | - | DSSAB Parry Sound | Miigwansag Child Care Centre | Journey Together | (CB) | - | - | - | 86 GIBSON ST | PARRY SOUND | P2A1X5 | 35-13-86-402 | Parry Sound | Parry Sound T | Parry Sound District | PARRY SOUND | Northeast | North | 45.349 | -80.0354 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 100000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 100000
304-001 | 304-001 | 304 | 304 - DSSAB Sault Ste Marie | - | DSSAB Sault Ste Marie | Rosedale Neighborhood Child Care/Rosedale Neighborhood EarlyON | Rosedale Neighborhood Child Care/Rosedale Neighborhood EarlyON | (CB) | - | - | - | 90 CHAPPLE AVE | SAULT STE. MARIE | P6B3P1 | 35-13-80-101 | Sault Ste Marie | Sault Ste. Marie C | Algoma District | ALGOMA | Northeast | North | 46.5237 | -84.3117 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 3 | 49 | Y | 2 | Approved | 43195 | 1550000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930000 | 620000 | 0 | 0 | 1550000 | 1550000 | 1550000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1550000
305-001 | 305-001 | 305 | 305 - DSSAB Timiskaming | - | DSSAB Timiskaming | Indigenous EarlyON New Liskeard | Indigenous EarlyON New Liskeard | (CB) | - | - | - | 121 SCOTT ST | NEW LISKEARD | P0J1P0 | 35-13-90-101 | Temiskaming Shores | Temiskaming Shores C | Timiskaming District | TIMISKAMING | Northeast | North | 47.5119 | -79.6839 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | N | 2 | Approved | 43195 | 1500000 | Construction Complete | Addition | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 1500000 | 1500000 | 1500000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1500000
306-001 | 306-001 | 306 | 306 - DSSAB Kenora | - | DSSAB Kenora | Dryden Children's Resource/EarlyON Dryden | Dryden Children's Resource/EarlyON Dryden | (CB) | - | - | - | 113 ALBERT ST | DRYDEN | P8N1J1 | 35-14-82-101 | Dryden | Dryden C | Kenora District | KENORA | Northwest | North | 49.7812 | -92.8335 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 3 | 40 | Y | 1 | Approved | 43195 | 400000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 400000 | 400000 | 400000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 400000
306-002 | 306-002 | 306 | 306 - DSSAB Kenora | - | DSSAB Kenora | EarlyON Sioux Lookout /Norah Love | EarlyON Sioux Lookout /Norah Love | (CB) | - | - | - | 54 PRINCESS ST | SIOUX LOOKOUT | P8T1H4 | 35-14-82-404 | Sioux Lookout | Sioux Lookout M | Kenora District | KENORA | Northwest | North | 50.1025 | -91.9173 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | 43195 | 2017-18 | 2018-19 | - | - | - | - | 2 | 20 | Y | 1 | Approved | 43195 | 1200000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 400000 | 0 | 0 | 1200000 | 1200000 | 1200000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1200000
306-003 | 306-003 | 306 | 306 - DSSAB Kenora | - | DSSAB Kenora | FIREFLY Child Care | FIREFLY Child Care | (CB) | - | - | - | 820 LAKEVIEW DR | KENORA | P9N3P7 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7633 | -94.528 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 400000 | Construction Complete | Retrofit | Community Based Child Care | 2019-20 | 43709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 400000 | 400000 | 400000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 400000
306-004 | 306-004 | 306 | 306 - DSSAB Kenora | - | DSSAB Kenora | Kids Zone Lakeside | Kids Zone Lakeside | (CB) | - | - | - | 216 SIXTH STREET S | KENORA | P9N1M7 | 35-14-82-102 | Kenora | Kenora C | Kenora District | KENORA | Northwest | North | 49.7588 | -94.486 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 1 | 15 | Y | - | Approved | 43195 | 350000 | Construction Complete | Retrofit | Community Based Child Care | 2018-19 | 43344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 350000 | 350000 | 350000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 350000
308-001 | 308-001 | 308 | 308 - DSSAB Rainy River | - | DSSAB Rainy River | United Native Friendship | United Native Friendship | (CB) | - | - | - | 821 MCIRVINE RD | FORT FRANCES | P9A3X7 | 35-14-87-401 | Fort Frances | Fort Frances T | Rainy River District | RAINY RIVER | Northwest | North | 48.6098 | -93.3956 | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | 43195 | 2017-18 | 2018-19 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 43195 | 2800000 | Construction Complete | Addition | Community Based Child Care | 2020-21 | 44075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000 | 0 | 0 | 0 | 2800000 | 2800000 | 2800000 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 2800000
13-150 | 13-150 | 13 | 229 - CMSM Durham | 66060 | Durham DSB | Seneca Trail | Seneca Trail Public Elementary School | ELE | 17265 | 19028 | 19028-B01 | 1915 QUEENSBURY DR | OSHAWA | L1K0S1 | 35-11-10-101 | Oshawa | Oshawa C | Durham R | DURHAM | GTA | South | 43.9575 | -78.8425 | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | 43090 | 2017-18 | 2017-18 | - | - | - | - | - | - | - | 3 | 49 | Y | - | Approved | 45168 | 4072915 | Planned | Addition | Child Care | 2023-24 | 45170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4072915 | 0 | 0 | 0 | 4072915 | 4072915 | 4072915 | 0 | - | N/A, Not a project reported on OB | Not Applicable | Not Applicable | YES as part of CC only | YES | 4072915

## Mode d'emplois (hidden)
MODE D'EMPLOI DU RAPPORT D'AVANCEMENT DES PROJETS D'IMMOBILISATION MAJEURS
Ce guide fournit des instructions sur la façon de remplir le rapport d'étape des projets d'immobilisation majeurs, visant à informer le ministère des principaux étapes de construction ainsi que sur les dépenses prévues des allocations restantes sur ces projets d'immobilisations.
Le rapport comprend les projets d’immobilisations majeurs qui ont été soutenus par le ministère avec les finacements suivants: Terrains prioritaires, Immobilisations prioritaires, Programme d'immobilisation de la maternelle et du jardin d'enfants à temps plein, Programme d'immobilisation des service de garde, Programme d'immobilisation ON y va et Subvention pour le replacement des carrefours communautaires.
Le rapport est déja rempli avec les dernières informations financières provenant du rapport SIFE de 2021-22.
Le rapport comprend tous les projets en cours et qui ont des allocations restantes, selon colonne 20 du tableau 3.2 selon le rapport SIFE de 2021-22.
Les allocations restantes sont au 31 auot 2022 (Rapport SIFE de 31 auot 2022).
Veuillez remplir chaque feuille (4) du rapport d'avancement des projets d'immobilisation majeurs.
La section Instructions ci-dessous fournit une explication de chacune des feuilles, cellules, colonnes et actions nécessaires pour compléter ce rapport.
FEUILLES
MCP-PIM Printemps 2023 : Rapporter les principales étapes de construction et le moment des dépenses prévues.
Saving-Économie : Pour déclarer les économies par projet selon les catégories de financement.
LP Req-Dem. TP : Rapporter au ministère les demandes potentielles du financement Terrains Prioritaires pour soutenir les acquisitions de sites.
To be retired-À être retiré : Pour confirmer les projets qui sont achevés et n'ont pas d'allocation restante et peuvent donc être supprimés des tableaux du réglement de l'Ontario.
RÉPERTOIRE DES CELLULES
Cellules modifiables, répondant à des questions spécifiques
Cellule de référence non modifiable
POUR OBTENIR DE L’AIDE, VEUILLEZ CONTACTER :
L'analyste des immobilisations de votre conseil
Mode d'emploi
MCP-PIM PRINTEMPS 2022 (Rapport sur les projets immobiliers majeurs)
Objectif : Le but de cette feuille est de rapporter au ministère les dates importantes des étapes de la construction ainsi que le moment où les dépenses sont prévues.
Section 1: Détails du projet
1 | Alerte: Cette cellule doit indiquer «Vrai» pour chaque ligne avant qu'un conseil scolaire ne soumette le modèle. "Faux" représente une erreur sur la ligne. Si vous avez besoin d'aide pour supprimer le message d'erreur, veuillez contacter votre analyste des immobilisations.
2 | ID du projet: Uniquement comme référence
3 | ID du conseil: Uniquement comme référence
4 | Nom du conseil scolaire: Uniquement comme référence
5 | Nom du projet: Uniquement comme référence
6 | Type de projet: Uniquement comme référence
7 | Catégorie de projet : Uniquement comme référence
Section 2 : Dates des étapes
8 | État de la construction: Menu déroulant avec les options suivants: "Pré-construction"; En Construction"; "Pratiquement terminé" ou "Achevé" pour les projets de construction. Pour les achats de site choisissez: "En négociation" , "Contrat de vente signé" ou "Achat completé". Veuillez fournir l'état de chaque projet au 31 mars 2023. Les définitions de chaque catégorie sont fournies ci-dessous:
Pré-construction: À partir de la date de la réception de l'approbation du financement jusqu'à l'approbation de procéder à l'appel d'offres du ministère et de l'attribution du contrat.
En construction: À partir de la date de l'attribution du contrat jusqu'à ce que le conseil scolaire ait la permission d'occuper l'installation.
Pratiquement terminé: À partir de la date où le conseil scolaire reçoit l'autorisation d'occuper l'installation et que le projet est terminé.
Achevé: La construction est 100% terminé et toutes les dépenses ont été encourus.
En négociation (Achat de site seulement): Le contract de vente n'est pas encore signé au 31 mars 2023.
Contract de vente signé: Le contract de vente a été signé au 31 mars 2023.
Contrat de vente completé(Achat de site seulement): Le contract de vente est completé au 31 mars 2023 et toutes les dépenses ont été encourus.
9 | Année de l'annonce : L'année scolaire où le ministère a annoncé son soutien au projet.
10 | Approbation d'aller de l'avant accordé par le ministère: Date de la plus récente approbation de procéder à l'appel d'offres qui a été accordée par le ministère.
11 | Date prévu pour faire la demande (révisée) auprès ministère pour sortir en appel d'offres: Si un conseil scolaire n'a pas reçu d'approbation du ministère pour sortir en appel d'offres ou n'a pas soumis une demande d'approbation, remplissez la colonne avec la date à laquelle le conseil scolaire prévoit de faire une demande (révisée) pour sortir en appel d'offres auprès du ministère pour chaque projet. Le ministère a pré-renseigné cette date en fonction des informations fournies dans la version du gabarit précédente. Veuillez réviser et mettre à jour au besoin. Veuillez remplir uniquement pour les nouvelles écoles, les ajouts et les rénovations.
12 | Début de la construction: Le ministère a pré-renseigné cette date en fonction des informations fournies dans la version du gabarit précédente. Veuillez réviser et mettre à jour au besoin. Date de l'attribution du contrat de construction ou la date prévue par le conseil scolaire.
13 | Pratiquement terminé: Voir au dessus (B41). Le ministère a pré-renseigné cette date en fonction des informations fournies dans la version du gabarit précédente. Veuillez réviser et mettre à jour au besoin. Veuillez remplir uniquement pour les nouvelles écoles, les ajouts et les rénovations.
14 | Ouverture: Le ministère a pré-renseigné cette date en fonction des informations fournies dans la version du gabarit précédente. Veuillez réviser et mettre à jour au besoin. Date prévue pour l'ouverture de l'instalation et l'acceuil des étudiants. Veuillez noter que le ministère ne s'attend pas à ce qu'un nouveau projet s'ouvre entre les mois de juin et août.
15 | Projet achevé: Voir au dessus (B42). Le ministère a pré-renseigné cette date en fonction des informations fournies dans la version du gabarit précédente. Veuillez réviser et mettre à jour au besoin. Veuillez remplir uniquement pour les nouvelles écoles, les ajouts et les rénovations.
Section 3: Financement approuvé du projet
16 | TP: Financement approuvé pour l'acquisition de sites ou les coûts de préparation du site soutenus par le programme de financement Terrains Prioritaires du ministère.
17 | IP: Financement approuvé pour la construction de nouvelles écoles, les ajouts et les rénovations soutenus par le programme de financement Immobilisation Prioritaires du ministère.
18 | PAJE: Financement approuvé pour la construction des salles pour la maternelle et le jardin d'enfants à temps plein.
19 | Service de garde: Financement approuvé pour la construction des salles de service de garde soutenues par le programme de financement Immobilisation service de garde.
20 | ON y va: Financement approuvé pour la construction de nouveaux centres ON y va soutenus par le programme de financement Immobilisation ON y va du ministère.
21 | Remplacement Carrefour Communautaire: Financement approuvé pour la construction des nouveaux carrefours communautaires soutenus par le programme de Subvention pour le replacement des carrefours communautaires du ministère.
22 | Autre: Financement approuvé pour la construction de projets d'immobilisations majeurs soutenus par les financements: réfection des écoles, amélioration de l'état des écoles, excédent accumulé, produit de l'aliénation, redevances d'aménagement scolaires (frais de préparation du site uniquement) et d'autres revenus de tiers.
23 | Financement total approuvé: Égale la somme des colonnes 16 à 22.
Section 4: Coût prévu du projet
24 | Terrain: Saisissez le coût total du terrain, comme les coûts d'acquisition du site et les améliorations du site. Veuillez saisir uniquement les coûts non éligibles à RAS.
25 | Bâtiment: Saisissez le coût total lié à la construction.
26 | Fourniture initiale: Saisissez le coût total pour meubler et équiper la nouvelle construction.
27 | Coût final prévu du projet: Somme des colonnes 24 à 26 et doit contenir le coût final prévu du projet.
28 | Écart: Colonne 23 moins Colonne 27.
Section 5: Allocations restantes
Allocations restantes au 31 aout 2022 = Financement total approuvé - les dépenses de la période précédente (Selon le tableau 3.2 du rapport SIFE de 2021-22)
29 | TP: Allocations restantes pour les terrains prioritaires.
30 | IP: Allocations restantes pour les immobilisations prioritaires.
31 | PAJE: Les conseils scolaires doivent rapporter l'allocation Immobilisation PAJE restante au 31 août 2022
32 | Service de garde: Allocations restantes pour immobilisation service de garde.
33 | ON y va: Allocations restantes pour immobilisation ON y va.
34 | Remplacement Carrefour Communautaire: Allocations restantes pour immobilisation remplacement carrefour communautaire.
35 | Autre: Allocations restantes des financements : réfection des écoles, amélioration de l'état des écoles, excédent accumulé, produit de l'aliénation, redevances d'aménagement scolaires (frais de préparation du site uniquement) et d'autres revenus de tiers restantes au 31 août 2021
36 | Total: Somme des colonnes 29-35.
37 | Économies du projet: Les conseils scolaires doivent saisir le montant des économies prévues. Les conseils scolaires doivent demander l'approbation du ministre avant de transférer les économies entre projets.
38 | Total des allocations restantes: colonne 36 moins colonne 37
Section 6: Allocations restantes à être encourues (pourcentage / année scolaire)
39-52 | 2021-22 - 2032-33: Inscrivez le pourcentage (Par exemple xx%) pour chaque période correspondante au cours de laquelle le conseil prévoit d'engager des dépenses liées à chaque projet d'immobilisations. Pour 2021-22 à 2024-25, veuillez entrer le pourcentage pour chaque période de septembre à mars et d'avril à août.
53 | Total: le total des pourcentages de toutes les dates doit être égal à 100%
Section 7: Commentaires
54 | Entrez les commentaires que le conseil scolaire pourrait avoir concernant chaque projet.
Section 8: Message d'erreur
55-56 | Veuillez vérifier tous les messages d'erreur avant de soumettre. Si vous avez besoin d'aide, veuillez contacter votre analyste des immobilisations.
Saving-Économie
Objectif: fournir une ventilation des économies par catégorie d'allocation. Les conseils scolaires peuvent demander l'approbation du ministre pour utiliser les économies réalisées dans le cadre de projets ayant des dépassements de coûts.
Section 1: Détails associés aux projets
2 | ID du projet: Uniquement comme référence
3 | ID du conseil: Uniquement comme référence
4 | Nom du conseil scolaire: Uniquement comme référence
5 | Nom du projet: Uniquement comme référence
Section 2: Économies faites dans les différents allocations
6 | TP: Saisissez les économies faites avec le financement terrains prioritaires.
7 | IP: Saisissez les économies faites avec le financement immobilisations prioritaires.
8 | PAJE: Saisissez les économies faites avec le financement Immobilisation PAJE.
9 | Service de garde: Saisissez les économies faites avec le financement immobilisation service de garde.
10 | ON y va: Saisissez les économies faites avec le financement immobilisation ON y va.
11 | Remplacement Carrefour Communautaire: Saisissez les économies faites avec le financement immobilisation remplacement carrefour communautaire.
12 | Autre: Saisissez les économies faites avec les autres financements
LP Req- Dem. TP (Demandes de financement pour les terrains prioritaires)
Objectif: Le but de cette feuille est de rapporter les demandes potentielles afin de soutenir les acquisitions de sites au cours des prochaines années. Ceci est pour les sites qui ne peuvent pas être pris en charge par les redevances d'aménagement scolaires. Veuillez noter que ceci est à titre informatif seulement et ne constitue pas une demande officielle de financement.
1 | ID du projet: Pour référence uniquement
2 | ID du conseil: Pour référence uniquement
3 | Nom du site (adresse): entrez le nom du site ou l'adresse du site que le conseil a l'intention d'acheter.
4 | Montant qui sera demandé: Montant du financement Immobilisation Terrain qui sera demandé auprès du ministère pour soutenir les coûts d'acquisition du site
5 | Le ministère a-t-il fourni du financement pour soutenir un projet associé à ce site? Entrez "Oui / Non". «Oui» indiquerait que le ministère a fourni, au 31 aout 2022, du financement dans le cadre du programme de financement Immobilisation Prioritaires pour soutenir la construction d'une nouvelle école ou d'un ajout.
6 | La demande de financement Terrain Prioritaires est à l'étude par le ministere? Entrez "Oui / Non". «Oui» indiquerait que le conseil scolaire a soumis une demande de financement Terrain Prioritaires pour soutenir l'acquisition d'un site que le ministère examine actuellement.
7-20 | Date anticipée de la fermeture de l'achat. Entrez 100% dans la période associée au cours de laquelle le contrat de vente devrait se conclure.
21 | Commentaires: Entrez les commentaires que le conseil scolaire pourrait avoir concernant chaque achat de site.

## Translations (hidden)
Output | English | French
Section 1
Label Out | Label English
Project Details
Project Name
Address
City
Postal Code
Project Type
Project Category
Project Status
Year of Announcement
Section 2
Project Phase
Construction Status
Project Phase
Phase Start Date
Phase End Date
Expected Phase Completion - Date
Section 3
Square Footage Specificiations
Do you anticipate needing a design change for this project?
Project Details - Square footage of New Construction
Project Details - Square footage of Renovation/Retrofit
Project Details - Square footage of Demolition
Project Details - Square footage of Child Care
Project Details - Square footage of EarlyOn
Section 4
Phase 1
Site Ownership Status
Site Purchase Date
Design Status
Child Care Floorplan Approval - Date
Site, Design, Child Care Related Comments: Include details of scope change if applicable
Section 5
Phase 2
Tender Process Begins - Date
Tender Closure - Date (A: Actual & E: Estimate)
Tender Contract Awarded - Date
Site Plan Approval Date
Section 6
Phase 3
Construction Start - Date
% of Progress Payments Made
Section 7
Phase 4
Substantial Completion Date (Construction Only)
Occupancy Date
Completion Date (Construction and Financial)
Child Care Operational Date
Section 8
Approved Project Funding
CP
CC
Other
Section 9
Projected Project Cost
Basis of Cost Estimate
Building Cost - School
Soft Costs - School
Site Cost

## Translation (hidden)
Project Commitment Tab
English | French
Key
Project ID
Project Name
Phase 1 - Start
Phase 1 -End
Phase 2 - Start
Phase 2 - End
Phase 3 - Start
Phase 3 - End
Phase 4 - Start
Phase 4 - End
Site Purchase
Space Template Finalized
Signed Joint Use Agreement
80% Design
Class A Cost Estimate
Site Plan Approval
Build Permit Obtained
Tender Issued
Construction Start
School Opening
Project Reconciliation
Cost of Project (excluding site)
Total Cost of Project (including site)
Total CP Request
Total Child Care Request
Project Phase Tab
Project ID
Project Name
Project Type
Project Category
Construction Status
Project Phase
Phase Start Date
Phase End Date
Expected Phase Completion - Date
Monthly Update Tab
Monthly Project Upates
Dates: Estimates (Green)
Actuals (Black)
Meeting Date
Project Details | Détails associés aux projets
Project ID
Project Name
Address
City
Postal Code
Project Type
Project Category
Project Status
Consruction Status
Section 2: Square Footage Specifications
Anticipate Design Change
Square footage of New Construction
Square footage of Renovation/Retrofit
Square footage of Demolition
Square footage of New Child Care
Square footage of New Community Space
Square footage of EarlyOn
Section 3: Phase 1 - Pre-Tender
Stie Ownership Status
Site Purchase Date
Space Template Approval Date
Type of Design Used
Class A - Date
Child Care Floor Plan Approval - Date

## List (hidden)
Actual/Estimated | Language | Construction Status | Phase | Yes / No | Site Ownership Status | Design Status | Cost Basis | Design | Site Plan | Project Category | Project Type
Actual | English | Planning | 1 | Yes / Oui | No Site Identified | <30% Complete | Board Estimate | New | Yes/Oui | Accommodation Pressure | Land
Estimate | French | Pre-Procurement | 1 | No / Non | Site Identified Only | 30%-80% Complete | Repeat Design | Repeat | No/Non | Facility Condition | New School
|  | Tender Issuance | 1 | Not Applicable | Site Under Option Agreement | >80% Complete | Architect Estimate | EDU Catalogue |  | School Consolidation | Addition
|  | Tender Closed | 1 |  | Site Purchased |  | Class D Estimate |  |  | French Language Access | Renovation
|  | Contract Awarded | 1 |  | Not Applicable |  | Class C Estimate |  |  | Other | Disposition
|  | Site Preparation | 2 |  |  |  | Class B Estimate |  |  |  | Demolition
|  | Construction | 2 |  |  |  | Class A Estimate |  |  |  | Purchase
|  | Substantial Completion | 3 |  |  |  | Tender Results |  |  |  | Other
|  | Completion | 4
Cost Reconciliation
% Construction Progress |  | Phase (List) | Project Status | Submission Type | Project Risks | Risk Rating | Site Funding Source | Mitigation Strategies
10 |  | 0 | Under Ministry Review | CP | Cost | Low | EDC | Accept
20 |  | 1 | In Progress | Ad Hoc | Delay | Medium | LP | Mitigate
30 |  | 2 | Remove from tracker (Cancelled) |  | Delay/Cost | High | LP/EDC | Transfer
40 |  | 3 | Remove from tracker (Complete) |  |  |  |  | Avoid
50 |  | 4 |  |  | Market Risk
60 |  |  |  |  | Governance Risk
70 |  |  |  |  | Organization/Project Management Risk
80 |  |  |  |  | Design Risk
90 |  |  |  |  | Procurement/Tender Risk
100 |  |  |  |  | Site Readiness/Enabling Works
Permit, Licenses and Approvals
Type of Design |  |  |  |  | Construction Risk
New |  |  |  |  | Testing and Commissioning
Repeat
Catalogue

## User Guide (hidden)
MAJOR CAPITAL PROJECT PROGRESS REPORT USER GUIDE
This guide provides instructions on how to fill-out the Major Capital Project Progress Report, which informs the ministry on key construction milestones along with anticipated spend of remaining allocations for capital projects.
The template includes major capital projects that are supported through the ministry's Land Priorities; Capital Priorities; Full-Day Kindergarten; Child Care; EarlyOn and Community Hub Replacement grant programs.
The template is pre-populated with the most up-to-date financial information as per the 2021-22 Financial Statements EFIS submission.
The template includes all projects that are in-progress and have remaining allocations as reported in Schedule 3.2 Col 20 of the 2021-22 Financial Statements Submission.
Remaining allocations are reported as of August 31, 2022.
Please fill out each tab (4) of the Major Capital Project Progress Report
The Instructions section below provides an explanation of each of the tabs, cells, columns, and actions required in order to complete this template.
TABS
MCP-PIM Spring-2023 - To report key construction milestones and the time of anticipated expenditures.
Saving-Économie - To report project savings by funding allocation.
LP Req-Dem. TP - To report potential requests to the ministry for Land Priorities funding to support site acquisitions.
CELL INDEX
Editable cells, answering specific questions
Not Editable Reference Cell
FOR SUPPORT, PLEASE CONTACT:
Your School Boards Capital Analyst
INSTRUCTIONS
MCP-PIM Spring 2023-(Report-Back on Major Capital Projects)
Purpose: The purpose of this sheet is to report back to the ministry on key construction milestone dates along with the timing of future expenditures.
Section 1: Project Details
1 | Control: This cell should report "True" for each line before a school board submits the template. "False" represents an error on the line. If assistance is required to clear the error message please contact your Capital Analyst.
2 | Project ID: For reference only
3 | Board ID: For reference only
4 | School Board: For reference only
5 | Project Name: For reference only
6 | Project Type: For reference only
7 | Project Category: For reference only
Section 2: Milestone Dates
8 | Construction Status: Drop-down menu chose either "Pre-Construction"; Under Construction"; Substantial Completion" or "Complete" for construction projects. For site acquisitions chose either: " Under Negotiation" or " Agreement of P&S Signed" or "Purchase completed". Please report the status of each project as of March 31, 2023. Definitions for each category are provided below: Pre-Construction - From time of receiving funding approval up to receiving an Approval to Proceed to Tender from the ministry and awarding the contract. Under Construction - From the time of awarding the contract until the school board has received permission to occupy the project. Substantial Complete - From the time the school board has received permission to occupy the project and project is complete. Complete - Construction is 100% and all expenditures have been incurred. Under Negotiation (For Site Acquisition only) - The Agreement of Purchase and Sale is still not signed as of March 31, 2023. Agreement of P&S Signed (For Site Acquisition only) - The Agreement Purchase and Sale has been signed as of March 31, 2023. Purchase completed (For Site Acquisition only) - The Agreement of Purchase and Sale has been completed and all the costs have been incurred as of March 31, 2023.
9 | Year of Annoucement: The school year the ministry announced support for the project.
10 | ATP Granted by the Ministry: Reflects the most recent Approval to Proceed to Tender (ATP) that has been granted by the ministry.
11 | Anticipated ATP/Revised ATP Submission: If a school board has not received an ATP / revised ATP for the project from the ministry or submitted an ATP / revised ATP for approval, then complete this column to indicate the date the school boards expects to submit an ATP / revised to the ministry for each project. The ministry has pre-populated this date based on information provided in the previous version of the template. Please review and update as required. Please complete for new schools, additoins and retrofits only.
12 | Construction Commencement: Enter the day the school board awarded the construction contract or plans to. Please note the ministry has pre-populated this date based on information provided in the previous version of the template. Please review and update as required.
13 | Substantial Completion: See definition above in row B38. The ministry has pre-populated based on information provided in the previous version of the template. Please review and update as required. Please complete for new schools, additions and retrofits only.
14 | Opening: The ministry has pre-poulated this date based on information provided in the pervious version of the template. Please review and update if required. Enter the date the project is expected to be opened and welcome students. Please note the ministry does not expect a school board to open a new project between the months of June to August.
15 | Project Completion: See definition above in row B38. The ministry has pre-populated based on information provided in the previous version of the template. Please review and update as required. Please complete for new schools, additions and retrofits only.
Section 3: Approved Project Funding
16 | LP: Identifies approved funding for site acquisition or site preparation costs that are supported through the ministry's Land Priorities funding program.
17 | CP: Identifies approved funding to support the construction of new schools, additions and retrofits supported through the ministry's Capital Priorities funding program.
18 | FDK: Identifies approved funding to support the construction of full-day kindergarten rooms.
19 | CC: Identifies approved funding to support the construction of new child care centers supported through the ministry's Child Care Capital funding program.
20 | EO: Identifies approved funding to support the construction of new EarlyOn centers supported through the ministry's EarlyOn funding program.
21 | CHR: Identifies approved funding to support the construction of new community hub replacement centers supported through the ministry's Community Hubs funding program.
22 | Other: Identifies approved funding to support the construction of major capital projects including School Renewal, School Condition Improvement, accumulated surplus, proceeds of disposition, education development charges (site prep costs only) and other third party revenue.
23 | Total Approved Funding: Equals the sum of column 16 to 22.
Section 4: Projected Project Cost
24 | Land: Enter the total cost attributed to land such as site acquistion costs and land improvements. Please enter non-EDC eligible costs only.
25 | Building: Enter the total cost attributed to the cost of construction.
26 | First Time Equipment: Enter the total cost attributed to first time equipping.
27 | Projected Final Project Cost: Equals Col 24 to 26 and should reflect the total cost of the project.
28 | Variance: Equals Col 23 less Col 27.
Section 5: Remaining Allocations
Remaining allocations (As of August 31, 2022) = Total Approved Funding - Prior Period Expenditures (EFIS - Schedule 3.2 - 2021-22 Financial Statements)
29 | LP: Reports remaining allocations for Land Priorities.
30 | CP: Reports remaining allocations for Capital Priorities.
31 | FDK: School boards are to add the remaining FDK allocation as of August 31, 2022.
32 | CC: Reports remaining allocations for Child Care.
33 | EO: Reports remaining allocations for EarlyON.
34 | CHR: Reports remaining allocations for Community Hubs Replacement funding.
35 | Other: School boards are to add the remaining allocations for other funding sources such as School Renewal, School Condition Improvement, education development charges or 3rd party revenue as of August 31, 2022.
36 | Total: Sums columns 29-35.
37 | Less Project Savings: School boards are to enter the amount of projected project savings if any. School boards are required to request Minister approval before transferring project savings between projects.
38 | Total Remaining Allocation: Col. 36 Less Col. 37.
Section 6: Remaining Allocations To Be Incurred (Percentage/School Year)
39-52 | 2021-22-2033-34: Enter the percentage (e.g. xxx%) for each relevant time period in which the board expects to incur expenditures related to each capital project. For 2022-23 to 2024-25 please enter the percentage for each time period Sep-Mar and Apr-Aug.
53 | Total: The total percentages from all the dates must add to 100%
Section 7: Comments
54 | Enter any comments the school board may have regarding each project.
Section 8: Error Messages
55 | Please clear all error messages before submitting. Please contact your Capital Analyst for assistance.
Saving-Économie
Purpose: To provide a break-down of savings by funding allocation. School boards are able to request Minister approval to using project savings on projects with cost overruns.
Section 1: Project Details
2 | Project ID: For reference only
3 | Board ID: For reference only
4 | School Board: For reference only
5 | Project Name: For reference only
Section 2: Savings By Allocation
6 | LP: Enter the project savings related to Land Priorities.
7 | CP: Enter the project savings related to Capital Priorities.
8 | FDK: Enter the project savings related to FDK.
9 | CC: Enter the project savings related to Child Care Captial.
10 | EO: Enter the project savings related to EarlyON
11 | CHR: Enter the project savings related to Community Hub Replacement.
12 | Other: Enter the project savings related to Other funding sources.
LP Req-Dem. TP (Land Priorities Request)
Purpose: The purpose of this sheet is to report potential requests to the ministry for Land Priorities funding to support site acquisitions over the next couple of years. This is for sites that cannot be supported through Education Development Charges. Please note this is for information purposes only and does not qualify as official request for funding.
1 | Board ID: For reference only
2 | School Board: For reference only
3 | Site Name (Address): Enter the site name or address of the site the board intends to purchase.
4 | Amount Requested: Enter the amount the funding that will be requested through the ministry's Land Priorities funding to support site acquisition costs.
5 | Has the ministry provided funding to support an associated project for this site? Enter "Yes/No". "Yes" would indicate that the ministry has as of August 31, 2022 provided funding through the Capital Priorities funding program to support the construction of a new school or addition.
6 | ATP Currently Under Ministry Review? Enter "Yes/No". "Yes" would indicate that the school board has submitted a request for Land Priorities funding to support site acquisition which the ministry is currently reviewing.
7-20 | Anticipated Close of Agreement of Purchase and Sale. Enter 100% in the associated time period in which the Agreement of Purchase and Sale is expected to close.
21 | Comments: Enter any comments the board may have regarding each site acquisition.