## Sheet1
Monthly Project Updates
Board Name | *((var.board_name
Board Number | *((var.board_number
All Fields Are Filled
Meeting Date | *((var.date_meeting | pt | pt | pt |  | pt | Analyst | pt | pt | Set to "Active" | Formula - Don't touch | monthly | monthly | Analyst to find | Analyst | Analyst | Analyst | Analyst | Analyst | Formula | Chris/Sophie to get back to me | Analyst | Analyst | Analyst | Analyst | Analyst | Analyst | Analyst | Formula | Analyst | Formula | monthly | analyst | Formula | Monthly | Formula | Monthly | Analyst | Analyst | Analyst | Frankenstein | pt | pt | pt | pt | pt (formula) | pt | monthly? | Analyst | Analyst | Analyst | Analyst | Analyst | Analyst
Section 1: Project Details | [11 empty] | Section 2: Phase 1: Planning/Design | [9 empty] | Section 3: Phase 2 - Tender | [7 empty] | Section 4: Phase 3 - Construction | [5 empty] | Section 5: Phase 4 - Project Completion |  |  |  |  | Section 6: Approved Project Funding | [6 empty] | Section 7: Projected Construction Cost |  |  |  | Section 8: Communications Protocol |  | Section 10: General Comments
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8 | Col 9 | Col 10 | Col 11 | Col 12 | Col 13 | Col 14 | Col 15 | Col 16 | Col 17 | Col 18 | Col 19 | Col 20 | Col 21 | Col 22 | Col 23 | Col 24 | Col 25 | Col 26 | Col 27 | Col 28 | Col 29 | Col 30 | Col 31 | Col 32 | Col 33 | Col 34 | Col 35 | Col 36 | Col 37 | Col 38 | Col 39 | Col 40 | Col 41 | Col 42 | Col 43 |  | Col 45 | Col 46 | Col 47 | Col 48 | Col 49 | Col 50 | Col 51 | Col 52 | Col 53 | Col 54 | Col 55
Project ID | Project Name | Address | City | Postal Code | Funding Program | Funding Year (FY) | Project Commitment Status | Project Type | Project Category | Project Status | Construction Status | Site Ownership Status | Site Purchase Date | Space Template Approval Date | Schematic Design Received? | Type of Design Used | Class A/B Cost Estimate Report Submission Date | Detailed Design (at least 80%) Submission Date | CPAF Form Received? | All Supporting Documents Received? | CA Signed Off on Phase Closing? | Site Plan Submission Date | Site Plan Approval Date | Build Permit Obtained | Tender Issued Date | Tender Closed | Child Care Floor Plan Approval Submission Date | CPAF Form Received? | All Supporting Documents Received? | Contract Awarded | Original PC - Construction Start Date | School Construction Start - Date | Child Care Construction Start - Date | % Construction Progress | Substantial Completion | Original PC - Opening | School Opening Date | Risk of Delay | Child Care Opening Date | Financial Close | Most Recent Approval - Date | LP | EDC | CP | CC | Other | Total Approved Funding | Basis of Cost Estimate | Risk of Cost Overage | Next Steps | Date of Anticipated CPAF | Signage | Signage Installation Date | CA Comments
Section 1: Project Details Col 1: No. de projet; Section 1: Project Details Col 2: Nom du projet; Section 1: Project Details Col 9: Type de projet; Section 1: Project Details Col 10: Catégorie de projet |  | IP | Service de garde | Autre | Financement total approuvé | Base de l'estimation des coûts
Section 1: Project Details Col 1: project.id; Section 1: Project Details Col 2: project.name; Section 1: Project Details Col 9: project.type; Section 1: Project Details Col 10: project.category; Section 3: Phase 2 - Tender Col 28: cc.floorplan.approved |  | lp.funding | cp.funding | fdk.funding | total.funding | cost.basis |  |  |  | Signage |  | comments
*((tbl.monthly_out*((col.project_id | *((col.project_name | *((col.location_address | *((col.location_city | *((col.location_postal_code |  | *((col.ori_fy | *((col.status_project_commitment | *((col.project_type | *((col.project_category | *((col.repopulate | *((col.construction_status | *((col.site_status | 2024-09-15 | 2024-04-01 | Yes / Oui | New | 2024-05-01 | May 1 2025 | Yes / Oui | Yes |  | 2024-03-01 | 2024-07-01 | 2025-11-01 | 2025-06-01 | 2025-02-01 | 2025-03-01 |  | Yes | 2024-04-01 | 2025-03-31 | 2026-01-01 |  |  | 2026-06-01 | 2025-02-01 | 2027-06-01 |  | 2025-10-01 | 2028-06-01 |  |  |  | 20000000 | 5000000 | 1000000 | 26000000 | Board Estimate |  |  |  | No/Non
11-139 | Levack Public Elementary School |  |  |  |  | 2024-25 |  | Retrofit | Consolidation |  | Project Reconciliation | Site Purchased | 2026-07-01 | 2024-02-01 | Yes / Oui | Repeat | 2024-06-01 | 2024-05-01 |  | No |  | 2024-03-02 | 2025-07-01 | March 1 2026 | May 1 2024 | March 15 2024 | 2025-04-01 |  | Yes | 2024-04-01 | 2025-03-31 | 2027-03-31 |  |  | 2026-07-01 | 2025-02-01 | 2026-07-01 |  | 2025-03-01 | 2027-07-01 | [6 empty] | 0 | Tender Results
11-138 | Sudbury Consolidation Public Elementary School | [6 empty] | New Construction | Consolidation |  | Completed | Site Purchased | 2027-09-01 | 2025-06-01 |  | New | 2025-04-01 | 2023-10-01 |  | No |  | 2024-03-03 | 2025-02-01 | 2025-03-01 | May 1 2025 | March 15 2025 | 2025-05-01 |  | Yes | 2024-04-01 | 2024-11-01 | 2027-09-01 |  |  | 2027-09-01 | 2024-09-01 | 2027-09-01 |  | 2025-03-02 | 2028-09-01 | [6 empty] | 0 | Tender Results
03-039 | Little Current Public Elementary School | [6 empty] | Retrofit | Child Care |  | Completed | Site Owned at Time of Approval |  | 2024-07-01 |  | EDU Catalogue | 2024-10-01 | 2023-11-01 |  | No |  | 2024-03-04 | 2028-04-01 | 2025-03-01 | May 1 2026 | March 15 2026 | 2025-06-01 |  | Yes | 2024-04-01 | 2024-11-02 | 2028-04-01 |  |  | 2028-04-01 | 2024-09-02 | 2028-04-01 |  | 2025-03-03 | 2029-04-01 | [6 empty] | 0
0
Pulled & Static | Pulled/Static | Pulled/Not Static | Pulled/Not Static | Pulled/Not Static | Pulled & Static | Pulled & Static | Drop Down | Pulled & Static | Pulled & Static | Drop down | Formula & Static | Drop Down | Pulled from Milestone tab | CA Input | Drop Down | Drop Down | CA Input | CA Input | Drop Down | Formula/Static | Drop Down | CA Input | Pulled from Milestone tab | CA Input | CA Input | CA Input | CA Input | Drop Down | Auto based on CPAF form | CA Input | Pulled from PC tab | Pulled from Milestone Tab | CA Input | Auto populate | Pulled from Milestone Tab | Pulled from PC tab | pulled and statics | TBD | CA input | Calculation - This is 12 months after school opening | Pulled in by Geordie | Pulled From Latest Approval |  | Pulled From Latest Approval | Pulled From Latest Approval | Pulled From Latest Approval | Calculated | Drop Down | Drop Down | Drop Down | CA input | Drop Down | CA Input | CA Input